## Sheet1
Freeze | Bill Code | Contract Code | Job | Phase | Name | Shared Saving | Category | Phase Type | Type | Method | Current Cost Budget | Spent/Committed Against Base Contract | Spent/Committed Total | Actual Cost | Spent/Committed (In Scope) | Complete % | Pending Internal PCI | Pending Internal PCI Cost To Complete | Pending External PCI Cost To Complete | Cost to Complete | Cost to Complete Override | Projected Cost Forecast | Projected Cost Forecast Override | Cost Variance | Pending CO | Pending CO (Incl. Risk) | Projected Cost Budget | Spent/Committed (Pending CO) | Cost To Complete (Pending CO) | Proj Cost Forecast (Incl. Pending CO) | Projected Cost Forecast (Incl Pending CO) Override | Cost Variance (Incl Pending CO) | Current Bill Budget | Pending CO | Original Cost<br/> Budget Amount | Original Bill<br/> Budget Amount | Pending CO (Incl. Risk) | Projected Bill Budget | Billed To Date | Revenue Forecast | Revenue Forecast Override | Revenue Variance | Adj Rev Forecast | Projected Profit | Current Period Cost | Previous Period Cost | Last Period Forecast | Cost Forercast /<br>Variance | Current Period Changes | Previous Period Changes | Current Period Commitments | Previous Period Commitments | Shared Saving Amt | Profit Incl Shared Saving | Pending PCI including Risk (revenue) | Pending PCI including Risk (Cost) | WIP Projected cost forecast including Risk | WIP Projected cost forecast | WIP Revenue amount | WIP adjusted Revenue amount | Adj Rev Forecast <br/> Variance | Billed Budget Qty | Billed Completed Qty | Billed Remaining Qty | Billed Projected Qty | Input Budget Qty | Input Completed Qty | Input Remaining Qty | Input Projected Qty | Input WM Code | Output Budget Qty | Output Completed Qty | Output Remaining Qty | Output Projected Qty | Output WM Code | Committed Amount | Committed Remaining Amount | Spent Against Commitment Amount | Total Cost to Complete Amt | Notes
Y | IPCRP1-0000-0005-L | IPCRP1 | IPCRP1 | 0000-0005 | AWO# ACM Abatement at Abandoned Rec Center | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | App DDC CO#04/ PCO #18 value is $988,868.00
Y | IPCRP1-0000-0005-R | IPCRP1 | IPCRP1 | 0000-0005 | AWO# ACM Abatement at Abandoned Rec Center | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0005-S | IPCRP1 | IPCRP1 | 0000-0005 | AWO# ACM Abatement at Abandoned Rec Center | N | S |  | UNIT | A | 0 | 934050 | 934050 | 934050 | 934050 | 100 | 0 | 0 | 0 | 0 | Y | 934050 | Y | -934050 | 0 | 0 | 0 | 0 | 0 | 934050 | Y | -934050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -934050 | 0 | 0 | 934050 | 0 | 0 | 0 | 0 | 0 | 0 | -934050 | 0 | 0 | 934050 | 934050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -3 | 0 | LS | 0 | 1 | 0 | 1 | LS | 934050 | 0 | 934050 | 0 | Finished
Y | IPCRP1-0000-0006-L | IPCRP1 | IPCRP1 | 0000-0006 | Repair CE MH60651 & Adjoining Oil-O-Static Feeders | N | L |  | UNIT | P | 0 | 28501.7 | 28501.7 | 28501.7 | 28501.7 | 100 | 0 | 0 | 0 | 0 | Y | 28501.7 | Y | -28501.7 | 0 | 0 | 0 | 0 | 0 | 28501.7 | Y | -28501.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28501.7 | 0 | 0 | 28501.7 | 0 | 0 | 0 | 0 | 0 | 0 | -28501.7 | 0 | 0 | 28501.7 | 28501.7 | 0 | 0 | 0 | 0 | 0 | 255 | 255 | 0 | 255 | 0 | 255 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Revenue will come directly from CE to IPC. Lump Sum Agreement value is $259,833.00, which we will receive in three (3) equal payments of $86,611.00, with the last payment coming when work is 100% complete. Labor = $190,000 (1500 MH), Material+Sub+Consumable+Equipment = $0.00, Total forecast = $190K.
Y | IPCRP1-0000-0007-L | IPCRP1 | IPCRP1 | 0000-0007 | Removal of Exist 59” Steel Sewer Casing at MH-E03 | N | L |  | UNIT | P | 0 | 18538.71 | 18538.71 | 18538.71 | 18538.71 | 31.6691 | 0 | 0 | 40000 | 0 | Y | 18538.71 | Y | -18538.71 | 0 | 40000 | 40000 | 0 | 40000 | 58538.71 | Y | -18538.71 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | N | 0 | 0 | -58538.71 | 0 | 0 | 18538.71 | 0 | 0 | 0 | 0 | 0 | 0 | -58538.71 | 0 | 0 | 18538.71 | 18538.71 | 0 | 0 | 0 | 0 | 0 | 152 | 152 | 0 | 152 | 0 | 152 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 40000 | Budget will be zero across the board. Revenue from this will come from Time & Material Records, which the project team and DDC are signing off daily on. PM Forecast will be as follows Quantity/ UOM 1.00 LS, Labor =$40,000 (300MH) , Material+Sub+Consumable+Equipment=$0.00, Total forecast = $40K.
Y | IPCRP1-0000-0007-R | IPCRP1 | IPCRP1 | 0000-0007 | Removal of Exist 59” Steel Sewer Casing at MH-E03 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 40000 | 0 | 0 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0008-C | IPCRP1 | IPCRP1 | 0000-0008 | Load Test for Helical Piles | N | C |  | UNIT | U | 0 | 158552 | 158552 | 158552 | 158552 | 100 | 0 | 0 | 0 | 0 | Y | 158552 | Y | -158552 | 0 | 0 | 0 | 0 | 0 | 158552 | Y | -158552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -158552 | 0 | 0 | 158552 | 0 | 0 | 0 | 0 | 0 | 0 | -158552 | 0 | 0 | 158552 | 158552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | -110 | 0 | NA | 2 | 2 | 0 | 2 | EA | 107122 | 0 | 107122 | 0
Y | IPCRP1-0000-0008-L | IPCRP1 | IPCRP1 | 0000-0008 | Load Test for Helical Piles | N | L |  | UNIT | P | 0 | 137372.31 | 137372.31 | 137372.31 | 137372.31 | 100 | 0 | 0 | 0 | 0 | Y | 137372.31 | Y | -137372.31 | 0 | 0 | 0 | 0 | 0 | 137372.31 | Y | -137372.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -137372.31 | 0 | 0 | 137372.31 | 0 | 0 | 0 | 0 | 0 | 0 | -137372.31 | 0 | 0 | 137372.31 | 137372.31 | 0 | 0 | 0 | 0 | 0 | 1069 | 1069 | 0 | 1069 | 0 | 1069 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0 | Slabjack PO#1011 ($107,122.00). Plus purchased & piaid outside of PO to Slabjack by check request ($51,430.00). Total = $158,552.00.
Y | IPCRP1-0000-0008-S | IPCRP1 | IPCRP1 | 0000-0008 | Load Test for Helical Piles | N | S |  | UNIT | A | 0 | 7440 | 7440 | 7440 | 7440 | 100 | 0 | 0 | 0 | 0 | N | 7440 | N | -7440 | 0 | 0 | 0 | 0 | 0 | 7440 | N | -7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7440 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | -7440 | 0 | 0 | 7440 | 7440 | 0 | 0 | 0 | 0 | 0 | 62 | 62 | 0 | 62 | 0 | 62 | NA | 2 | 2 | 0 | 2 | EA | 7440 | 0 | 7440 | 0
Y | IPCRP1-0000-0009-C | IPCRP1 | IPCRP1 | 0000-0009 | Helical Piles for 10th St Sewer (VECP No. 02) | N | C |  | UNIT | U | 0 | 1526.97 | 668.05 | 1526.97 | 1526.97 | 100 | 0 | 0 | 0 | 0 | Y | 1526.97 | Y | -1526.97 | 0 | 0 | 0 | 0 | 0 | 1526.97 | Y | -1526.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1526.97 | 0 | 0 | 1526.97 | 0 | 0 | 0 | 0 | 0 | 0 | -1526.97 | 0 | 0 | 1526.97 | 1526.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -21 | 0 | NA | 38620 | 30280.25 | 0 | 30280.25 | LF | -858.92 | -858.92 | 0 | 0
Y | IPCRP1-0000-0009-L | IPCRP1 | IPCRP1 | 0000-0009 | Helical Piles for 10th St Sewer (VECP No. 02) | N | L |  | UNIT | P | 0 | 506369.53 | 506369.53 | 506369.53 | 506369.53 | 100 | 0 | 0 | 0 | 0 | Y | 506369.53 | Y | -506369.53 | 0 | 0 | 0 | 0 | 0 | 506369.53 | Y | -506369.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -506369.53 | 0 | 0 | 506369.53 | 0 | 0 | 0 | 0 | 0 | 0 | -506369.53 | 0 | 0 | 506369.53 | 506369.53 | 0 | 0 | 0 | 0 | 0 | 3608.5 | 3608.5 | 0 | 3608.5 | 0 | 3608.5 | HR | 38620 | 30280.25 | 0 | 30280.25 | LF | 0 | 0 | 0 | 0 | Magnum Geo-Solution (121K) + PMF KMA (33K).
Y | IPCRP1-0000-0009-M | IPCRP1 | IPCRP1 | 0000-0009 | Helical Piles for 10th St Sewer (VECP No. 02) | N | M |  | UNIT | U | 0 | 3750815.5 | 3750815.5 | 3100368 | 3750815.5 | 100 | 0 | 0 | 0 | -650447.5 | Y | 3100368 | Y | -3100368 | 0 | 0 | 0 | 0 | 0 | 3100368 | Y | -3100368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3100368 | 0 | 0 | 3100368 | 0 | 0 | 0 | 0 | 0 | 0 | -3100368 | 0 | 0 | 3100368 | 3100368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276.67 | -2276.67 | 0 | NA | 38620 | 30280.25 | 0 | 30280.25 | LF | 3750815.5 | 650447.5 | 3100368 | -650447.5 | negative CO needed
Y | IPCRP1-0000-0009-S | IPCRP1 | IPCRP1 | 0000-0009 | Helical Piles for 10th St Sewer (VECP No. 02) | N | S |  | UNIT | A | 0 | 168941.75 | 168941.75 | 152941.75 | 168941.75 | 100 | 0 | 0 | 0 | -16000 | Y | 152941.75 | Y | -152941.75 | 0 | 0 | 0 | 0 | 0 | 152941.75 | Y | -152941.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -152941.75 | 0 | 0 | 152941.75 | 0 | 0 | 0 | 0 | 0 | 0 | -152941.75 | 0 | 0 | 152941.75 | 152941.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2680 | -2680 | 0 | NA | 38620 | 30280.25 | 0 | 30280.25 | LF | 168941.75 | 16000 | 152941.75 | -16000
Y | IPCRP1-0000-0010-L | IPCRP1 | IPCRP1 | 0000-0010 | VECP No 1. Sewer Foundation Redesign and Const Sav | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0010-R | IPCRP1 | IPCRP1 | 0000-0010 | VECP No 1. Sewer Foundation Redesign and Const Sav | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9091149.43 | 0 | 0 | 0 | 0 | 9091149.43 | 0 | 0 | N | 9091149.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9091149.43 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0015-L | IPCRP1 | IPCRP1 | 0000-0015 | SBS Boring Sub, Aquifer Drilling & Testing (ADT) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0015-S | IPCRP1 | IPCRP1 | 0000-0015 | SBS Boring Sub, Aquifer Drilling & Testing (ADT) | N | S |  | UNIT | A | 0 | 13800 | 13800 | 13800 | 13800 | 0 | 0 | 0 | 0 | -13800 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | -13800 | 13800 | -13800 | CO from DDC cancelled on 5/15/2023
Y | IPCRP1-0000-0016-C | IPCRP1 | IPCRP1 | 0000-0016 | SBS Boring Sub, Support | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0016-E | IPCRP1 | IPCRP1 | 0000-0016 | SBS Boring Sub, Support | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0016-L | IPCRP1 | IPCRP1 | 0000-0016 | SBS Boring Sub, Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | This is a CO
Y | IPCRP1-0000-0016-S | IPCRP1 | IPCRP1 | 0000-0016 | SBS Boring Sub, Support | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0020-L | IPCRP1 | IPCRP1 | 0000-0020 | FDR Settlement, Testing & Replacement | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26000 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | -26000 | 0 | 0 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 200 | 200 | HR | 1 | 0.8 | 0.2 | 1 | LS | 0 | 0 | 0 | 26000
Y | IPCRP1-0000-0020-S | IPCRP1 | IPCRP1 | 0000-0020 | FDR Settlement, Testing & Replacement | N | S |  | UNIT | A | 0 | 54798.35 | 54798.35 | 48708.35 | 54798.35 | 81.1806 | 0 | 0 | 0 | 5201.65 | Y | 60000 | Y | -60000 | 0 | 0 | 0 | 0 | 0 | 60000 | Y | -60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60000 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | -60000 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | -456 | 0 | NA | 1 | 0.8 | 0.2 | 1 | LS | 54798.35 | 6090 | 48708.35 | 5201.65 | ADT (54.3K) + PMF KMA (6.7K).
Y | IPCRP1-0000-0025-C | IPCRP1 | IPCRP1 | 0000-0025 | Carbon Fiber work in Reach A/B - Sub (CTI) | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 550 | 0 | 550 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0025-L | IPCRP1 | IPCRP1 | 0000-0025 | Carbon Fiber work in Reach A/B - Sub (CTI) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 550 | 0 | 550 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0025-S | IPCRP1 | IPCRP1 | 0000-0025 | Carbon Fiber work in Reach A/B - Sub (CTI) | N | S |  | UNIT | P | 0 | 3875229.2 | 3875229.2 | 3875229.2 | 3875229.2 | 100 | 0 | 0 | 0 | 0 | Y | 3875229.2 | Y | -3875229.2 | 0 | 0 | 0 | 0 | 0 | 3875229.2 | Y | -3875229.2 | 0 | 0 | -3965136.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3875229.2 | 0 | 0 | 3875229.2 | 0 | 0 | 0 | 0 | 0 | 0 | -3875229.2 | 0 | 0 | 3875229.2 | 3875229.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553.76 | -553.76 | 0 | NA | 0 | 550 | 0 | 550 | LF | 3875229.2 | 0 | 3875229.2 | 0 | CTI SCO#7 ($3,814,651.50) & SCO#8 ($14,970.77), plus Pinnacle SCO #6 ($150,000.00) plus SCO #7 (-$59,696.04). Pinnacle SCO#9 moves $45,197.03 cost/commit from this code to cc:0000-0028.
Y | IPCRP1-0000-0026-L | IPCRP1 | IPCRP1 | 0000-0026 | Carbon Fiber work in Reach A/B - Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | -93426.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0026-S | IPCRP1 | IPCRP1 | 0000-0026 | Carbon Fiber work in Reach A/B - Support | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | -12712.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0027-C | IPCRP1 | IPCRP1 | 0000-0027 | Carbon Fiber work in Reach A/B - Exc & Sheet | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | -304481.93 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 585 | 0 | 585 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0027-L | IPCRP1 | IPCRP1 | 0000-0027 | Carbon Fiber work in Reach A/B - Exc & Sheet | N | L |  | UNIT | P | 0 | 213501.66 | 213501.66 | 213501.66 | 213501.66 | 100 | 0 | 0 | 0 | 0 | Y | 213501.66 | Y | -213501.66 | 0 | 0 | 0 | 0 | 0 | 213501.66 | Y | -213501.66 | 0 | 0 | -678477.66 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -213501.66 | 0 | 0 | 213501.66 | 0 | 0 | 0 | 0 | 0 | 0 | -213501.66 | 0 | 0 | 213501.66 | 213501.66 | 0 | 0 | 0 | 0 | 0 | 1627 | 1627 | 0 | 1627 | 0 | 1627 | HR | 0 | 585 | 0 | 585 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0027-S | IPCRP1 | IPCRP1 | 0000-0027 | Carbon Fiber work in Reach A/B - Exc & Sheet | N | S |  | UNIT | A | 0 | 238.37 | 238.37 | 238.37 | 238.37 | 100 | 0 | 0 | 0 | 0 | N | 238.37 | N | -238.37 | 0 | 0 | 0 | 0 | 0 | 238.37 | N | -238.37 | 0 | 0 | -52007.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -238.37 | 0 | 0 | 238.37 | 0 | 0 | 0 | 0 | 0 | 0 | -238.37 | 0 | 0 | 238.37 | 238.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -2 | 0 | NA | 0 | 585 | 0 | 585 | LF | 238.37 | 0 | 238.37 | 0
Y | IPCRP1-0000-0028-L | IPCRP1 | IPCRP1 | 0000-0028 | Carbon Fiber work in Reach A/B - Backfill & Pull | N | L |  | UNIT | P | 0 | 41230.79 | 41230.79 | 41230.79 | 41230.79 | 100 | 0 | 0 | 0 | 0 | Y | 41230.79 | Y | -41230.79 | 0 | 0 | 0 | 0 | 0 | 41230.79 | Y | -41230.79 | 0 | 0 | -369424.42 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -41230.79 | 0 | 0 | 41230.79 | 0 | 0 | 0 | 0 | 0 | 0 | -41230.79 | 0 | 0 | 41230.79 | 41230.79 | 0 | 0 | 0 | 0 | 0 | 294 | 294 | 0 | 294 | 0 | 294 | HR | 0 | 562 | 0 | 562 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0028-S | IPCRP1 | IPCRP1 | 0000-0028 | Carbon Fiber work in Reach A/B - Backfill & Pull | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | -32648.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 562 | 0 | 562 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0030-C | IPCRP1 | IPCRP1 | 0000-0030 | Montgomery St Permanent DOT Fiber Work (T&M) | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0030-E | IPCRP1 | IPCRP1 | 0000-0030 | Montgomery St Permanent DOT Fiber Work (T&M) | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0030-L | IPCRP1 | IPCRP1 | 0000-0030 | Montgomery St Permanent DOT Fiber Work (T&M) | N | L |  | UNIT | P | 0 | 37995.14 | 37995.14 | 37995.14 | 37995.14 | 100 | 0 | 0 | 0 | 0 | Y | 37995.14 | Y | -37995.14 | 0 | 0 | 0 | 0 | 0 | 37995.14 | Y | -37995.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37995.14 | 0 | 0 | 37995.14 | 0 | 0 | 0 | 0 | 0 | 0 | -37995.14 | 0 | 0 | 37995.14 | 37995.14 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 300 | 0 | 300 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | This is PCO#087.
Y | IPCRP1-0000-0030-M | IPCRP1 | IPCRP1 | 0000-0030 | Montgomery St Permanent DOT Fiber Work (T&M) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0030-R | IPCRP1 | IPCRP1 | 0000-0030 | Montgomery St Permanent DOT Fiber Work (T&M) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0030-S | IPCRP1 | IPCRP1 | 0000-0030 | Montgomery St Permanent DOT Fiber Work (T&M) | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Added micropiles to Keller subcontract. GO (12/15) DONE
Y | IPCRP1-0000-0031-L | IPCRP1 | IPCRP1 | 0000-0031 | CF Wrap Part 2, Reach A/B, sub (CTI) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 940 | 0 | 940 | LF | 0 | 0 | 0 | 0 | CTI SCO#9 ($3,063,194.00) & SCO#10 ($14,721.81
Y | IPCRP1-0000-0031-S | IPCRP1 | IPCRP1 | 0000-0031 | CF Wrap Part 2, Reach A/B, sub (CTI) | N | S |  | UNIT | A | 0 | 3100153.31 | 3100153.31 | 3100153.31 | 3100153.31 | 100 | 0 | 0 | 0 | 0 | Y | 3100153.31 | Y | -3100153.31 | 0 | 0 | 0 | 0 | 0 | 3100153.31 | Y | -3100153.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3100153.31 | 0 | 0 | 3100153.31 | 0 | 0 | 0 | 0 | 0 | 0 | -3100153.31 | 0 | 0 | 3100153.31 | 3100153.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | -1339 | 0 | NA | 0 | 940 | 0 | 940 | LF | 3100153.31 | 0 | 3100153.31 | 0 | CTI SCO#9 ($3,063,194.00) & SCO#10 ($14,721.81
Y | IPCRP1-0000-0032-L | IPCRP1 | IPCRP1 | 0000-0032 | CF Wrap Part 2, Reach A/B, sub support | N | L |  | UNIT | P | 0 | 2226.6 | 2226.6 | 2226.6 | 2226.6 | 100 | 0 | 0 | 0 | 0 | Y | 2226.6 | Y | -2226.6 | 0 | 0 | 0 | 0 | 0 | 2226.6 | Y | -2226.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2226.6 | 0 | 0 | 2226.6 | 0 | 0 | 0 | 0 | 0 | 0 | -2226.6 | 0 | 0 | 2226.6 | 2226.6 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 18 | 0 | 18 | HR | 0 | 2 | 0 | 2 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0032-S | IPCRP1 | IPCRP1 | 0000-0032 | CF Wrap Part 2, Reach A/B, sub support | N | S |  | UNIT | A | 0 | 117364.83 | 117364.83 | 117364.83 | 117364.83 | 100 | 0 | 0 | 0 | 0 | Y | 117364.83 | Y | -117364.83 | 0 | 0 | 0 | 0 | 0 | 117364.83 | Y | -117364.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -117364.83 | 0 | 0 | 117364.83 | 0 | 0 | 0 | 0 | 0 | 0 | -117364.83 | 0 | 0 | 117364.83 | 117364.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -2 | 0 | NA | 0 | 2 | 0 | 2 | SH | 117364.83 | 0 | 117364.83 | 0
Y | IPCRP1-0000-0033-C | IPCRP1 | IPCRP1 | 0000-0033 | CF Wrap Part 2, Reach A/B - excavate & sheet | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 470 | 0 | 470 | LF | 0 | 0 | 0 | 0 | Change PMF (Consumables) from $408,656.46 to $200,000.00
Y | IPCRP1-0000-0033-L | IPCRP1 | IPCRP1 | 0000-0033 | CF Wrap Part 2, Reach A/B - excavate & sheet | N | L |  | UNIT | P | 0 | 202523.44 | 202523.44 | 202523.44 | 202523.44 | 100 | 0 | 0 | 0 | 0 | Y | 202523.44 | Y | -202523.44 | 0 | 0 | 0 | 0 | 0 | 202523.44 | Y | -202523.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -202523.44 | 0 | 0 | 202523.44 | 0 | 0 | 0 | 0 | 0 | 0 | -202523.44 | 0 | 0 | 202523.44 | 202523.44 | 0 | 0 | 0 | 0 | 0 | 1522.5 | 1522.5 | 0 | 1522.5 | 0 | 1522.5 | HR | 0 | 470 | 0 | 470 | LF | 0 | 0 | 0 | 0 | Change PMF (MH) from 3,344.03 to 1,923.00, Change PMF (Labor) from $512,066.72 to $250,000.00
Y | IPCRP1-0000-0033-S | IPCRP1 | IPCRP1 | 0000-0033 | CF Wrap Part 2, Reach A/B - excavate & sheet | N | S |  | UNIT | A | 0 | 17091.11 | 17091.11 | 17091.11 | 17091.11 | 100 | 0 | 0 | 0 | 0 | Y | 17091.11 | Y | -17091.11 | 0 | 0 | 0 | 0 | 0 | 17091.11 | Y | -17091.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17091.11 | 0 | 0 | 17091.11 | 0 | 0 | 0 | 0 | 0 | 0 | -17091.11 | 0 | 0 | 17091.11 | 17091.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | -136 | 0 | NA | 0 | 470 | 0 | 470 | LF | 17091.11 | 0 | 17091.11 | 0
Y | IPCRP1-0000-0034-L | IPCRP1 | IPCRP1 | 0000-0034 | CF Wrap Part 2, Reach A-B, backfill & pull sht | N | L |  | UNIT | P | 0 | 76993.35 | 76993.35 | 76993.35 | 76993.35 | 100 | 0 | 0 | 0 | 0 | Y | 76993.35 | Y | -76993.35 | 0 | 0 | 0 | 0 | 0 | 76993.35 | Y | -76993.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -76993.35 | 0 | 0 | 76993.35 | 0 | 0 | 0 | 0 | 0 | 0 | -76993.35 | 0 | 0 | 76993.35 | 76993.35 | 0 | 0 | 0 | 0 | 0 | 597.5 | 597.5 | 0 | 597.5 | 0 | 597.5 | HR | 0 | 470 | 0 | 470 | LF | 0 | 0 | 0 | 0 | Change PMF (MH) from 1,571.00 to 961.00, Change PMF (Labor) from $235,972.92 to $125,000.00
Y | IPCRP1-0000-0034-S | IPCRP1 | IPCRP1 | 0000-0034 | CF Wrap Part 2, Reach A-B, backfill & pull sht | N | S |  | UNIT | A | 0 | 7563.25 | 7563.25 | 7563.25 | 7563.25 | 100 | 0 | 0 | 0 | 0 | Y | 7563.25 | Y | -7563.25 | 0 | 0 | 0 | 0 | 0 | 7563.25 | Y | -7563.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7563.25 | 0 | 0 | 7563.25 | 0 | 0 | 0 | 0 | 0 | 0 | -7563.25 | 0 | 0 | 7563.25 | 7563.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.5 | -61.5 | 0 | NA | 0 | 470 | 0 | 470 | LF | 7563.25 | 0 | 7563.25 | 0
Y | IPCRP1-0000-0035-L | IPCRP1 | IPCRP1 | 0000-0035 | CF Wrap Part 2, Reach A/B, temp ramp if nec | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | Change PMF (MH) from 468 to 0.00, Change PMF (Labor) from $73,555.03 to $0.00
Y | IPCRP1-0000-0035-S | IPCRP1 | IPCRP1 | 0000-0035 | CF Wrap Part 2, Reach A/B, temp ramp if nec | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0040-C | IPCRP1 | IPCRP1 | 0000-0040 | Assemble & Install Work Platforms for Pier Work | N | C |  | UNIT | U | 0 | 42768.78 | 42768.78 | 35929.41 | 42768.78 | 98.5697 | 0 | 0 | 0 | -6318.02 | Y | 36450.76 | Y | -36450.76 | 0 | 0 | 0 | 0 | 0 | 36450.76 | Y | -36450.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36450.76 | 6318.02 | 0 | 36450.76 | 0 | 0 | 0 | 5272.82 | 0 | 0 | -36450.76 | 0 | 0 | 36450.76 | 36450.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562.39 | -3562.39 | 0 | LS | 0 | 95.75 | 53.25 | 149 | EA | 42768.78 | 6839.37 | 35929.41 | -6318.02 | Original quantity from VECP#4 was 142.00. Sumit requested increase to 149.00, to ensure all Phase 2 Piers can be claimed. Quantity in Phase 1 increased due to non-VECP piers requiring platforms/lifelines. RAPID STEEL SUPPLY CORP. How many work platforms are there for Pier Work?
Y | IPCRP1-0000-0040-L | IPCRP1 | IPCRP1 | 0000-0040 | Assemble & Install Work Platforms for Pier Work | N | L |  | UNIT | P | 0 | 202258.88 | 202258.88 | 202258.88 | 202258.88 | 54.7829 | 0 | 0 | 0 | 166942.12 | Y | 369201 | Y | -369201 | 0 | 0 | 0 | 0 | 0 | 369201 | Y | -369201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -369201 | 10552.76 | 15701.54 | 369201 | 0 | 0 | 0 | 0 | 0 | 0 | -369201 | 0 | 0 | 369201 | 369201 | 0 | 0 | 0 | 0 | 0 | 2877.15 | 2877.15 | 0 | 1635.5 | 1241.65 | 2877.15 | HR | 0 | 95.75 | 53.25 | 149 | EA | 0 | 0 | 0 | 166942.12 | Change PMF (MH) from 3,760.00 to 2,840.00, Change PMF (Labor) from $482,596.00 to $369,200.00 How many work platforms are there for Pier Work?
Y | IPCRP1-0000-0040-S | IPCRP1 | IPCRP1 | 0000-0040 | Assemble & Install Work Platforms for Pier Work | N | S |  | UNIT | A | 0 | 2194.19 | 2194.19 | 2194.19 | 2194.19 | 215.8298 | 0 | 0 | 0 | 0 | N | 1016.63 | N | -1016.63 | 0 | 0 | 0 | 0 | 0 | 1016.63 | N | -1016.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1016.63 | 129.13 | 1048.43 | 1016.63 | 0 | 0 | 0 | 0 | 129.13 | 0 | -1016.63 | 0 | 0 | 1016.63 | 1016.63 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 0 | 95.75 | 53.25 | 149 | EA | 2194.19 | 0 | 2194.19 | 0
Y | IPCRP1-0000-0041-L | IPCRP1 | IPCRP1 | 0000-0041 | Scarify Top of Pier Caps | N | L |  | UNIT | P | 0 | 134564.52 | 134564.52 | 134564.52 | 134564.52 | 57.0189 | 0 | 0 | 0 | 101435.48 | Y | 236000 | Y | -236000 | 0 | 0 | 0 | 0 | 0 | 236000 | Y | -236000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -236000 | 4602.13 | 13983.21 | 236000 | 0 | 0 | 0 | 0 | 0 | 0 | -236000 | 0 | 0 | 236000 | 236000 | 0 | 0 | 0 | 0 | 0 | 1971 | 1971 | 0 | 1260 | 711 | 1971 | HR | 0 | 106 | 38 | 144 | EA | 0 | 0 | 0 | 101435.48 | Updated and Matched Going Forward Labor Rate to Actual Current Labor Rate. 142ea from VECP#4 (58F + 64E = 142Total) Add 2ea more (new F piers in Phase 1, P#73 & #75) for final total of 144ea).
N | IPCRP1-0000-0041-S | IPCRP1 | IPCRP1 | 0000-0041 | Scarify Top of Pier Caps | N | S |  | UNIT | A | 0 | 516.54 | 516.54 | 516.54 | 516.54 | 100 | 0 | 0 | 0 | 0 | N | 516.54 | N | -516.54 | 0 | 0 | 0 | 0 | 0 | 516.54 | N | -516.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -516.54 | 516.54 | 0 | 516.54 | 0 | 0 | 0 | 0 | 516.54 | 0 | -516.54 | 0 | 0 | 516.54 | 516.54 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | NA | 0 | 106 | 38 | 144 | EA | 516.54 | 0 | 516.54 | 0
Y | IPCRP1-0000-0042-L | IPCRP1 | IPCRP1 | 0000-0042 | Form & Pour Concrete for FIXED Pier Cap Resurfacin | N | L |  | UNIT | P | 0 | 88237.42 | 88237.42 | 88237.42 | 88237.42 | 47.6959 | 0 | 0 | 0 | 96762.58 | Y | 185000 | Y | -185000 | 0 | 0 | 0 | 0 | 0 | 185000 | Y | -185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -185000 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | -185000 | 0 | 0 | 185000 | 185000 | 0 | 0 | 0 | 0 | 0 | 1541.98 | 1541.98 | 0 | 757 | 784.98 | 1541.98 | HR | 0 | 30 | 33 | 63 | EA | 0 | 0 | 0 | 96762.58
Y | IPCRP1-0000-0042-M | IPCRP1 | IPCRP1 | 0000-0042 | Form & Pour Concrete for FIXED Pier Cap Resurfacin | N | M |  | UNIT | U | 0 | 49678.28 | 49678.28 | 49678.28 | 49678.28 | 136.0578 | 0 | 0 | 0 | -13165.65 | Y | 36512.63 | Y | -36512.63 | 0 | 0 | 0 | 0 | 0 | 36512.63 | Y | -36512.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36512.63 | 9990.85 | 3174.8 | 36512.63 | 0 | 0 | 0 | 0 | 13165.65 | 0 | -36512.63 | 0 | 0 | 36512.63 | 36512.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2412 | -2412 | 0 | NA | 0 | 30 | 33 | 63 | EA | 49279.3 | -398.98 | 49678.28 | -13165.65
Y | IPCRP1-0000-0042-S | IPCRP1 | IPCRP1 | 0000-0042 | Form & Pour Concrete for FIXED Pier Cap Resurfacin | N | S |  | UNIT | A | 0 | 254.13 | 254.13 | 254.13 | 254.13 | 100 | 0 | 0 | 0 | 0 | N | 254.13 | N | -254.13 | 0 | 0 | 0 | 0 | 0 | 254.13 | N | -254.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -254.13 | 0 | 0 | 254.13 | 0 | 0 | 0 | 0 | 0 | 0 | -254.13 | 0 | 0 | 254.13 | 254.13 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 0 | 30 | 33 | 63 | EA | 254.13 | 0 | 254.13 | 0
Y | IPCRP1-0000-0043-L | IPCRP1 | IPCRP1 | 0000-0043 | Form & Pour Concrete for EXP Pier Cap Resurfacing | N | L |  | UNIT | P | 0 | 256267.36 | 256267.36 | 256267.36 | 256267.36 | 50.8466 | 0 | 0 | 0 | 247734.08 | Y | 504001.44 | Y | -504001.44 | 0 | 0 | 0 | 0 | 0 | 504001.44 | Y | -504001.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -504001.44 | 10009.74 | 0 | 504001.44 | 0 | 0 | 0 | 0 | 0 | 0 | -504001.44 | 0 | 0 | 504001.44 | 504001.44 | 0 | 0 | 0 | 0 | 0 | 4196.55 | 4196.55 | 0 | 2154.5 | 2042.05 | 4196.55 | HR | 0 | 53 | 32 | 85 | EA | 0 | 0 | 0 | 247734.08 | Change PMF (MH) from 3,760.00 to 2,840.00, Change PMF (Labor) from $482,596.00 to $369,200.00 Updated and matched Going Forward Rate to Actual Production Rate in October 2023.
Y | IPCRP1-0000-0043-M | IPCRP1 | IPCRP1 | 0000-0043 | Form & Pour Concrete for EXP Pier Cap Resurfacing | N | M |  | UNIT | U | 0 | 74465.33 | 74465.33 | 70328.91 | 74465.33 | 74.818 | 0 | 0 | 0 | 19534.67 | Y | 94000 | Y | -94000 | 0 | 0 | 0 | 0 | 0 | 94000 | Y | -94000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -94000 | 0 | 12184.38 | 94000 | 0 | 0 | 0 | 2970.11 | 11191.16 | 0 | -94000 | 0 | 0 | 94000 | 94000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6430 | -6430 | 0 | LS | 0 | 53 | 32 | 85 | EA | 74465.33 | 4136.42 | 70328.91 | 19534.67 | Cost for small tools & consumables, and equipment will be coded to the respective project general codes. Small Tools - 9000-1240 (Small Tools & Supplies), and Equipment - 2000-1230 (Job Site Bare Equipment) & 2000- 1240 (Job Site Fuel & Maintenance), will place concrete and/or patching material cost here now, but will move at a later date
Y | IPCRP1-0000-0044-C | IPCRP1 | IPCRP1 | 0000-0044 | Install & Strip Forms for UHPC Joints | N | C |  | UNIT | U | 0 | 86660.77 | 86660.77 | 86660.77 | 86660.77 | 34.6643 | 0 | 0 | 0 | 163339.23 | Y | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14522 | -14522 | 0 | NA | 0 | 8061.1 | 9478.9 | 17540 | LF | 62123.92 | -24536.85 | 86660.77 | 163339.23
Y | IPCRP1-0000-0044-L | IPCRP1 | IPCRP1 | 0000-0044 | Install & Strip Forms for UHPC Joints | N | L |  | UNIT | P | 0 | 396430.55 | 396430.55 | 396430.55 | 396430.55 | 31.6726 | 0 | 0 | 0 | 855221.8 | Y | 1251652.35 | Y | -1251652.35 | 0 | 0 | 0 | 0 | 0 | 1251652.35 | Y | -1251652.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1251652.35 | 0 | 0 | 1251652.35 | 0 | 0 | 0 | 0 | 0 | 0 | -1251652.35 | 0 | 0 | 1251652.35 | 1251652.35 | 0 | 0 | 0 | 0 | 0 | 9628.38 | 9628.38 | 0 | 3145 | 6483.38 | 9628.38 | HR | 0 | 8061.1 | 9478.9 | 17540 | LF | 0 | 0 | 0 | 855221.8 | All SIP forms purchased & stored in CME yard, NJ
Y | IPCRP1-0000-0044-S | IPCRP1 | IPCRP1 | 0000-0044 | Install & Strip Forms for UHPC Joints | N | S |  | UNIT | A | 0 | 346991.77 | 346991.77 | 346991.77 | 346991.77 | 99.1405 | 0 | 0 | 0 | 3008.23 | Y | 350000 | Y | -350000 | 0 | 0 | 0 | 0 | 0 | 350000 | Y | -350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -350000 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | -350000 | 0 | 0 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 18 | -17 | 1 | NA | 0 | 8061.1 | 9478.9 | 17540 | LF | 346991.77 | 0 | 346991.77 | 3008.23
Y | IPCRP1-0000-0045-C | IPCRP1 | IPCRP1 | 0000-0045 | PM, UHPC Material w/ Tech Assistance | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11900 | Y | 11900 | Y | -11900 | 0 | 0 | 0 | 0 | 0 | 11900 | Y | -11900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11900 | 0 | 0 | 11900 | 0 | 0 | 0 | 0 | 0 | 0 | -11900 | 0 | 0 | 11900 | 11900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 182.45 | 220.55 | 403 | CY | 0 | 0 | 0 | 11900
Y | IPCRP1-0000-0045-L | IPCRP1 | IPCRP1 | 0000-0045 | PM, UHPC Material w/ Tech Assistance | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 182.45 | 220.55 | 403 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0045-M | IPCRP1 | IPCRP1 | 0000-0045 | PM, UHPC Material w/ Tech Assistance | N | M |  | UNIT | U | 0 | 1382343.15 | 1382343.15 | 649640.48 | 1382343.15 | 46.9956 | 0 | 0 | 0 | 0 | Y | 1382343.15 | Y | -1382343.15 | 0 | 0 | 0 | 0 | 0 | 1382343.15 | Y | -1382343.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1382343.15 | 0 | 0 | 1382343.15 | 0 | 0 | 0 | 0 | 0 | 0 | -1382343.15 | 0 | 0 | 1382343.15 | 1382343.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12900.15 | -12900.15 | 0 | NA | 0 | 182.45 | 220.55 | 403 | CY | 1382343.15 | 732702.67 | 649640.48 | 0 | ATLAS INDUSTRIES CO., INC. @$52,246.87 ,AUSTER RUBBER COMPANY @$5,835.70 ,HOLCIM (US) INC @$1,361,581.00 ,Grand Total @$1,419,663.57 (GO, 10/3/23) Change PMF (Mat) from $1,419,663.57 to $1,361,343.16 (to match Commitment)
Y | IPCRP1-0000-0046-C | IPCRP1 | IPCRP1 | 0000-0046 | Prep, Mix, Place & Cure UHPC Joints | N | C |  | UNIT | U | 0 | 8803.83 | 8803.83 | 8697.76 | 8803.83 | 98.7952 | 0 | 0 | 0 | 0 | Y | 8803.83 | Y | -8803.83 | 0 | 0 | 0 | 0 | 0 | 8803.83 | Y | -8803.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8803.83 | 0 | 0 | 8803.83 | 0 | 0 | 0 | 0 | 0 | 0 | -8803.83 | 0 | 0 | 8803.83 | 8803.83 | 0 | 0 | 0 | 0 | 0 | 880.89 | 880.89 | 0 | 972 | -91.11 | 880.89 | NA | 0 | 8061.1 | 9478.9 | 17540 | LF | 8803.83 | 106.07 | 8697.76 | 0
Y | IPCRP1-0000-0046-L | IPCRP1 | IPCRP1 | 0000-0046 | Prep, Mix, Place & Cure UHPC Joints | N | L |  | UNIT | P | 0 | 466764.35 | 466764.35 | 466764.35 | 466764.35 | 30.5781 | 0 | 0 | 0 | 1059701.41 | Y | 1526465.76 | Y | -1526465.76 | 0 | 0 | 0 | 0 | 0 | 1526465.76 | Y | -1526465.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1526465.76 | 0 | 0 | 1526465.76 | 0 | 0 | 0 | 0 | 0 | 0 | -1526465.76 | 0 | 0 | 1526465.76 | 1526465.76 | 0 | 0 | 0 | 0 | 0 | 11945.26 | 11945.26 | 0 | 3959 | 7986.26 | 11945.26 | HR | 0 | 8061.1 | 9478.9 | 17540 | LF | 0 | 0 | 0 | 1059701.41
Y | IPCRP1-0000-0046-S | IPCRP1 | IPCRP1 | 0000-0046 | Prep, Mix, Place & Cure UHPC Joints | N | S |  | UNIT | A | 0 | 4152.1 | 4152.1 | 4152.1 | 4152.1 | 125.329 | 0 | 0 | 0 | 0 | N | 3312.96 | N | -3312.96 | 0 | 0 | 0 | 0 | 0 | 3312.96 | N | -3312.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3312.96 | 0 | 0 | 3312.96 | 0 | 0 | 0 | 0 | 0 | 0 | -3312.96 | 0 | 0 | 3312.96 | 3312.96 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 0 | 35.5 | -6.5 | 29 | NA | 0 | 8061.1 | 9478.9 | 17540 | LF | 4152.1 | 0 | 4152.1 | 0
Y | IPCRP1-0000-0047-C | IPCRP1 | IPCRP1 | 0000-0047 | Set Esplanade PC Barrier | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 155 | 155 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0047-L | IPCRP1 | IPCRP1 | 0000-0047 | Set Esplanade PC Barrier | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 155 | 155 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0047-S | IPCRP1 | IPCRP1 | 0000-0047 | Set Esplanade PC Barrier | N | S |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 155 | 155 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0048-C | IPCRP1 | IPCRP1 | 0000-0048 | Form & Pour Lock Curb Adj to PC Barrier | N | C |  | UNIT | U | 0 | 4666.98 | 4666.98 | 4666.97 | 4666.98 | 99.9998 | 0 | 0 | 0 | 0 | Y | 4666.98 | Y | -4666.98 | 0 | 0 | 0 | 0 | 0 | 4666.98 | Y | -4666.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4666.98 | 0 | 0 | 4666.98 | 0 | 0 | 0 | 0 | 0 | 0 | -4666.98 | 0 | 0 | 4666.98 | 4666.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912 | -912 | 0 | NA | 0 | 2423.89 | 2316.58 | 4740.47 | LF | 4666.98 | 0.01 | 4666.97 | 0
Y | IPCRP1-0000-0048-E | IPCRP1 | IPCRP1 | 0000-0048 | Form & Pour Lock Curb Adj to PC Barrier | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 2423.89 | 2316.58 | 4740.47 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0048-L | IPCRP1 | IPCRP1 | 0000-0048 | Form & Pour Lock Curb Adj to PC Barrier | N | L |  | UNIT | P | 0 | 226585.23 | 226585.23 | 226585.23 | 226585.23 | 43.2758 | 0 | 0 | 0 | 296998.94 | Y | 523584.17 | Y | -523584.17 | 0 | 0 | 0 | 0 | 0 | 523584.17 | Y | -523584.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -523584.17 | 463.3 | 0 | 523584.17 | 0 | 0 | 0 | 0 | 0 | 0 | -523584.17 | 0 | 0 | 523584.17 | 523584.17 | 0 | 0 | 0 | 0 | 0 | 4055.18 | 4055.18 | 0 | 1908.5 | 2146.68 | 4055.18 | HR | 0 | 2423.89 | 2316.58 | 4740.47 | LF | 0 | 0 | 0 | 296998.94 | Curb dimensions are 15" x 15". Forms = 7,077 SF, Conc = 328 CY. Using 2SF/MH and 1.5MH/CY projects out to be 3,539 + 492 = 4,031 MH. Sub scope converted to self-perform in Jan-24.
Y | IPCRP1-0000-0048-M | IPCRP1 | IPCRP1 | 0000-0048 | Form & Pour Lock Curb Adj to PC Barrier | N | M |  | UNIT | U | 0 | 9059.19 | 9059.19 | 9041.53 | 9059.19 | 90.4153 | 0 | 0 | 0 | 940.81 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 841 | -841 | 0 | NA | 0 | 2423.89 | 2316.58 | 4740.47 | LF | 9059.19 | 17.66 | 9041.53 | 940.81
Y | IPCRP1-0000-0048-S | IPCRP1 | IPCRP1 | 0000-0048 | Form & Pour Lock Curb Adj to PC Barrier | N | S |  | UNIT | P | 0 | 129.1 | 129.1 | 129.1 | 129.1 | 12.91 | 0 | 0 | 0 | 870.9 | Y | 1000 | Y | -1000 | 0 | 0 | 0 | 0 | 0 | 1000 | Y | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 0 | LF | 0 | 2423.89 | 2316.58 | 4740.47 | LF | 129.1 | 0 | 129.1 | 870.9
Y | IPCRP1-0000-0060-L | IPCRP1 | IPCRP1 | 0000-0060 | Rem Roadway Excavate to Subgrade, VECP-06 | N | L |  | UNIT | P | 0 | 39575.98 | 39575.98 | 39575.98 | 39575.98 | 100 | 0 | 0 | 0 | 0 | Y | 39575.98 | Y | -39575.98 | 0 | 0 | 0 | 0 | 0 | 39575.98 | Y | -39575.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39575.98 | 0 | 0 | 39575.98 | 0 | 0 | 0 | 0 | 0 | 0 | -39575.98 | 0 | 0 | 39575.98 | 39575.98 | 0 | 0 | 0 | 0 | 0 | 293 | 293 | 0 | 293 | 0 | 293 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0060-S | IPCRP1 | IPCRP1 | 0000-0060 | Rem Roadway Excavate to Subgrade, VECP-06 | N | S |  | UNIT | A | 0 | 1168.52 | 1168.52 | 1168.52 | 1168.52 | 100 | 0 | 0 | 0 | 0 | N | 1168.52 | N | -1168.52 | 0 | 0 | 0 | 0 | 0 | 1168.52 | N | -1168.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1168.52 | 0 | 0 | 1168.52 | 0 | 0 | 0 | 0 | 0 | 0 | -1168.52 | 0 | 0 | 1168.52 | 1168.52 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 10 | NA | 0 | 1 | 0 | 1 | LS | 1168.52 | 0 | 1168.52 | 0
Y | IPCRP1-0000-0061-C | IPCRP1 | IPCRP1 | 0000-0061 | Perform Load Test (Lat, Comp, Ten), VECP-06 | N | C |  | UNIT | U | 0 | 9446.66 | 9446.66 | 9446.66 | 9446.66 | 100 | 0 | 0 | 0 | 0 | Y | 9446.66 | Y | -9446.66 | 0 | 0 | 0 | 0 | 0 | 9446.66 | Y | -9446.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9446.66 | 0 | 0 | 9446.66 | 0 | 0 | 0 | 0 | 0 | 0 | -9446.66 | 0 | 0 | 9446.66 | 9446.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.25 | -22.25 | 0 | NA | 0 | 3 | 0 | 3 | EA | 5719.56 | -3727.1 | 9446.66 | 0
Y | IPCRP1-0000-0061-L | IPCRP1 | IPCRP1 | 0000-0061 | Perform Load Test (Lat, Comp, Ten), VECP-06 | N | L |  | UNIT | P | 0 | 44705.01 | 44705.01 | 44705.01 | 44705.01 | 100 | 0 | 0 | 0 | 0 | Y | 44705.01 | Y | -44705.01 | 0 | 0 | 0 | 0 | 0 | 44705.01 | Y | -44705.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -44705.01 | 0 | 0 | 44705.01 | 0 | 0 | 0 | 0 | 0 | 0 | -44705.01 | 0 | 0 | 44705.01 | 44705.01 | 0 | 0 | 0 | 0 | 0 | 326 | 326 | 0 | 326 | 0 | 326 | HR | 0 | 3 | 0 | 3 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0062-C | IPCRP1 | IPCRP1 | 0000-0062 | Furn 12.75inx0.50in Steel Pipe Piles, VECP06 | N | C |  | UNIT | U | 0 | 39467.93 | 39467.93 | 39453.12 | 39467.93 | 100 | 0 | 0 | 0 | -14.81 | Y | 39453.12 | Y | -39453.12 | 0 | 0 | 0 | 0 | 0 | 39453.12 | Y | -39453.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39453.12 | 0 | 0 | 39453.12 | 0 | 0 | 0 | 0 | 0 | 0 | -39453.12 | 0 | 0 | 39453.12 | 39453.12 | 0 | 0 | 0 | 0 | 0 | 715 | 715 | 0 | 715 | 0 | 715 | NA | 0 | 76 | 0 | 76 | EA | 39467.93 | 14.81 | 39453.12 | -14.81
Y | IPCRP1-0000-0062-L | IPCRP1 | IPCRP1 | 0000-0062 | Furn 12.75inx0.50in Steel Pipe Piles, VECP06 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 76 | 0 | 76 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0062-M | IPCRP1 | IPCRP1 | 0000-0062 | Furn 12.75inx0.50in Steel Pipe Piles, VECP06 | N | M |  | UNIT | U | 0 | 400749.66 | 400749.66 | 400749.66 | 400749.66 | 100 | 0 | 0 | 0 | 0 | Y | 400749.66 | Y | -400749.66 | 0 | 0 | 0 | 0 | 0 | 400749.66 | Y | -400749.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -400749.66 | 0 | 0 | 400749.66 | 0 | 0 | 0 | 0 | 0 | 0 | -400749.66 | 0 | 0 | 400749.66 | 400749.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16148.85 | -16148.85 | 0 | NA | 0 | 76 | 0 | 76 | EA | 399831.42 | -3205.6 | 403037.02 | 0 | As per Rob D (12/6) $45,189.64 of this mat code belongs to 0000-0110 (VECP#12) & 0000-0112 (VCP#11), $32,097.95 belongs o 0000-0120 (VECP#14) & $13,600.83 belongs to 0348-1000 (JG/MP Sub AP&F)
Y | IPCRP1-0000-0063-C | IPCRP1 | IPCRP1 | 0000-0063 | Install 12.75in x 0.5in Steel Pipe Piles, VECP-06 | N | C |  | UNIT | U | 0 | 68013.29 | 68013.29 | 55829.62 | 68013.29 | 100 | 0 | 0 | 0 | -12183.67 | Y | 55829.62 | Y | -55829.62 | 0 | 0 | 0 | 0 | 0 | 55829.62 | Y | -55829.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -55829.62 | 0 | 0 | 55829.62 | 0 | 0 | 0 | 0 | 0 | 0 | -55829.62 | 0 | 0 | 55829.62 | 55829.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647 | -647 | 0 | NA | 0 | 76 | 0 | 76 | EA | 55132.28 | 12183.67 | 42948.61 | -12183.67
Y | IPCRP1-0000-0063-L | IPCRP1 | IPCRP1 | 0000-0063 | Install 12.75in x 0.5in Steel Pipe Piles, VECP-06 | N | L |  | UNIT | P | 0 | 594821.41 | 594821.41 | 594821.41 | 594821.41 | 100 | 0 | 0 | 0 | 0 | Y | 594821.41 | Y | -594821.41 | 0 | 0 | 0 | 0 | 0 | 594821.41 | Y | -594821.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -594821.41 | 0 | 0 | 594821.41 | 0 | 0 | 0 | 0 | 0 | 0 | -594821.41 | 0 | 0 | 594821.41 | 594821.41 | 0 | 0 | 0 | 0 | 0 | 4143.5 | 4143.5 | 0 | 4143.5 | 0 | 4143.5 | HR | 0 | 76 | 0 | 76 | EA | 0 | 0 | 0 | 0 | 76 piles are complete except for anchor plate and nuts. (Lloyd's email on 6/27/24). As per Lloyd (9/18) 9 man days remain (max) for final cut & inst plates/nuts
Y | IPCRP1-0000-0063-S | IPCRP1 | IPCRP1 | 0000-0063 | Install 12.75in x 0.5in Steel Pipe Piles, VECP-06 | N | S |  | UNIT | A | 0 | 7781.9 | 7781.9 | 7781.9 | 7781.9 | 100 | 0 | 0 | 0 | 0 | Y | 7781.9 | Y | -7781.9 | 0 | 0 | 0 | 0 | 0 | 7781.9 | Y | -7781.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7781.9 | 0 | 0 | 7781.9 | 0 | 0 | 0 | 0 | 0 | 0 | -7781.9 | 0 | 0 | 7781.9 | 7781.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.5 | -68.5 | 0 | NA | 0 | 76 | 0 | 76 | EA | 7781.9 | 0 | 7781.9 | 0
Y | IPCRP1-0000-0064-L | IPCRP1 | IPCRP1 | 0000-0064 | Furn Steel Sheeting, VECP-06 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0.01 | HR | 0 | 4028 | 0 | 4028 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0064-M | IPCRP1 | IPCRP1 | 0000-0064 | Furn Steel Sheeting, VECP-06 | N | M |  | UNIT | U | 0 | 101559.81 | 101559.81 | 101559.81 | 101559.81 | 100 | 0 | 0 | 0 | 0 | Y | 101559.81 | Y | -101559.81 | 0 | 0 | 0 | 0 | 0 | 101559.81 | Y | -101559.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -101559.81 | 0 | 0 | 101559.81 | 0 | 0 | 0 | 0 | 0 | 0 | -101559.81 | 0 | 0 | 101559.81 | 101559.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 4028 | 0 | 4028 | SF | 98741.05 | -2818.76 | 101559.81 | 0 | Skyline ($89,845.95), GMS Piling ($8,895.10) Change PMF (Mat) from $115,371.00 to $89,845.95 (matching Commitment)
Y | IPCRP1-0000-0065-L | IPCRP1 | IPCRP1 | 0000-0065 | Install Steel Sheeting, VECP-06 | N | L |  | UNIT | P | 0 | 78636.34 | 78636.34 | 78636.34 | 78636.34 | 100 | 0 | 0 | 0 | 0 | Y | 78636.34 | Y | -78636.34 | 0 | 0 | 0 | 0 | 0 | 78636.34 | Y | -78636.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -78636.34 | 0 | 0 | 78636.34 | 0 | 0 | 0 | 0 | 0 | 0 | -78636.34 | 0 | 0 | 78636.34 | 78636.34 | 0 | 0 | 0 | 0 | 0 | 546 | 546 | 0 | 546 | 0 | 546 | HR | 0 | 4857 | 0 | 4857 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0065-S | IPCRP1 | IPCRP1 | 0000-0065 | Install Steel Sheeting, VECP-06 | N | S |  | UNIT | A | 0 | 701.11 | 701.11 | 701.11 | 701.11 | 100 | 0 | 0 | 0 | 0 | N | 701.11 | N | -701.11 | 0 | 0 | 0 | 0 | 0 | 701.11 | N | -701.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -701.11 | 0 | 0 | 701.11 | 0 | 0 | 0 | 0 | 0 | 0 | -701.11 | 0 | 0 | 701.11 | 701.11 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 0 | 4857 | 0 | 4857 | LF | 701.11 | 0 | 701.11 | 0
Y | IPCRP1-0000-0066-L | IPCRP1 | IPCRP1 | 0000-0066 | Furn & Install Jet Grout, VECP-06 | N | L |  | UNIT | P | 0 | 3323.72 | 3323.72 | 3323.72 | 3323.72 | 100 | 0 | 0 | 0 | 0 | Y | 3323.72 | Y | -3323.72 | 0 | 0 | 0 | 0 | 0 | 3323.72 | Y | -3323.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3323.72 | 0 | 0 | 3323.72 | 0 | 0 | 0 | 0 | 0 | 0 | -3323.72 | 0 | 0 | 3323.72 | 3323.72 | 0 | 0 | 0 | 0 | 0 | 23.5 | 23.5 | 0 | 23.5 | 0 | 23.5 | HR | 0 | 235 | 0 | 235 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0066-S | IPCRP1 | IPCRP1 | 0000-0066 | Furn & Install Jet Grout, VECP-06 | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 235 | 0 | 235 | CY | 0 | 0 | 0 | 0 | Sub costs included in cc: 0138-1000 (Jet Grout Sub - Atlantic Pile)
Y | IPCRP1-0000-0067-C | IPCRP1 | IPCRP1 | 0000-0067 | Form & Strip for Floodwall, VECP-06 | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 4658.26 | 0 | 4658.26 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0067-L | IPCRP1 | IPCRP1 | 0000-0067 | Form & Strip for Floodwall, VECP-06 | N | L |  | UNIT | P | 0 | 261820.45 | 261820.45 | 261820.45 | 261820.45 | 100 | 0 | 0 | 0 | 0 | Y | 261820.45 | Y | -261820.45 | 0 | 0 | 0 | 0 | 0 | 261820.45 | Y | -261820.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -261820.45 | 0 | 0 | 261820.45 | 0 | 0 | 0 | 0 | 0 | 0 | -261820.45 | 0 | 0 | 261820.45 | 261820.45 | 0 | 0 | 0 | 0 | 0 | 1943 | 1943 | 0 | 1943 | 0 | 1943 | HR | 0 | 4658.26 | 0 | 4658.26 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0067-S | IPCRP1 | IPCRP1 | 0000-0067 | Form & Strip for Floodwall, VECP-06 | N | S |  | UNIT | A | 0 | 1678.28 | 1678.28 | 1678.28 | 1678.28 | 100 | 0 | 0 | 0 | 0 | N | 1678.28 | N | -1678.28 | 0 | 0 | 0 | 0 | 0 | 1678.28 | N | -1678.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1678.28 | 0 | 0 | 1678.28 | 0 | 0 | 0 | 0 | 0 | 0 | -1678.28 | 0 | 0 | 1678.28 | 1678.28 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 13 | 0 | 13 | NA | 0 | 4658.26 | 0 | 4658.26 | SF | 1678.28 | 0 | 1678.28 | 0
Y | IPCRP1-0000-0068-L | IPCRP1 | IPCRP1 | 0000-0068 | Pour Concrete for Floodwall, VECP-06 | N | L |  | UNIT | P | 0 | 60002.01 | 60002.01 | 60002.01 | 60002.01 | 100 | 0 | 0 | 0 | 0 | Y | 60002.01 | Y | -60002.01 | 0 | 0 | 0 | 0 | 0 | 60002.01 | Y | -60002.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60002.01 | 0 | 0 | 60002.01 | 0 | 0 | 0 | 0 | 0 | 0 | -60002.01 | 0 | 0 | 60002.01 | 60002.01 | 0 | 0 | 0 | 0 | 0 | 466 | 466 | 0 | 466 | 0 | 466 | HR | 0 | 520.01 | 0 | 520.01 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0068-S | IPCRP1 | IPCRP1 | 0000-0068 | Pour Concrete for Floodwall, VECP-06 | N | S |  | UNIT | A | 0 | 1327.87 | 1327.87 | 1327.87 | 1327.87 | 100 | 0 | 0 | 0 | 0 | N | 1327.87 | N | -1327.87 | 0 | 0 | 0 | 0 | 0 | 1327.87 | N | -1327.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1327.87 | 0 | 0 | 1327.87 | 0 | 0 | 0 | 0 | 0 | 0 | -1327.87 | 0 | 0 | 1327.87 | 1327.87 | 0 | 0 | 0 | 0 | 0 | 10.5 | 10.5 | 0 | 10.5 | 0 | 10.5 | NA | 0 | 520.01 | 0 | 520.01 | CY | 1327.87 | 0 | 1327.87 | 0
Y | IPCRP1-0000-0069-L | IPCRP1 | IPCRP1 | 0000-0069 | Backfill at Floodwall, VECP-06 | N | L |  | UNIT | P | 0 | 12077.38 | 12077.38 | 12077.38 | 12077.38 | 100 | 0 | 0 | 0 | 0 | Y | 12077.38 | Y | -12077.38 | 0 | 0 | 0 | 0 | 0 | 12077.38 | Y | -12077.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12077.38 | 0 | 0 | 12077.38 | 0 | 0 | 0 | 0 | 0 | 0 | -12077.38 | 0 | 0 | 12077.38 | 12077.38 | 0 | 0 | 0 | 0 | 0 | 93.5 | 93.5 | 0 | 93.5 | 0 | 93.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0069-S | IPCRP1 | IPCRP1 | 0000-0069 | Backfill at Floodwall, VECP-06 | N | S |  | UNIT | A | 0 | 4674.16 | 4674.16 | 4674.16 | 4674.16 | 100 | 0 | 0 | 0 | 0 | N | 4674.16 | N | -4674.16 | 0 | 0 | 0 | 0 | 0 | 4674.16 | N | -4674.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4674.16 | 0 | 0 | 4674.16 | 0 | 0 | 0 | 0 | 0 | 0 | -4674.16 | 0 | 0 | 4674.16 | 4674.16 | 0 | 0 | 0 | 0 | 0 | 37 | 37 | 0 | 37 | 0 | 37 | NA | 0 | 1 | 0 | 1 | LS | 4674.16 | 0 | 4674.16 | 0
Y | IPCRP1-0000-0070-L | IPCRP1 | IPCRP1 | 0000-0070 | Roadway Restoration, VECP-06 | N | L |  | UNIT | P | 0 | 9361.07 | 9361.07 | 9361.07 | 9361.07 | 100 | 0 | 0 | 0 | 0 | Y | 9361.07 | Y | -9361.07 | 0 | 0 | 0 | 0 | 0 | 9361.07 | Y | -9361.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9361.07 | 0 | 0 | 9361.07 | 0 | 0 | 0 | 0 | 0 | 0 | -9361.07 | 0 | 0 | 9361.07 | 9361.07 | 0 | 0 | 0 | 0 | 0 | 70.5 | 70.5 | 0 | 70.5 | 0 | 70.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0070-S | IPCRP1 | IPCRP1 | 0000-0070 | Roadway Restoration, VECP-06 | N | S |  | UNIT | A | 0 | 1678.28 | 1678.28 | 1678.28 | 1678.28 | 100 | 0 | 0 | 0 | 0 | Y | 1678.28 | Y | -1678.28 | 0 | 0 | 0 | 0 | 0 | 1678.28 | Y | -1678.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1678.28 | 0 | 0 | 1678.28 | 0 | 0 | 0 | 0 | 0 | 0 | -1678.28 | 0 | 0 | 1678.28 | 1678.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | -13 | 0 | NA | 0 | 1 | 0 | 1 | LS | 1678.28 | 0 | 1678.28 | 0
Y | IPCRP1-0000-0075-C | IPCRP1 | IPCRP1 | 0000-0075 | Support for DDC Art Work | N | C |  | UNIT | U | 0 | 1831.12 | 1831.12 | 1831.12 | 1831.12 | 100 | 0 | 0 | 0 | 0 | Y | 1831.12 | Y | -1831.12 | 0 | 0 | 0 | 0 | 0 | 1831.12 | Y | -1831.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1831.12 | 0 | 0 | 1831.12 | 0 | 0 | 0 | 0 | 0 | 0 | -1831.12 | 0 | 0 | 1831.12 | 1831.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2316 | -2316 | 0 | NA | 0 | 1 | 0 | 1 | LS | 1831.12 | 0 | 1831.12 | 0
Y | IPCRP1-0000-0075-E | IPCRP1 | IPCRP1 | 0000-0075 | Support for DDC Art Work | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0075-L | IPCRP1 | IPCRP1 | 0000-0075 | Support for DDC Art Work | N | L |  | UNIT | P | 0 | 31836.81 | 31836.81 | 31836.81 | 31836.81 | 100 | 0 | 0 | 0 | 0 | Y | 31836.81 | Y | -31836.81 | 0 | 0 | 0 | 0 | 0 | 31836.81 | Y | -31836.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31836.81 | 0 | 0 | 31836.81 | 0 | 0 | 0 | 0 | 0 | 0 | -31836.81 | 0 | 0 | 31836.81 | 31836.81 | 0 | 0 | 0 | 0 | 0 | 301 | 301 | 0 | 301 | 0 | 301 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Paid for under iten 9.06 HW (seq #333) Allowance for Decorative Mesh Fabric, Paid $69,411.63 in Dec 2023
Y | IPCRP1-0000-0075-M | IPCRP1 | IPCRP1 | 0000-0075 | Support for DDC Art Work | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0075-S | IPCRP1 | IPCRP1 | 0000-0075 | Support for DDC Art Work | N | S |  | UNIT | A | 0 | 1281.76 | 1281.76 | 1281.76 | 1281.76 | 100 | 0 | 0 | 0 | 0 | Y | 1281.76 | Y | -1281.76 | 0 | 0 | 0 | 0 | 0 | 1281.76 | Y | -1281.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1281.76 | 0 | 0 | 1281.76 | 0 | 0 | 0 | 0 | 0 | 0 | -1281.76 | 0 | 0 | 1281.76 | 1281.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | -11 | 0 | NA | 0 | 1 | 0 | 1 | LS | 1281.76 | 0 | 1281.76 | 0
Y | IPCRP1-0000-0080-C | IPCRP1 | IPCRP1 | 0000-0080 | Sheeting/Backfill at NYCHA Utility E10th | N | C |  | UNIT | U | 0 | 1502.28 | 1502.28 | 1502.28 | 1502.28 | 100 | 0 | 0 | 0 | 0 | N | 1502.28 | N | -1502.28 | 0 | 0 | 0 | 0 | 0 | 1502.28 | N | -1502.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1502.28 | 0 | 0 | 1502.28 | 0 | 0 | 0 | 0 | 0 | 0 | -1502.28 | 0 | 0 | 1502.28 | 1502.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 0 | 8 | 0 | 8 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0080-L | IPCRP1 | IPCRP1 | 0000-0080 | Sheeting/Backfill at NYCHA Utility E10th | N | L |  | UNIT | P | 0 | 175084.24 | 175084.24 | 175084.24 | 175084.24 | 100 | 0 | 0 | 0 | 0 | Y | 175084.24 | Y | -175084.24 | 0 | 0 | 0 | 0 | 0 | 175084.24 | Y | -175084.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -175084.24 | 0 | 0 | 175084.24 | 0 | 0 | 0 | 0 | 0 | 0 | -175084.24 | 0 | 0 | 175084.24 | 175084.24 | 0 | 0 | 0 | 0 | 0 | 1303 | 1303 | 0 | 1303 | 0 | 1303 | HR | 0 | 8 | 0 | 8 | EA | 0 | 0 | 0 | 0 | Included in LS portion of DDC CO#20 (PCO#73). DDC included 5.0ea in our LS Payment (& paid entire LS in Feb 2024 CO PP). We are tracking & doing 8.0ea DDC CO#20 (PCO#73)
Y | IPCRP1-0000-0080-M | IPCRP1 | IPCRP1 | 0000-0080 | Sheeting/Backfill at NYCHA Utility E10th | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 8 | 0 | 8 | EA | 0 | 0 | 0 | 0 | CO/extra work
Y | IPCRP1-0000-0080-S | IPCRP1 | IPCRP1 | 0000-0080 | Sheeting/Backfill at NYCHA Utility E10th | N | S |  | UNIT | A | 0 | 11441.73 | 11441.73 | 11441.73 | 11441.73 | 100 | 0 | 0 | 0 | 0 | N | 11441.73 | N | -11441.73 | 0 | 0 | 0 | 0 | 0 | 11441.73 | N | -11441.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11441.73 | 0 | 0 | 11441.73 | 0 | 0 | 0 | 0 | 0 | 0 | -11441.73 | 0 | 0 | 11441.73 | 11441.73 | 0 | 0 | 0 | 0 | 0 | 97 | 97 | 0 | 97 | 0 | 97 | NA | 0 | 8 | 0 | 8 | EA | 11441.73 | 0 | 11441.73 | 0
Y | IPCRP1-0000-0081-L | IPCRP1 | IPCRP1 | 0000-0081 | Demo & Replace NYCHA MH Structures E10th | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 10 | Included in LS portion of DDC CO#20 (PCO#73). DDC CO#20 (PCO#73)
Y | IPCRP1-0000-0081-M | IPCRP1 | IPCRP1 | 0000-0081 | Demo & Replace NYCHA MH Structures E10th | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | DDC CO#20 (PCO#73)
Y | IPCRP1-0000-0082-L | IPCRP1 | IPCRP1 | 0000-0082 | Fluming/Dewatering (T&M) for NYCHA Utility, E10th | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | $ | 0 | 0 | 0 | 0 | CO/extra work
Y | IPCRP1-0000-0083-L | IPCRP1 | IPCRP1 | 0000-0083 | Remove Exist St Sheeting at MH#2 (Extra Work) | N | L |  | UNIT | P | 0 | 90433.41 | 90433.41 | 90433.41 | 90433.41 | 100 | 0 | 0 | 0 | 0 | Y | 90433.41 | Y | -90433.41 | 0 | 0 | 0 | 0 | 0 | 90433.41 | Y | -90433.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -90433.41 | 0 | 0 | 90433.41 | 0 | 0 | 0 | 0 | 0 | 0 | -90433.41 | 0 | 0 | 90433.41 | 90433.41 | 0 | 0 | 0 | 0 | 0 | 717 | 717 | 0 | 717 | 0 | 717 | HR | 0 | 717 | 0 | 717 | HR | 0 | 0 | 0 | 0 | Final Payment = $127,078.69 10th Street and Ave D extra work. PCO#140, acknowledged to proceed under T&M in Targeted Issue Meeting Agenda 1/16 & 1/23/24.
Y | IPCRP1-0000-0083-S | IPCRP1 | IPCRP1 | 0000-0083 | Remove Exist St Sheeting at MH#2 (Extra Work) | N | S |  | UNIT | A | 0 | 5881.84 | 5881.84 | 5881.84 | 5881.84 | 100 | 0 | 0 | 0 | 0 | Y | 5881.84 | Y | -5881.84 | 0 | 0 | 0 | 0 | 0 | 5881.84 | Y | -5881.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5881.84 | 0 | 0 | 5881.84 | 0 | 0 | 0 | 0 | 0 | 0 | -5881.84 | 0 | 0 | 5881.84 | 5881.84 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 0 | 52 | 0 | 52 | NA | 0 | 717 | 0 | 717 | HR | 5881.84 | 0 | 5881.84 | 0
Y | IPCRP1-0000-0085-C | IPCRP1 | IPCRP1 | 0000-0085 | Temp Decking (Item 70.21) for PC Sewer | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0085-L | IPCRP1 | IPCRP1 | 0000-0085 | Temp Decking (Item 70.21) for PC Sewer | N | L |  | UNIT | P | 0 | 196733.3 | 196733.3 | 196733.3 | 196733.3 | 100 | 0 | 0 | 0 | 0 | Y | 196733.3 | Y | -196733.3 | 0 | 0 | 0 | 0 | 0 | 196733.3 | Y | -196733.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -196733.3 | 0 | 0 | 196733.3 | 0 | 0 | 0 | 0 | 0 | 0 | -196733.3 | 0 | 0 | 196733.3 | 196733.3 | 0 | 0 | 0 | 0 | 0 | 1368 | 1368 | 0 | 1368 | 0 | 1368 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#115, neg price $142,380.00. DDC CO #33
Y | IPCRP1-0000-0085-S | IPCRP1 | IPCRP1 | 0000-0085 | Temp Decking (Item 70.21) for PC Sewer | N | S |  | UNIT | A | 0 | 910.58 | 910.58 | 910.58 | 910.58 | 100 | 0 | 0 | 0 | 0 | N | 910.58 | N | -910.58 | 0 | 0 | 0 | 0 | 0 | 910.58 | N | -910.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -910.58 | 0 | 0 | 910.58 | 0 | 0 | 0 | 0 | 0 | 0 | -910.58 | 0 | 0 | 910.58 | 910.58 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 0 | 1 | 0 | 1 | LS | 910.58 | 0 | 910.58 | 0
Y | IPCRP1-0000-0090-L | IPCRP1 | IPCRP1 | 0000-0090 | Temp Decking at Delancey St West for Temp Driveway | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | CO/extra work
Y | IPCRP1-0000-0095-C | IPCRP1 | IPCRP1 | 0000-0095 | Removal of UG Storage Tank at Houston St | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0095-E | IPCRP1 | IPCRP1 | 0000-0095 | Removal of UG Storage Tank at Houston St | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0095-L | IPCRP1 | IPCRP1 | 0000-0095 | Removal of UG Storage Tank at Houston St | N | L |  | UNIT | P | 0 | 30258.04 | 30258.04 | 30258.04 | 30258.04 | 100 | 0 | 0 | 0 | 0 | Y | 30258.04 | Y | -30258.04 | 0 | 0 | 0 | 0 | 0 | 30258.04 | Y | -30258.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30258.04 | 0 | 0 | 30258.04 | 0 | 0 | 0 | 0 | 0 | 0 | -30258.04 | 0 | 0 | 30258.04 | 30258.04 | 0 | 0 | 0 | 0 | 0 | 209.5 | 209.5 | 0 | 209.5 | 0 | 209.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Final Payment = $72,426.40 PCO #123, will be paid for under T&M. Miller Environmental ($24,875.45), AES ($7,200.00) KMA ($913.16)
Y | IPCRP1-0000-0095-M | IPCRP1 | IPCRP1 | 0000-0095 | Removal of UG Storage Tank at Houston St | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0095-S | IPCRP1 | IPCRP1 | 0000-0095 | Removal of UG Storage Tank at Houston St | N | S |  | UNIT | A | 0 | 32988.61 | 32988.61 | 32988.61 | 32988.61 | 100 | 0 | 0 | 0 | 0 | Y | 32988.61 | Y | -32988.61 | 0 | 0 | 0 | 0 | 0 | 32988.61 | Y | -32988.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32988.61 | 0 | 0 | 32988.61 | 0 | 0 | 0 | 0 | 0 | 0 | -32988.61 | 0 | 0 | 32988.61 | 32988.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | -13 | 0 | NA | 0 | 1 | 0 | 1 | LS | 32988.61 | 0 | 32988.61 | 0
Y | IPCRP1-0000-0098-C | IPCRP1 | IPCRP1 | 0000-0098 | Coastal Resiliency, Winter Storm Costs | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0098-E | IPCRP1 | IPCRP1 | 0000-0098 | Coastal Resiliency, Winter Storm Costs | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0098-L | IPCRP1 | IPCRP1 | 0000-0098 | Coastal Resiliency, Winter Storm Costs | N | L |  | UNIT | P | 0 | 36.97 | 36.97 | 36.97 | 36.97 | 28.4385 | 0 | 0 | 0 | 93.03 | Y | 130 | Y | -130 | 0 | 0 | 0 | 0 | 0 | 130 | Y | -130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | -130 | 0 | 0 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 93.03 | PCO#142, created & used only if DDC authorizes work.
Y | IPCRP1-0000-0098-M | IPCRP1 | IPCRP1 | 0000-0098 | Coastal Resiliency, Winter Storm Costs | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0098-S | IPCRP1 | IPCRP1 | 0000-0098 | Coastal Resiliency, Winter Storm Costs | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0100-C | IPCRP1 | IPCRP1 | 0000-0100 | Sewer House Conn at NYCHA Bldg #9 (PCO#144) | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0100-E | IPCRP1 | IPCRP1 | 0000-0100 | Sewer House Conn at NYCHA Bldg #9 (PCO#144) | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0100-L | IPCRP1 | IPCRP1 | 0000-0100 | Sewer House Conn at NYCHA Bldg #9 (PCO#144) | N | L |  | UNIT | P | 0 | 49720.11 | 49720.11 | 49720.11 | 49720.11 | 100 | 0 | 0 | 0 | 0 | Y | 49720.11 | Y | -49720.11 | 0 | 0 | 0 | 0 | 0 | 49720.11 | Y | -49720.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -49720.11 | 0 | 0 | 49720.11 | 0 | 0 | 0 | 0 | 0 | 0 | -49720.11 | 0 | 0 | 49720.11 | 49720.11 | 0 | 0 | 0 | 0 | 0 | 394 | 394 | 0 | 394 | 0 | 394 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | Work paid under contract item 52.11D12 - 12" DIP. DDC paid 89.0' (Sep 25) & 48.0' (Oct 25), 137' total, $102,750.00 Add NOTE: PCO #144, sub R1, 3/22/24, $89,252.46. DDC will instruct us to do under T&M DDC paid 89.0' in Sep 25 and 48.0' in Oct 25 (137', $102,750 total)
Y | IPCRP1-0000-0100-M | IPCRP1 | IPCRP1 | 0000-0100 | Sewer House Conn at NYCHA Bldg #9 (PCO#144) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0100-S | IPCRP1 | IPCRP1 | 0000-0100 | Sewer House Conn at NYCHA Bldg #9 (PCO#144) | N | S |  | UNIT | A | 0 | 5671.35 | 5671.35 | 5671.35 | 5671.35 | 100 | 0 | 0 | 0 | 0 | Y | 5671.35 | Y | -5671.35 | 0 | 0 | 0 | 0 | 0 | 5671.35 | Y | -5671.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5671.35 | 0 | 0 | 5671.35 | 0 | 0 | 0 | 0 | 0 | 0 | -5671.35 | 0 | 0 | 5671.35 | 5671.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | -46 | 0 | NA | 0 | 0 | 1 | 1 | LS | 5671.35 | 0 | 5671.35 | 0
Y | IPCRP1-0000-0105-C | IPCRP1 | IPCRP1 | 0000-0105 | CF Wrap, Part 3 (Jackson St), Excavate & Sheet | N | C |  | UNIT | U | 0 | 8344.17 | 8344.17 | 8344.17 | 8344.17 | 100 | 0 | 0 | 0 | 0 | Y | 8344.17 | Y | -8344.17 | 0 | 0 | 0 | 0 | 0 | 8344.17 | Y | -8344.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8344.17 | 0 | 0 | 8344.17 | 0 | 0 | 0 | 0 | 0 | 0 | -8344.17 | 0 | 0 | 8344.17 | 8344.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | -241 | 0 | NA | 0 | 160 | 0 | 160 | LF | 8344.17 | 0 | 8344.17 | 0
Y | IPCRP1-0000-0105-L | IPCRP1 | IPCRP1 | 0000-0105 | CF Wrap, Part 3 (Jackson St), Excavate & Sheet | N | L |  | UNIT | P | 0 | 47980.54 | 47980.54 | 47980.54 | 47980.54 | 100 | 0 | 0 | 0 | 0 | Y | 47980.54 | Y | -47980.54 | 0 | 0 | 0 | 0 | 0 | 47980.54 | Y | -47980.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -47980.54 | 0 | 0 | 47980.54 | 0 | 0 | 0 | 0 | 0 | 0 | -47980.54 | 0 | 0 | 47980.54 | 47980.54 | 0 | 0 | 0 | 0 | 0 | 382 | 382 | 0 | 382 | 0 | 382 | HR | 0 | 160 | 0 | 160 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0105-S | IPCRP1 | IPCRP1 | 0000-0105 | CF Wrap, Part 3 (Jackson St), Excavate & Sheet | N | S |  | UNIT | A | 0 | 5529.93 | 5529.93 | 5529.93 | 5529.93 | 100 | 0 | 0 | 0 | 0 | Y | 5529.93 | Y | -5529.93 | 0 | 0 | 0 | 0 | 0 | 5529.93 | Y | -5529.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5529.93 | 0 | 0 | 5529.93 | 0 | 0 | 0 | 0 | 0 | 0 | -5529.93 | 0 | 0 | 5529.93 | 5529.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | -49 | 0 | NA | 0 | 160 | 0 | 160 | LF | 5529.93 | 0 | 5529.93 | 0
Y | IPCRP1-0000-0106-L | IPCRP1 | IPCRP1 | 0000-0106 | CF Wrap, Part 3 (Jackson St), Backfill & Pull Shee | N | L |  | UNIT | P | 0 | 7404.4 | 7404.4 | 7404.4 | 7404.4 | 100 | 0 | 0 | 0 | 0 | Y | 7404.4 | Y | -7404.4 | 0 | 0 | 0 | 0 | 0 | 7404.4 | Y | -7404.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7404.4 | 0 | 0 | 7404.4 | 0 | 0 | 0 | 0 | 0 | 0 | -7404.4 | 0 | 0 | 7404.4 | 7404.4 | 0 | 0 | 0 | 0 | 0 | 58 | 58 | 0 | 58 | 0 | 58 | HR | 0 | 160 | 0 | 160 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0106-M | IPCRP1 | IPCRP1 | 0000-0106 | CF Wrap, Part 3 (Jackson St), Backfill & Pull Shee | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 160 | 0 | 160 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0106-S | IPCRP1 | IPCRP1 | 0000-0106 | CF Wrap, Part 3 (Jackson St), Backfill & Pull Shee | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 160 | 0 | 160 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0107-L | IPCRP1 | IPCRP1 | 0000-0107 | CF Wrap, Part 3 (Jackson St), Work at MH, Sta 21+5 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0107-S | IPCRP1 | IPCRP1 | 0000-0107 | CF Wrap, Part 3 (Jackson St), Work at MH, Sta 21+5 | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0108-L | IPCRP1 | IPCRP1 | 0000-0108 | CF Wrap, Part 3 (Jackson St) CTI Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 30 | 0 | 30 | SH | 0 | 0 | 0 | 0 | Includes both CTI work ($1,109,081.00) and Pinnacle Env work ($69,500.00)
Y | IPCRP1-0000-0108-S | IPCRP1 | IPCRP1 | 0000-0108 | CF Wrap, Part 3 (Jackson St) CTI Support | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 30 | 0 | 30 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0109-L | IPCRP1 | IPCRP1 | 0000-0109 | CF Wrap, Part 3 (Jackson St) CTI Work | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Includes both CTI work ($1,109,081.00) and Pinnacle Env work ($69,500.00)
Y | IPCRP1-0000-0109-S | IPCRP1 | IPCRP1 | 0000-0109 | CF Wrap, Part 3 (Jackson St) CTI Work | N | S |  | UNIT | A | 0 | 1178581 | 1178581 | 1178580.96 | 1178581 | 100 | 0 | 0 | 0 | -0.04 | Y | 1178580.96 | Y | -1178580.96 | 0 | 0 | 0 | 0 | 0 | 1178580.96 | Y | -1178580.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1178580.96 | 0 | 0 | 1178580.96 | 0 | 0 | 0 | 0 | 0 | 0 | -1178580.96 | 0 | 0 | 1178580.96 | 1178580.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69832 | -69832 | 0 | LS | 0 | 1 | 0 | 1 | LS | 1178581 | 0.04 | 1178580.96 | -0.04 | Includes both CTI work ($1,109,081.00) and Pinnacle Env work ($69,500.00)
Y | IPCRP1-0000-0110-L | IPCRP1 | IPCRP1 | 0000-0110 | PM for MP in VECP #12 (Montgomery St) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 576 | 0 | 576 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0110-M | IPCRP1 | IPCRP1 | 0000-0110 | PM for MP in VECP #12 (Montgomery St) | N | M |  | UNIT | U | 0 | 16609.79 | 16609.79 | 16609.79 | 16609.79 | 100 | 0 | 0 | 0 | 0 | Y | 16609.79 | Y | -16609.79 | 0 | 0 | 0 | 0 | 0 | 16609.79 | Y | -16609.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16609.79 | 0 | 0 | 16609.79 | 0 | 0 | 0 | 0 | 0 | 0 | -16609.79 | 0 | 0 | 16609.79 | 16609.79 | 0 | 0 | 0 | 0 | 0 | 715 | 715 | 0 | 2515 | -1800 | 715 | NA | 0 | 576 | 0 | 576 | LF | 6278.4 | -157.83 | 6436.23 | 0 | Some Mat purchased was charged to 0000-0062 (VECP#6).
Y | IPCRP1-0000-0111-L | IPCRP1 | IPCRP1 | 0000-0111 | Install MP in VECP 12 (Montgomery St) | N | L |  | UNIT | P | 0 | 85750.21 | 85750.21 | 85750.21 | 85750.21 | 100 | 0 | 0 | 0 | 0 | N | 85750.21 | N | -85750.21 | 0 | 0 | 0 | 0 | 0 | 85750.21 | N | -85750.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -85750.21 | 0 | 0 | 85750.21 | 0 | 0 | 0 | 0 | 0 | 0 | -85750.21 | 0 | 0 | 85750.21 | 85750.21 | 0 | 0 | 0 | 0 | 0 | 582 | 582 | 0 | 582 | 0 | 582 | HR | 0 | 576 | 0 | 576 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0111-S | IPCRP1 | IPCRP1 | 0000-0111 | Install MP in VECP 12 (Montgomery St) | N | S |  | UNIT | A | 0 | 188.19 | 188.19 | 188.19 | 188.19 | 100 | 0 | 0 | 0 | 0 | N | 188.19 | N | -188.19 | 0 | 0 | 0 | 0 | 0 | 188.19 | N | -188.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -188.19 | 0 | 0 | 188.19 | 0 | 0 | 0 | 0 | 0 | 0 | -188.19 | 0 | 0 | 188.19 | 188.19 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 1.5 | 0 | 1.5 | NA | 0 | 576 | 0 | 576 | LF | 188.19 | 0 | 188.19 | 0
Y | IPCRP1-0000-0112-L | IPCRP1 | IPCRP1 | 0000-0112 | PM for MP in VECP #11 (Reach B near CE Vault) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1110 | 0 | 1110 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0112-M | IPCRP1 | IPCRP1 | 0000-0112 | PM for MP in VECP #11 (Reach B near CE Vault) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1110 | 0 | 1110 | LF | 0 | 0 | 0 | 1 | Some Mat purchased was charged to 0000-0062 (VECP#6).
Y | IPCRP1-0000-0112-S | IPCRP1 | IPCRP1 | 0000-0112 | PM for MP in VECP #11 (Reach B near CE Vault) | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1110 | 0 | 1110 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0113-L | IPCRP1 | IPCRP1 | 0000-0113 | Install MP in VECP #11 (Reach B near CE Vault) | N | L |  | UNIT | P | 0 | 149581.93 | 149581.93 | 149581.93 | 149581.93 | 100 | 0 | 0 | 0 | 0 | Y | 149581.93 | Y | -149581.93 | 0 | 0 | 0 | 0 | 0 | 149581.93 | Y | -149581.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -149581.93 | 0 | 1918.24 | 149581.93 | 0 | 0 | 0 | 0 | 0 | 0 | -149581.93 | 0 | 0 | 149581.93 | 149581.93 | 0 | 0 | 0 | 0 | 0 | 916 | 916 | 0 | 916 | 0 | 916 | HR | 0 | 1110 | 0 | 1110 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0113-M | IPCRP1 | IPCRP1 | 0000-0113 | Install MP in VECP #11 (Reach B near CE Vault) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1110 | 0 | 1110 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0113-S | IPCRP1 | IPCRP1 | 0000-0113 | Install MP in VECP #11 (Reach B near CE Vault) | N | S |  | UNIT | A | 0 | 998.44 | 998.44 | 998.44 | 998.44 | 100 | 0 | 0 | 0 | 0 | Y | 998.44 | Y | -998.44 | 0 | 0 | 0 | 0 | 0 | 998.44 | Y | -998.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -998.44 | 0 | 0 | 998.44 | 0 | 0 | 0 | 0 | 0 | 0 | -998.44 | 0 | 0 | 998.44 | 998.44 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 8 | -2 | 6 | NA | 0 | 1110 | 0 | 1110 | LF | 998.44 | 0 | 998.44 | 0
Y | IPCRP1-0000-0115-L | IPCRP1 | IPCRP1 | 0000-0115 | Replace Exist 6in Water Service to NYCHA Bldg #11 | N | L |  | UNIT | P | 0 | 5687.71 | 5687.71 | 5687.71 | 5687.71 | 100 | 0 | 0 | 0 | 0 | Y | 5687.71 | Y | -5687.71 | 0 | 0 | 0 | 0 | 0 | 5687.71 | Y | -5687.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5687.71 | 0 | 0 | 5687.71 | 0 | 0 | 0 | 0 | 0 | 0 | -5687.71 | 0 | 0 | 5687.71 | 5687.71 | 0 | 0 | 0 | 0 | 0 | 43.5 | 43.5 | 0 | 43.5 | 0 | 43.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#163, DDC CO 58.3, final T&M value $22,678.04.
Y | IPCRP1-0000-0115-S | IPCRP1 | IPCRP1 | 0000-0115 | Replace Exist 6in Water Service to NYCHA Bldg #11 | N | S |  | UNIT | A | 0 | 12635.8 | 12635.8 | 12635.8 | 12635.8 | 100 | 0 | 0 | 0 | 0 | N | 12635.8 | N | -12635.8 | 0 | 0 | 0 | 0 | 0 | 12635.8 | N | -12635.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12635.8 | 0 | 0 | 12635.8 | 0 | 0 | 0 | 0 | 0 | 0 | -12635.8 | 0 | 0 | 12635.8 | 12635.8 | 0 | 0 | 0 | 0 | 0 | 103 | 103 | 0 | 103 | 0 | 103 | NA | 0 | 1 | 0 | 1 | LS | 12635.8 | 0 | 12635.8 | 0
Y | IPCRP1-0000-0116-C | IPCRP1 | IPCRP1 | 0000-0116 | NYCHA Bldg #7 & #12 WM Wet Connections | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0116-E | IPCRP1 | IPCRP1 | 0000-0116 | NYCHA Bldg #7 & #12 WM Wet Connections | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0116-L | IPCRP1 | IPCRP1 | 0000-0116 | NYCHA Bldg #7 & #12 WM Wet Connections | N | L |  | UNIT | P | 0 | 16355.89 | 16355.89 | 16355.89 | 16355.89 | 100 | 0 | 0 | 0 | 0 | N | 16355.89 | N | -16355.89 | 0 | 0 | 0 | 0 | 0 | 16355.89 | N | -16355.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16355.89 | 0 | 0 | 16355.89 | 0 | 0 | 0 | 0 | 0 | 0 | -16355.89 | 0 | 0 | 16355.89 | 16355.89 | 0 | 0 | 0 | 0 | 0 | 123 | 123 | 0 | 123 | 0 | 123 | HR | 0 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0 | New note - PCO#162A, DDC CO#58.1, final T&M value $8,074.73 and PCO#162B, DDC CO#58.2, final T&M value $29,284.79. Old note -PCO#162A, DDC CO#58.1, final T&M value $8,074.73 and PCO#162B, DDC CO#58.2, final T&M value $29,284.79.
Y | IPCRP1-0000-0116-M | IPCRP1 | IPCRP1 | 0000-0116 | NYCHA Bldg #7 & #12 WM Wet Connections | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0116-S | IPCRP1 | IPCRP1 | 0000-0116 | NYCHA Bldg #7 & #12 WM Wet Connections | N | S |  | UNIT | A | 0 | 507.21 | 507.21 | 507.21 | 507.21 | 100 | 0 | 0 | 0 | 0 | N | 507.21 | N | -507.21 | 0 | 0 | 0 | 0 | 0 | 507.21 | N | -507.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -507.21 | 0 | 0 | 507.21 | 0 | 0 | 0 | 0 | 0 | 0 | -507.21 | 0 | 0 | 507.21 | 507.21 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 0 | 2 | 0 | 2 | EA | 507.21 | 0 | 507.21 | 0
Y | IPCRP1-0000-0120-C | IPCRP1 | IPCRP1 | 0000-0120 | VECP#14 Transition #1&#2 Micropiles along FDR Driv | N | C |  | UNIT | U | 0 | 28611.69 | 28611.69 | 28611.69 | 28611.69 | 100 | 0 | 0 | 0 | 0 | Y | 28611.69 | Y | -28611.69 | 0 | 0 | 0 | 0 | 0 | 28611.69 | Y | -28611.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28611.69 | 0 | 0 | 28611.69 | 0 | 0 | 0 | 0 | 0 | 0 | -28611.69 | 0 | 0 | 28611.69 | 28611.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | -66 | 0 | NA | 0 | 28 | 0 | 28 | EA | 28529.75 | 0 | 28529.75 | 0
Y | IPCRP1-0000-0120-L | IPCRP1 | IPCRP1 | 0000-0120 | VECP#14 Transition #1&#2 Micropiles along FDR Driv | N | L |  | UNIT | P | 0 | 283491.71 | 283491.71 | 283491.71 | 283491.71 | 100 | 0 | 0 | 0 | 0 | Y | 283491.71 | Y | -283491.71 | 0 | 0 | 0 | 0 | 0 | 283491.71 | Y | -283491.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -283491.71 | 0 | 0 | 283491.71 | 0 | 0 | 0 | 0 | 0 | 0 | -283491.71 | 0 | 0 | 283491.71 | 283491.71 | 0 | 0 | 0 | 0 | 0 | 1812.5 | 1812.5 | 0 | 1812.5 | 0 | 1812.5 | HR | 0 | 28 | 0 | 28 | EA | 0 | 0 | 0 | 0 | Some Mat purchased (32K) was charged to 0000-0062 (VECP#6) VECP#14 registered 7/31/24 as DDC CO#39. Equipment costs are included in Job Sie Equipment Costs (2000-1230). Value of Const Cost = 504K. Value of Engineering = $39,400.00 . Deleted note - VECP#14 not approved yet. Equipment costs are included in Job Site Equipment Costs (2000-1230).
Y | IPCRP1-0000-0120-M | IPCRP1 | IPCRP1 | 0000-0120 | VECP#14 Transition #1&#2 Micropiles along FDR Driv | N | M |  | UNIT | U | 0 | 36098.06 | 36098.06 | 36098.06 | 36098.06 | 100 | 0 | 0 | 0 | 0 | Y | 36098.06 | Y | -36098.06 | 0 | 0 | 0 | 0 | 0 | 36098.06 | Y | -36098.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36098.06 | 0 | 0 | 36098.06 | 0 | 0 | 0 | 0 | 0 | 0 | -36098.06 | 0 | 0 | 36098.06 | 36098.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | -232 | 0 | NA | 0 | 28 | 0 | 28 | EA | 36180 | 0 | 36180 | 0 | VECP#14 registered 7/31/24 as DDC CO#39. Equipment costs are included in Job Sie Equipment Costs (2000-1230). Value of Const Cost = 504K. Value of Engineering = $39,400.00
Y | IPCRP1-0000-0125-L | IPCRP1 | IPCRP1 | 0000-0125 | PCO#89 MPT on FDR for WM Work (CLOSED) | N | L |  | UNIT | P | 0 | 2393.88 | 2393.88 | 2393.88 | 2393.88 | 100 | 0 | 0 | 0 | 0 | Y | 2393.88 | Y | -2393.88 | 0 | 0 | 0 | 0 | 0 | 2393.88 | Y | -2393.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2393.88 | 0 | 0 | 2393.88 | 0 | 0 | 0 | 0 | 0 | 0 | -2393.88 | 0 | 0 | 2393.88 | 2393.88 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 22 | 0 | 22 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0125-S | IPCRP1 | IPCRP1 | 0000-0125 | PCO#89 MPT on FDR for WM Work (CLOSED) | N | S |  | UNIT | A | 0 | 6720.57 | 6720.57 | 6720.57 | 6720.57 | 100 | 0 | 0 | 0 | 0 | Y | 6720.57 | Y | -6720.57 | 0 | 0 | 0 | 0 | 0 | 6720.57 | Y | -6720.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6720.57 | 0 | 0 | 6720.57 | 0 | 0 | 0 | 0 | 0 | 0 | -6720.57 | 0 | 0 | 6720.57 | 6720.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | -53 | 0 | NA | 0 | 0 | 0 | 0 | EA | 6720.57 | 0 | 6720.57 | 0
Y | IPCRP1-0000-0126-C | IPCRP1 | IPCRP1 | 0000-0126 | PCO#89 Watermain Work on FDR Crossings (T&M) | N | C |  | UNIT | P | 0 | 1073.51 | 1073.51 | 1073.51 | 1073.51 | 100 | 0 | 0 | 0 | 0 | Y | 1073.51 | Y | -1073.51 | 0 | 0 | 0 | 0 | 0 | 1073.51 | Y | -1073.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1073.51 | 0 | 0 | 1073.51 | 0 | 0 | 0 | 0 | 0 | 0 | -1073.51 | 0 | 0 | 1073.51 | 1073.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | -4 | 0 | NA | 0 | 1 | 0 | 1 | LS | 1073.51 | 0 | 1073.51 | 0
Y | IPCRP1-0000-0126-E | IPCRP1 | IPCRP1 | 0000-0126 | PCO#89 Watermain Work on FDR Crossings (T&M) | N | E |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0126-L | IPCRP1 | IPCRP1 | 0000-0126 | PCO#89 Watermain Work on FDR Crossings (T&M) | N | L |  | UNIT | P | 0 | 230897.75 | 230897.75 | 230897.75 | 230897.75 | 100 | 0 | 0 | 0 | 0 | Y | 230897.75 | Y | -230897.75 | 0 | 0 | 0 | 0 | 0 | 230897.75 | Y | -230897.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -230897.75 | 0 | 0 | 230897.75 | 0 | 0 | 0 | 0 | 0 | 0 | -230897.75 | 0 | 0 | 230897.75 | 230897.75 | 0 | 0 | 0 | 0 | 0 | 1787 | 1787 | 0 | 1787 | 0 | 1787 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Scope includes 2 WM crossings (1 location at Jackson St, 1 at Delancy St). It does not include WM X-ing at North end of project, which was in base contract.
Y | IPCRP1-0000-0126-M | IPCRP1 | IPCRP1 | 0000-0126 | PCO#89 Watermain Work on FDR Crossings (T&M) | N | M |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0126-S | IPCRP1 | IPCRP1 | 0000-0126 | PCO#89 Watermain Work on FDR Crossings (T&M) | N | S |  | UNIT | A | 0 | 76162.44 | 76162.44 | 67412.44 | 76162.44 | 100 | 0 | 0 | 0 | -8750 | Y | 67412.44 | Y | -67412.44 | 0 | 0 | 0 | 0 | 0 | 67412.44 | Y | -67412.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -67412.44 | 0 | 0 | 67412.44 | 0 | 0 | 0 | 0 | 0 | 0 | -67412.44 | 0 | 0 | 67412.44 | 67412.44 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 319.5 | -304.5 | 15 | NA | 0 | 1 | 0 | 1 | LS | 76162.44 | 8750 | 67412.44 | -8750
Y | IPCRP1-0000-0127-L | IPCRP1 | IPCRP1 | 0000-0127 | PCO#89 MPT for CE & WM Work | N | L |  | UNIT | P | 0 | 485085.29 | 485085.29 | 485085.29 | 485085.29 | 94.1894 | 0 | 0 | 0 | 29924.99 | Y | 515010.28 | Y | -515010.28 | 0 | 0 | 0 | 0 | 0 | 515010.28 | Y | -515010.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -515010.28 | 0 | 0 | 515010.28 | 0 | 0 | 0 | 0 | 0 | 0 | -515010.28 | 0 | 0 | 515010.28 | 515010.28 | 0 | 0 | 0 | 0 | 0 | 4555 | 4555 | 0 | 4330 | 225 | 4555 | HR | 0 | 121 | 5 | 126 | EA | 0 | 0 | 0 | 29924.99 | QTD thru 12/31/25 is 121.00ea. Saving 5 lane closures to replace temp asphalt at Grand St crossing. VS (1/26) From PCO#89: ONE work area (M-Th) 56ea, Fri (14ea), Sat (13ea), TWO work areas (M-Th) 101ea, Fri (25ea), Sat (24ea). Total = 233ea.
Y | IPCRP1-0000-0127-S | IPCRP1 | IPCRP1 | 0000-0127 | PCO#89 MPT for CE & WM Work | N | S |  | UNIT | A | 0 | 266010.92 | 266010.92 | 266010.92 | 266010.92 | 96.0328 | 0 | 0 | 0 | 10989.08 | Y | 277000 | Y | -277000 | 0 | 0 | 0 | 0 | 0 | 277000 | Y | -277000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -277000 | 0 | 0 | 277000 | 0 | 0 | 0 | 0 | 0 | 0 | -277000 | 0 | 0 | 277000 | 277000 | 0 | 0 | 0 | 0 | 0 | 394 | 394 | 0 | 2139 | -1745 | 394 | NA | 0 | 121 | 5 | 126 | EA | 266010.92 | 0 | 266010.92 | 10989.08
Y | IPCRP1-0000-0128-C | IPCRP1 | IPCRP1 | 0000-0128 | PCO#89 Con Ed Work on FDR Crossings | N | C |  | UNIT | U | 0 | 13369.01 | 13369.01 | 12387.38 | 13369.01 | 92.6574 | 0 | 0 | 0 | 0 | Y | 13369.01 | Y | -13369.01 | 0 | 0 | 0 | 0 | 0 | 13369.01 | Y | -13369.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13369.01 | 0 | 0 | 13369.01 | 0 | 0 | 0 | 0 | 0 | 0 | -13369.01 | 0 | 0 | 13369.01 | 13369.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | -51 | 0 | NA | 0 | 39 | 0 | 39 | EA | 13369.01 | 981.63 | 12387.38 | 0
Y | IPCRP1-0000-0128-E | IPCRP1 | IPCRP1 | 0000-0128 | PCO#89 Con Ed Work on FDR Crossings | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 39 | 0 | 39 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0128-L | IPCRP1 | IPCRP1 | 0000-0128 | PCO#89 Con Ed Work on FDR Crossings | N | L |  | UNIT | P | 0 | 664176.51 | 664176.51 | 664176.51 | 664176.51 | 94.3561 | 0 | 0 | 0 | 39727.74 | Y | 703904.25 | Y | -703904.25 | 0 | 0 | 0 | 0 | 0 | 703904.25 | Y | -703904.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -703904.25 | 0 | 0 | 703904.25 | 0 | 0 | 0 | 0 | 0 | 0 | -703904.25 | 0 | 0 | 703904.25 | 703904.25 | 0 | 0 | 0 | 0 | 0 | 5300 | 5300 | 0 | 5002 | 298 | 5300 | HR | 0 | 39 | 0 | 39 | EA | 0 | 0 | 0 | 39727.74 | Worked from R6 estimate, deducted out ESC scope, so cost ties into negotiated Revenue. Then took at 80% if cost for Labor & Trucking. E, CM & PM to be charged elsewhere
Y | IPCRP1-0000-0128-M | IPCRP1 | IPCRP1 | 0000-0128 | PCO#89 Con Ed Work on FDR Crossings | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 39 | 0 | 39 | EA | 0 | 0 | 0 | 1
Y | IPCRP1-0000-0128-S | IPCRP1 | IPCRP1 | 0000-0128 | PCO#89 Con Ed Work on FDR Crossings | N | S |  | UNIT | A | 0 | 128311.15 | 128311.15 | 116136.15 | 128311.15 | 89.3355 | 0 | 0 | 0 | 1688.85 | Y | 130000 | Y | -130000 | 0 | 0 | 0 | 0 | 0 | 130000 | Y | -130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130000 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | -130000 | 0 | 0 | 130000 | 130000 | 0 | 0 | 0 | 0 | 0 | 135 | 135 | 0 | 735.13 | -600.13 | 135 | NA | 0 | 39 | 0 | 39 | EA | 128311.15 | 12175 | 116136.15 | 1688.85
Y | IPCRP1-0000-0130-L | IPCRP1 | IPCRP1 | 0000-0130 | SWO at Amphitheater Canopy Foundations (PCO #185) | N | L |  | UNIT | P | 0 | 27291.87 | 27291.87 | 27291.87 | 27291.87 | 100 | 0 | 0 | 0 | 0 | Y | 27291.87 | Y | -27291.87 | 0 | 0 | 0 | 0 | 0 | 27291.87 | Y | -27291.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27291.87 | 0 | 0 | 27291.87 | 0 | 0 | 0 | 0 | 0 | 0 | -27291.87 | 0 | 0 | 27291.87 | 27291.87 | 0 | 0 | 0 | 0 | 0 | 211 | 211 | 0 | 211 | 0 | 211 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | closed PCO#185 and combined with PCO#196 (Field Memo #5 - Amphitheater H-Pile Rebar (& SWO at Amp Canopy Found) Signed DDC CO#85, 12/23/25, $4,200.04.
Y | IPCRP1-0000-0130-S | IPCRP1 | IPCRP1 | 0000-0130 | SWO at Amphitheater Canopy Foundations (PCO #185) | N | S |  | UNIT | A | 0 | 466.59 | 466.59 | 466.59 | 466.59 | 100 | 0 | 0 | 0 | 0 | N | 466.59 | N | -466.59 | 0 | 0 | 0 | 0 | 0 | 466.59 | N | -466.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -466.59 | 0 | 0 | 466.59 | 0 | 0 | 0 | 0 | 0 | 0 | -466.59 | 0 | 0 | 466.59 | 466.59 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 0 | 1 | 0 | 1 | LS | 466.59 | 0 | 466.59 | 0
Y | IPCRP1-0000-0135-L | IPCRP1 | IPCRP1 | 0000-0135 | Work for EXTENET (Cable Company) | N | L |  | UNIT | P | 0 | 19238.81 | 19238.81 | 19238.81 | 19238.81 | 100 | 0 | 0 | 0 | 0 | Y | 19238.81 | Y | -19238.81 | 0 | 0 | 0 | 0 | 0 | 19238.81 | Y | -19238.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19238.81 | 0 | 0 | 19238.81 | 0 | 0 | 0 | 0 | 0 | 0 | -19238.81 | 0 | 0 | 19238.81 | 19238.81 | 0 | 0 | 0 | 0 | 0 | 139.5 | 139.5 | 0 | 139.5 | 0 | 139.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0135-S | IPCRP1 | IPCRP1 | 0000-0135 | Work for EXTENET (Cable Company) | N | S |  | UNIT | A | 0 | 1122.84 | 1122.84 | 1122.84 | 1122.84 | 100 | 0 | 0 | 0 | 0 | N | 1122.84 | N | -1122.84 | 0 | 0 | 0 | 0 | 0 | 1122.84 | N | -1122.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1122.84 | 0 | 0 | 1122.84 | 0 | 0 | 0 | 0 | 0 | 0 | -1122.84 | 0 | 0 | 1122.84 | 1122.84 | 0 | 0 | 0 | 0 | 0 | 9.5 | 9.5 | 0 | 9.5 | 0 | 9.5 | NA | 0 | 1 | 0 | 1 | LS | 1122.84 | 0 | 1122.84 | 0
Y | IPCRP1-0000-0139-C | IPCRP1 | IPCRP1 | 0000-0139 | Restore Proposed Comfort Station Area at F 1/2 | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0139-L | IPCRP1 | IPCRP1 | 0000-0139 | Restore Proposed Comfort Station Area at F 1/2 | N | L |  | UNIT | P | 0 | 1964.82 | 1964.82 | 1964.82 | 1964.82 | 100 | 0 | 0 | 0 | 0 | N | 1964.82 | N | -1964.82 | 0 | 0 | 0 | 0 | 0 | 1964.82 | N | -1964.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1964.82 | 0 | 0 | 1964.82 | 0 | 0 | 0 | 0 | 0 | 0 | -1964.82 | 0 | 0 | 1964.82 | 1964.82 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 15 | 0 | 15 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#311 (closed) & included w/ PCO#303A. (cost code: 0000-0273).
Y | IPCRP1-0000-0139-S | IPCRP1 | IPCRP1 | 0000-0139 | Restore Proposed Comfort Station Area at F 1/2 | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0140-C | IPCRP1 | IPCRP1 | 0000-0140 | Utility Modification for Prop Comfort Station in R | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0140-E | IPCRP1 | IPCRP1 | 0000-0140 | Utility Modification for Prop Comfort Station in R | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0140-L | IPCRP1 | IPCRP1 | 0000-0140 | Utility Modification for Prop Comfort Station in R | N | L |  | UNIT | P | 0 | 12768.92 | 12768.92 | 12768.92 | 12768.92 | 100 | 0 | 0 | 0 | 0 | Y | 12768.92 | Y | -12768.92 | 0 | 0 | 0 | 0 | 0 | 12768.92 | Y | -12768.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12768.92 | 0 | 0 | 12768.92 | 0 | 0 | 0 | 0 | 0 | 0 | -12768.92 | 0 | 0 | 12768.92 | 12768.92 | 0 | 0 | 0 | 0 | 0 | 102 | 102 | 0 | 102 | 0 | 102 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO #125E, sub 10/24/24, $173,909.17
Y | IPCRP1-0000-0140-M | IPCRP1 | IPCRP1 | 0000-0140 | Utility Modification for Prop Comfort Station in R | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0140-S | IPCRP1 | IPCRP1 | 0000-0140 | Utility Modification for Prop Comfort Station in R | N | S |  | UNIT | A | 0 | 115.9 | 115.9 | 115.9 | 115.9 | 100 | 0 | 0 | 0 | 0 | N | 115.9 | N | -115.9 | 0 | 0 | 0 | 0 | 0 | 115.9 | N | -115.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -115.9 | 0 | 0 | 115.9 | 0 | 0 | 0 | 0 | 0 | 0 | -115.9 | 0 | 0 | 115.9 | 115.9 | 0 | 0 | 0 | 0 | 0 | 862.81 | 862.81 | 0 | 1 | 861.81 | 862.81 | NA | 0 | 1 | 0 | 1 | LS | 115.9 | 0 | 115.9 | 0
Y | IPCRP1-0000-0141-E | IPCRP1 | IPCRP1 | 0000-0141 | Impact Costs due 2 Proposed Comfort Station CLOSED | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0141-L | IPCRP1 | IPCRP1 | 0000-0141 | Impact Costs due 2 Proposed Comfort Station CLOSED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0141-S | IPCRP1 | IPCRP1 | 0000-0141 | Impact Costs due 2 Proposed Comfort Station CLOSED | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0142-L | IPCRP1 | IPCRP1 | 0000-0142 | Field Memo #3 – Deck Alignment at FBH (Ex Pier 30) | N | L |  | UNIT | P | 0 | 546.35 | 546.35 | 546.35 | 546.35 | 100 | 0 | 0 | 0 | 0 | Y | 546.35 | Y | -546.35 | 0 | 0 | 0 | 0 | 0 | 546.35 | Y | -546.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -546.35 | 0 | 0 | 546.35 | 0 | 0 | 0 | 0 | 0 | 0 | -546.35 | 0 | 0 | 546.35 | 546.35 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | PCO#198, sub 12/30/24, $6,023.30 , signed DDC CO#67.1 on 5/2/25, $6,195.11
Y | IPCRP1-0000-0147-L | IPCRP1 | IPCRP1 | 0000-0147 | Demo of OH Sign Structure #1 Foundation | N | L |  | UNIT | P | 0 | 23914.64 | 23914.64 | 23914.64 | 23914.64 | 100 | 0 | 0 | 0 | 0 | N | 23914.64 | N | -23914.64 | 0 | 0 | 0 | 0 | 0 | 23914.64 | N | -23914.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23914.64 | 0 | 0 | 23914.64 | 0 | 0 | 0 | 0 | 0 | 0 | -23914.64 | 0 | 0 | 23914.64 | 23914.64 | 0 | 0 | 0 | 0 | 0 | 162.5 | 162.5 | 0 | 162.5 | 0 | 162.5 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#200
Y | IPCRP1-0000-0147-S | IPCRP1 | IPCRP1 | 0000-0147 | Demo of OH Sign Structure #1 Foundation | N | S |  | UNIT | A | 0 | 1049.83 | 1049.83 | 1049.83 | 1049.83 | 100 | 0 | 0 | 0 | 0 | N | 1049.83 | N | -1049.83 | 0 | 0 | 0 | 0 | 0 | 1049.83 | N | -1049.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1049.83 | 0 | 0 | 1049.83 | 0 | 0 | 0 | 0 | 0 | 0 | -1049.83 | 0 | 0 | 1049.83 | 1049.83 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 9 | 0 | 9 | NA | 1 | 1 | 0 | 1 | LS | 1049.83 | 0 | 1049.83 | 0
Y | IPCRP1-0000-0150-L | IPCRP1 | IPCRP1 | 0000-0150 | Set Up Interim Path from DSB to Fields 1 & 2 | N | L |  | UNIT | P | 0 | 383.88 | 383.88 | 383.88 | 383.88 | 100 | 0 | 0 | 0 | 0 | Y | 383.88 | Y | -383.88 | 0 | 0 | 0 | 0 | 0 | 383.88 | Y | -383.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -383.88 | 0 | 0 | 383.88 | 0 | 0 | 0 | 0 | 0 | 0 | -383.88 | 0 | 0 | 383.88 | 383.88 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Paid under bid item HW-900H - Allowance for City Work Acceleration (seq #514). Sub costs included under 0687-1000 (Sign-Rail-Fence Subs - Multiple).
Y | IPCRP1-0000-0151-L | IPCRP1 | IPCRP1 | 0000-0151 | Maintain Interim Path from DSB to Fields 1 & 2 | N | L |  | UNIT | P | 0 | 66459.44 | 66459.44 | 66459.44 | 66459.44 | 72.3108 | 0 | 0 | 0 | 25448.6 | Y | 91908.04 | Y | -91908.04 | 0 | 0 | 0 | 0 | 0 | 91908.04 | Y | -91908.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -91908.04 | 1598.32 | 0 | 91908.04 | 0 | 0 | 0 | 0 | 0 | 0 | -91908.04 | 0 | 0 | 91908.04 | 91908.04 | 0 | 0 | 0 | 0 | 0 | 735.97 | 735.97 | 0 | 545.5 | 190.47 | 735.97 | HR | 0 | 19 | 5 | 24 | MO | 0 | 0 | 0 | 25448.6 | null
Y | IPCRP1-0000-0151-S | IPCRP1 | IPCRP1 | 0000-0151 | Maintain Interim Path from DSB to Fields 1 & 2 | N | S |  | UNIT | A | 0 | 122.18 | 122.18 | 122.18 | 122.18 | 100 | 0 | 0 | 0 | 0 | N | 122.18 | N | -122.18 | 0 | 0 | 0 | 0 | 0 | 122.18 | N | -122.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -122.18 | 0 | 0 | 122.18 | 0 | 0 | 0 | 0 | 0 | 0 | -122.18 | 0 | 0 | 122.18 | 122.18 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 0 | 19 | 5 | 24 | MO | 122.18 | 0 | 122.18 | 0
Y | IPCRP1-0000-0152-L | IPCRP1 | IPCRP1 | 0000-0152 | Remove Interim Path from DSB to Fields 1 & 2 | N | L |  | UNIT | P | 0 | 890.85 | 890.85 | 890.85 | 890.85 | 100 | 0 | 0 | 0 | 0 | Y | 890.85 | Y | -890.85 | 0 | 0 | 0 | 0 | 0 | 890.85 | Y | -890.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -890.85 | 0 | 0 | 890.85 | 0 | 0 | 0 | 0 | 0 | 0 | -890.85 | 0 | 0 | 890.85 | 890.85 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0155-C | IPCRP1 | IPCRP1 | 0000-0155 | FBH Gravity Wall to Relieving Platform Joint Repai | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0155-E | IPCRP1 | IPCRP1 | 0000-0155 | FBH Gravity Wall to Relieving Platform Joint Repai | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0155-L | IPCRP1 | IPCRP1 | 0000-0155 | FBH Gravity Wall to Relieving Platform Joint Repai | N | L |  | UNIT | P | 0 | 99232.16 | 99232.16 | 99232.16 | 99232.16 | 100 | 0 | 0 | 0 | 0 | Y | 99232.16 | Y | -99232.16 | 0 | 0 | 0 | 0 | 0 | 99232.16 | Y | -99232.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -99232.16 | 0 | 0 | 99232.16 | 0 | 0 | 0 | 0 | 0 | 0 | -99232.16 | 0 | 0 | 99232.16 | 99232.16 | 0 | 0 | 0 | 0 | 0 | 738.5 | 738.5 | 0 | 738.5 | 0 | 738.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO #214A Directed to do under T&M s per Field Memo #9, dated 8/29/24 & rcd 9/3/24.
Y | IPCRP1-0000-0155-M | IPCRP1 | IPCRP1 | 0000-0155 | FBH Gravity Wall to Relieving Platform Joint Repai | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0155-S | IPCRP1 | IPCRP1 | 0000-0155 | FBH Gravity Wall to Relieving Platform Joint Repai | N | S |  | UNIT | A | 0 | 3787.55 | 3787.55 | 3787.55 | 3787.55 | 100 | 0 | 0 | 0 | 0 | Y | 3787.55 | Y | -3787.55 | 0 | 0 | 0 | 0 | 0 | 3787.55 | Y | -3787.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3787.55 | 0 | 0 | 3787.55 | 0 | 0 | 0 | 0 | 0 | 0 | -3787.55 | 0 | 0 | 3787.55 | 3787.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | -31 | 0 | NA | 0 | 1 | 0 | 1 | LS | 3787.55 | 0 | 3787.55 | 0
Y | IPCRP1-0000-0160-L | IPCRP1 | IPCRP1 | 0000-0160 | VECP#15, Reach B MP Work, Sta 22+89 to Sta 23+10 | N | L |  | UNIT | P | 0 | 11305.03 | 11305.03 | 11305.03 | 11305.03 | 100 | 0 | 0 | 0 | 0 | Y | 11305.03 | Y | -11305.03 | 0 | 0 | 0 | 0 | 0 | 11305.03 | Y | -11305.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11305.03 | 0 | 0 | 11305.03 | 0 | 0 | 0 | 0 | 0 | 0 | -11305.03 | 0 | 0 | 11305.03 | 11305.03 | 0 | 0 | 0 | 0 | 0 | 63.5 | 63.5 | 0 | 63.5 | 0 | 63.5 | HR | 0 | 90 | 0 | 90 | LF | 0 | 0 | 0 | 0 | VECP #15, Const cost Savings = $135,198.85. Design Cost = $562.50. DDC CO#52 registered 11/22/24
Y | IPCRP1-0000-0165-L | IPCRP1 | IPCRP1 | 0000-0165 | Removal of UST at FDR SR SB & E10h St | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0165-S | IPCRP1 | IPCRP1 | 0000-0165 | Removal of UST at FDR SR SB & E10h St | N | S |  | UNIT | A | 0 | 18375.67 | 18375.67 | 18375.67 | 18375.67 | 100 | 0 | 0 | 0 | 0 | Y | 18375.67 | Y | -18375.67 | 0 | 0 | 0 | 0 | 0 | 18375.67 | Y | -18375.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18375.67 | 0 | 0 | 18375.67 | 0 | 0 | 0 | 0 | 0 | 0 | -18375.67 | 0 | 0 | 18375.67 | 18375.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | -0.74 | 0 | NA | 0 | 1 | 0 | 1 | LS | 18375.67 | 0 | 18375.67 | 0
Y | IPCRP1-0000-0170-L | IPCRP1 | IPCRP1 | 0000-0170 | Closure at Existing FBH South Side T&M (PCO 227) | N | L |  | UNIT | P | 0 | 30632.92 | 30632.92 | 30632.92 | 30632.92 | 100 | 0 | 0 | 0 | 0 | Y | 30632.92 | Y | -30632.92 | 0 | 0 | 0 | 0 | 0 | 30632.92 | Y | -30632.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30632.92 | 0 | 0 | 30632.92 | 0 | 0 | 0 | 0 | 0 | 0 | -30632.92 | 0 | 0 | 30632.92 | 30632.92 | 0 | 0 | 0 | 0 | 0 | 232.5 | 232.5 | 0 | 232.5 | 0 | 232.5 | HR | 0 | 232.5 | 0 | 232.5 | HR | 0 | 0 | 0 | 0 | PCO #227, submitted 4/4/25 for $60,138.32, previously signed as DDC CO #70.2 on 5/30/25 for $10,574.10. Updated to CO 72, dated 9/10/25, for $56,330.70.
Y | IPCRP1-0000-0170-S | IPCRP1 | IPCRP1 | 0000-0170 | Closure at Existing FBH South Side T&M (PCO 227) | N | S |  | UNIT | A | 0 | 736.62 | 736.62 | 736.62 | 736.62 | 100 | 0 | 0 | 0 | 0 | N | 736.62 | N | -736.62 | 0 | 0 | 0 | 0 | 0 | 736.62 | N | -736.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -736.62 | 0 | 0 | 736.62 | 0 | 0 | 0 | 0 | 0 | 0 | -736.62 | 0 | 0 | 736.62 | 736.62 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 0 | 232.5 | 0 | 232.5 | HR | 736.62 | 0 | 736.62 | 0
Y | IPCRP1-0000-0175-L | IPCRP1 | IPCRP1 | 0000-0175 | TEMP IRRIGATION UNTIL PERM IRRG SYST IN PLACE | N | L |  | UNIT | P | 0 | 2076.36 | 2076.36 | 2076.36 | 2076.36 | 100 | 0 | 0 | 0 | 0 | Y | 2076.36 | Y | -2076.36 | 0 | 0 | 0 | 0 | 0 | 2076.36 | Y | -2076.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2076.36 | 0 | 0 | 2076.36 | 0 | 0 | 0 | 0 | 0 | 0 | -2076.36 | 0 | 0 | 2076.36 | 2076.36 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 17 | 0 | 17 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO #234, agreed to value $3,186.26, waiting on DDC CO
Y | IPCRP1-0000-0175-S | IPCRP1 | IPCRP1 | 0000-0175 | TEMP IRRIGATION UNTIL PERM IRRG SYST IN PLACE | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0180-L | IPCRP1 | IPCRP1 | 0000-0180 | Adjust Bridge Fence Base Plates to Align w Bridge | N | L |  | UNIT | P | 0 | 6276.26 | 6276.26 | 6276.26 | 6276.26 | 100 | 0 | 0 | 0 | 0 | Y | 6276.26 | Y | -6276.26 | 0 | 0 | 0 | 0 | 0 | 6276.26 | Y | -6276.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6276.26 | 0 | 0 | 6276.26 | 0 | 0 | 0 | 0 | 0 | 0 | -6276.26 | 0 | 0 | 6276.26 | 6276.26 | 0 | 0 | 0 | 0 | 0 | 48.5 | 48.5 | 0 | 48.5 | 0 | 48.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | T&M, PCO #235, sub 8/8/25, $23,703.45, sub value $16,255.00
Y | IPCRP1-0000-0185-L | IPCRP1 | IPCRP1 | 0000-0185 | Change WM Fitting from 4 Way to 3 Way, Grand St & | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 13000 | PCO# 239
Y | IPCRP1-0000-0186-L | IPCRP1 | IPCRP1 | 0000-0186 | Unknown 6” WM Spur, Grand St & SB FDR SR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 10 | PCO# 240 PCO#240, sub 7/15/25, $10,804.07, PMCM denied, says CE to pay, w/ Nick M Work performed on 11/12/24 (30MH) & moved elsewhere
Y | IPCRP1-0000-0190-L | IPCRP1 | IPCRP1 | 0000-0190 | Retaining Wall Joint Seals (PCO#193) | N | L |  | UNIT | P | 0 | 14204.25 | 14204.25 | 14204.25 | 14204.25 | 100 | 0 | 0 | 0 | 0 | Y | 14204.25 | Y | -14204.25 | 0 | 0 | 0 | 0 | 0 | 14204.25 | Y | -14204.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14204.25 | 0 | 0 | 14204.25 | 0 | 0 | 0 | 0 | 0 | 0 | -14204.25 | 0 | 0 | 14204.25 | 14204.25 | 0 | 0 | 0 | 0 | 0 | 130.5 | 130.5 | 0 | 130.5 | 0 | 130.5 | HR | 0 | 97.71 | 0 | 97.71 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0195-L | IPCRP1 | IPCRP1 | 0000-0195 | Adjust & Modification near FBH from RFI #967 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0195-S | IPCRP1 | IPCRP1 | 0000-0195 | Adjust & Modification near FBH from RFI #967 | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0200-L | IPCRP1 | IPCRP1 | 0000-0200 | Houston St, Jet Grout Test Program – Keller SCO | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0200-S | IPCRP1 | IPCRP1 | 0000-0200 | Houston St, Jet Grout Test Program – Keller SCO | N | S |  | UNIT | A | 0 | 387930 | 387930 | 387891.21 | 387930 | 99.99 | 0 | 0 | 0 | 0 | Y | 387930 | Y | -387930 | 0 | 0 | 0 | 0 | 0 | 387930 | Y | -387930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -387930 | 0 | 0 | 387930 | 0 | 0 | 0 | 0 | 0 | 0 | -387930 | 0 | 0 | 387930 | 387930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 0 | NA | 0 | 1 | 0 | 1 | LS | 387930 | 38.79 | 387891.21 | 0 | PCO-150 Jet Grout (~12,500 cy)- Houston Street Retaining Wall Test program, pay to be made under item HW900H Acceleration Allowance
Y | IPCRP1-0000-0201-L | IPCRP1 | IPCRP1 | 0000-0201 | Houston St, Jet Grout Test Program – Support | N | L |  | UNIT | P | 0 | 19188.36 | 19188.36 | 19188.36 | 19188.36 | 100 | 0 | 0 | 0 | 0 | Y | 19188.36 | Y | -19188.36 | 0 | 0 | 0 | 0 | 0 | 19188.36 | Y | -19188.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19188.36 | 0 | 0 | 19188.36 | 0 | 0 | 0 | 0 | 0 | 0 | -19188.36 | 0 | 0 | 19188.36 | 19188.36 | 0 | 0 | 0 | 0 | 0 | 155 | 155 | 0 | 155 | 0 | 155 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO-150 Jet Grout (~12,500 cy)- Houston Street Retaining Wall Test program
Y | IPCRP1-0000-0201-S | IPCRP1 | IPCRP1 | 0000-0201 | Houston St, Jet Grout Test Program – Support | N | S |  | UNIT | A | 0 | 3374.96 | 3374.96 | 3374.96 | 3374.96 | 100 | 0 | 0 | 0 | 0 | N | 3374.96 | N | -3374.96 | 0 | 0 | 0 | 0 | 0 | 3374.96 | N | -3374.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3374.96 | 0 | 0 | 3374.96 | 0 | 0 | 0 | 0 | 0 | 0 | -3374.96 | 0 | 0 | 3374.96 | 3374.96 | 0 | 0 | 0 | 0 | 0 | 27 | 27 | 0 | 27 | 0 | 27 | NA | 0 | 1 | 0 | 1 | LS | 3374.96 | 0 | 3374.96 | 0
Y | IPCRP1-0000-0202-L | IPCRP1 | IPCRP1 | 0000-0202 | Subcontractor Mob-Demob for Houston St Jet Groutin | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Pay to be made under item HW900H Acceleration Allowance
Y | IPCRP1-0000-0202-S | IPCRP1 | IPCRP1 | 0000-0202 | Subcontractor Mob-Demob for Houston St Jet Groutin | N | S |  | UNIT | A | 0 | 407000 | 407000 | 407000 | 407000 | 100 | 0 | 0 | 0 | 0 | Y | 407000 | Y | -407000 | 0 | 0 | 0 | 0 | 0 | 407000 | Y | -407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -407000 | 0 | 0 | 407000 | 0 | 0 | 0 | 0 | 0 | 0 | -407000 | 0 | 0 | 407000 | 407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -3 | 0 | NA | 0 | 1 | 0 | 1 | LS | 407000 | 0 | 407000 | 0
Y | IPCRP1-0000-0203-L | IPCRP1 | IPCRP1 | 0000-0203 | Keller– Houston St Jet Grout – Pilot, Prod, Obst | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 9212 | 0 | 9212 | CY | 0 | 0 | 0 | 0 | Final Quantities earned were: 396cy (Pilot), 5,586cy (Production), 3,230cy (Obstruction). Total = 9,212cy. Refer to Keller SCO#21 for more details
Y | IPCRP1-0000-0203-S | IPCRP1 | IPCRP1 | 0000-0203 | Keller– Houston St Jet Grout – Pilot, Prod, Obst | N | S |  | UNIT | A | 0 | 9663810 | 9663810 | 9663810 | 9663810 | 100 | 0 | 0 | 0 | 0 | Y | 9663810 | Y | -9663810 | 0 | 0 | 0 | 0 | 0 | 9663810 | Y | -9663810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9663810 | 0 | 0 | 9663810 | 0 | 0 | 0 | 0 | 0 | 0 | -9663810 | 0 | 0 | 9663810 | 9663810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9212 | -9212 | 0 | NA | 0 | 9212 | 0 | 9212 | CY | 9663810 | 0 | 9663810 | 0 | DDC CO#65 (PC PCO#150B) Final IPC Quan (at 11/11): CO 65.3 (pilot prog) 475.00cy; CO 65.4 (unobstructed) 6,380.22cy; CO 65.5 (obstructed) 2,851.52cy. Total: 9,706.74cy
Y | IPCRP1-0000-0204-L | IPCRP1 | IPCRP1 | 0000-0204 | McVac – Houston St Jet Grout, Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0204-S | IPCRP1 | IPCRP1 | 0000-0204 | McVac – Houston St Jet Grout, Support | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 10 | DDC CO#65 (PC PCO#150B)
Y | IPCRP1-0000-0205-C | IPCRP1 | IPCRP1 | 0000-0205 | T&D – Houston St Jet Grout Spoils | N | C |  | UNIT | U | 0 | 121940 | 121940 | 73181.56 | 121940 | 100 | 0 | 0 | 0 | -48758.44 | Y | 73181.56 | Y | -73181.56 | 0 | 0 | 0 | 0 | 0 | 73181.56 | Y | -73181.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -73181.56 | 0 | 0 | 73181.56 | 0 | 0 | 0 | 0 | 0 | 0 | -73181.56 | 0 | 0 | 73181.56 | 73181.56 | 0 | 0 | 0 | 0 | 0 | 210.87 | 210.87 | 0 | 210.87 | 0 | 210.87 | NA | 0 | 2608.27 | 0 | 2608.27 | CY | 121940 | 48758.44 | 73181.56 | -48758.44 | DDC CO#65 (PC PCO#150B) 3. As per Justin (11/11) Disp Quan thru 10/31: 11,370.76 TN to Bayshore (paid under cc: 0498-1000), 2,608.27 TN to PPark (paid under this cc). Total JG Volume to date: 13,979 TN
Y | IPCRP1-0000-0205-L | IPCRP1 | IPCRP1 | 0000-0205 | T&D – Houston St Jet Grout Spoils | N | L |  | UNIT | P | 0 | 349.36 | 349.36 | 349.36 | 349.36 | 100 | 0 | 0 | 0 | 0 | Y | 349.36 | Y | -349.36 | 0 | 0 | 0 | 0 | 0 | 349.36 | Y | -349.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -349.36 | 0 | 0 | 349.36 | 0 | 0 | 0 | 0 | 0 | 0 | -349.36 | 0 | 0 | 349.36 | 349.36 | 0 | 0 | 0 | 0 | 0 | -0.26 | -0.26 | 0 | 4 | -4.26 | -0.26 | HR | 0 | 2608.27 | 0 | 2608.27 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0206-C | IPCRP1 | IPCRP1 | 0000-0206 | IPC Support Houston St Jet Grout Work | N | C |  | UNIT | U | 0 | 62753.72 | 62753.72 | 54608.28 | 62753.72 | 100 | 0 | 0 | 0 | -8145.44 | Y | 54608.28 | Y | -54608.28 | 0 | 0 | 0 | 0 | 0 | 54608.28 | Y | -54608.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -54608.28 | 0 | 0 | 54608.28 | 0 | 0 | 0 | 0 | 0 | 0 | -54608.28 | 0 | 0 | 54608.28 | 54608.28 | 0 | 0 | 0 | 0 | 0 | 2173.69 | 2173.69 | 0 | 2184 | -10.31 | 2173.69 | NA | 0 | 117.66 | 3.34 | 121 | DY | 62753.72 | 8145.44 | 54608.28 | -8145.44
Y | IPCRP1-0000-0206-L | IPCRP1 | IPCRP1 | 0000-0206 | IPC Support Houston St Jet Grout Work | N | L |  | UNIT | P | 0 | 351366.9 | 351366.9 | 351366.9 | 351366.9 | 87.8408 | 0 | 0 | 0 | 48637.33 | Y | 400004.23 | Y | -400004.23 | 0 | 0 | 0 | 0 | 0 | 400004.23 | Y | -400004.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -400004.23 | 0 | 0 | 400004.23 | 0 | 0 | 0 | 0 | 0 | 0 | -400004.23 | 0 | 0 | 400004.23 | 400004.23 | 0 | 0 | 0 | 0 | 0 | 2615 | 2615 | 0 | 2381.5 | 233.5 | 2615 | HR | 0 | 117.66 | 3.34 | 121 | DY | 0 | 0 | 0 | 48637.33 | null
Y | IPCRP1-0000-0206-S | IPCRP1 | IPCRP1 | 0000-0206 | IPC Support Houston St Jet Grout Work | N | S |  | UNIT | A | 0 | 39090.06 | 39090.06 | 39090.06 | 39090.06 | 100 | 0 | 0 | 0 | 0 | Y | 39090.06 | Y | -39090.06 | 0 | 0 | 0 | 0 | 0 | 39090.06 | Y | -39090.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39090.06 | 0 | 786.32 | 39090.06 | 0 | 0 | 0 | 0 | 0 | 0 | -39090.06 | 0 | 0 | 39090.06 | 39090.06 | 0 | 0 | 0 | 0 | 0 | 299.5 | 299.5 | 0 | 299.5 | 0 | 299.5 | NA | 0 | 117.66 | 3.34 | 121 | DY | 39090.06 | 0 | 39090.06 | 0
Y | IPCRP1-0000-0210-C | IPCRP1 | IPCRP1 | 0000-0210 | Congestion Pricing | N | C |  | UNIT | U | 0 | 15983.41 | 15983.41 | 11210.34 | 15983.41 | 44.8414 | 0 | 0 | 0 | 9016.59 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 927.85 | 1191.77 | 25000 | 0 | 0 | 0 | 894.2 | 869.35 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6973.81 | -6973.81 | 0 | NA | 0 | 15 | 21 | 36 | MO | 15983.41 | 4773.07 | 11210.34 | 9016.59 | Changed Condition via PCO #261
Y | IPCRP1-0000-0210-L | IPCRP1 | IPCRP1 | 0000-0210 | Congestion Pricing | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 15 | 21 | 36 | MO | 0 | 0 | 0 | 0 | null
Y | IPCRP1-0000-0210-S | IPCRP1 | IPCRP1 | 0000-0210 | Congestion Pricing | N | S |  | UNIT | A | 0 | 76000 | 76000 | 64646.07 | 76000 | 85.0606 | 0 | 0 | 0 | 0 | Y | 76000 | Y | -76000 | 0 | 0 | 0 | 0 | 0 | 76000 | Y | -76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -76000 | 0 | 2224.8 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | -76000 | 0 | 0 | 76000 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | -1.94 | 0 | NA | 0 | 15 | 21 | 36 | MO | 76000 | 11353.93 | 64646.07 | 0
Y | IPCRP1-0000-0215-L | IPCRP1 | IPCRP1 | 0000-0215 | PCO#257 – Repair to RW at FBH, near Bent 30 | N | L |  | UNIT | P | 0 | 6957.59 | 6957.59 | 6957.59 | 6957.59 | 100 | 0 | 0 | 0 | 0 | N | 6957.59 | N | -6957.59 | 0 | 0 | 0 | 0 | 0 | 6957.59 | N | -6957.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6957.59 | 0 | 0 | 6957.59 | 0 | 0 | 0 | 0 | 0 | 0 | -6957.59 | 0 | 0 | 6957.59 | 6957.59 | 0 | 0 | 0 | 0 | 0 | 58 | 58 | 0 | 58 | 0 | 58 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | 2. DDC paying temporarily under HW900 in Sep 2025 (PP#56) until CO gets registered. PCO#257, DDC CO #67.3, signed 5/14/25, $20,000.00
Y | IPCRP1-0000-0215-S | IPCRP1 | IPCRP1 | 0000-0215 | PCO#257 – Repair to RW at FBH, near Bent 30 | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0216-L | IPCRP1 | IPCRP1 | 0000-0216 | Back Charge to Phantom for Soil Spill | N | L |  | UNIT | P | 0 | 4191.59 | 4191.59 | 4191.59 | 4191.59 | 100 | 0 | 0 | 0 | 0 | Y | 4191.59 | Y | -4191.59 | 0 | 0 | 0 | 0 | 0 | 4191.59 | Y | -4191.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4191.59 | 0 | 0 | 4191.59 | 0 | 0 | 0 | 0 | 0 | 0 | -4191.59 | 0 | 0 | 4191.59 | 4191.59 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 0 | 33 | 0 | 33 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | bc test
Y | IPCRP1-0000-0216-S | IPCRP1 | IPCRP1 | 0000-0216 | Back Charge to Phantom for Soil Spill | N | S |  | UNIT | A | 0 | -5279.48 | -5279.48 | -5279.48 | -5279.48 | 100 | 0 | 0 | 0 | 0 | Y | -5279.48 | Y | 5279.48 | 0 | 0 | 0 | 0 | 0 | -5279.48 | Y | 5279.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 5279.48 | 0 | 0 | -5279.48 | 0 | 0 | 0 | 0 | 0 | 0 | 5279.48 | 0 | 0 | -5279.48 | -5279.48 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 0 | 1 | 0 | 1 | LS | -5279.48 | 0 | -5279.48 | 0
Y | IPCRP1-0000-0220-L | IPCRP1 | IPCRP1 | 0000-0220 | Remove Jet Gout From Exist 24inch D Sewer South S | N | L |  | UNIT | P | 0 | 115790.39 | 115790.39 | 115790.39 | 115790.39 | 100 | 0 | 0 | 0 | 0 | Y | 115790.39 | Y | -115790.39 | 0 | 0 | 0 | 0 | 0 | 115790.39 | Y | -115790.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -115790.39 | 0 | 0 | 115790.39 | 0 | 0 | 0 | 0 | 0 | 0 | -115790.39 | 0 | 0 | 115790.39 | 115790.39 | 0 | 0 | 0 | 0 | 0 | 924.5 | 924.5 | 0 | 924.5 | 0 | 924.5 | HR | 0 | 88 | 0 | 88 | LF | 0 | 0 | 0 | 0 | 1. This is not a CO, it is REWORK. When costs stop hitting, we will move to the 3000 code series. 2. Subs: CCC ($2,500), KMA ($15,953.69) EnTech ($7,310)
Y | IPCRP1-0000-0220-S | IPCRP1 | IPCRP1 | 0000-0220 | Remove Jet Gout From Exist 24inch D Sewer South S | N | S |  | UNIT | A | 0 | 26514.28 | 26514.28 | 26514.28 | 26514.28 | 100 | 0 | 0 | 0 | 0 | Y | 26514.28 | Y | -26514.28 | 0 | 0 | 0 | 0 | 0 | 26514.28 | Y | -26514.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26514.28 | 0 | 0 | 26514.28 | 0 | 0 | 0 | 0 | 0 | 0 | -26514.28 | 0 | 0 | 26514.28 | 26514.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | -164 | 0 | NA | 0 | 88 | 0 | 88 | LF | 26514.28 | 0 | 26514.28 | 0
Y | IPCRP1-0000-0225-L | IPCRP1 | IPCRP1 | 0000-0225 | FM#15 & #17, Restore Traffic at Montgomery & South | N | L |  | UNIT | P | 0 | 4925.32 | 4925.32 | 4925.32 | 4925.32 | 100 | 0 | 0 | 0 | 0 | Y | 4925.32 | Y | -4925.32 | 0 | 0 | 0 | 0 | 0 | 4925.32 | Y | -4925.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4925.32 | 0 | 0 | 4925.32 | 0 | 0 | 0 | 0 | 0 | 0 | -4925.32 | 0 | 0 | 4925.32 | 4925.32 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 0 | 40 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#287, sub 10/6/25, $17,754.92
Y | IPCRP1-0000-0225-S | IPCRP1 | IPCRP1 | 0000-0225 | FM#15 & #17, Restore Traffic at Montgomery & South | N | S |  | UNIT | A | 0 | 251.28 | 251.28 | 251.28 | 251.28 | 100 | 0 | 0 | 0 | 0 | N | 251.28 | N | -251.28 | 0 | 0 | 0 | 0 | 0 | 251.28 | N | -251.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -251.28 | 0 | 0 | 251.28 | 0 | 0 | 0 | 0 | 0 | 0 | -251.28 | 0 | 0 | 251.28 | 251.28 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 0 | 1 | 0 | 1 | LS | 251.28 | 0 | 251.28 | 0
Y | IPCRP1-0000-0230-L | IPCRP1 | IPCRP1 | 0000-0230 | FM#16, Delancey St Curb W of ERH Driveway (T&M) | N | L |  | UNIT | P | 0 | 4034.53 | 4034.53 | 4034.53 | 4034.53 | 100 | 0 | 0 | 0 | 0 | N | 4034.53 | N | -4034.53 | 0 | 0 | 0 | 0 | 0 | 4034.53 | N | -4034.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4034.53 | 0 | 0 | 4034.53 | 0 | 0 | 0 | 0 | 0 | 0 | -4034.53 | 0 | 0 | 4034.53 | 4034.53 | 0 | 0 | 0 | 0 | 0 | 32.5 | 32.5 | 0 | 32.5 | 0 | 32.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO #304, sub 5/12/25, $13,046.47 agreed to $11,947.01 on 11/24/25 PCO #304, sub 5/12/25, $13,046.47
Y | IPCRP1-0000-0235-L | IPCRP1 | IPCRP1 | 0000-0235 | PCO#220, Floodwall Skate Deterrent Plates | N | L |  | UNIT | P | 0 | 878.68 | 878.68 | 878.68 | 878.68 | 100 | 0 | 0 | 0 | 0 | Y | 878.68 | Y | -878.68 | 0 | 0 | 0 | 0 | 0 | 878.68 | Y | -878.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -878.68 | 0 | 0 | 878.68 | 0 | 0 | 0 | 0 | 0 | 0 | -878.68 | 0 | 0 | 878.68 | 878.68 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO #220, negotiated value $11,670.00 , will get paid under item ESCR-564 CT (Struct Steel coated) 2,334.04 lbs = $11,670.00
Y | IPCRP1-0000-0235-M | IPCRP1 | IPCRP1 | 0000-0235 | PCO#220, Floodwall Skate Deterrent Plates | N | M |  | UNIT | U | 0 | 5382 | 5382 | 5382 | 5382 | 100 | 0 | 0 | 0 | 0 | Y | 5382 | Y | -5382 | 0 | 0 | 0 | 0 | 0 | 5382 | Y | -5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5382 | 0 | 0 | 5382 | 0 | 0 | 0 | 0 | 0 | 0 | -5382 | 0 | 0 | 5382 | 5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | -23 | 0 | NA | 0 | 1 | 0 | 1 | LS | 5382 | 0 | 5382 | 0
Y | IPCRP1-0000-0240-L | IPCRP1 | IPCRP1 | 0000-0240 | PCO#309, NYCHA Bldg 11 - Sewer Service Replacement | N | L |  | UNIT | P | 0 | 31297.14 | 31297.14 | 31297.14 | 31297.14 | 100 | 0 | 0 | 0 | 0 | Y | 31297.14 | Y | -31297.14 | 0 | 0 | 0 | 0 | 0 | 31297.14 | Y | -31297.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31297.14 | 0 | 0 | 31297.14 | 0 | 0 | 0 | 0 | 0 | 0 | -31297.14 | 0 | 0 | 31297.14 | 31297.14 | 0 | 0 | 0 | 0 | 0 | 238.5 | 238.5 | 0 | 238.5 | 0 | 238.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | 1. Initial notification made under PCO#298, via BS email 4/7/25. 2. PCO#298 CLOSED, and included with PCO#309, sub 5/21/25, agreed to $63,143.88. Waiting for DDC to process. PCO #298, refer to Bobby S email dated 4/7/25 for initial notification
Y | IPCRP1-0000-0245-L | IPCRP1 | IPCRP1 | 0000-0245 | PCO#300 Paver Base over Top CutOff Wall RFI#1095 | N | L |  | UNIT | P | 0 | 8863.25 | 8863.25 | 8863.25 | 8863.25 | 100 | 0 | 0 | 0 | 0 | N | 8863.25 | N | -8863.25 | 0 | 0 | 0 | 0 | 0 | 8863.25 | N | -8863.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8863.25 | 0 | 0 | 8863.25 | 0 | 0 | 0 | 0 | 0 | 0 | -8863.25 | 0 | 0 | 8863.25 | 8863.25 | 0 | 0 | 0 | 0 | 0 | 74.5 | 74.5 | 0 | 74.5 | 0 | 74.5 | HR | 0 | 1221.86 | 0 | 1221.86 | SF | 0 | 0 | 0 | 0 | PCO #300, sub 10/27/25, $60,642.95
Y | IPCRP1-0000-0245-M | IPCRP1 | IPCRP1 | 0000-0245 | PCO#300 Paver Base over Top CutOff Wall RFI#1095 | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1221.86 | 0 | 1221.86 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0250-C | IPCRP1 | IPCRP1 | 0000-0250 | GRES Wall at Houston St to Facilitate JG/Backfilli | N | C |  | UNIT | U | 0 | 25750.01 | 25750.01 | 24756.52 | 25750.01 | 100 | 0 | 0 | 0 | -993.49 | Y | 24756.52 | Y | -24756.52 | 0 | 0 | 0 | 0 | 0 | 24756.52 | Y | -24756.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24756.52 | 0 | 0 | 24756.52 | 0 | 0 | 0 | 0 | 0 | 0 | -24756.52 | 0 | 0 | 24756.52 | 24756.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 2213.06 | 0 | 2213.06 | SF | 25750.01 | 993.49 | 24756.52 | -993.49
N | IPCRP1-0000-0250-L | IPCRP1 | IPCRP1 | 0000-0250 | GRES Wall at Houston St to Facilitate JG/Backfilli | N | L |  | UNIT | P | 0 | 31938.51 | 31938.51 | 31938.51 | 31938.51 | 100 | 0 | 0 | 0 | 0 | N | 31938.51 | N | -31938.51 | 0 | 0 | 0 | 0 | 0 | 31938.51 | N | -31938.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31938.51 | 0 | 0 | 31938.51 | 0 | 0 | 0 | 0 | 0 | 0 | -31938.51 | 0 | 0 | 31938.51 | 31938.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245 | -245 | 0 | HR | 0 | 2213.06 | 0 | 2213.06 | SF | 0 | 0 | 0 | 0 | PCO #301, sub 8/11/25, $107,354.23 (50.85/SF) for completed work, and $1,160,574.97 ($61.96/SF) for proposed Phase 2 work
Y | IPCRP1-0000-0250-S | IPCRP1 | IPCRP1 | 0000-0250 | GRES Wall at Houston St to Facilitate JG/Backfilli | N | S |  | UNIT | A | 0 | 251.28 | 251.28 | 251.28 | 251.28 | 100 | 0 | 0 | 0 | 0 | N | 251.28 | N | -251.28 | 0 | 0 | 0 | 0 | 0 | 251.28 | N | -251.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -251.28 | 0 | 0 | 251.28 | 0 | 0 | 0 | 0 | 0 | 0 | -251.28 | 0 | 0 | 251.28 | 251.28 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 0 | 2213.06 | 0 | 2213.06 | SF | 251.28 | 0 | 251.28 | 0
Y | IPCRP1-0000-0255-L | IPCRP1 | IPCRP1 | 0000-0255 | PCO#307 RFI#1121 Adjust Grades Adj Tennis Stepdown | N | L |  | UNIT | P | 0 | 1245.15 | 1245.15 | 1245.15 | 1245.15 | 100 | 0 | 0 | 0 | 0 | Y | 1245.15 | Y | -1245.15 | 0 | 0 | 0 | 0 | 0 | 1245.15 | Y | -1245.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1245.15 | 0 | 0 | 1245.15 | 0 | 0 | 0 | 0 | 0 | 0 | -1245.15 | 0 | 0 | 1245.15 | 1245.15 | 0 | 0 | 0 | 0 | 0 | 10.5 | 10.5 | 0 | 10.5 | 0 | 10.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#307, sub 7/7/2025, $2,228.69 Agreed to $2,204.32 (9/12/25)
Y | IPCRP1-0000-0260-L | IPCRP1 | IPCRP1 | 0000-0260 | PCO#308 RFI#1135 Adjust Height MH-C03 New Grade | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | Y | 130 | Y | -130 | 0 | 0 | 0 | 0 | 0 | 130 | Y | -130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | -130 | 0 | 0 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 130 | PCO#308, work completed, but IPC having a hard time finding propoer documentation for completed work to submit PCO
Y | IPCRP1-0000-0260-M | IPCRP1 | IPCRP1 | 0000-0260 | PCO#308 RFI#1135 Adjust Height MH-C03 New Grade | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0270-C | IPCRP1 | IPCRP1 | 0000-0270 | Temp Water/Elect for Phase 1A Opening | N | C |  | UNIT | U | 0 | 6210.08 | 6210.08 | 5741.95 | 6210.08 | 100 | 0 | 0 | 0 | -468.13 | Y | 5741.95 | Y | -5741.95 | 0 | 0 | 0 | 0 | 0 | 5741.95 | Y | -5741.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5741.95 | 0 | 0 | 5741.95 | 0 | 0 | 0 | 0 | 0 | 0 | -5741.95 | 0 | 0 | 5741.95 | 5741.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | -5 | 0 | NA | 0 | 1 | 0 | 1 | LS | 6210.08 | 468.13 | 5741.95 | -468.13
Y | IPCRP1-0000-0270-L | IPCRP1 | IPCRP1 | 0000-0270 | Temp Water/Elect for Phase 1A Opening | N | L |  | UNIT | P | 0 | 11801.67 | 11801.67 | 11801.67 | 11801.67 | 100 | 0 | 0 | 0 | 0 | Y | 11801.67 | Y | -11801.67 | 0 | 0 | 0 | 0 | 0 | 11801.67 | Y | -11801.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11801.67 | 0 | 0 | 11801.67 | 0 | 0 | 0 | 0 | 0 | 0 | -11801.67 | 0 | 0 | 11801.67 | 11801.67 | 0 | 0 | 0 | 0 | 0 | 92 | 92 | 0 | 92 | 0 | 92 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | 1. PCO#293A1 (Temp Water LS) - paid under contract item PK-ESCR-049. 2. PCO#293A2 (Temp Water T&M) - agreed to value $82,883.86, need to write Akela SCO for $78,937.01, will be paid for under item HW900H. 3. PCO#293B1a (Grand St Cable Pull, IPC Support) - will be paid for / day under cc: 0000-0127. 4. PCO#293B1b (Grand St Cable Pull, EJ) - CE LS Agreement for $150,000, EJ SCO#64 for $138,453.00. 5. PCO#293D (IPC Util support for Phase 1 Opening) sub on 7/9 for $29, 364.42
Y | IPCRP1-0000-0270-S | IPCRP1 | IPCRP1 | 0000-0270 | Temp Water/Elect for Phase 1A Opening | N | S |  | UNIT | A | 0 | 1740.06 | 1740.06 | 1740.06 | 1740.06 | 100 | 0 | 0 | 0 | 0 | Y | 1740.06 | Y | -1740.06 | 0 | 0 | 0 | 0 | 0 | 1740.06 | Y | -1740.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1740.06 | 0 | 0 | 1740.06 | 0 | 0 | 0 | 0 | 0 | 0 | -1740.06 | 0 | 0 | 1740.06 | 1740.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | -14 | 0 | NA | 0 | 1 | 0 | 1 | LS | 1740.06 | 0 | 1740.06 | 0
Y | IPCRP1-0000-0271-C | IPCRP1 | IPCRP1 | 0000-0271 | Temp Power (Generator) Phase 1A - Set Up | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0271-L | IPCRP1 | IPCRP1 | 0000-0271 | Temp Power (Generator) Phase 1A - Set Up | N | L |  | UNIT | P | 0 | 10923 | 10923 | 10923 | 10923 | 100 | 0 | 0 | 0 | 0 | Y | 10923 | Y | -10923 | 0 | 0 | 0 | 0 | 0 | 10923 | Y | -10923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10923 | 0 | 0 | 10923 | 0 | 0 | 0 | 0 | 0 | 0 | -10923 | 0 | 0 | 10923 | 10923 | 0 | 0 | 0 | 0 | 0 | 91 | 91 | 0 | 91 | 0 | 91 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#293B3.1 - paid under item HW900H in PP#52 (June 25) payment, $330,039.13. EJ SCO#67 -$313,322.98 exectued 10/20/25 PCO#293B3.1, sub 5/12/25, $643,068.73, app $330,039.13, to be paid undre item HW900H - Acceleration Allowance
Y | IPCRP1-0000-0271-S | IPCRP1 | IPCRP1 | 0000-0271 | Temp Power (Generator) Phase 1A - Set Up | N | S |  | UNIT | A | 0 | 994.32 | 994.32 | 994.32 | 994.32 | 100 | 0 | 0 | 0 | 0 | Y | 994.32 | Y | -994.32 | 0 | 0 | 0 | 0 | 0 | 994.32 | Y | -994.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -994.32 | 0 | 0 | 994.32 | 0 | 0 | 0 | 0 | 0 | 0 | -994.32 | 0 | 0 | 994.32 | 994.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | -8 | 0 | NA | 0 | 1 | 0 | 1 | LS | 994.32 | 0 | 994.32 | 0
Y | IPCRP1-0000-0272-C | IPCRP1 | IPCRP1 | 0000-0272 | Temp Power (Generator) Phase 1A - Maintenance | N | C |  | UNIT | U | 0 | 0 | -0.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1551.71 | -1551.71 | 0 | NA | 0 | 4.5 | 0 | 4.5 | MO | -0.38 | -0.38 | 0 | 0
Y | IPCRP1-0000-0272-L | IPCRP1 | IPCRP1 | 0000-0272 | Temp Power (Generator) Phase 1A - Maintenance | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 4.5 | 0 | 4.5 | MO | 0 | 0 | 0 | 0 | PCO#293B3.2, start 5/16/25, took out of service 10/2/25, and returned generator 10/7/25.
Y | IPCRP1-0000-0272-S | IPCRP1 | IPCRP1 | 0000-0272 | Temp Power (Generator) Phase 1A - Maintenance | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 4.5 | 0 | 4.5 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0273-C | IPCRP1 | IPCRP1 | 0000-0273 | Temp Facility for Parks Dept - Set Up | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0.5 | 0.5 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0273-L | IPCRP1 | IPCRP1 | 0000-0273 | Temp Facility for Parks Dept - Set Up | N | L |  | UNIT | P | 0 | 8824.54 | 8824.54 | 8824.54 | 8824.54 | 45.7478 | 0 | 0 | 0 | 10465 | Y | 19289.54 | Y | -19289.54 | 0 | 0 | 0 | 0 | 0 | 19289.54 | Y | -19289.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19289.54 | 0 | 0 | 19289.54 | 0 | 0 | 0 | 0 | 0 | 0 | -19289.54 | 0 | 0 | 19289.54 | 19289.54 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 69.5 | 80.5 | 150 | HR | 0 | 0.5 | 0.5 | 1 | LS | 0 | 0 | 0 | 10465 | PCO #303A (mob & reoccurring charges), paid under HW900H in Aug 25,(PP#55) $32,275.75, for work thru Aug 2025 , $32,275.75 for Sep, $8,456.32 for Oct
Y | IPCRP1-0000-0273-S | IPCRP1 | IPCRP1 | 0000-0273 | Temp Facility for Parks Dept - Set Up | N | S |  | UNIT | A | 0 | 25773.84 | 25773.84 | 21897.82 | 25773.84 | 84.9614 | 0 | 0 | 0 | 0 | Y | 25773.84 | Y | -25773.84 | 0 | 0 | 0 | 0 | 0 | 25773.84 | Y | -25773.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25773.84 | 1259.36 | 0 | 25773.84 | 0 | 0 | 0 | 0 | 0 | 0 | -25773.84 | 0 | 0 | 25773.84 | 25773.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.63 | -54.63 | 0 | NA | 0 | 0.5 | 0.5 | 1 | LS | 25773.84 | 3876.02 | 21897.82 | 0
Y | IPCRP1-0000-0274-C | IPCRP1 | IPCRP1 | 0000-0274 | Temp Facility for Parks Dept - Maintenance | N | C |  | UNIT | U | 0 | 136847.18 | 136847.18 | 95696.67 | 136847.18 | 93.9762 | 0 | 0 | 0 | -35016.39 | Y | 101830.79 | Y | -101830.79 | 0 | 0 | 0 | 0 | 0 | 101830.79 | Y | -101830.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -101830.79 | 17546.31 | 17655.19 | 101830.79 | 0 | 0 | 0 | 15695.41 | 13768.35 | 0 | -101830.79 | 0 | 0 | 101830.79 | 101830.79 | 0 | 0 | 0 | 0 | 0 | 277.4 | 277.4 | 0 | 1726.9 | -1449.5 | 277.4 | NA | 0 | 10.5 | 1.5 | 12 | MO | 136847.18 | 41150.51 | 95696.67 | -35016.39
Y | IPCRP1-0000-0274-L | IPCRP1 | IPCRP1 | 0000-0274 | Temp Facility for Parks Dept - Maintenance | N | L |  | UNIT | P | 0 | 1065.61 | 1065.61 | 1065.61 | 1065.61 | 4.0986 | 0 | 0 | 0 | 24933.59 | Y | 25999.2 | Y | -25999.2 | 0 | 0 | 0 | 0 | 0 | 25999.2 | Y | -25999.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25999.2 | 0 | 0 | 25999.2 | 0 | 0 | 0 | 0 | 0 | 0 | -25999.2 | 0 | 0 | 25999.2 | 25999.2 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | 9 | 231 | 240 | HR | 0 | 10.5 | 1.5 | 12 | MO | 0 | 0 | 0 | 24933.59 | null
Y | IPCRP1-0000-0274-S | IPCRP1 | IPCRP1 | 0000-0274 | Temp Facility for Parks Dept - Maintenance | N | S |  | UNIT | A | 0 | 23894.79 | 23894.79 | 19861.52 | 23894.79 | 86.8259 | 0 | 0 | 0 | 0 | N | 22875.11 | N | -22875.11 | 0 | 0 | 0 | 0 | 0 | 22875.11 | N | -22875.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22875.11 | 118.67 | 379 | 22875.11 | 0 | 0 | 0 | 0 | 0 | 0 | -22875.11 | 0 | 0 | 22875.11 | 22875.11 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 0 | 39.67 | 6.33 | 46 | NA | 0 | 10.5 | 1.5 | 12 | MO | 23894.79 | 4033.27 | 19861.52 | 0
Y | IPCRP1-0000-0275-C | IPCRP1 | IPCRP1 | 0000-0275 | Temp Facility for Public - Set Up | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0275-L | IPCRP1 | IPCRP1 | 0000-0275 | Temp Facility for Public - Set Up | N | L |  | UNIT | P | 0 | 3409.99 | 3409.99 | 3409.99 | 3409.99 | 52.4614 | 0 | 0 | 0 | 3090.01 | Y | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6500 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 31 | 19 | 50 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 3090.01 | Revenue included with PCO #303A
Y | IPCRP1-0000-0275-S | IPCRP1 | IPCRP1 | 0000-0275 | Temp Facility for Public - Set Up | N | S |  | UNIT | A | 0 | 3367.03 | 3367.03 | 3367.03 | 3367.03 | 100 | 0 | 0 | 0 | 0 | N | 3367.03 | N | -3367.03 | 0 | 0 | 0 | 0 | 0 | 3367.03 | N | -3367.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3367.03 | 0 | 0 | 3367.03 | 0 | 0 | 0 | 0 | 0 | 0 | -3367.03 | 0 | 0 | 3367.03 | 3367.03 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 0 | 1 | 0 | 1 | LS | 3367.03 | 0 | 3367.03 | 0
Y | IPCRP1-0000-0276-C | IPCRP1 | IPCRP1 | 0000-0276 | Temp Facility for Public - Maintenance | N | C |  | UNIT | U | 0 | 11867.38 | 11867.38 | 8516.3 | 11867.38 | 35.4846 | 0 | 0 | 0 | 12132.62 | Y | 24000 | Y | -24000 | 0 | 0 | 0 | 0 | 0 | 24000 | Y | -24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24000 | 1197.63 | 1197.63 | 24000 | 0 | 0 | 0 | 435.5 | 435.5 | 0 | -24000 | 0 | 0 | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854 | -854 | 0 | NA | 0 | 10.5 | 1.5 | 12 | MO | 11867.38 | 3351.08 | 8516.3 | 12132.62
Y | IPCRP1-0000-0276-L | IPCRP1 | IPCRP1 | 0000-0276 | Temp Facility for Public - Maintenance | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 10.5 | 1.5 | 12 | MO | 0 | 0 | 0 | 0 | null
Y | IPCRP1-0000-0276-S | IPCRP1 | IPCRP1 | 0000-0276 | Temp Facility for Public - Maintenance | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 10.5 | 1.5 | 12 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0277-C | IPCRP1 | IPCRP1 | 0000-0277 | (PCO 260) Exclusion Zone at FBH | N | C |  | UNIT | U | 0 | 15563.56 | 15563.56 | 15525.45 | 15563.56 | 77.6273 | 0 | 0 | 0 | 4436.44 | Y | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 2190 | 2190 | 0 | 2190 | 0 | 2190 | NA | 0 | 1 | 0 | 1 | LS | 15563.56 | 38.11 | 15525.45 | 4436.44
Y | IPCRP1-0000-0277-L | IPCRP1 | IPCRP1 | 0000-0277 | (PCO 260) Exclusion Zone at FBH | N | L |  | UNIT | P | 0 | 658.22 | 658.22 | 658.22 | 658.22 | 10.1265 | 0 | 0 | 0 | 5841.78 | Y | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6500 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 6 | 44 | 50 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 5841.78 | Includes PCO #260A (FBH Temp Fence), PCO #260B (IPC Work Completed < SWO), PCO #260C (Park Furnishing Storage) , PCO #260D (United Asphalt Paving), PCO #260E (VIF Asphalt Paver Base). PCO#260A ($28,500.00) to be paid under HW-900H PCO#260A ($28,500.00) to be paid under HW-900H in PP#52 (Jun 25. PCO#260B (sub $78,995.50). PCO#260C (sub $6,000.00). PCO#260D ($51,395.45) paid under HW-900H in PP#54 (Jul 25). PCO#260E (sub $34,806.52)
Y | IPCRP1-0000-0277-S | IPCRP1 | IPCRP1 | 0000-0277 | (PCO 260) Exclusion Zone at FBH | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0278-C | IPCRP1 | IPCRP1 | 0000-0278 | Inspection of Soil for MGP, Field Order #33 | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0278-E | IPCRP1 | IPCRP1 | 0000-0278 | Inspection of Soil for MGP, Field Order #33 | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0278-L | IPCRP1 | IPCRP1 | 0000-0278 | Inspection of Soil for MGP, Field Order #33 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0280-C | IPCRP1 | IPCRP1 | 0000-0280 | PCO#305 (RFI#1021) New MH A-04 w/Sluice Gate | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 5000
Y | IPCRP1-0000-0280-L | IPCRP1 | IPCRP1 | 0000-0280 | PCO#305 (RFI#1021) New MH A-04 w/Sluice Gate | N | L |  | UNIT | P | 0 | 8307.14 | 8307.14 | 8307.14 | 8307.14 | 31.9505 | 0 | 0 | 0 | 17692.86 | Y | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26000 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | -26000 | 0 | 0 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 65 | 135 | 200 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 17692.86 | PCO #305
Y | IPCRP1-0000-0280-M | IPCRP1 | IPCRP1 | 0000-0280 | PCO#305 (RFI#1021) New MH A-04 w/Sluice Gate | N | M |  | UNIT | U | 0 | 16500 | 16500 | 0 | 16500 | 0 | 0 | 0 | 0 | 17500 | Y | 34000 | Y | -34000 | 0 | 0 | 0 | 0 | 0 | 34000 | Y | -34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -34000 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 16500 | 0 | -34000 | 0 | 0 | 34000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 16500 | 16500 | 0 | 17500
Y | IPCRP1-0000-0280-S | IPCRP1 | IPCRP1 | 0000-0280 | PCO#305 (RFI#1021) New MH A-04 w/Sluice Gate | N | S |  | UNIT | A | 0 | 2251.77 | 2251.77 | 2251.77 | 2251.77 | 100 | 0 | 0 | 0 | 0 | N | 2251.77 | N | -2251.77 | 0 | 0 | 0 | 0 | 0 | 2251.77 | N | -2251.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2251.77 | 0 | 0 | 2251.77 | 0 | 0 | 0 | 0 | 0 | 0 | -2251.77 | 0 | 0 | 2251.77 | 2251.77 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 18 | 0 | 18 | NA | 0 | 0 | 1 | 1 | LS | 2251.77 | 0 | 2251.77 | 0
Y | IPCRP1-0000-0285-L | IPCRP1 | IPCRP1 | 0000-0285 | FM#26, Prot of Amphitheater Canopy AB with Sidewal | N | L |  | UNIT | P | 0 | 13263.04 | 13263.04 | 13263.04 | 13263.04 | 100 | 0 | 0 | 0 | 0 | Y | 13263.04 | Y | -13263.04 | 0 | 0 | 0 | 0 | 0 | 13263.04 | Y | -13263.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13263.04 | 0 | 0 | 13263.04 | 0 | 0 | 0 | 0 | 0 | 0 | -13263.04 | 0 | 0 | 13263.04 | 13263.04 | 0 | 0 | 0 | 0 | 0 | 112 | 112 | 0 | 112 | 0 | 112 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | PCO #76D, sub 7/14/25, $16,645.20 (DELETED NOTES Work may be converted to contract pay items upon completion. Keeping costs separate now for ease in transferring at a later date if needed.)
Y | IPCRP1-0000-0285-S | IPCRP1 | IPCRP1 | 0000-0285 | FM#26, Prot of Amphitheater Canopy AB with Sidewal | N | S |  | UNIT | A | 0 | 1626.28 | 1626.28 | 1626.28 | 1626.28 | 100 | 0 | 0 | 0 | 0 | N | 1626.28 | N | -1626.28 | 0 | 0 | 0 | 0 | 0 | 1626.28 | N | -1626.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1626.28 | 0 | 0 | 1626.28 | 0 | 0 | 0 | 0 | 0 | 0 | -1626.28 | 0 | 0 | 1626.28 | 1626.28 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 13 | 0 | 13 | NA | 0 | 0 | 1 | 1 | LS | 1626.28 | 0 | 1626.28 | 0
Y | IPCRP1-0000-0290-C | IPCRP1 | IPCRP1 | 0000-0290 | PCO#299, Potential Costs Impact Due to New Fed Imp | N | C |  | UNIT | U | 0 | 1553.97 | 1553.97 | 1548.4 | 1553.97 | 30.968 | 0 | 0 | 0 | 3446.03 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 631.58 | 0 | 5000 | 0 | 0 | 0 | 631.58 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.29 | -449.29 | 0 | NA | 0 | 1 | 0 | 1 | LS | 1553.97 | 5.57 | 1548.4 | 3446.03
Y | IPCRP1-0000-0290-L | IPCRP1 | IPCRP1 | 0000-0290 | PCO#299, Potential Costs Impact Due to New Fed Imp | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#299
Y | IPCRP1-0000-0290-M | IPCRP1 | IPCRP1 | 0000-0290 | PCO#299, Potential Costs Impact Due to New Fed Imp | N | M |  | UNIT | U | 0 | 344656.73 | 344656.73 | 344656.73 | 344656.73 | 100.5173 | 0 | 0 | 0 | -1773.84 | Y | 342882.89 | Y | -342882.89 | 0 | 0 | 0 | 0 | 0 | 342882.89 | Y | -342882.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -342882.89 | 1773.84 | 156.04 | 342882.89 | 0 | 0 | 0 | 1917.16 | 0 | 0 | -342882.89 | 0 | 0 | 342882.89 | 342882.89 | 0 | 0 | 0 | 0 | 0 | 552.63 | 552.63 | 0 | 553.63 | -1 | 552.63 | NA | 0 | 1 | 0 | 1 | LS | 344643.95 | -12.78 | 344656.73 | -1773.84
Y | IPCRP1-0000-0295-L | IPCRP1 | IPCRP1 | 0000-0295 | PCO#316 (RFI#1047), Rework to Completed Parks Fini | N | L |  | UNIT | P | 0 | 75143.82 | 75143.82 | 75143.82 | 75143.82 | 80.1 | 0 | 0 | 0 | 18668.69 | N | 93812.51 | N | -93812.51 | 0 | 0 | 0 | 0 | 0 | 93812.51 | N | -93812.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -93812.51 | 0 | 0 | 93812.51 | 0 | 0 | 0 | 0 | 0 | 0 | -93812.51 | 0 | 0 | 93812.51 | 93812.51 | 0 | 0 | 0 | 0 | 0 | 701.85 | 701.85 | 0 | 638.5 | 63.35 | 701.85 | HR | 0 | 0.8 | 0.2 | 1 | LS | 0 | 0 | 0 | 18668.69
Y | IPCRP1-0000-0295-S | IPCRP1 | IPCRP1 | 0000-0295 | PCO#316 (RFI#1047), Rework to Completed Parks Fini | N | S |  | UNIT | A | 0 | 5740.35 | 5740.35 | 5740.35 | 5740.35 | 100 | 0 | 0 | 0 | 0 | Y | 5740.35 | Y | -5740.35 | 0 | 0 | 0 | 0 | 0 | 5740.35 | Y | -5740.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5740.35 | 0 | 0 | 5740.35 | 0 | 0 | 0 | 0 | 0 | 0 | -5740.35 | 0 | 0 | 5740.35 | 5740.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | -45 | 0 | NA | 0 | 0.8 | 0.2 | 1 | LS | 5740.35 | 0 | 5740.35 | 0
Y | IPCRP1-0000-0300-L | IPCRP1 | IPCRP1 | 0000-0300 | NYCHA Utility Interference w/ Reach K Sewer | N | L |  | UNIT | P | 0 | 38556.53 | 38556.53 | 38556.53 | 38556.53 | 100 | 0 | 0 | 0 | 0 | N | 38556.53 | N | -38556.53 | 0 | 0 | 0 | 0 | 0 | 38556.53 | N | -38556.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -38556.53 | 0 | 0 | 38556.53 | 0 | 0 | 0 | 0 | 0 | 0 | -38556.53 | 0 | 0 | 38556.53 | 38556.53 | 0 | 0 | 0 | 0 | 0 | 393 | 393 | 0 | 293 | 100 | 393 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | PCO #330, sub 8/21/25, $30,200.24
Y | IPCRP1-0000-0300-S | IPCRP1 | IPCRP1 | 0000-0300 | NYCHA Utility Interference w/ Reach K Sewer | N | S |  | UNIT | A | 0 | 7848.56 | 7848.56 | 7848.56 | 7848.56 | 100 | 0 | 0 | 0 | 0 | N | 7848.56 | N | -7848.56 | 0 | 0 | 0 | 0 | 0 | 7848.56 | N | -7848.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7848.56 | 0 | 0 | 7848.56 | 0 | 0 | 0 | 0 | 0 | 0 | -7848.56 | 0 | 0 | 7848.56 | 7848.56 | 0 | 0 | 0 | 0 | 0 | 61.5 | 61.5 | 0 | 61.5 | 0 | 61.5 | NA | 0 | 0 | 1 | 1 | LS | 7848.56 | 0 | 7848.56 | 0
Y | IPCRP1-0000-0305-L | IPCRP1 | IPCRP1 | 0000-0305 | FM#29, Remove & Salvage Esplanade Sea Rail | N | L |  | UNIT | P | 0 | 47522.73 | 47522.73 | 47522.73 | 47522.73 | 100 | 0 | 0 | 0 | 0 | Y | 47522.73 | Y | -47522.73 | 0 | 0 | 0 | 0 | 0 | 47522.73 | Y | -47522.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -47522.73 | 0 | 0 | 47522.73 | 0 | 0 | 0 | 0 | 0 | 0 | -47522.73 | 0 | 0 | 47522.73 | 47522.73 | 0 | 0 | 0 | 0 | 0 | 368 | 368 | 0 | 368 | 0 | 368 | HR | 0 | 1350 | 0 | 1350 | LF | 0 | 0 | 0 | 0 | PCO#335, sub 10/24/25, $89,350.28
Y | IPCRP1-0000-0305-S | IPCRP1 | IPCRP1 | 0000-0305 | FM#29, Remove & Salvage Esplanade Sea Rail | N | S |  | UNIT | A | 0 | 4911.03 | 4911.03 | 4911.03 | 4911.03 | 100 | 0 | 0 | 0 | 0 | N | 4911.03 | N | -4911.03 | 0 | 0 | 0 | 0 | 0 | 4911.03 | N | -4911.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4911.03 | 0 | 0 | 4911.03 | 0 | 0 | 0 | 0 | 0 | 0 | -4911.03 | 0 | 0 | 4911.03 | 4911.03 | 0 | 0 | 0 | 0 | 0 | 46.43 | 46.43 | 0 | 38 | 8.43 | 46.43 | NA | 0 | 1350 | 0 | 1350 | LF | 4911.03 | 0 | 4911.03 | 0
Y | IPCRP1-0000-0310-L | IPCRP1 | IPCRP1 | 0000-0310 | FO#34, Crosswalk & MPT, Mont St for BMCR Contract | N | L |  | UNIT | P | 0 | 1509 | 1509 | 1509 | 1509 | 100 | 0 | 0 | 0 | 0 | Y | 1509 | Y | -1509 | 0 | 0 | 0 | 0 | 0 | 1509 | Y | -1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1509 | 0 | 0 | 1509 | 0 | 0 | 0 | 0 | 0 | 0 | -1509 | 0 | 0 | 1509 | 1509 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 13 | 0 | 13 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO #333, sub 2/2/26, $32,512.54
Y | IPCRP1-0000-0310-S | IPCRP1 | IPCRP1 | 0000-0310 | FO#34, Crosswalk & MPT, Mont St for BMCR Contract | N | S |  | UNIT | A | 0 | 1806.11 | 1806.11 | 1806.11 | 1806.11 | 100 | 0 | 0 | 0 | 0 | N | 1806.11 | N | -1806.11 | 0 | 0 | 0 | 0 | 0 | 1806.11 | N | -1806.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1806.11 | 0 | 0 | 1806.11 | 0 | 0 | 0 | 0 | 0 | 0 | -1806.11 | 0 | 0 | 1806.11 | 1806.11 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 14 | 0 | 14 | NA | 0 | 1 | 0 | 1 | LS | 1806.11 | 0 | 1806.11 | 0
Y | IPCRP1-0000-0315-L | IPCRP1 | IPCRP1 | 0000-0315 | FM#28, Adjust Esplanade Wall & Rail Near Bent 0 | N | L |  | UNIT | P | 0 | 26506.8 | 26506.8 | 26506.8 | 26506.8 | 100 | 0 | 0 | 0 | 0 | Y | 26506.8 | Y | -26506.8 | 0 | 0 | 0 | 0 | 0 | 26506.8 | Y | -26506.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26506.8 | 0 | 0 | 26506.8 | 0 | 0 | 0 | 0 | 0 | 0 | -26506.8 | 0 | 0 | 26506.8 | 26506.8 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 0 | 215 | 0 | 215 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#331
Y | IPCRP1-0000-0315-M | IPCRP1 | IPCRP1 | 0000-0315 | FM#28, Adjust Esplanade Wall & Rail Near Bent 0 | N | M |  | UNIT | U | 0 | 1245.31 | 1245.31 | 1143.8 | 1245.31 | 91.8486 | 0 | 0 | 0 | 0 | N | 1245.31 | N | -1245.31 | 0 | 0 | 0 | 0 | 0 | 1245.31 | N | -1245.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1245.31 | 0 | 0 | 1245.31 | 0 | 0 | 0 | 0 | 0 | 0 | -1245.31 | 0 | 0 | 1245.31 | 1245.31 | 0 | 0 | 0 | 0 | 0 | 114 | 114 | 0 | 114 | 0 | 114 | NA | 0 | 1 | 0 | 1 | LS | 1245.31 | 101.51 | 1143.8 | 0
Y | IPCRP1-0000-0315-S | IPCRP1 | IPCRP1 | 0000-0315 | FM#28, Adjust Esplanade Wall & Rail Near Bent 0 | N | S |  | UNIT | A | 0 | 323.09 | 323.09 | 323.09 | 323.09 | 100 | 0 | 0 | 0 | 0 | Y | 323.09 | Y | -323.09 | 0 | 0 | 0 | 0 | 0 | 323.09 | Y | -323.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -323.09 | 0 | 0 | 323.09 | 0 | 0 | 0 | 0 | 0 | 0 | -323.09 | 0 | 0 | 323.09 | 323.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | -2.5 | 0 | NA | 0 | 1 | 0 | 1 | LS | 323.09 | 0 | 323.09 | 0
Y | IPCRP1-0000-0320-L | IPCRP1 | IPCRP1 | 0000-0320 | FM#27, Remob Costs, CHP Shared Use Path (NCCD #11 | N | L |  | UNIT | P | 0 | 2748.48 | 2748.48 | 2748.48 | 2748.48 | 100 | 0 | 0 | 0 | 0 | Y | 2748.48 | Y | -2748.48 | 0 | 0 | 0 | 0 | 0 | 2748.48 | Y | -2748.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2748.48 | 0 | 0 | 2748.48 | 0 | 0 | 0 | 0 | 0 | 0 | -2748.48 | 0 | 0 | 2748.48 | 2748.48 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 22 | 0 | 22 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#325
Y | IPCRP1-0000-0320-S | IPCRP1 | IPCRP1 | 0000-0320 | FM#27, Remob Costs, CHP Shared Use Path (NCCD #11 | N | S |  | UNIT | A | 0 | 1719.73 | 1719.73 | 1719.73 | 1719.73 | 100 | 0 | 0 | 0 | 0 | Y | 1719.73 | Y | -1719.73 | 0 | 0 | 0 | 0 | 0 | 1719.73 | Y | -1719.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1719.73 | 0 | 0 | 1719.73 | 0 | 0 | 0 | 0 | 0 | 0 | -1719.73 | 0 | 0 | 1719.73 | 1719.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5 | -13.5 | 0 | NA | 0 | 1 | 0 | 1 | LS | 1719.73 | 0 | 1719.73 | 0
Y | IPCRP1-0000-0325-L | IPCRP1 | IPCRP1 | 0000-0325 | Changes to W Side WBB Fence (RFI#1140) | N | L |  | UNIT | P | 0 | 7638.95 | 7638.95 | 7638.95 | 7638.95 | 100 | 0 | 0 | 0 | 0 | Y | 7638.95 | Y | -7638.95 | 0 | 0 | 0 | 0 | 0 | 7638.95 | Y | -7638.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7638.95 | 0 | 0 | 7638.95 | 0 | 0 | 0 | 0 | 0 | 0 | -7638.95 | 0 | 0 | 7638.95 | 7638.95 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 60 | 0 | 60 | HR | 0 | 0.9 | 0.1 | 1 | LS | 0 | 0 | 0 | 0 | PCO#285 re-entered on 7/24/25 ***not 341
Y | IPCRP1-0000-0325-S | IPCRP1 | IPCRP1 | 0000-0325 | Changes to W Side WBB Fence (RFI#1140) | N | S |  | UNIT | A | 0 | 765.17 | 765.17 | 765.17 | 765.17 | 15.3034 | 0 | 0 | 0 | 4234.83 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -6 | 0 | NA | 0 | 0.9 | 0.1 | 1 | LS | 765.17 | 0 | 765.17 | 4234.83
Y | IPCRP1-0000-0330-C | IPCRP1 | IPCRP1 | 0000-0330 | Cherry St Park Side Extra Electric Work (PCO#336) | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | Y | 3000 | Y | -3000 | 0 | 0 | 0 | 0 | 0 | 3000 | Y | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0.76 | 0.24 | 1 | LS | 0 | 0 | 0 | 3000
Y | IPCRP1-0000-0330-L | IPCRP1 | IPCRP1 | 0000-0330 | Cherry St Park Side Extra Electric Work (PCO#336) | N | L |  | UNIT | P | 0 | 27865.81 | 27865.81 | 27865.81 | 27865.81 | 76 | 0 | 0 | 0 | 8799.73 | N | 36665.54 | N | -36665.54 | 0 | 0 | 0 | 0 | 0 | 36665.54 | N | -36665.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36665.54 | 0 | 0 | 36665.54 | 0 | 0 | 0 | 0 | 0 | 0 | -36665.54 | 0 | 0 | 36665.54 | 36665.54 | 0 | 0 | 0 | 0 | 0 | 214.5 | 214.5 | 0 | 214.5 | 0 | 214.5 | HR | 0 | 0.76 | 0.24 | 1 | LS | 0 | 0 | 0 | 8799.73 | PCO #336. This is for Additional Work specified by DDC to bring power to Property Box Stub Out as shown on contract drawing BC190 from Cheery Street Crossing added to contract via Change Order.
Y | IPCRP1-0000-0330-M | IPCRP1 | IPCRP1 | 0000-0330 | Cherry St Park Side Extra Electric Work (PCO#336) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0.76 | 0.24 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0330-S | IPCRP1 | IPCRP1 | 0000-0330 | Cherry St Park Side Extra Electric Work (PCO#336) | N | S |  | UNIT | A | 0 | 3367.23 | 3367.23 | 3367.23 | 3367.23 | 16.0344 | 0 | 0 | 0 | 17632.77 | Y | 21000 | Y | -21000 | 0 | 0 | 0 | 0 | 0 | 21000 | Y | -21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21000 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | -21000 | 0 | 0 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5 | -26.5 | 0 | NA | 0 | 0.76 | 0.24 | 1 | LS | 3367.23 | 0 | 3367.23 | 17632.77
Y | IPCRP1-0000-0335-C | IPCRP1 | IPCRP1 | 0000-0335 | PCO#337, Phase One Labor Day Opening Extra’s | N | C |  | UNIT | U | 0 | 8165.63 | 8165.63 | 8165.63 | 8165.63 | 100 | 0 | 0 | 0 | 0 | N | 8165.63 | N | -8165.63 | 0 | 0 | 0 | 0 | 0 | 8165.63 | N | -8165.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8165.63 | 0 | 0 | 8165.63 | 0 | 0 | 0 | 0 | 0 | 0 | -8165.63 | 0 | 0 | 8165.63 | 8165.63 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 0 | 0 | 1 | 1 | LS | 8165.63 | 0 | 8165.63 | 0
Y | IPCRP1-0000-0335-L | IPCRP1 | IPCRP1 | 0000-0335 | PCO#337, Phase One Labor Day Opening Extra’s | N | L |  | UNIT | P | 0 | 11911.12 | 11911.12 | 11911.12 | 11911.12 | 100 | 0 | 0 | 0 | 0 | Y | 11911.12 | Y | -11911.12 | 0 | 0 | 0 | 0 | 0 | 11911.12 | Y | -11911.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11911.12 | 0 | 0 | 11911.12 | 0 | 0 | 0 | 0 | 0 | 0 | -11911.12 | 0 | 0 | 11911.12 | 11911.12 | 0 | 0 | 0 | 0 | 0 | 96.5 | 96.5 | 0 | 96.5 | 0 | 96.5 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | PCO #337. IPC closed Packages 2 & 3. Package 4, sub 12/16/25, $5,149.12, paid in PP#59 (Nov 25) item HW-900H. Package 1 sub 8/27/25, $96,828.20, app $29,062.96 but need to add EJ T&M to this, before PMCM finalizes
Y | IPCRP1-0000-0335-S | IPCRP1 | IPCRP1 | 0000-0335 | PCO#337, Phase One Labor Day Opening Extra’s | N | S |  | UNIT | A | 0 | 1270.65 | 1270.65 | 1270.65 | 1270.65 | 100 | 0 | 0 | 0 | 0 | N | 1270.65 | N | -1270.65 | 0 | 0 | 0 | 0 | 0 | 1270.65 | N | -1270.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1270.65 | 0 | 0 | 1270.65 | 0 | 0 | 0 | 0 | 0 | 0 | -1270.65 | 0 | 0 | 1270.65 | 1270.65 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 10 | NA | 0 | 0 | 1 | 1 | LS | 1270.65 | 0 | 1270.65 | 0
Y | IPCRP1-0000-0340-L | IPCRP1 | IPCRP1 | 0000-0340 | FM#32, Shared Path at CHP Entrance & Cherry st (CL | N | L |  | UNIT | P | 0 | 401.97 | 401.97 | 401.97 | 401.97 | 100 | 0 | 0 | 0 | 0 | Y | 401.97 | Y | -401.97 | 0 | 0 | 0 | 0 | 0 | 401.97 | Y | -401.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -401.97 | 0 | 0 | 401.97 | 0 | 0 | 0 | 0 | 0 | 0 | -401.97 | 0 | 0 | 401.97 | 401.97 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0340-S | IPCRP1 | IPCRP1 | 0000-0340 | FM#32, Shared Path at CHP Entrance & Cherry st (CL | N | S |  | UNIT | A | 0 | 508.26 | 508.26 | 508.26 | 508.26 | 100 | 0 | 0 | 0 | 0 | N | 508.26 | N | -508.26 | 0 | 0 | 0 | 0 | 0 | 508.26 | N | -508.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -508.26 | 0 | 0 | 508.26 | 0 | 0 | 0 | 0 | 0 | 0 | -508.26 | 0 | 0 | 508.26 | 508.26 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 0 | 1 | 0 | 1 | LS | 508.26 | 0 | 508.26 | 0
Y | IPCRP1-0000-0345-C | IPCRP1 | IPCRP1 | 0000-0345 | Backcharge to ASW for M&O2 Building Repairs | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0345-L | IPCRP1 | IPCRP1 | 0000-0345 | Backcharge to ASW for M&O2 Building Repairs | N | L |  | UNIT | P | 0 | 10363.53 | 10363.53 | 10363.53 | 10363.53 | 100 | 0 | 0 | 0 | 0 | Y | 10363.53 | Y | -10363.53 | 0 | 0 | 0 | 0 | 0 | 10363.53 | Y | -10363.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10363.53 | 0 | 0 | 10363.53 | 0 | 0 | 0 | 0 | 0 | 0 | -10363.53 | 0 | 0 | 10363.53 | 10363.53 | 0 | 0 | 0 | 0 | 0 | 89 | 89 | 0 | 89 | 0 | 89 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0345-S | IPCRP1 | IPCRP1 | 0000-0345 | Backcharge to ASW for M&O2 Building Repairs | N | S |  | UNIT | A | 0 | 645.49 | 645.49 | 645.49 | 645.49 | 100 | 0 | 0 | 0 | 0 | Y | 645.49 | Y | -645.49 | 0 | 0 | 0 | 0 | 0 | 645.49 | Y | -645.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -645.49 | 0 | 0 | 645.49 | 0 | 0 | 0 | 0 | 0 | 0 | -645.49 | 0 | 0 | 645.49 | 645.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | -5 | 0 | NA | 0 | 1 | 0 | 1 | LS | 645.49 | 0 | 645.49 | 0
Y | IPCRP1-0000-0350-L | IPCRP1 | IPCRP1 | 0000-0350 | Type 3 Catch Basin, Reach A Shared Path (RFI#1138, | N | L |  | UNIT | P | 0 | 15956.01 | 15956.01 | 15956.01 | 15956.01 | 100 | 0 | 0 | 0 | 0 | Y | 15956.01 | Y | -15956.01 | 0 | 0 | 0 | 0 | 0 | 15956.01 | Y | -15956.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15956.01 | 0 | 0 | 15956.01 | 0 | 0 | 0 | 0 | 0 | 0 | -15956.01 | 0 | 0 | 15956.01 | 15956.01 | 0 | 0 | 0 | 0 | 0 | 124.5 | 124.5 | 0 | 124.5 | 0 | 124.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO #362
Y | IPCRP1-0000-0350-M | IPCRP1 | IPCRP1 | 0000-0350 | Type 3 Catch Basin, Reach A Shared Path (RFI#1138, | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0350-S | IPCRP1 | IPCRP1 | 0000-0350 | Type 3 Catch Basin, Reach A Shared Path (RFI#1138, | N | S |  | UNIT | A | 0 | 3356.56 | 3356.56 | 3356.56 | 3356.56 | 100 | 0 | 0 | 0 | 0 | N | 3356.56 | N | -3356.56 | 0 | 0 | 0 | 0 | 0 | 3356.56 | N | -3356.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3356.56 | 0 | 0 | 3356.56 | 0 | 0 | 0 | 0 | 0 | 0 | -3356.56 | 0 | 0 | 3356.56 | 3356.56 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 26 | 0 | 26 | NA | 0 | 1 | 0 | 1 | LS | 3356.56 | 0 | 3356.56 | 0
Y | IPCRP1-0000-0355-C | IPCRP1 | IPCRP1 | 0000-0355 | Amphitheatre Canopy – IPC Protection & Support | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0355-L | IPCRP1 | IPCRP1 | 0000-0355 | Amphitheatre Canopy – IPC Protection & Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174000 | Y | 174000 | Y | -174000 | 0 | 0 | 0 | 0 | 0 | 174000 | Y | -174000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -174000 | 0 | 0 | 174000 | 0 | 0 | 0 | 0 | 0 | 0 | -174000 | 0 | 0 | 174000 | 174000 | 0 | 0 | 0 | 0 | 0 | 1328.04 | 1328.04 | 0 | 0 | 1328.04 | 1328.04 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 174000 | 1. IPC support includes Labor to F&I DOB fence, F&P grout pads & place gravel near AB assemblies. (app 804MH, $104K). Plus Labor to support ASW (app 524 MH, 70K) which we hope not to utilize. 2. Equipment cost in estimate were negligible (11K) & will be absorbed in our Equipment cc’s, as will Supervision & STS.
Y | IPCRP1-0000-0355-M | IPCRP1 | IPCRP1 | 0000-0355 | Amphitheatre Canopy – IPC Protection & Support | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26000 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | -26000 | 0 | 0 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 26000
Y | IPCRP1-0000-0355-S | IPCRP1 | IPCRP1 | 0000-0355 | Amphitheatre Canopy – IPC Protection & Support | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0356-L | IPCRP1 | IPCRP1 | 0000-0356 | Amphitheatre Canopy – ASW Cost to Erect Canopy | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0356-S | IPCRP1 | IPCRP1 | 0000-0356 | Amphitheatre Canopy – ASW Cost to Erect Canopy | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 10 | 1. Price is not finalized yet. ASW was at 3.9M, IPC at 3.8M. Hoping to split difference & settle.
Y | IPCRP1-0000-0357-L | IPCRP1 | IPCRP1 | 0000-0357 | Amphitheatre Canopy – PM Furnishing Canopy | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0357-M | IPCRP1 | IPCRP1 | 0000-0357 | Amphitheatre Canopy – PM Furnishing Canopy | N | M |  | UNIT | U | 0 | 4290182.61 | 4290182.61 | 421009.77 | 4290182.61 | 9.9556 | 0 | 0 | 0 | -61295.61 | Y | 4228887 | Y | -4228887 | 0 | 0 | 0 | 0 | 0 | 4228887 | Y | -4228887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4228887 | 141933.77 | 0 | 4228887 | 0 | 0 | 0 | 61295.61 | 0 | 0 | -4228887 | 0 | 0 | 4228887 | 4228887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378046.77 | -378046.77 | 0 | NA | 0 | 0 | 0 | 0 | LS | 4290182.61 | 3869172.84 | 421009.77 | -61295.61 | 1. Structural Steel (Rebellion) $2,732,733 which includes delegated design, plus mockup ($117,000), not taking giveback (-80,000) as we may need for full scale mockup. 2. GFRC (Stromberg) $1,278,260 plus mockup ($85,424). 3. Plus Misc ($10,000.00). 4. Still need to buyout, and may want to consider adding P&P bond.
Y | IPCRP1-0000-0358-L | IPCRP1 | IPCRP1 | 0000-0358 | Amphitheatre Canopy – Other Subcontractor Scope | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0358-S | IPCRP1 | IPCRP1 | 0000-0358 | Amphitheatre Canopy – Other Subcontractor Scope | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197350 | Y | 197350 | Y | -197350 | 0 | 0 | 0 | 0 | 0 | 197350 | Y | -197350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -197350 | 0 | 0 | 197350 | 0 | 0 | 0 | 0 | 0 | 0 | -197350 | 0 | 0 | 197350 | 197350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 197350 | 1. Carry here for now, so captured in PMF. Will be charged elsewhere at a later date and zeroed out. 2. Dreamland Security ($111,350), Crossroads ($45,000), Testing Lab Services ($11,000), RPO (20K)
Y | IPCRP1-0000-0365-L | IPCRP1 | IPCRP1 | 0000-0365 | Test Pit for NYCHA Steam in Reach K (RFI#1191) | N | L |  | UNIT | P | 0 | 14198.53 | 14198.53 | 14198.53 | 14198.53 | 100 | 0 | 0 | 0 | 0 | Y | 14198.53 | Y | -14198.53 | 0 | 0 | 0 | 0 | 0 | 14198.53 | Y | -14198.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14198.53 | 0 | 0 | 14198.53 | 0 | 0 | 0 | 0 | 0 | 0 | -14198.53 | 0 | 0 | 14198.53 | 14198.53 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 120 | 0 | 120 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0365-S | IPCRP1 | IPCRP1 | 0000-0365 | Test Pit for NYCHA Steam in Reach K (RFI#1191) | N | S |  | UNIT | A | 0 | 2425.01 | 2425.01 | 2425.01 | 2425.01 | 100 | 0 | 0 | 0 | 0 | N | 2425.01 | N | -2425.01 | 0 | 0 | 0 | 0 | 0 | 2425.01 | N | -2425.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2425.01 | 0 | 0 | 2425.01 | 0 | 0 | 0 | 0 | 0 | 0 | -2425.01 | 0 | 0 | 2425.01 | 2425.01 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 0 | 19 | 0 | 19 | NA | 0 | 1 | 0 | 1 | LS | 2425.01 | 0 | 2425.01 | 0
Y | IPCRP1-0000-0370-L | IPCRP1 | IPCRP1 | 0000-0370 | Add Efforts to Inst Retract Bollards in Open Park | N | L |  | UNIT | P | 0 | 10314.27 | 10314.27 | 10314.27 | 10314.27 | 100 | 0 | 0 | 0 | 0 | Y | 10314.27 | Y | -10314.27 | 0 | 0 | 0 | 0 | 0 | 10314.27 | Y | -10314.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10314.27 | 0 | 0 | 10314.27 | 0 | 0 | 0 | 0 | 0 | 0 | -10314.27 | 0 | 0 | 10314.27 | 10314.27 | 0 | 0 | 0 | 0 | 0 | 87.5 | 87.5 | 0 | 87.5 | 0 | 87.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0370-S | IPCRP1 | IPCRP1 | 0000-0370 | Add Efforts to Inst Retract Bollards in Open Park | N | S |  | UNIT | A | 0 | 3956.6 | 3956.6 | 3956.6 | 3956.6 | 100 | 0 | 0 | 0 | 0 | N | 3956.6 | N | -3956.6 | 0 | 0 | 0 | 0 | 0 | 3956.6 | N | -3956.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3956.6 | 0 | 0 | 3956.6 | 0 | 0 | 0 | 0 | 0 | 0 | -3956.6 | 0 | 0 | 3956.6 | 3956.6 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 0 | 31 | 0 | 31 | NA | 0 | 1 | 0 | 1 | LS | 3956.6 | 0 | 3956.6 | 0
Y | IPCRP1-0000-0375-L | IPCRP1 | IPCRP1 | 0000-0375 | Exist Sheet in New CombiWall in Reach H-I-J PCO390 | N | L |  | UNIT | P | 0 | 80438.08 | 80438.08 | 80438.08 | 80438.08 | 100 | 0 | 0 | 0 | 0 | Y | 80438.08 | Y | -80438.08 | 0 | 0 | 0 | 0 | 0 | 80438.08 | Y | -80438.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -80438.08 | 0 | 20253.69 | 80438.08 | 0 | 0 | 0 | 0 | 0 | 0 | -80438.08 | 0 | 0 | 80438.08 | 80438.08 | 0 | 0 | 0 | 0 | 0 | 577.5 | 577.5 | 0 | 577.5 | 0 | 577.5 | HR | 0 | 0.4 | 0.6 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0375-S | IPCRP1 | IPCRP1 | 0000-0375 | Exist Sheet in New CombiWall in Reach H-I-J PCO390 | N | S |  | UNIT | A | 0 | 11473.28 | 11473.28 | 11473.28 | 11473.28 | 110.579 | 0 | 0 | 0 | -1097.64 | Y | 10375.64 | Y | -10375.64 | 0 | 0 | 0 | 0 | 0 | 10375.64 | Y | -10375.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10375.64 | 1097.64 | 1703.69 | 10375.64 | 0 | 0 | 0 | 0 | 1097.64 | 0 | -10375.64 | 0 | 0 | 10375.64 | 10375.64 | 0 | 0 | 0 | 0 | 0 | 68 | 68 | 0 | 68 | 0 | 68 | NA | 0 | 0.4 | 0.6 | 1 | LS | 11473.28 | 0 | 11473.28 | -1097.64
Y | IPCRP1-0000-0380-L | IPCRP1 | IPCRP1 | 0000-0380 | Obstruction Beneath FDR Median at Delancey St | N | L |  | UNIT | P | 0 | 11289.68 | 11289.68 | 11289.68 | 11289.68 | 67.0004 | 0 | 0 | 0 | 5560.5 | Y | 16850.18 | Y | -16850.18 | 0 | 0 | 0 | 0 | 0 | 16850.18 | Y | -16850.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16850.18 | 0 | 0 | 16850.18 | 0 | 0 | 0 | 0 | 0 | 0 | -16850.18 | 0 | 0 | 16850.18 | 16850.18 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 67 | 33 | 100 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 5560.5
Y | IPCRP1-0000-0380-S | IPCRP1 | IPCRP1 | 0000-0380 | Obstruction Beneath FDR Median at Delancey St | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0385-L | IPCRP1 | IPCRP1 | 0000-0385 | RFI#1234, As Built MP & Exist Footing at Houston S | N | L |  | UNIT | P | 0 | 17731.57 | 17731.57 | 17731.57 | 17731.57 | 99.3844 | 0 | 0 | 0 | 109.84 | Y | 17841.41 | Y | -17841.41 | 0 | 0 | 0 | 0 | 0 | 17841.41 | Y | -17841.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17841.41 | 0 | 0 | 17841.41 | 0 | 0 | 0 | 0 | 0 | 0 | -17841.41 | 0 | 0 | 17841.41 | 17841.41 | 0 | 0 | 0 | 0 | 0 | 158.5 | 158.5 | 0 | 157.5 | 1 | 158.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 109.84
Y | IPCRP1-0000-0385-S | IPCRP1 | IPCRP1 | 0000-0385 | RFI#1234, As Built MP & Exist Footing at Houston S | N | S |  | UNIT | A | 0 | 2167.99 | 2167.99 | 2167.99 | 2167.99 | 36.1332 | 0 | 0 | 0 | 3832.01 | Y | 6000 | Y | -6000 | 0 | 0 | 0 | 0 | 0 | 6000 | Y | -6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | -6000 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 17 | 0 | 17 | NA | 0 | 1 | 0 | 1 | LS | 2167.99 | 0 | 2167.99 | 3832.01
Y | IPCRP1-0000-0390-L | IPCRP1 | IPCRP1 | 0000-0390 | Reach K, MGP Soil in Sewer Trench, Temp Work | N | L |  | UNIT | P | 0 | 3700.79 | 3700.79 | 3700.79 | 3700.79 | 100 | 0 | 0 | 0 | 0 | Y | 3700.79 | Y | -3700.79 | 0 | 0 | 0 | 0 | 0 | 3700.79 | Y | -3700.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3700.79 | 0 | 0 | 3700.79 | 0 | 0 | 0 | 0 | 0 | 0 | -3700.79 | 0 | 0 | 3700.79 | 3700.79 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 32 | 0 | 32 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0390-S | IPCRP1 | IPCRP1 | 0000-0390 | Reach K, MGP Soil in Sewer Trench, Temp Work | N | S |  | UNIT | A | 0 | 1020.23 | 1020.23 | 1020.23 | 1020.23 | 100 | 0 | 0 | 0 | 0 | Y | 1020.23 | Y | -1020.23 | 0 | 0 | 0 | 0 | 0 | 1020.23 | Y | -1020.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1020.23 | 0 | 0 | 1020.23 | 0 | 0 | 0 | 0 | 0 | 0 | -1020.23 | 0 | 0 | 1020.23 | 1020.23 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 0 | 1 | 0 | 1 | LS | 1020.23 | 0 | 1020.23 | 0
Y | IPCRP1-0000-0395-L | IPCRP1 | IPCRP1 | 0000-0395 | FM#38, Relocate 3 Trees from Fields 1-2 to CHP | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | PCO#401
Y | IPCRP1-0000-0395-S | IPCRP1 | IPCRP1 | 0000-0395 | FM#38, Relocate 3 Trees from Fields 1-2 to CHP | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | Y | 8000 | Y | -8000 | 0 | 0 | 0 | 0 | 0 | 8000 | Y | -8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | -8000 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 8000
Y | IPCRP1-0000-0400-C | IPCRP1 | IPCRP1 | 0000-0400 | FM#39, Park Drainage Grates, Replace for ADA Compl | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | Y | 2000 | Y | -2000 | 0 | 0 | 0 | 0 | 0 | 2000 | Y | -2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 20 | 20 | EA | 0 | 0 | 0 | 2000
Y | IPCRP1-0000-0400-L | IPCRP1 | IPCRP1 | 0000-0400 | FM#39, Park Drainage Grates, Replace for ADA Compl | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | Y | 21000 | Y | -21000 | 0 | 0 | 0 | 0 | 0 | 21000 | Y | -21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21000 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | -21000 | 0 | 0 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 0 | 0 | 160 | 160 | HR | 0 | 0 | 20 | 20 | EA | 0 | 0 | 0 | 21000 | PCO#402
Y | IPCRP1-0000-0400-M | IPCRP1 | IPCRP1 | 0000-0400 | FM#39, Park Drainage Grates, Replace for ADA Compl | N | M |  | UNIT | U | 0 | 85500 | 85500 | 0 | 85500 | 0 | 0 | 0 | 0 | 0 | Y | 85500 | Y | -85500 | 0 | 0 | 0 | 0 | 0 | 85500 | Y | -85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -85500 | 0 | 0 | 85500 | 0 | 0 | 0 | 0 | 85500 | 0 | -85500 | 0 | 0 | 85500 | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 20 | 20 | EA | 85500 | 85500 | 0 | 0
Y | IPCRP1-0000-0405-L | IPCRP1 | IPCRP1 | 0000-0405 | FM#32 REV 1 – Modifications to CHP Entrance at Che | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26000 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | -26000 | 0 | 0 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 200 | 200 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 26000 | PCO #351
Y | IPCRP1-0000-0405-M | IPCRP1 | IPCRP1 | 0000-0405 | FM#32 REV 1 – Modifications to CHP Entrance at Che | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 5000
Y | IPCRP1-0000-0410-L | IPCRP1 | IPCRP1 | 0000-0410 | PCO#109 – IPC Support Cost, Houston St Retain Wall | N | L |  | UNIT | P | 0 | 66094.8 | 66094.8 | 66094.8 | 66094.8 | 137.3678 | 0 | 0 | 0 | -17979.61 | Y | 48115.19 | Y | -48115.19 | 0 | 0 | 0 | 0 | 0 | 48115.19 | Y | -48115.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -48115.19 | 17979.61 | 2788.74 | 48115.19 | 0 | 0 | 0 | 0 | 0 | 0 | -48115.19 | 0 | 0 | 48115.19 | 48115.19 | 0 | 0 | 0 | 0 | 0 | 415.5 | 415.5 | 0 | 594.5 | -179 | 415.5 | HR | 0 | 0.75 | 0.25 | 1 | LS | 0 | 0 | 0 | -17979.61 | PCO#109
N | IPCRP1-0000-0410-S | IPCRP1 | IPCRP1 | 0000-0410 | PCO#109 – IPC Support Cost, Houston St Retain Wall | N | S |  | UNIT | A | 0 | 1502.32 | 1502.32 | 1502.32 | 1502.32 | 100 | 0 | 0 | 0 | 0 | N | 1502.32 | N | -1502.32 | 0 | 0 | 0 | 0 | 0 | 1502.32 | N | -1502.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1502.32 | 322.84 | 1179.48 | 1502.32 | 0 | 0 | 0 | 0 | 322.84 | 0 | -1502.32 | 0 | 0 | 1502.32 | 1502.32 | 0 | 0 | 0 | 0 | 0 | 11.5 | 11.5 | 0 | 0 | 11.5 | 11.5 | NA | 0 | 0.75 | 0.25 | 1 | LS | 1502.32 | 0 | 1502.32 | 0
Y | IPCRP1-0000-0415-E | IPCRP1 | IPCRP1 | 0000-0415 | CFW, Reach K, Excavate & Sheet | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 120 | 40 | 160 | LF | 0 | 0 | 0 | 100000
Y | IPCRP1-0000-0415-L | IPCRP1 | IPCRP1 | 0000-0415 | CFW, Reach K, Excavate & Sheet | N | L |  | UNIT | P | 0 | 42094.36 | 42094.36 | 42094.36 | 42094.36 | 40.4753 | 0 | 0 | 0 | 61905.64 | Y | 104000 | Y | -104000 | 0 | 0 | 0 | 0 | 0 | 104000 | Y | -104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -104000 | 0 | 8342.34 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | -104000 | 0 | 0 | 104000 | 104000 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 305 | 495 | 800 | HR | 0 | 120 | 40 | 160 | LF | 0 | 0 | 0 | 61905.64 | Refer to BS email 1/17/26 where CE accepts proposal for 1.272M plus CTI work under JB123 & JB 450.3 items. Total value = 3.48M
Y | IPCRP1-0000-0415-S | IPCRP1 | IPCRP1 | 0000-0415 | CFW, Reach K, Excavate & Sheet | N | S |  | UNIT | A | 0 | 1066.39 | 1066.39 | 1066.39 | 1066.39 | 100 | 0 | 0 | 0 | 0 | Y | 1066.39 | Y | -1066.39 | 0 | 0 | 0 | 0 | 0 | 1066.39 | Y | -1066.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1066.39 | 0 | 0 | 1066.39 | 0 | 0 | 0 | 0 | 0 | 0 | -1066.39 | 0 | 0 | 1066.39 | 1066.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | -8.5 | 0 | NA | 0 | 120 | 40 | 160 | LF | 1066.39 | 0 | 1066.39 | 0
Y | IPCRP1-0000-0416-L | IPCRP1 | IPCRP1 | 0000-0416 | CFW, Reach K, Backfill & Sheet | N | L |  | UNIT | P | 0 | -99.53 | -99.53 | -99.53 | -99.53 | -0.38281 | 0 | 0 | 0 | 26099.53 | Y | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 26000 | Y | -26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26000 | 0 | -8342.34 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | -26000 | 0 | 0 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 200 | 200 | HR | 0 | 0 | 160 | 160 | LF | 0 | 0 | 0 | 26099.53
Y | IPCRP1-0000-0416-S | IPCRP1 | IPCRP1 | 0000-0416 | CFW, Reach K, Backfill & Sheet | N | S |  | UNIT | A | 0 | 125.46 | 125.46 | 125.46 | 125.46 | 100 | 0 | 0 | 0 | 0 | N | 125.46 | N | -125.46 | 0 | 0 | 0 | 0 | 0 | 125.46 | N | -125.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -125.46 | 0 | 0 | 125.46 | 0 | 0 | 0 | 0 | 0 | 0 | -125.46 | 0 | 0 | 125.46 | 125.46 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 0 | 0 | 160 | 160 | LF | 125.46 | 0 | 125.46 | 0
Y | IPCRP1-0000-0417-L | IPCRP1 | IPCRP1 | 0000-0417 | CFW, Reach K, CTI Work | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | CTI accepts at 1.536M, VS adds 12 barrels wraps @5k/ ea = 1.596M
Y | IPCRP1-0000-0417-S | IPCRP1 | IPCRP1 | 0000-0417 | CFW, Reach K, CTI Work | N | S |  | UNIT | A | 0 | 1536000 | 1536000 | 0 | 1536000 | 0 | 0 | 0 | 0 | 60000 | Y | 1596000 | Y | -1596000 | 0 | 0 | 0 | 0 | 0 | 1596000 | Y | -1596000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1596000 | 0 | 0 | 1596000 | 0 | 0 | 0 | 0 | 0 | 0 | -1596000 | 0 | 0 | 1596000 | 1596000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 1536000 | 1536000 | 0 | 60000
Y | IPCRP1-0000-0418-L | IPCRP1 | IPCRP1 | 0000-0418 | CFW, Reach K, CTI Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 13000 | need to $30,000 for subcontractor (Pinnacle)
Y | IPCRP1-0000-0418-S | IPCRP1 | IPCRP1 | 0000-0418 | CFW, Reach K, CTI Support | N | S |  | UNIT | A | 0 | 258.27 | 258.27 | 258.27 | 258.27 | 0.8609 | 0 | 0 | 0 | 29741.73 | Y | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30000 | 258.27 | 0 | 30000 | 0 | 0 | 0 | 0 | 258.27 | 0 | -30000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 258.27 | 0 | 258.27 | 29741.73
Y | IPCRP1-0000-0420-L | IPCRP1 | IPCRP1 | 0000-0420 | Add Demo at Exist North Embayment (NCCD#132) | N | L |  | UNIT | P | 0 | 48055.73 | 48055.73 | 48055.73 | 48055.73 | 171.0946 | 0 | 0 | 0 | -19968.51 | Y | 28087.22 | Y | -28087.22 | 0 | 0 | 0 | 0 | 0 | 28087.22 | Y | -28087.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28087.22 | 19968.51 | 28087.22 | 28087.22 | 0 | 0 | 0 | 0 | 0 | 0 | -28087.22 | 0 | 0 | 28087.22 | 28087.22 | 0 | 0 | 0 | 0 | 0 | 195 | 195 | 0 | 314 | -119 | 195 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | -19968.51 | NCCD#132. This will be PCO#416. Work started on January 12, 2026, so we will have to go back and move costs and generate T&M tickets.
N | IPCRP1-0000-0420-S | IPCRP1 | IPCRP1 | 0000-0420 | Add Demo at Exist North Embayment (NCCD#132) | N | S |  | UNIT | A | 0 | 3163.8 | 3163.8 | 3163.8 | 3163.8 | 100 | 0 | 0 | 0 | 0 | N | 3163.8 | N | -3163.8 | 0 | 0 | 0 | 0 | 0 | 3163.8 | N | -3163.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3163.8 | 3163.8 | 0 | 3163.8 | 0 | 0 | 0 | 0 | 3163.8 | 0 | -3163.8 | 0 | 0 | 3163.8 | 3163.8 | 0 | 0 | 0 | 0 | 0 | 24.5 | 24.5 | 0 | 0 | 24.5 | 24.5 | NA | 0 | 0 | 1 | 1 | LS | 3163.8 | 0 | 3163.8 | 0
Y | IPCRP1-0000-0425-C | IPCRP1 | IPCRP1 | 0000-0425 | Vent Details at Exist & New Houston St Retaining W | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 5000
Y | IPCRP1-0000-0425-E | IPCRP1 | IPCRP1 | 0000-0425 | Vent Details at Exist & New Houston St Retaining W | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 10000
Y | IPCRP1-0000-0425-L | IPCRP1 | IPCRP1 | 0000-0425 | Vent Details at Exist & New Houston St Retaining W | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 599.99 | 599.99 | 0 | 0 | 599.99 | 599.99 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 100000
Y | IPCRP1-0000-0425-M | IPCRP1 | IPCRP1 | 0000-0425 | Vent Details at Exist & New Houston St Retaining W | N | M |  | UNIT | U | 0 | 160464.04 | 160464.04 | 94288.53 | 160464.04 | 58.9303 | 0 | 0 | 0 | -464.04 | Y | 160000 | Y | -160000 | 0 | 0 | 0 | 0 | 0 | 160000 | Y | -160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -160000 | 94288.53 | 0 | 160000 | 0 | 0 | 0 | 5585.72 | 133064.16 | 0 | -160000 | 0 | 0 | 160000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505 | -505 | 0 | NA | 0 | 0 | 1 | 1 | LS | 160464.04 | 66175.51 | 94288.53 | -464.04
Y | IPCRP1-0000-0430-L | IPCRP1 | IPCRP1 | 0000-0430 | FM#19, Pier 42 Elect Scope Completion, RFI#1349 | N | L |  | UNIT | P | 0 | 2932.4 | 2932.4 | 2932.4 | 2932.4 | 45.1138 | 0 | 0 | 0 | 3567.6 | Y | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6500 | 0 | 810.06 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 26 | 24 | 50 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 3567.6 | PCO#422, RFI #1350
Y | IPCRP1-0000-0430-M | IPCRP1 | IPCRP1 | 0000-0430 | FM#19, Pier 42 Elect Scope Completion, RFI#1349 | N | M |  | UNIT | U | 0 | 17545 | 17545 | 0 | 17545 | 0 | 0 | 0 | 0 | -12545 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 17545 | 17545 | 0 | -12545
Y | IPCRP1-0000-0430-S | IPCRP1 | IPCRP1 | 0000-0430 | FM#19, Pier 42 Elect Scope Completion, RFI#1349 | N | S |  | UNIT | A | 0 | 193.7 | 193.7 | 193.7 | 193.7 | 3.874 | 0 | 0 | 0 | 4806.3 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 193.7 | 0 | 5000 | 0 | 0 | 0 | 0 | 193.7 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 193.7 | 0 | 193.7 | 4806.3
Y | IPCRP1-0000-0435-L | IPCRP1 | IPCRP1 | 0000-0435 | Montgomery St Boulder Hardscape (RFI 1329) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 50 | 50 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | PCO No. 427 - Montgomery St Boulder Hardscape (RFI 1329)
Y | IPCRP1-0000-0440-L | IPCRP1 | IPCRP1 | 0000-0440 | Abandoned MH in Conflict w/ HS RW W5 (RFI#1368) | N | L |  | UNIT | P | 0 | 8722.29 | 8722.29 | 8722.29 | 8722.29 | 134.1891 | 0 | 0 | 0 | -2222.29 | Y | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6500 | 3236.38 | 5485.91 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 70 | -20 | 50 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | -2222.29
Y | IPCRP1-0000-0440-M | IPCRP1 | IPCRP1 | 0000-0440 | Abandoned MH in Conflict w/ HS RW W5 (RFI#1368) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | Y | 1000 | Y | -1000 | 0 | 0 | 0 | 0 | 0 | 1000 | Y | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 1000
N | IPCRP1-0000-0440-S | IPCRP1 | IPCRP1 | 0000-0440 | Abandoned MH in Conflict w/ HS RW W5 (RFI#1368) | N | S |  | UNIT | A | 0 | 1097.64 | 1097.64 | 1097.64 | 1097.64 | 100 | 0 | 0 | 0 | 0 | N | 1097.64 | N | -1097.64 | 0 | 0 | 0 | 0 | 0 | 1097.64 | N | -1097.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1097.64 | 1097.64 | 0 | 1097.64 | 0 | 0 | 0 | 0 | 1097.64 | 0 | -1097.64 | 0 | 0 | 1097.64 | 1097.64 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8.5 | 0 | 0 | 8.5 | 8.5 | NA | 0 | 1 | 0 | 1 | LS | 1097.64 | 0 | 1097.64 | 0
Y | IPCRP1-0000-0445-L | IPCRP1 | IPCRP1 | 0000-0445 | W1-W3 Rebar Changes, RFI’s #1350, 1362, 1369 | N | L |  | UNIT | P | 0 | 13625.19 | 13625.19 | 13625.19 | 13625.19 | 100 | 0 | 0 | 0 | 0 | Y | 13625.19 | Y | -13625.19 | 0 | 0 | 0 | 0 | 0 | 13625.19 | Y | -13625.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13625.19 | 0 | 13625.19 | 13625.19 | 0 | 0 | 0 | 0 | 0 | 0 | -13625.19 | 0 | 0 | 13625.19 | 13625.19 | 0 | 0 | 0 | 0 | 0 | 120.5 | 120.5 | 0 | 120.5 | 0 | 120.5 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0000-0445-M | IPCRP1 | IPCRP1 | 0000-0445 | W1-W3 Rebar Changes, RFI’s #1350, 1362, 1369 | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | Y | 2000 | Y | -2000 | 0 | 0 | 0 | 0 | 0 | 2000 | Y | -2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 2000 | RFI #813 doesn’t belong in the CO. It can be paid for by the pound under the item. Changes as / RFI #1350, 1362 & 1369 (couplers, chopping, cutting, etc) belong in this change order. Detailing changes should be keep separate & included in the next detailing CO.
Y | IPCRP1-0000-0445-S | IPCRP1 | IPCRP1 | 0000-0445 | W1-W3 Rebar Changes, RFI’s #1350, 1362, 1369 | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 5000
Y | IPCRP1-0000-0450-L | IPCRP1 | IPCRP1 | 0000-0450 | Chop Bump Outs from Exist Houston St Ret Walls | N | L |  | UNIT | P | 0 | 3403.41 | 3403.41 | 3403.41 | 3403.41 | 26.1801 | 0 | 0 | 0 | 9596.59 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 1091.46 | 2311.95 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 29 | 71 | 100 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 9596.59 | PCO NO. 435.
Y | IPCRP1-0000-0450-S | IPCRP1 | IPCRP1 | 0000-0450 | Chop Bump Outs from Exist Houston St Ret Walls | N | S |  | UNIT | A | 0 | 322.84 | 322.84 | 322.84 | 322.84 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 322.84 | 0 | 0 | 0 | 0 | 0 | 0 | 322.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 322.84 | 0 | 322.84 | 0
N | IPCRP1-0000-0460-C | IPCRP1 | IPCRP1 | 0000-0460 | Incremental MGP Cost, Non-CE (JB-122) Util Work | N | C |  | UNIT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
N | IPCRP1-0000-0460-L | IPCRP1 | IPCRP1 | 0000-0460 | Incremental MGP Cost, Non-CE (JB-122) Util Work | N | L |  | UNIT | P | 0 | 109.85 | 109.85 | 109.85 | 109.85 | 0.027463 | 0 | 0 | 0 | 399890.15 | Y | 400000 | Y | -400000 | 0 | 0 | 0 | 0 | 0 | 400000 | Y | -400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -400000 | 109.85 | 0 | 0 | -400000 | 0 | 0 | 0 | 0 | 0 | -400000 | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 2839.9 | 2839.9 | 0 | 1 | 2838.9 | 2839.9 | HR | 0 | 0 | 10000 | 10000 | TN | 0 | 0 | 0 | 399890.15
N | IPCRP1-0000-0465-L | IPCRP1 | IPCRP1 | 0000-0465 | FM#54 – Esplanade Cross Slopes at 1.5% Target | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 0 | 0 | 130 | 130 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 13000 | PCO #437 (FM#54) Changing Target Esplanade Cross Slope to 1.5%
Y | IPCRP1-0001-0000-L | IPCRP1 | IPCRP1 | 0001-0000 | REM EX SUPERSTRUCT # 1 (DELANCY ST) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0001-0000-R | IPCRP1 | IPCRP1 | 0001-0000 | REM EX SUPERSTRUCT # 1 (DELANCY ST) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000000 | 0 | 0 | 5000000 | 0 | 5000000 | 21000000 | 0 | N | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0001-0000-S | IPCRP1 | IPCRP1 | 0001-0000 | REM EX SUPERSTRUCT # 1 (DELANCY ST) | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0002-0000-L | IPCRP1 | IPCRP1 | 0002-0000 | REM EX SUPERSTRUCT # 2 (E 10TH ST) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0002-0000-R | IPCRP1 | IPCRP1 | 0002-0000 | REM EX SUPERSTRUCT # 2 (E 10TH ST) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000000 | 0 | 0 | 5000000 | 0 | 5000000 | 4900000 | 0 | N | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0003-0000-L | IPCRP1 | IPCRP1 | 0003-0000 | REM EX SUPERSTRUCT # 3 (CORLEARS HOOK) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0003-0000-R | IPCRP1 | IPCRP1 | 0003-0000 | REM EX SUPERSTRUCT # 3 (CORLEARS HOOK) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10000000 | 0 | 0 | 10000000 | 0 | 10000000 | 10000000 | 0 | N | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0004-0000-L | IPCRP1 | IPCRP1 | 0004-0000 | REMOVAL OF SUBSTRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0004-0000-R | IPCRP1 | IPCRP1 | 0004-0000 | REMOVAL OF SUBSTRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 348750 | 0 | 0 | 348750 | 0 | 348750 | 202225 | 0 | N | 348750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0004-1000-C | IPCRP1 | IPCRP1 | 0004-1000 | Demo & Sewer H-Pile Sub (Gateway Demo/Civil) | N | C |  | UNIT | U | 0 | 225967 | 225967 | 225967 | 225967 | 100 | 0 | 0 | 0 | 0 | Y | 225967 | Y | -225967 | 0 | 0 | 0 | 0 | 0 | 225967 | Y | -225967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -225967 | 0 | 0 | 225967 | 0 | 0 | 0 | 0 | 0 | 0 | -225967 | 0 | 0 | 225967 | 225967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 0.7 | 0.3 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0004-1000-L | IPCRP1 | IPCRP1 | 0004-1000 | Demo & Sewer H-Pile Sub (Gateway Demo/Civil) | N | L |  | UNIT | P | 0 | 80592.11 | 80592.11 | 80592.11 | 80592.11 | 84.2646 | 0 | 0 | 0 | 15049.63 | Y | 95641.74 | Y | -95641.74 | 0 | 0 | 0 | 0 | 0 | 95641.74 | Y | -95641.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -95641.74 | 1424.43 | 0 | 95641.74 | 0 | 0 | 0 | 0 | 0 | 0 | -95641.74 | 0 | 0 | 95641.74 | 95641.74 | 0 | 0 | 0 | 0 | 0 | 661.97 | 661.97 | 0 | 567 | 94.97 | 661.97 | HR | 1 | 0.7 | 0.3 | 1 | LS | 0 | 0 | 0 | 15049.63
Y | IPCRP1-0004-1000-M | IPCRP1 | IPCRP1 | 0004-1000 | Demo & Sewer H-Pile Sub (Gateway Demo/Civil) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7236 | 7236 | 0 | 150 | 7086 | 7236 | NA | 1 | 0.7 | 0.3 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0004-1000-S | IPCRP1 | IPCRP1 | 0004-1000 | Demo & Sewer H-Pile Sub (Gateway Demo/Civil) | N | S |  | NR | A | 23105231.02 | 25662758.46 | 25662758.46 | 19270183.87 | 25662758.46 | 77.3513 | 0 | 0 | 0 | -750200 | Y | 24912558.46 | Y | -1807327.44 | 0 | 0 | 23105231.02 | 0 | 0 | 24912558.46 | Y | -1807327.44 | 0 | 0 | 23018318 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24912558.46 | 0 | 133293.6 | 24912558.46 | 0 | 0 | 0 | 0 | 0 | 0 | -24912558.46 | 0 | 0 | 24912558.46 | 24912558.46 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 188880.64 | 55543.36 | 244424 | LS | 1 | 0.7 | 0.3 | 1 | LS | 25662758.46 | 6392574.59 | 19270183.87 | -750200 | PMF increased from $22,567,597.00 to $28,071,221.90 (adding Gateway CO #1 subcontract value $5,489,187.40, and CO#2 @$14,437.50). Gateway Static Load Test CO@$69,400 2. VS reduced PMF by $750,200 until SCO for anticipated underrun of H-Piles. (app 6,000 LF @$79.20/LF and app 2,500 LF @110.00/LF)
Y | IPCRP1-0004.0000.01-L | IPCRP1 | IPCRP1 | 0004.0000.01 | 0004.0000.01 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-0005-0000-L | IPCRP1 | IPCRP1 | 0005-0000 | EMBANKMENT IN PLACE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0005-0000-R | IPCRP1 | IPCRP1 | 0005-0000 | EMBANKMENT IN PLACE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 28000 | 0 | 0 | 28000 | 0 | 28000 | 0 | 0 | N | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0005-1000-E | IPCRP1 | IPCRP1 | 0005-1000 | Inst Embankment in Place | N | E |  | NR | P | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6300 | 0 | 0 | 6300 | 0 | 0 | 0 | Y | 6300 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 140 | 0 | 140 | 140 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0005-1000-L | IPCRP1 | IPCRP1 | 0005-1000 | Inst Embankment in Place | N | L |  | NR | P | 10167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10167 | N | 10167 | N | 0 | 0 | 0 | 10167 | 0 | 0 | 10167 | N | 0 | 0 | 0 | 10167 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10167 | 0 | 0 | 10167 | 0 | 0 | 0 | 0 | 0 | 0 | -10167 | 0 | 0 | 10167 | 10167 | 0 | 0 | 0 | 96 | 0 | 96 | 96 | 96 | 0 | 96 | 96 | HR | 140 | 0 | 140 | 140 | CY | 0 | 0 | 0 | 10167
Y | IPCRP1-0006-0000-L | IPCRP1 | IPCRP1 | 0006-0000 | EXPANDED POLYSTYRENE FILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CF | 0 | 0 | 0 | 0
Y | IPCRP1-0006-0000-R | IPCRP1 | IPCRP1 | 0006-0000 | EXPANDED POLYSTYRENE FILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100556 | 0 | 0 | 100556 | 0 | 100556 | 60835.74 | 0 | N | 100556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | CF | 0 | 0 | 0 | 0
Y | IPCRP1-0006-1000-E | IPCRP1 | IPCRP1 | 0006-1000 | Inst Expanded Polystyrene Fill | N | E |  | NR | P | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 7190 | 0 | 0 | 7200 | 0 | 0 | 10 | Y | 7190 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | SF | 50278 | 30417.94 | 41051.06 | 71469 | CF | 0 | 0 | 0 | 10
Y | IPCRP1-0006-1000-L | IPCRP1 | IPCRP1 | 0006-1000 | Inst Expanded Polystyrene Fill | N | L |  | NR | P | 31838.16 | 53257.72 | 53257.72 | 53257.72 | 53257.72 | 30.433 | 0 | 0 | 0 | 121742.45 | Y | 175000.17 | Y | -143162.01 | 0 | 0 | 31838.16 | 0 | 0 | 175000.17 | Y | -143162.01 | 0 | 0 | 31838.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -175000.17 | 0 | 0 | 175000.17 | 0 | 0 | 0 | 0 | 0 | 0 | -175000.17 | 0 | 0 | 175000.17 | 175000.17 | 0 | 0 | 0 | 288 | 0 | 1435.41 | 1435.41 | 288 | 446 | 989.41 | 1435.41 | HR | 50278 | 30417.94 | 41051.06 | 71469 | CF | 0 | 0 | 0 | 121742.45
Y | IPCRP1-0006-1000-S | IPCRP1 | IPCRP1 | 0006-1000 | Inst Expanded Polystyrene Fill | N | S |  | UNIT | A | 0 | 1998.68 | 1998.68 | 1998.68 | 1998.68 | 100 | 0 | 0 | 0 | 0 | N | 1998.68 | N | -1998.68 | 0 | 0 | 0 | 0 | 0 | 1998.68 | N | -1998.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1998.68 | 0 | 0 | 1998.68 | 0 | 0 | 0 | 0 | 0 | 0 | -1998.68 | 0 | 0 | 1998.68 | 1998.68 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 17 | 0 | 17 | NA | 50278 | 30417.94 | 41051.06 | 71469 | CF | 1998.68 | 0 | 1998.68 | 0
Y | IPCRP1-0006-1010-L | IPCRP1 | IPCRP1 | 0006-1010 | PM - Expanded Polystyrene Fill | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 50278 | 30417.94 | 48992.06 | 79410 | CF | 0 | 0 | 0 | 0
Y | IPCRP1-0006-1010-M | IPCRP1 | IPCRP1 | 0006-1010 | PM - Expanded Polystyrene Fill | N | M |  | NR | P | 132733.92 | 387376.94 | 387376.94 | 199507.07 | 387376.94 | 51.3209 | 0 | 0 | 0 | 1367.42 | Y | 388744.36 | Y | -256010.44 | 0 | 0 | 132733.92 | 0 | 0 | 388744.36 | Y | -256010.44 | 0 | 0 | 132733.92 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -388744.36 | 0 | -1255.5 | 388744.36 | 0 | 0 | 0 | -1367.42 | 0 | 0 | -388744.36 | 0 | 0 | 388744.36 | 388744.36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 35127.66 | -35127.66 | 0 | CY | 50278 | 30417.94 | 48992.06 | 79410 | CF | 389303.16 | 187869.87 | 201433.29 | 1367.42 | Change PMF (Mat) from $132,733.92 to $310,548.60
Y | IPCRP1-0007-0000-L | IPCRP1 | IPCRP1 | 0007-0000 | SELECT GRANULAR FILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0007-0000-R | IPCRP1 | IPCRP1 | 0007-0000 | SELECT GRANULAR FILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 127500 | 0 | 0 | 127500 | 0 | 127500 | 50820 | 0 | N | 127500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0007-1000-E | IPCRP1 | IPCRP1 | 0007-1000 | Inst Select Granular Fill | N | E |  | NR | P | 13104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 13104 | 0 | 0 | 13104 | 0 | 0 | 0 | Y | 13104 | 0 | 0 | 13104 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 780 | 204 | 576 | 780 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0007-1000-L | IPCRP1 | IPCRP1 | 0007-1000 | Inst Select Granular Fill | N | L |  | NR | P | 41389.61 | 30536.61 | 30536.61 | 30536.61 | 30536.61 | 30.1144 | 0 | 0 | 0 | 70865.35 | Y | 101401.96 | Y | -60012.35 | 0 | 0 | 41389.61 | 0 | 0 | 101401.96 | Y | -60012.35 | 0 | 0 | 41389.61 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -101401.96 | 0 | 0 | 101401.96 | 0 | 0 | 0 | 0 | 0 | 0 | -101401.96 | 0 | 0 | 101401.96 | 101401.96 | 0 | 0 | 0 | 374.4 | 0 | 781.26 | 781.26 | 374.4 | 242 | 539.26 | 781.26 | HR | 780 | 204 | 576 | 780 | LF | 0 | 0 | 0 | 70865.35
Y | IPCRP1-0008-0000-L | IPCRP1 | IPCRP1 | 0008-0000 | PREFABRICATED VERTICAL DRAINS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0008-0000-R | IPCRP1 | IPCRP1 | 0008-0000 | PREFABRICATED VERTICAL DRAINS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 14825250 | 0 | 0 | 14825250 | 0 | 14825250 | 3423774.01 | 0 | N | 14825250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14825250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0009-0000-L | IPCRP1 | IPCRP1 | 0009-0000 | FURN EQUIP FOR INSTALL PREFAB VERT DRAINS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0009-0000-R | IPCRP1 | IPCRP1 | 0009-0000 | FURN EQUIP FOR INSTALL PREFAB VERT DRAINS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2500000 | 0 | 0 | 2500000 | 0 | 2500000 | 2500000 | 0 | N | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0009-1000-L | IPCRP1 | IPCRP1 | 0009-1000 | Ground Improve Sub #1 (Keller) wick drain/stone c | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.57 | 0.43 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0009-1000-S | IPCRP1 | IPCRP1 | 0009-1000 | Ground Improve Sub #1 (Keller) wick drain/stone c | N | S |  | NR | A | 23180293 | 37252704.6 | 37252704.6 | 21518994.04 | 37252704.6 | 57.7649 | 0 | 0 | 0 | 0 | Y | 37252704.6 | Y | -14072411.6 | 0 | 0 | 23180293 | 0 | 0 | 37252704.6 | Y | -14072411.6 | 0 | 0 | 23180293 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37252704.6 | 0 | 659711.89 | 37252704.6 | 0 | 0 | 0 | 0 | 10696484.91 | 0 | -37252704.6 | 0 | 0 | 37252704.6 | 37252704.6 | 0 | 0 | 0 | 0 | 0 | 1839735.45 | 1839735.45 | 0 | 600204.42 | 1239531.03 | 1839735.45 | HR | 1 | 0.57 | 0.43 | 1 | LS | 37252704.6 | 15733710.56 | 21518994.04 | 0 | Keller subcontract now includes Stone Columns, Wick Drains, & percentage of Micro Piles. 130K of their subcontract is coded to 0423-1020 (Drive Piles) for predrilling task Keller subcontract for wick drains and stone columns. Added micropiles to Keller subcontract.
Y | IPCRP1-0009-1010-C | IPCRP1 | IPCRP1 | 0009-1010 | Support for Keller Micropiles | N | C |  | UNIT | U | 0 | 104367.66 | 104367.66 | 93181.42 | 104367.66 | 116.4768 | 0 | 0 | 0 | -24367.66 | Y | 80000 | Y | -80000 | 0 | 0 | 0 | 0 | 0 | 80000 | Y | -80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -80000 | 19784.28 | 5489.97 | 80000 | 0 | 0 | 0 | 29731.9 | 8557.44 | 0 | -80000 | 0 | 0 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 4876.11 | 4876.11 | 0 | 5845.2 | -969.09 | 4876.11 | NA | 0 | 404 | 52 | 456 | EA | 104367.66 | 11186.24 | 93181.42 | -24367.66
Y | IPCRP1-0009-1010-E | IPCRP1 | IPCRP1 | 0009-1010 | Support for Keller Micropiles | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 404 | 52 | 456 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0009-1010-L | IPCRP1 | IPCRP1 | 0009-1010 | Support for Keller Micropiles | N | L |  | UNIT | P | 0 | 213478.56 | 213478.56 | 213478.56 | 213478.56 | 85.3914 | 0 | 0 | 0 | 36521.44 | Y | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250000 | 39738.84 | 64434.68 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 1906.07 | 1906.07 | 0 | 1678 | 228.07 | 1906.07 | HR | 0 | 404 | 52 | 456 | EA | 0 | 0 | 0 | 36521.44 | 452ea @ Houston St,17ea @ Transition #1, 11ea @ Transition #2, 12ea @ Montgomery St Roller Gate West. 452ea @ Houston St,17ea @ Transition #1, 11ea @ Transition #2, 12ea @ Montgomery St Roller Gate West.
Y | IPCRP1-0009-1010-M | IPCRP1 | IPCRP1 | 0009-1010 | Support for Keller Micropiles | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 404 | 52 | 456 | EA | 0 | 0 | 0 | 1
Y | IPCRP1-0009-1010-S | IPCRP1 | IPCRP1 | 0009-1010 | Support for Keller Micropiles | N | S |  | UNIT | A | 0 | 59569.01 | 59569.01 | 52932.53 | 59569.01 | 46.0283 | 0 | 0 | 0 | 55430.99 | Y | 115000 | Y | -115000 | 0 | 0 | 0 | 0 | 0 | 115000 | Y | -115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -115000 | 8006.35 | 12236.16 | 115000 | 0 | 0 | 0 | 0 | 23256.35 | 0 | -115000 | 0 | 0 | 115000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.48 | -9.48 | 0 | NA | 0 | 404 | 52 | 456 | EA | 59569.01 | 6636.48 | 52932.53 | 55430.99
Y | IPCRP1-0010-0000-L | IPCRP1 | IPCRP1 | 0010-0000 | PREP SURFACE FOR PREFAB VERT DRAINS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0010-0000-R | IPCRP1 | IPCRP1 | 0010-0000 | PREP SURFACE FOR PREFAB VERT DRAINS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 656212.5 | 0 | 0 | 656212.5 | 0 | 656212.5 | 171841.42 | 0 | N | 656212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0010-1000-E | IPCRP1 | IPCRP1 | 0010-1000 | Level Concrete Surface for Wick Drains | N | E |  | NR | P | 52497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 52497 | 0 | 0 | 52497 | 0 | 0 | 0 | Y | 52497 | 0 | 0 | 52497 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 437475 | 114560.94 | 322914.06 | 437475 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0010-1000-L | IPCRP1 | IPCRP1 | 0010-1000 | Level Concrete Surface for Wick Drains | N | L |  | NR | P | 161982.99 | 15342.11 | 15342.11 | 15342.11 | 15342.11 | 100 | 0 | 0 | 0 | 0 | Y | 15342.11 | Y | 146640.88 | 0 | 0 | 161982.99 | 0 | 0 | 15342.11 | Y | 146640.88 | 0 | 0 | 161982.99 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15342.11 | 0 | 0 | 15342.11 | 0 | 0 | 0 | 0 | 0 | 0 | -15342.11 | 0 | 0 | 15342.11 | 15342.11 | 0 | 0 | 0 | 1399.92 | 0 | 86.5 | 86.5 | 1399.92 | 86.5 | 0 | 86.5 | HR | 437475 | 114560.94 | 322914.06 | 437475 | SF | 0 | 0 | 0 | 0 | null
Y | IPCRP1-0010-1000-S | IPCRP1 | IPCRP1 | 0010-1000 | Level Concrete Surface for Wick Drains | N | S |  | UNIT | A | 0 | 971.64 | 971.64 | 971.64 | 971.64 | 100 | 0 | 0 | 0 | 0 | Y | 971.64 | Y | -971.64 | 0 | 0 | 0 | 0 | 0 | 971.64 | Y | -971.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -971.64 | 0 | 0 | 971.64 | 0 | 0 | 0 | 0 | 0 | 0 | -971.64 | 0 | 0 | 971.64 | 971.64 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 8 | -4 | 4 | NA | 437475 | 114560.94 | 322914.06 | 437475 | SF | 971.64 | 0 | 971.64 | 0
Y | IPCRP1-0010-1010-E | IPCRP1 | IPCRP1 | 0010-1010 | Inst Adhesive for Wick Drains | N | E |  | NR | P | 52497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 52497 | 0 | 0 | 52497 | 0 | 0 | 0 | Y | 52497 | 0 | 0 | 52497 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 437475 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0010-1010-L | IPCRP1 | IPCRP1 | 0010-1010 | Inst Adhesive for Wick Drains | N | L |  | NR | P | 161982.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 161982.99 | 0 | 0 | 161982.99 | 0 | 0 | 0 | Y | 161982.99 | 0 | 0 | 161982.99 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1399.92 | 0 | 0 | 0 | 1399.92 | 0 | 0 | 0 | HR | 437475 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0010-1020-L | IPCRP1 | IPCRP1 | 0010-1020 | PM - Adhesive for Wick Drains | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 437475 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0010-1020-M | IPCRP1 | IPCRP1 | 0010-1020 | PM - Adhesive for Wick Drains | N | M |  | NR | P | 218737.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 218737.5 | 0 | 0 | 218737.5 | 0 | 0 | 0 | Y | 218737.5 | 0 | 0 | 218737.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 437475 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0011-0000-L | IPCRP1 | IPCRP1 | 0011-0000 | SELECT GRANULAR SUBGRADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0011-0000-R | IPCRP1 | IPCRP1 | 0011-0000 | SELECT GRANULAR SUBGRADE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 36000 | 0 | 0 | 36000 | 0 | 36000 | 0 | 0 | N | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0011-1000-E | IPCRP1 | IPCRP1 | 0011-1000 | Inst Select Gran Subgrade | N | E |  | NR | P | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5400 | 0 | 0 | 5400 | 0 | 0 | 0 | Y | 5400 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | TN | 90 | 0 | 90 | 90 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0011-1000-L | IPCRP1 | IPCRP1 | 0011-1000 | Inst Select Gran Subgrade | N | L |  | NR | P | 18399.6 | -14.25 | -14.25 | -14.25 | -14.25 | -0.077447 | 0 | 0 | 0 | 18413.85 | N | 18399.6 | N | 0 | 0 | 0 | 18399.6 | 0 | 0 | 18399.6 | N | 0 | 0 | 0 | 18399.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18399.6 | 0 | 0 | 18399.6 | 0 | 0 | 0 | 0 | 0 | 0 | -18399.6 | 0 | 0 | 18399.6 | 18399.6 | 0 | 0 | 0 | 168 | 0 | 168 | 168 | 168 | 0 | 168 | 168 | HR | 90 | 0 | 90 | 90 | CY | 0 | 0 | 0 | 18413.85
Y | IPCRP1-0012-0000-L | IPCRP1 | IPCRP1 | 0012-0000 | SELECT STRUCTURAL FILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0012-0000-R | IPCRP1 | IPCRP1 | 0012-0000 | SELECT STRUCTURAL FILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 584250 | 0 | 0 | 584250 | 0 | 584250 | 226996.5 | 0 | N | 584250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0012-1000-E | IPCRP1 | IPCRP1 | 0012-1000 | Inst Select Structural Fill | N | E |  | NR | P | 56088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 56088 | 0 | 0 | 56088 | 0 | 0 | 0 | Y | 56088 | 0 | 0 | 56088 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 7790 | 3134.73 | 4655.27 | 7790 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0012-1000-L | IPCRP1 | IPCRP1 | 0012-1000 | Inst Select Structural Fill | N | L |  | NR | P | 166125.16 | 206587.3 | 206587.3 | 206587.3 | 206587.3 | 55.2489 | 0 | 0 | 0 | 167333.65 | Y | 373920.95 | Y | -207795.79 | 0 | 0 | 166125.16 | 0 | 0 | 373920.95 | Y | -207795.79 | 0 | 0 | 166125.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -373920.95 | 4989.92 | 2275.9 | 373920.95 | 0 | 0 | 0 | 0 | 0 | 0 | -373920.95 | 0 | 0 | 373920.95 | 373920.95 | 0 | 0 | 0 | 1495.68 | 0 | 3116.05 | 3116.05 | 1495.68 | 1694.5 | 1421.55 | 3116.05 | HR | 7790 | 3134.73 | 4655.27 | 7790 | CY | 0 | 0 | 0 | 167333.65 | Change PMF (MH) from 1,495.68 to 3,116.00, Change PMF (Labor) from $166,125.16 to $373,920.00
Y | IPCRP1-0012-1000-S | IPCRP1 | IPCRP1 | 0012-1000 | Inst Select Structural Fill | N | S |  | UNIT | A | 0 | 7844.97 | 7844.97 | 7844.97 | 7844.97 | 107.0484 | 0 | 0 | 0 | -516.54 | Y | 7328.43 | Y | -7328.43 | 0 | 0 | 0 | 0 | 0 | 7328.43 | Y | -7328.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7328.43 | 516.54 | 0 | 7328.43 | 0 | 0 | 0 | 0 | 516.54 | 0 | -7328.43 | 0 | 0 | 7328.43 | 7328.43 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 64.5 | -56.5 | 8 | NA | 7790 | 3134.73 | 4655.27 | 7790 | CY | 7844.97 | 0 | 7844.97 | -516.54 | KMA CO
Y | IPCRP1-0013-0000-L | IPCRP1 | IPCRP1 | 0013-0000 | SAND BACKFILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0013-0000-R | IPCRP1 | IPCRP1 | 0013-0000 | SAND BACKFILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 52000 | 0 | 0 | 52000 | 0 | 52000 | 20332 | 0 | N | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0013-1000-E | IPCRP1 | IPCRP1 | 0013-1000 | Instl Sand Backfill | N | E |  | NR | P | 740.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 740.25 | 0 | 0 | 740.25 | 0 | 0 | 0 | Y | 740.25 | 0 | 0 | 740.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 185 | 50.83 | 134.17 | 185 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0013-1000-L | IPCRP1 | IPCRP1 | 0013-1000 | Instl Sand Backfill | N | L |  | NR | P | 6271.02 | 13176.77 | 13176.77 | 13176.77 | 13176.77 | 26.7594 | 0 | 0 | 0 | 36064.9 | Y | 49241.67 | Y | -42970.65 | 0 | 0 | 6271.02 | 0 | 0 | 49241.67 | Y | -42970.65 | 0 | 0 | 6271.02 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -49241.67 | 0 | 0 | 49241.67 | 0 | 0 | 0 | 0 | 0 | 0 | -49241.67 | 0 | 0 | 49241.67 | 49241.67 | 0 | 0 | 0 | 59.21 | 0 | 414.54 | 414.54 | 59.21 | 114 | 300.54 | 414.54 | HR | 185 | 50.83 | 134.17 | 185 | CY | 0 | 0 | 0 | 36064.9
Y | IPCRP1-0014-0000-L | IPCRP1 | IPCRP1 | 0014-0000 | GRANULAR DRAINAGE BLANKET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0014-0000-R | IPCRP1 | IPCRP1 | 0014-0000 | GRANULAR DRAINAGE BLANKET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2916600 | 0 | 0 | 2916600 | 0 | 2916600 | 1687867.2 | 0 | N | 2916600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0014-1000-E | IPCRP1 | IPCRP1 | 0014-1000 | Inst Granular Drain Blanket | N | E |  | NR | P | 72915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 72915 | 0 | 0 | 72915 | 0 | 0 | 0 | Y | 72915 | 0 | 0 | 72915 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 24305 | 14065.56 | 10239.44 | 24305 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0014-1000-L | IPCRP1 | IPCRP1 | 0014-1000 | Inst Granular Drain Blanket | N | L |  | NR | P | 617796.65 | 70886.85 | 70886.85 | 70886.85 | 70886.85 | 13.8722 | 0 | 0 | 0 | 440113.15 | Y | 511000 | Y | 106796.65 | 0 | 0 | 617796.65 | 0 | 0 | 511000 | Y | 106796.65 | 0 | 0 | 617796.65 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -511000 | 242.88 | 0 | 511000 | 0 | 0 | 0 | 0 | 0 | 0 | -511000 | 0 | 0 | 511000 | 511000 | 0 | 0 | 0 | 5833.2 | 0 | 3649.94 | 3649.94 | 5833.2 | 506.5 | 3143.44 | 3649.94 | HR | 24305 | 14065.56 | 10239.44 | 24305 | CY | 0 | 0 | 0 | 440113.15
Y | IPCRP1-0014-1000-S | IPCRP1 | IPCRP1 | 0014-1000 | Inst Granular Drain Blanket | N | S |  | UNIT | A | 0 | 10074.99 | 10074.99 | 10074.99 | 10074.99 | 100 | 0 | 0 | 0 | 0 | N | 10074.99 | N | -10074.99 | 0 | 0 | 0 | 0 | 0 | 10074.99 | N | -10074.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10074.99 | 0 | 0 | 10074.99 | 0 | 0 | 0 | 0 | 0 | 0 | -10074.99 | 0 | 0 | 10074.99 | 10074.99 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 80 | 0 | 80 | NA | 24305 | 14065.56 | 10239.44 | 24305 | CY | 10074.99 | 0 | 10074.99 | 0
Y | IPCRP1-0015-0000-L | IPCRP1 | IPCRP1 | 0015-0000 | DEEP SOIL MIXING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0015-0000-R | IPCRP1 | IPCRP1 | 0015-0000 | DEEP SOIL MIXING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20250000 | 0 | 0 | 20250000 | 0 | 20250000 | 0 | 0 | N | 20250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0015-1000-L | IPCRP1 | IPCRP1 | 0015-1000 | Deep Soil Mixing Sub (Geo Solutions) | N | L |  | UNIT | P | 0 | 737.26 | 737.26 | 737.26 | 737.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -6 | 0 | HR | 40500 | 0 | 40500 | 40500 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0015-1000-S | IPCRP1 | IPCRP1 | 0015-1000 | Deep Soil Mixing Sub (Geo Solutions) | N | S |  | NR | A | 8311806.9 | 8474044.6 | 8474044.6 | 0 | 8474044.6 | 0 | 0 | 0 | 0 | -7674044.6 | Y | 800000 | Y | 7511806.9 | 0 | 0 | 8311806.9 | 0 | 0 | 800000 | Y | 7511806.9 | 0 | 0 | 8311806.9 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -800000 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | -800000 | 0 | 0 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 40500 | 0 | 40500 | 40500 | CY | 8474044.6 | 8474044.6 | 0 | -7674044.6 | Geo Solutions subcontract ($7,851,745.00). commitment can get entered after subcontract is executed.
Y | IPCRP1-0015-1010-C | IPCRP1 | IPCRP1 | 0015-1010 | Mob/ Relocate Soil Mixing/ Obstruct Clear Equip | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 10
Y | IPCRP1-0015-1010-L | IPCRP1 | IPCRP1 | 0015-1010 | Mob/ Relocate Soil Mixing/ Obstruct Clear Equip | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | Working from Sean C DSM Cost tab (10shifts in + 10 shifts out for 9-man crew x 9hr/day) per setup = 1,620MH x 2 setups = 3,240MH.
Y | IPCRP1-0015-1020-L | IPCRP1 | IPCRP1 | 0015-1020 | Deep Soll Mixing (Self Perform) | N | L |  | UNIT | P | 0 | 70.43 | 70.43 | 70.43 | 70.43 | 100 | 0 | 0 | 0 | 0 | N | 70.43 | N | -70.43 | 0 | 0 | 0 | 0 | 0 | 70.43 | N | -70.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -70.43 | 0 | 0 | 70.43 | 0 | 0 | 0 | 0 | 0 | 0 | -70.43 | 0 | 0 | 70.43 | 70.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | -0.5 | 0 | HR | 0 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0015-1030-L | IPCRP1 | IPCRP1 | 0015-1030 | Obstruction Clear for DSM (Self-Perform) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | HR | 0 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 10 | Working from Sean C Predrill Cost – Kelly, where daily Labor cost ($6,546.46) and daily Equipment cost ($8,814.75) total $15,361.21 and 605 shifts are estimated to predrill 151683 of Obstruction Drilling.
Y | IPCRP1-0015-1040-L | IPCRP1 | IPCRP1 | 0015-1040 | Material for DSM (Self-Perform) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0015-1040-M | IPCRP1 | IPCRP1 | 0015-1040 | Material for DSM (Self-Perform) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 10 | Y | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 10 | working from Sean C summary tab, cement cost = 2,929,972.50 for 44,038 CY. Factor down to 40,500.00 CY = $2,694.580.00
Y | IPCRP1-0016-0000-L | IPCRP1 | IPCRP1 | 0016-0000 | CONTROLLED LOW STRENGTH MATERIAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0016-0000-R | IPCRP1 | IPCRP1 | 0016-0000 | CONTROLLED LOW STRENGTH MATERIAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 253500 | 0 | 0 | 253500 | 0 | 253500 | 75303 | 0 | N | 253500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0016-1000-E | IPCRP1 | IPCRP1 | 0016-1000 | Instl CLSM Concrete | N | E |  | NR | P | 22532.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 22532.5 | 0 | 0 | 22532.5 | 0 | 0 | 0 | N | 22532.5 | 0 | 0 | 22532.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 845 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0016-1000-L | IPCRP1 | IPCRP1 | 0016-1000 | Instl CLSM Concrete | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 86913.02 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 811.19 | 0 | 0 | 0 | 811.19 | 0 | 0 | 0 | HR | 845 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | Increased the budget in seq #16 (lab) by $86,913.02 the same amount and increased the Budget in seq #4 (sub) by $86,913.02, from $23,018,318 to $23,105,231.02.
Y | IPCRP1-0017-0000-L | IPCRP1 | IPCRP1 | 0017-0000 | STRUCTURAL EXCAVATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0017-0000-R | IPCRP1 | IPCRP1 | 0017-0000 | STRUCTURAL EXCAVATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1584750 | 0 | 0 | 1584750 | 0 | 1584750 | 1052409 | 0 | N | 1584750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0017-1000-E | IPCRP1 | IPCRP1 | 0017-1000 | STRUCTURAL EXCAVATION | N | E |  | NR | P | 304712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 304712 | 0 | 0 | 304712 | 0 | 0 | 0 | Y | 304712 | 0 | 0 | 304712 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 10565 | 8088.78 | 2476.22 | 10565 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0017-1000-L | IPCRP1 | IPCRP1 | 0017-1000 | STRUCTURAL EXCAVATION | N | L |  | NR | P | 226359.78 | 388078.23 | 388078.23 | 388078.23 | 388078.23 | 82.9217 | 0 | 0 | 0 | 79927.43 | Y | 468005.66 | Y | -241645.88 | 0 | 0 | 226359.78 | 0 | 0 | 468005.66 | Y | -241645.88 | 0 | 0 | 226359.78 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -468005.66 | 29845.74 | 57926.29 | 468005.66 | 0 | 0 | 0 | 0 | 0 | 0 | -468005.66 | 0 | 0 | 468005.66 | 468005.66 | 0 | 0 | 0 | 2028.48 | 0 | 3600 | 3600 | 2028.48 | 3133.5 | 466.5 | 3600 | HR | 10565 | 8088.78 | 2476.22 | 10565 | CY | 0 | 0 | 0 | 79927.43
Y | IPCRP1-0017-1000-S | IPCRP1 | IPCRP1 | 0017-1000 | STRUCTURAL EXCAVATION | N | S |  | UNIT | A | 0 | 36668.27 | 36668.27 | 36668.27 | 36668.27 | 166.587 | 0 | 0 | 0 | -14656.78 | Y | 22011.49 | Y | -22011.49 | 0 | 0 | 0 | 0 | 0 | 22011.49 | Y | -22011.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22011.49 | 14656.78 | 6683.73 | 22011.49 | 0 | 0 | 0 | 0 | 14656.78 | 0 | -22011.49 | 0 | 0 | 22011.49 | 22011.49 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 126.5 | -62.5 | 64 | NA | 10565 | 8088.78 | 2476.22 | 10565 | CY | 36668.27 | 0 | 36668.27 | -14656.78
Y | IPCRP1-0018-0000-L | IPCRP1 | IPCRP1 | 0018-0000 | GEOTEXTILE DRAINAGE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0018-0000-R | IPCRP1 | IPCRP1 | 0018-0000 | GEOTEXTILE DRAINAGE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1040 | 0 | 0 | 1040 | 0 | 1040 | 48.5 | 0 | N | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0018-1000-L | IPCRP1 | IPCRP1 | 0018-1000 | PM - Geotextile Drainage | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1040 | 48.5 | 991.5 | 1040 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0018-1000-M | IPCRP1 | IPCRP1 | 0018-1000 | PM - Geotextile Drainage | N | M |  | NR | P | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | N | 1300 | N | 0 | 0 | 0 | 1300 | 0 | 0 | 1300 | N | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1300 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | -1300 | 0 | 0 | 1300 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 1040 | 48.5 | 991.5 | 1040 | SY | 0 | 0 | 0 | 1300
Y | IPCRP1-0019-0000-L | IPCRP1 | IPCRP1 | 0019-0000 | GEOMEMBRANE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0019-0000-R | IPCRP1 | IPCRP1 | 0019-0000 | GEOMEMBRANE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 68000 | 0 | 0 | 68000 | 0 | 68000 | 29653.75 | 0 | N | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0019-1000-E | IPCRP1 | IPCRP1 | 0019-1000 | Inst Geomembrane | N | E |  | NR | P | 6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6528 | 0 | 0 | 6528 | 0 | 0 | 0 | Y | 6528 | 0 | 0 | 6528 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2720 | 1186.15 | 1533.85 | 2720 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0019-1000-L | IPCRP1 | IPCRP1 | 0019-1000 | Inst Geomembrane | N | L |  | NR | P | 47130.64 | 15571.7 | 15571.7 | 15571.7 | 15571.7 | 33.0394 | 0 | 0 | 0 | 31558.94 | N | 47130.64 | N | 0 | 0 | 0 | 47130.64 | 0 | 0 | 47130.64 | N | 0 | 0 | 0 | 47130.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -47130.64 | 0 | 0 | 47130.64 | 0 | 0 | 0 | 0 | 0 | 0 | -47130.64 | 0 | 0 | 47130.64 | 47130.64 | 0 | 0 | 0 | 435.2 | 0 | 435.2 | 435.2 | 435.2 | 126.5 | 308.7 | 435.2 | HR | 2720 | 1186.15 | 1533.85 | 2720 | SY | 0 | 0 | 0 | 31558.94
Y | IPCRP1-0019-1010-L | IPCRP1 | IPCRP1 | 0019-1010 | PM - Geomembrane | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2720 | 1186.15 | 1533.85 | 2720 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0019-1010-M | IPCRP1 | IPCRP1 | 0019-1010 | PM - Geomembrane | N | M |  | NR | P | 8160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8160 | N | 8160 | N | 0 | 0 | 0 | 8160 | 0 | 0 | 8160 | N | 0 | 0 | 0 | 8160 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8160 | 0 | 0 | 8160 | 0 | 0 | 0 | 0 | 0 | 0 | -8160 | 0 | 0 | 8160 | 8160 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2720 | 1186.15 | 1533.85 | 2720 | SY | 0 | 0 | 0 | 8160
Y | IPCRP1-0020-0000-L | IPCRP1 | IPCRP1 | 0020-0000 | PREFAB COMP STRUCTURAL DRAIN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0020-0000-R | IPCRP1 | IPCRP1 | 0020-0000 | PREFAB COMP STRUCTURAL DRAIN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2100 | 0 | 0 | 2100 | 0 | 2100 | 607.58 | 0 | N | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0020-1000-E | IPCRP1 | IPCRP1 | 0020-1000 | Inst Prefab Comp Struct Drain | N | E |  | NR | P | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3120 | 0 | 0 | 3120 | 0 | 0 | 0 | Y | 3120 | 0 | 0 | 3120 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1300 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | J. D'Annunzio & Sons, Inc.
Y | IPCRP1-0020-1000-L | IPCRP1 | IPCRP1 | 0020-1000 | Inst Prefab Comp Struct Drain | N | L |  | NR | P | 93278.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 93278.33 | 0 | 0 | 93278.33 | 0 | 0 | 0 | Y | 93278.33 | 0 | 0 | 93278.33 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915.2 | 0 | 0 | 0 | 915.2 | 0 | 0 | 0 | HR | 1300 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc 0147-1070
Y | IPCRP1-0020-1010-L | IPCRP1 | IPCRP1 | 0020-1010 | PM - Prefab Comp Struct Drain | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1300 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0020-1010-M | IPCRP1 | IPCRP1 | 0020-1010 | PM - Prefab Comp Struct Drain | N | M |  | NR | P | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 13000 | 0 | 0 | 13000 | 0 | 0 | 0 | N | 13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1300 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc 0147-1070
Y | IPCRP1-0021-0000-L | IPCRP1 | IPCRP1 | 0021-0000 | SUBBASE COURSE, TYPE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0021-0000-R | IPCRP1 | IPCRP1 | 0021-0000 | SUBBASE COURSE, TYPE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15000 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | N | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0021-1000-E | IPCRP1 | IPCRP1 | 0021-1000 | Inst Subbase Course Type 1 | N | E |  | NR | P | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | Y | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 50 | 0 | 345.78 | 345.78 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0021-1000-L | IPCRP1 | IPCRP1 | 0021-1000 | Inst Subbase Course Type 1 | N | L |  | NR | P | 3727.68 | 2290.33 | 2290.33 | 2290.33 | 2290.33 | 61.4412 | 0 | 0 | 0 | 1437.35 | N | 3727.68 | N | 0 | 0 | 0 | 3727.68 | 0 | 0 | 3727.68 | N | 0 | 0 | 0 | 3727.68 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3727.68 | 0 | 0 | 3727.68 | 0 | 0 | 0 | 0 | 0 | 0 | -3727.68 | 0 | 0 | 3727.68 | 3727.68 | 0 | 0 | 0 | 32 | 0 | 32 | 32 | 32 | 20 | 12 | 32 | HR | 50 | 0 | 345.78 | 345.78 | CY | 0 | 0 | 0 | 1437.35
Y | IPCRP1-0021-1000-S | IPCRP1 | IPCRP1 | 0021-1000 | Inst Subbase Course Type 1 | N | S |  | UNIT | A | 0 | 2033.05 | 2033.05 | 2033.05 | 2033.05 | 100 | 0 | 0 | 0 | 0 | N | 2033.05 | N | -2033.05 | 0 | 0 | 0 | 0 | 0 | 2033.05 | N | -2033.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2033.05 | 0 | 0 | 2033.05 | 0 | 0 | 0 | 0 | 0 | 0 | -2033.05 | 0 | 0 | 2033.05 | 2033.05 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 16 | 0 | 16 | NA | 50 | 0 | 345.78 | 345.78 | CY | 2033.05 | 0 | 2033.05 | 0
Y | IPCRP1-0022-0000-L | IPCRP1 | IPCRP1 | 0022-0000 | ASPH MACADAM PVMNT, 6 in THICK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0022-0000-R | IPCRP1 | IPCRP1 | 0022-0000 | ASPH MACADAM PVMNT, 6 in THICK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1181600 | 0 | 0 | 1181600 | 0 | 1181600 | 152880 | 0 | N | 1181600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1181600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0023-0000-L | IPCRP1 | IPCRP1 | 0023-0000 | ASPH CONC WEARING COURSE, 1.5 in THICK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0023-0000-R | IPCRP1 | IPCRP1 | 0023-0000 | ASPH CONC WEARING COURSE, 1.5 in THICK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 47950 | 0 | 0 | 47950 | 0 | 47950 | 0 | 0 | N | 47950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0023-1000-C | IPCRP1 | IPCRP1 | 0023-1000 | ASPH CONC WEARING COURSE, 1.5 in THICK | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287.66 | Y | 1287.66 | Y | -1287.66 | 0 | 0 | 0 | 0 | 0 | 1287.66 | Y | -1287.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1287.66 | 0 | 0 | 1287.66 | 0 | 0 | 0 | 0 | 0 | 0 | -1287.66 | 0 | 0 | 1287.66 | 1287.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1918 | 0 | 1918 | 1918 | SY | 0 | 0 | 0 | 1287.66
Y | IPCRP1-0023-1000-E | IPCRP1 | IPCRP1 | 0023-1000 | ASPH CONC WEARING COURSE, 1.5 in THICK | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1918 | 0 | 1918 | 1918 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0023-1000-L | IPCRP1 | IPCRP1 | 0023-1000 | ASPH CONC WEARING COURSE, 1.5 in THICK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26600.52 | Y | 26600.52 | Y | -26600.52 | 0 | 0 | 0 | 0 | 0 | 26600.52 | Y | -26600.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26600.52 | 0 | 0 | 26600.52 | 0 | 0 | 0 | 0 | 0 | 0 | -26600.52 | 0 | 0 | 26600.52 | 26600.52 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 200 | 200 | HR | 1918 | 0 | 1918 | 1918 | SY | 0 | 0 | 0 | 26600.52 | 1,918 SY @ 1.5 Inches = 175 T, at est $60.00/TON = $10,500.00 (Mat).
Y | IPCRP1-0023-1000-M | IPCRP1 | IPCRP1 | 0023-1000 | ASPH CONC WEARING COURSE, 1.5 in THICK | N | M |  | UNIT | U | 0 | 14310.63 | 14310.63 | 0 | 14310.63 | 0 | 0 | 0 | 0 | 0 | Y | 14310.63 | Y | -14310.63 | 0 | 0 | 0 | 0 | 0 | 14310.63 | Y | -14310.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14310.63 | 0 | 0 | 14310.63 | 0 | 0 | 0 | 0 | 0 | 0 | -14310.63 | 0 | 0 | 14310.63 | 14310.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1918 | 0 | 1918 | 1918 | SY | 14310.63 | 14310.63 | 0 | 0
Y | IPCRP1-0023-1000-S | IPCRP1 | IPCRP1 | 0023-1000 | ASPH CONC WEARING COURSE, 1.5 in THICK | N | S |  | NR | A | 40987.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | Y | 3200 | Y | 37787.66 | 0 | 0 | 40987.66 | 0 | 0 | 3200 | Y | 37787.66 | 0 | 0 | 40987.66 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3200 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | -3200 | 0 | 0 | 3200 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1918 | 0 | 1918 | 1918 | SY | 0 | 0 | 0 | 3200
Y | IPCRP1-0024-0000-L | IPCRP1 | IPCRP1 | 0024-0000 | ASPH CONC WEARING COURSE, 3 in THICK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0024-0000-R | IPCRP1 | IPCRP1 | 0024-0000 | ASPH CONC WEARING COURSE, 3 in THICK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 311025 | 0 | 0 | 311025 | 0 | 311025 | 138234.75 | 0 | N | 311025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0024-1000-C | IPCRP1 | IPCRP1 | 0024-1000 | ASPH CONC WEARING COURSE, 3 THICK | N | C |  | UNIT | U | 0 | 21528.75 | 21528.75 | 21528.75 | 21528.75 | 100 | 0 | 0 | 0 | 0 | Y | 21528.75 | Y | -21528.75 | 0 | 0 | 0 | 0 | 0 | 21528.75 | Y | -21528.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21528.75 | 0 | 0 | 21528.75 | 0 | 0 | 0 | 0 | 0 | 0 | -21528.75 | 0 | 0 | 21528.75 | 21528.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 12441 | 6251.39 | 6189.61 | 12441 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0024-1000-E | IPCRP1 | IPCRP1 | 0024-1000 | ASPH CONC WEARING COURSE, 3 THICK | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 12441 | 6251.39 | 6189.61 | 12441 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0024-1000-L | IPCRP1 | IPCRP1 | 0024-1000 | ASPH CONC WEARING COURSE, 3 THICK | N | L |  | UNIT | P | 0 | 109170.96 | 109170.96 | 109170.96 | 109170.96 | 40.7906 | 0 | 0 | 0 | 158466.47 | Y | 267637.43 | Y | -267637.43 | 0 | 0 | 0 | 0 | 0 | 267637.43 | Y | -267637.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -267637.43 | 12106.25 | 0 | 267637.43 | 0 | 0 | 0 | 0 | 0 | 0 | -267637.43 | 0 | 0 | 267637.43 | 267637.43 | 0 | 0 | 0 | 0 | 0 | 1999.96 | 1999.96 | 0 | 829.5 | 1170.46 | 1999.96 | HR | 12441 | 6251.39 | 6189.61 | 12441 | SY | 0 | 0 | 0 | 158466.47
Y | IPCRP1-0024-1000-M | IPCRP1 | IPCRP1 | 0024-1000 | ASPH CONC WEARING COURSE, 3 THICK | N | M |  | UNIT | U | 0 | 164031.74 | 164031.74 | 43378.45 | 164031.74 | 26.4452 | 0 | 0 | 0 | 0 | Y | 164031.74 | Y | -164031.74 | 0 | 0 | 0 | 0 | 0 | 164031.74 | Y | -164031.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -164031.74 | 0 | 0 | 164031.74 | 0 | 0 | 0 | 0 | 0 | 0 | -164031.74 | 0 | 0 | 164031.74 | 164031.74 | 0 | 0 | 0 | 0 | 0 | 419.54 | 419.54 | 0 | 634.5 | -214.96 | 419.54 | NA | 12441 | 6251.39 | 6189.61 | 12441 | SY | 164031.74 | 120653.29 | 43378.45 | 0
Y | IPCRP1-0024-1000-S | IPCRP1 | IPCRP1 | 0024-1000 | ASPH CONC WEARING COURSE, 3 THICK | N | S |  | NR | A | 294105.24 | 2151.11 | 2151.11 | 2151.11 | 2151.11 | 10.7555 | 0 | 0 | 0 | 17848.89 | Y | 20000 | Y | 274105.24 | 0 | 0 | 294105.24 | 0 | 0 | 20000 | Y | 274105.24 | 0 | 0 | 294105.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17 | -17 | 0 | LF | 12441 | 6251.39 | 6189.61 | 12441 | SY | 2151.11 | 0 | 2151.11 | 17848.89
Y | IPCRP1-0025-0000-L | IPCRP1 | IPCRP1 | 0025-0000 | BINDER MIXTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0025-0000-R | IPCRP1 | IPCRP1 | 0025-0000 | BINDER MIXTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 39325 | 0 | 0 | 39325 | 0 | 39325 | 58603.87 | 0 | N | 39325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0025-1000-C | IPCRP1 | IPCRP1 | 0025-1000 | BINDER MIXTURE | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 143 | 231.53 | 0 | 231.53 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0025-1000-E | IPCRP1 | IPCRP1 | 0025-1000 | BINDER MIXTURE | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 143 | 231.53 | 0 | 231.53 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0025-1000-L | IPCRP1 | IPCRP1 | 0025-1000 | BINDER MIXTURE | N | L |  | UNIT | P | 0 | 6476.68 | 6476.68 | 6476.68 | 6476.68 | 100 | 0 | 0 | 0 | 0 | Y | 6476.68 | Y | -6476.68 | 0 | 0 | 0 | 0 | 0 | 6476.68 | Y | -6476.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6476.68 | 0 | 0 | 6476.68 | 0 | 0 | 0 | 0 | 0 | 0 | -6476.68 | 0 | 0 | 6476.68 | 6476.68 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 36 | 0 | 36 | HR | 143 | 231.53 | 0 | 231.53 | TN | 0 | 0 | 0 | 0 | DDC paid 82.04 T used sporadically prior to May 2025. DDC paid 149.49 T in June at Delancey St as filler to correct grade. Material cost included in 0024-1000
Y | IPCRP1-0025-1000-M | IPCRP1 | IPCRP1 | 0025-1000 | BINDER MIXTURE | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 143 | 231.53 | 0 | 231.53 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0025-1000-S | IPCRP1 | IPCRP1 | 0025-1000 | BINDER MIXTURE | N | S |  | NR | A | 37651.9 | 1098.52 | 1098.52 | 1098.52 | 1098.52 | 100 | 0 | 0 | 0 | 0 | Y | 1098.52 | Y | 36553.38 | 0 | 0 | 37651.9 | 0 | 0 | 1098.52 | Y | 36553.38 | 0 | 0 | 37651.9 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1098.52 | 0 | 0 | 1098.52 | 0 | 0 | 0 | 0 | 0 | 0 | -1098.52 | 0 | 0 | 1098.52 | 1098.52 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8.5 | -8.5 | 0 | LF | 143 | 231.53 | 0 | 231.53 | TN | 1098.52 | 0 | 1098.52 | 0
Y | IPCRP1-0026-0000-L | IPCRP1 | IPCRP1 | 0026-0000 | ASPH CONCRETE MIXTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0026-0000-R | IPCRP1 | IPCRP1 | 0026-0000 | ASPH CONCRETE MIXTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 208075 | 0 | 0 | 208075 | 0 | 208075 | 216637.75 | 0 | N | 208075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0026-1000-E | IPCRP1 | IPCRP1 | 0026-1000 | ASPH CONCRETE MIXTURE | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1189 | 1237.93 | 0 | 1237.93 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0026-1000-L | IPCRP1 | IPCRP1 | 0026-1000 | ASPH CONCRETE MIXTURE | N | L |  | UNIT | P | 0 | 111470.01 | 111470.01 | 111470.01 | 111470.01 | 100 | 0 | 0 | 0 | 0 | Y | 111470.01 | Y | -111470.01 | 0 | 0 | 0 | 0 | 0 | 111470.01 | Y | -111470.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -111470.01 | 0 | 0 | 111470.01 | 0 | 0 | 0 | 0 | 0 | 0 | -111470.01 | 0 | 0 | 111470.01 | 111470.01 | 0 | 0 | 0 | 0 | 0 | 782 | 782 | 0 | 782 | 0 | 782 | HR | 1189 | 1237.93 | 0 | 1237.93 | TN | 0 | 0 | 0 | 0 | DDC uses this for Temp Asphalt as needed. Material for temp asphalt included in cc: 0219-1060 (Temp Asphalt) Bid as a sub (plug), converted to self perform. (VS, 2/15/22)
Y | IPCRP1-0026-1000-M | IPCRP1 | IPCRP1 | 0026-1000 | ASPH CONCRETE MIXTURE | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1189 | 1237.93 | 0 | 1237.93 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0026-1000-S | IPCRP1 | IPCRP1 | 0026-1000 | ASPH CONCRETE MIXTURE | N | S |  | NR | A | 200489.18 | 6294.07 | 6294.07 | 6294.07 | 6294.07 | 21.8544 | 0 | 0 | 0 | 22505.93 | Y | 28800 | Y | 171689.18 | 0 | 0 | 200489.18 | 0 | 0 | 28800 | Y | 171689.18 | 0 | 0 | 200489.18 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28800 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | -28800 | 0 | 0 | 28800 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 51.5 | -51.5 | 0 | LF | 1189 | 1237.93 | 0 | 1237.93 | TN | 6294.07 | 0 | 6294.07 | 22505.93
Y | IPCRP1-0027-0000-L | IPCRP1 | IPCRP1 | 0027-0000 | CONC BASE FOR PVMNT, 6 inTHICK, CL B-32 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0027-0000-R | IPCRP1 | IPCRP1 | 0027-0000 | CONC BASE FOR PVMNT, 6 inTHICK, CL B-32 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12950 | 0 | 0 | 12950 | 0 | 12950 | 0 | 0 | N | 12950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0027-1000-C | IPCRP1 | IPCRP1 | 0027-1000 | Inst Conc Base Pvmnt, 6 inThick, Cl B-32 | N | C |  | NR | P | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 200 | 0 | 0 | 200 | 0 | 0 | 0 | Y | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 37 | 0 | 37 | 37 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0027-1000-E | IPCRP1 | IPCRP1 | 0027-1000 | Inst Conc Base Pvmnt, 6 inThick, Cl B-32 | N | E |  | NR | P | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 100 | 0 | 0 | 100 | 0 | 0 | 0 | Y | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 37 | 0 | 37 | 37 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0027-1000-L | IPCRP1 | IPCRP1 | 0027-1000 | Inst Conc Base Pvmnt, 6 inThick, Cl B-32 | N | L |  | NR | P | 4301.83 | 4425.18 | 4425.18 | 4425.18 | 4425.18 | 100 | 0 | 0 | 0 | 0 | Y | 4425.18 | Y | -123.35 | 0 | 0 | 4301.83 | 0 | 0 | 4425.18 | Y | -123.35 | 0 | 0 | 4301.83 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4425.18 | 0 | 0 | 4425.18 | 0 | 0 | 0 | 0 | 0 | 0 | -4425.18 | 0 | 0 | 4425.18 | 4425.18 | 0 | 0 | 0 | 40 | 0 | 35 | 35 | 40 | 0 | 35 | 35 | HR | 37 | 0 | 37 | 37 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0027-1000-S | IPCRP1 | IPCRP1 | 0027-1000 | Inst Conc Base Pvmnt, 6 inThick, Cl B-32 | N | S |  | UNIT | A | 0 | 889.46 | 889.46 | 889.46 | 889.46 | 100 | 0 | 0 | 0 | 0 | N | 889.46 | N | -889.46 | 0 | 0 | 0 | 0 | 0 | 889.46 | N | -889.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -889.46 | 0 | 0 | 889.46 | 0 | 0 | 0 | 0 | 0 | 0 | -889.46 | 0 | 0 | 889.46 | 889.46 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 7 | NA | 37 | 0 | 37 | 37 | CY | 889.46 | 0 | 889.46 | 0
Y | IPCRP1-0028-0000-L | IPCRP1 | IPCRP1 | 0028-0000 | CONC BASE FOR PVMNT, VAR THICK, TREN REST, HI EAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0028-0000-R | IPCRP1 | IPCRP1 | 0028-0000 | CONC BASE FOR PVMNT, VAR THICK, TREN REST, HI EAR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6000 | 0 | 0 | 6000 | 0 | 6000 | 0 | 0 | N | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0028-1000-C | IPCRP1 | IPCRP1 | 0028-1000 | Inst Conc Base Pvmnt, Var Thick, Trench Rest, Hi | N | C |  | NR | P | 86.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.4 | N | 86.4 | N | 0 | 0 | 0 | 86.4 | 0 | 0 | 86.4 | N | 0 | 0 | 0 | 86.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -86.4 | 0 | 0 | 86.4 | 0 | 0 | 0 | 0 | 0 | 0 | -86.4 | 0 | 0 | 86.4 | 86.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 16 | 0 | 16 | 16 | CY | 0 | 0 | 0 | 86.4
Y | IPCRP1-0028-1000-E | IPCRP1 | IPCRP1 | 0028-1000 | Inst Conc Base Pvmnt, Var Thick, Trench Rest, Hi | N | E |  | NR | P | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 50 | 0 | 0 | 50 | 0 | 0 | 0 | Y | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 16 | 0 | 16 | 16 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0028-1000-L | IPCRP1 | IPCRP1 | 0028-1000 | Inst Conc Base Pvmnt, Var Thick, Trench Rest, Hi | N | L |  | NR | P | 2150.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150.91 | N | 2150.91 | N | 0 | 0 | 0 | 2150.91 | 0 | 0 | 2150.91 | N | 0 | 0 | 0 | 2150.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2150.91 | 0 | 0 | 2150.91 | 0 | 0 | 0 | 0 | 0 | 0 | -2150.91 | 0 | 0 | 2150.91 | 2150.91 | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 20 | 0 | 20 | 20 | HR | 16 | 0 | 16 | 16 | CY | 0 | 0 | 0 | 2150.91
Y | IPCRP1-0029-0000-L | IPCRP1 | IPCRP1 | 0029-0000 | CONC BASE FOR PVMNT, 8 inTHICK, HIGH EARLY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0029-0000-R | IPCRP1 | IPCRP1 | 0029-0000 | CONC BASE FOR PVMNT, 8 inTHICK, HIGH EARLY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 254250 | 0 | 0 | 254250 | 0 | 254250 | 157900 | 0 | N | 254250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0029-1000-C | IPCRP1 | IPCRP1 | 0029-1000 | Inst Conc Base fPvmnt, 8 inThick, Hi Early | N | C |  | NR | P | 20370.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20370.3 | N | 20370.3 | N | 0 | 0 | 0 | 20370.3 | 0 | 0 | 20370.3 | N | 0 | 0 | 0 | 20370.3 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20370.3 | 0 | 0 | 20370.3 | 0 | 0 | 0 | 0 | 0 | 0 | -20370.3 | 0 | 0 | 20370.3 | 20370.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1017 | 631.6 | 385.4 | 1017 | CY | 0 | 0 | 0 | 20370.3
Y | IPCRP1-0029-1000-E | IPCRP1 | IPCRP1 | 0029-1000 | Inst Conc Base fPvmnt, 8 inThick, Hi Early | N | E |  | NR | P | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 600 | 0 | 0 | 600 | 0 | 0 | 0 | Y | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1017 | 631.6 | 385.4 | 1017 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0029-1000-L | IPCRP1 | IPCRP1 | 0029-1000 | Inst Conc Base fPvmnt, 8 inThick, Hi Early | N | L |  | NR | P | 35925.01 | 64237.93 | 64237.93 | 64237.93 | 64237.93 | 52.6348 | 0 | 0 | 0 | 57806.62 | Y | 122044.55 | Y | -86119.54 | 0 | 0 | 35925.01 | 0 | 0 | 122044.55 | Y | -86119.54 | 0 | 0 | 35925.01 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -122044.55 | 0 | 0 | 122044.55 | 0 | 0 | 0 | 0 | 0 | 0 | -122044.55 | 0 | 0 | 122044.55 | 122044.55 | 0 | 0 | 0 | 336 | 0 | 1017 | 1017 | 336 | 568 | 449 | 1017 | HR | 1017 | 631.6 | 385.4 | 1017 | CY | 0 | 0 | 0 | 57806.62
Y | IPCRP1-0029-1000-S | IPCRP1 | IPCRP1 | 0029-1000 | Inst Conc Base fPvmnt, 8 inThick, Hi Early | N | S |  | UNIT | A | 0 | 1562.13 | 1562.13 | 1562.13 | 1562.13 | 100 | 0 | 0 | 0 | 0 | N | 1562.13 | N | -1562.13 | 0 | 0 | 0 | 0 | 0 | 1562.13 | N | -1562.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1562.13 | 0 | 0 | 1562.13 | 0 | 0 | 0 | 0 | 0 | 0 | -1562.13 | 0 | 0 | 1562.13 | 1562.13 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 0 | 12.5 | 0 | 12.5 | NA | 1017 | 631.6 | 385.4 | 1017 | CY | 1562.13 | 0 | 1562.13 | 0
Y | IPCRP1-0030-0000-L | IPCRP1 | IPCRP1 | 0030-0000 | CONC BASE FOR PVMNT, 9 in THICK, HIGH EARLY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0030-0000-R | IPCRP1 | IPCRP1 | 0030-0000 | CONC BASE FOR PVMNT, 9 in THICK, HIGH EARLY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 364100 | 0 | 0 | 364100 | 0 | 364100 | 67292.5 | 0 | N | 364100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0030-1000-C | IPCRP1 | IPCRP1 | 0030-1000 | Inst Conc Base Pvmnt, 9 in Thick, Hi Early | N | C |  | NR | P | 25950.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25950.4 | N | 25950.4 | N | 0 | 0 | 0 | 25950.4 | 0 | 0 | 25950.4 | N | 0 | 0 | 0 | 25950.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25950.4 | 0 | 0 | 25950.4 | 0 | 0 | 0 | 0 | 0 | 0 | -25950.4 | 0 | 0 | 25950.4 | 25950.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1324 | 244.7 | 1079.3 | 1324 | CY | 0 | 0 | 0 | 25950.4
Y | IPCRP1-0030-1000-E | IPCRP1 | IPCRP1 | 0030-1000 | Inst Conc Base Pvmnt, 9 in Thick, Hi Early | N | E |  | NR | P | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | Y | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1324 | 244.7 | 1079.3 | 1324 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0030-1000-L | IPCRP1 | IPCRP1 | 0030-1000 | Inst Conc Base Pvmnt, 9 in Thick, Hi Early | N | L |  | NR | P | 64527.4 | 14460.8 | 14460.8 | 14460.8 | 14460.8 | 22.4103 | 0 | 0 | 0 | 50066.6 | N | 64527.4 | N | 0 | 0 | 0 | 64527.4 | 0 | 0 | 64527.4 | N | 0 | 0 | 0 | 64527.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -64527.4 | 0 | 0 | 64527.4 | 0 | 0 | 0 | 0 | 0 | 0 | -64527.4 | 0 | 0 | 64527.4 | 64527.4 | 0 | 0 | 0 | 600 | 0 | 600 | 600 | 600 | 121.5 | 478.5 | 600 | HR | 1324 | 244.7 | 1079.3 | 1324 | CY | 0 | 0 | 0 | 50066.6
Y | IPCRP1-0031-0000-L | IPCRP1 | IPCRP1 | 0031-0000 | HIGH EARLY STRENGTH RC PVMNT (FULL WIDTH PVMNT) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0031-0000-R | IPCRP1 | IPCRP1 | 0031-0000 | HIGH EARLY STRENGTH RC PVMNT (FULL WIDTH PVMNT) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 52500 | 0 | 0 | 52500 | 0 | 52500 | 0 | 0 | N | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0031-1000-C | IPCRP1 | IPCRP1 | 0031-1000 | Inst Hi Early RC Pvmnt (Full Width) | N | C |  | NR | P | 1003.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003.5 | N | 1003.5 | N | 0 | 0 | 0 | 1003.5 | 0 | 0 | 1003.5 | N | 0 | 0 | 0 | 1003.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1003.5 | 0 | 0 | 1003.5 | 0 | 0 | 0 | 0 | 0 | 0 | -1003.5 | 0 | 0 | 1003.5 | 1003.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 105 | 0 | 105 | 105 | CY | 0 | 0 | 0 | 1003.5
Y | IPCRP1-0031-1000-E | IPCRP1 | IPCRP1 | 0031-1000 | Inst Hi Early RC Pvmnt (Full Width) | N | E |  | NR | P | 1560.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1560.52 | 0 | 0 | 1560.52 | 0 | 0 | 0 | Y | 1560.52 | 0 | 0 | 1560.52 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 105 | 0 | 105 | 105 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0031-1000-L | IPCRP1 | IPCRP1 | 0031-1000 | Inst Hi Early RC Pvmnt (Full Width) | N | L |  | NR | P | 19502.94 | 1923.17 | 1923.17 | 1923.17 | 1923.17 | 9.8609 | 0 | 0 | 0 | 17579.77 | N | 19502.94 | N | 0 | 0 | 0 | 19502.94 | 0 | 0 | 19502.94 | N | 0 | 0 | 0 | 19502.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19502.94 | 0 | 0 | 19502.94 | 0 | 0 | 0 | 0 | 0 | 0 | -19502.94 | 0 | 0 | 19502.94 | 19502.94 | 0 | 0 | 0 | 176 | 0 | 176 | 176 | 176 | 0 | 176 | 176 | HR | 105 | 0 | 105 | 105 | CY | 0 | 0 | 0 | 17579.77
Y | IPCRP1-0031-1000-M | IPCRP1 | IPCRP1 | 0031-1000 | Inst Hi Early RC Pvmnt (Full Width) | N | M |  | NR | P | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4635 | N | 4635 | N | 0 | 0 | 0 | 4635 | 0 | 0 | 4635 | N | 0 | 0 | 0 | 4635 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4635 | 0 | 0 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | -4635 | 0 | 0 | 4635 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 105 | 0 | 105 | 105 | CY | 0 | 0 | 0 | 4635
Y | IPCRP1-0032-0000-L | IPCRP1 | IPCRP1 | 0032-0000 | CONCRETE IN STRUCTURES, CL A-40 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0032-0000-R | IPCRP1 | IPCRP1 | 0032-0000 | CONCRETE IN STRUCTURES, CL A-40 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 112500 | 0 | 0 | 112500 | 0 | 112500 | 5775 | 0 | N | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0032-1000-L | IPCRP1 | IPCRP1 | 0032-1000 | Install & Strip Formwork | N | L |  | NR | P | 27570.22 | 6.03 | 6.03 | 6.03 | 6.03 | 0.021871 | 0 | 0 | 0 | 27564.19 | N | 27570.22 | N | 0 | 0 | 0 | 27570.22 | 0 | 0 | 27570.22 | N | 0 | 0 | 0 | 27570.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27570.22 | 0 | 0 | 27570.22 | 0 | 0 | 0 | 0 | 0 | 0 | -27570.22 | 0 | 0 | 27570.22 | 27570.22 | 0 | 0 | 0 | 233.33 | 0 | 233.33 | 233.33 | 233.33 | 0 | 233.33 | 233.33 | HR | 3125 | 0 | 3125 | 3125 | SF | 0 | 0 | 0 | 27564.19
Y | IPCRP1-0032-1010-L | IPCRP1 | IPCRP1 | 0032-1010 | Place Concrete | N | L |  | NR | P | 11745.93 | -0.06 | -0.06 | -0.06 | -0.06 | -0.00051082 | 0 | 0 | 0 | 11745.99 | N | 11745.93 | N | 0 | 0 | 0 | 11745.93 | 0 | 0 | 11745.93 | N | 0 | 0 | 0 | 11745.93 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11745.93 | 0 | 0 | 11745.93 | 0 | 0 | 0 | 0 | 0 | 0 | -11745.93 | 0 | 0 | 11745.93 | 11745.93 | 0 | 0 | 0 | 116.67 | 0 | 116.67 | 116.67 | 116.67 | 0 | 116.67 | 116.67 | HR | 75 | 3.85 | 71.15 | 75 | CY | 0 | 0 | 0 | 11745.99
Y | IPCRP1-0032-1020-C | IPCRP1 | IPCRP1 | 0032-1020 | Furn Formwork | N | C |  | NR | P | 10208 | 0.27 | 0.27 | 0 | 0.27 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 10208 | 0 | 0 | 10208 | 0 | 0 | 0 | N | 10208 | 0 | 0 | 10208 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1674 | -1674 | 0 | EA | 3125 | 0 | 0 | 0 | SF | 0.27 | 0.27 | 0 | 0
Y | IPCRP1-0032-1020-L | IPCRP1 | IPCRP1 | 0032-1020 | Furn Formwork | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0.01 | HR | 3125 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Change PMF (Quantity) from 3,125.00 to 0.00
Y | IPCRP1-0033-0000-L | IPCRP1 | IPCRP1 | 0033-0000 | RESET GRANITE CURB | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0033-0000-R | IPCRP1 | IPCRP1 | 0033-0000 | RESET GRANITE CURB | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18125 | 0 | 0 | 18125 | 0 | 18125 | 0 | 0 | N | 18125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0034-0000-L | IPCRP1 | IPCRP1 | 0034-0000 | CONCRETE CURB (18 DEEP) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0034-0000-R | IPCRP1 | IPCRP1 | 0034-0000 | CONCRETE CURB (18 DEEP) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20125 | 0 | 0 | 20125 | 0 | 20125 | 99350.8 | 0 | N | 20125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0035-0000-L | IPCRP1 | IPCRP1 | 0035-0000 | STRAIGHT SFC CURB (18 in DEEP) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0035-0000-R | IPCRP1 | IPCRP1 | 0035-0000 | STRAIGHT SFC CURB (18 in DEEP) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 217455 | 0 | 0 | 217455 | 0 | 217455 | 26276.05 | 0 | N | 217455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0036-0000-L | IPCRP1 | IPCRP1 | 0036-0000 | STRAIGHT SFC CURB (21 in DEEP) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0036-0000-R | IPCRP1 | IPCRP1 | 0036-0000 | STRAIGHT SFC CURB (21 in DEEP) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 109500 | 0 | 0 | 109500 | 0 | 109500 | 90945 | 0 | N | 109500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0037-0000-L | IPCRP1 | IPCRP1 | 0037-0000 | DEPRESSED SFC CURB (18 in DEEP) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0037-0000-R | IPCRP1 | IPCRP1 | 0037-0000 | DEPRESSED SFC CURB (18 in DEEP) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12200 | 0 | 0 | 12200 | 0 | 12200 | 2200 | 0 | N | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0038-0000-L | IPCRP1 | IPCRP1 | 0038-0000 | DEPRESSED SFC CURB (21 in DEEP) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0038-0000-R | IPCRP1 | IPCRP1 | 0038-0000 | DEPRESSED SFC CURB (21 in DEEP) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18000 | 0 | 0 | 18000 | 0 | 18000 | 0 | 0 | N | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0039-0000-L | IPCRP1 | IPCRP1 | 0039-0000 | CORNER SFC CURB (18 in DEEP) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0039-0000-R | IPCRP1 | IPCRP1 | 0039-0000 | CORNER SFC CURB (18 in DEEP) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 36225 | 0 | 0 | 36225 | 0 | 36225 | 0 | 0 | N | 36225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0040-0000-L | IPCRP1 | IPCRP1 | 0040-0000 | CORNER SFC CURB (21 in DEEP) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0040-0000-R | IPCRP1 | IPCRP1 | 0040-0000 | CORNER SFC CURB (21 in DEEP) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 33775 | 0 | 0 | 33775 | 0 | 33775 | 17461.5 | 0 | N | 33775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0040-1000-C | IPCRP1 | IPCRP1 | 0040-1000 | F&I Curbs - All Types & Sizes | N | C |  | UNIT | U | 0 | 15452.7 | 15452.7 | 15309.5 | 15452.7 | 99.0733 | 0 | 0 | 0 | 0 | Y | 15452.7 | Y | -15452.7 | 0 | 0 | 0 | 0 | 0 | 15452.7 | Y | -15452.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15452.7 | 0 | 0 | 15452.7 | 0 | 0 | 0 | 0 | 0 | 0 | -15452.7 | 0 | 0 | 15452.7 | 15452.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 972 | -972 | 0 | NA | 4406 | 2171.74 | 2234.26 | 4406 | LF | 15452.7 | 143.2 | 15309.5 | 0
Y | IPCRP1-0040-1000-E | IPCRP1 | IPCRP1 | 0040-1000 | F&I Curbs - All Types & Sizes | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 4406 | 2171.74 | 2234.26 | 4406 | LF | 0 | 0 | 0 | 0 | Change PMF (Equip) from $30,000.00 to $26,226.00
Y | IPCRP1-0040-1000-L | IPCRP1 | IPCRP1 | 0040-1000 | F&I Curbs - All Types & Sizes | N | L |  | UNIT | P | 0 | 251962.6 | 251962.6 | 251962.6 | 251962.6 | 47.888 | 0 | 0 | 0 | 274187.23 | Y | 526149.83 | Y | -526149.83 | 0 | 0 | 0 | 0 | 0 | 526149.83 | Y | -526149.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -526149.83 | 1491.95 | 0 | 526149.83 | 0 | 0 | 0 | 0 | 0 | 0 | -526149.83 | 0 | 0 | 526149.83 | 526149.83 | 0 | 0 | 0 | 0 | 0 | 4406 | 4406 | 0 | 2045.5 | 2360.5 | 4406 | HR | 4406 | 2171.74 | 2234.26 | 4406 | LF | 0 | 0 | 0 | 274187.23
Y | IPCRP1-0040-1000-M | IPCRP1 | IPCRP1 | 0040-1000 | F&I Curbs - All Types & Sizes | N | M |  | UNIT | U | 0 | 217114.7 | 217114.7 | 52106.7 | 217114.7 | 23.9996 | 0 | 0 | 0 | 0 | Y | 217114.7 | Y | -217114.7 | 0 | 0 | 0 | 0 | 0 | 217114.7 | Y | -217114.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -217114.7 | 0 | 0 | 217114.7 | 0 | 0 | 0 | 0 | 0 | 0 | -217114.7 | 0 | 0 | 217114.7 | 217114.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | -2054 | 0 | NA | 4406 | 2171.74 | 2234.26 | 4406 | LF | 217114.7 | 165008 | 52106.7 | 0
Y | IPCRP1-0040-1000-S | IPCRP1 | IPCRP1 | 0040-1000 | F&I Curbs - All Types & Sizes | N | S |  | NR | A | 456227 | 16717.36 | 16717.36 | 16717.36 | 16717.36 | 100 | 0 | 0 | 0 | 0 | Y | 16717.36 | Y | 439509.64 | 0 | 0 | 456227 | 0 | 0 | 16717.36 | Y | 439509.64 | 0 | 0 | 456227 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16717.36 | 0 | 0 | 16717.36 | 0 | 0 | 0 | 0 | 0 | 0 | -16717.36 | 0 | 0 | 16717.36 | 16717.36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 131.5 | -131.5 | 0 | EA | 4406 | 2171.74 | 2234.26 | 4406 | LF | 16717.36 | 0 | 16717.36 | 0
Y | IPCRP1-0041-0000-L | IPCRP1 | IPCRP1 | 0041-0000 | 4 in CONC SIDEWALK (UNPIGMENTED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0041-0000-R | IPCRP1 | IPCRP1 | 0041-0000 | 4 in CONC SIDEWALK (UNPIGMENTED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 835646 | 0 | 0 | 835646 | 0 | 835646 | 134593.34 | 0 | N | 835646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0042-0000-L | IPCRP1 | IPCRP1 | 0042-0000 | 7 in CONC SIDEWALK (UNPIGMENTED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0042-0000-R | IPCRP1 | IPCRP1 | 0042-0000 | 7 in CONC SIDEWALK (UNPIGMENTED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 82025 | 0 | 0 | 82025 | 0 | 82025 | 21241.5 | 0 | N | 82025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0043-0000-L | IPCRP1 | IPCRP1 | 0043-0000 | 7 in REINF CONC SIDEWALK (UNPIGMENTED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0043-0000-R | IPCRP1 | IPCRP1 | 0043-0000 | 7 in REINF CONC SIDEWALK (UNPIGMENTED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 403142 | 0 | 0 | 403142 | 0 | 403142 | 7301.13 | 0 | N | 403142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0043-1000-L | IPCRP1 | IPCRP1 | 0043-1000 | Concrete Sidewalk - All Types & Depths | N | L |  | UNIT | P | 0 | 161962.16 | 161962.16 | 161962.16 | 161962.16 | 14.3444 | 0 | 0 | 0 | 967133.82 | Y | 1129095.98 | Y | -1129095.98 | 0 | 0 | 0 | 0 | 0 | 1129095.98 | Y | -1129095.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1129095.98 | 1029.02 | 0 | 1129095.98 | 0 | 0 | 0 | 0 | 0 | 0 | -1129095.98 | 0 | 0 | 1129095.98 | 1129095.98 | 0 | 0 | 0 | 0 | 0 | 9430 | 9430 | 0 | 1369 | 8061 | 9430 | HR | 85732 | 11247.58 | 74484.42 | 85732 | SF | 0 | 0 | 0 | 967133.82 | Labor: $5.00/SF, assume 1500 SF/DAY, 85,732/1500 = 57 days = 342 crew hours x 6 men = 2,736 MH, round up to 2,750 MH x $130/MH = $357,500.00
N | IPCRP1-0043-1000-M | IPCRP1 | IPCRP1 | 0043-1000 | Concrete Sidewalk - All Types & Depths | N | M |  | UNIT | U | 0 | 4027.5 | 4027.5 | 3832.5 | 4027.5 | 95.1583 | 0 | 0 | 0 | 0 | N | 4027.5 | N | -4027.5 | 0 | 0 | 0 | 0 | 0 | 4027.5 | N | -4027.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4027.5 | 3832.5 | 0 | 0 | -4027.5 | 0 | 0 | 4027.5 | 0 | 0 | -4027.5 | 0 | 0 | 4027.5 | 4027.5 | 0 | 0 | 0 | 0 | 0 | 633 | 633 | 0 | 438 | 195 | 633 | NA | 85732 | 11247.58 | 74484.42 | 85732 | SF | 4027.5 | 195 | 3832.5 | 0
Y | IPCRP1-0043-1000-S | IPCRP1 | IPCRP1 | 0043-1000 | Concrete Sidewalk - All Types & Depths | N | S |  | NR | A | 1289239 | 8430.07 | 8430.07 | 8430.07 | 8430.07 | 24.0859 | 0 | 0 | 0 | 26569.93 | Y | 35000 | Y | 1254239 | 0 | 0 | 1289239 | 0 | 0 | 35000 | Y | 1254239 | 0 | 0 | 1289239 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -35000 | 774.81 | 0 | 35000 | 0 | 0 | 0 | 0 | 774.81 | 0 | -35000 | 0 | 0 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 60 | -60 | 0 | EA | 85732 | 11247.58 | 74484.42 | 85732 | SF | 8430.07 | 0 | 8430.07 | 26569.93 | Sub + self-perform
Y | IPCRP1-0044-0000-L | IPCRP1 | IPCRP1 | 0044-0000 | EMBEDDED PREF DETECTABLE WARNING UNITS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0044-0000-R | IPCRP1 | IPCRP1 | 0044-0000 | EMBEDDED PREF DETECTABLE WARNING UNITS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13260 | 0 | 0 | 13260 | 0 | 13260 | 2400 | 0 | N | 13260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
N | IPCRP1-0044-1000-C | IPCRP1 | IPCRP1 | 0044-1000 | Embedded Prefab Detectable Warning Units | N | C |  | UNIT | U | 0 | 540.05 | 540.05 | 0 | 540.05 | 0 | 0 | 0 | 0 | 0 | N | 540.05 | N | -540.05 | 0 | 0 | 0 | 0 | 0 | 540.05 | N | -540.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -540.05 | -4431.54 | 4431.54 | 4431.54 | 3891.49 | 0 | 0 | 540.05 | 0 | 0 | -540.05 | 0 | 0 | 540.05 | 540.05 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 64 | 64 | NA | 221 | 66 | 155 | 221 | SF | 540.05 | 540.05 | 0 | 0
Y | IPCRP1-0044-1000-L | IPCRP1 | IPCRP1 | 0044-1000 | Embedded Prefab Detectable Warning Units | N | L |  | UNIT | P | 0 | 1161.1 | 1161.1 | 1161.1 | 1161.1 | 17.8631 | 0 | 0 | 0 | 5338.9 | Y | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 6500 | Y | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6500 | 1161.1 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 8 | 42 | 50 | HR | 221 | 66 | 155 | 221 | SF | 0 | 0 | 0 | 5338.9
N | IPCRP1-0044-1000-M | IPCRP1 | IPCRP1 | 0044-1000 | Embedded Prefab Detectable Warning Units | N | M |  | UNIT | U | 0 | 4431.54 | 4431.54 | 4431.54 | 4431.54 | 69.2428 | 0 | 0 | 0 | 1968.46 | Y | 6400 | Y | -6400 | 0 | 0 | 0 | 0 | 0 | 6400 | Y | -6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6400 | 4431.54 | 0 | 6400 | 0 | 0 | 0 | 4088.16 | 0 | 0 | -6400 | 0 | 0 | 6400 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 221 | 66 | 155 | 221 | SF | 4088.16 | -343.38 | 4431.54 | 1968.46
Y | IPCRP1-0044-1000-S | IPCRP1 | IPCRP1 | 0044-1000 | Embedded Prefab Detectable Warning Units | N | S |  | NR | A | 12974.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 12974.91 | 0 | 0 | 12974.91 | 0 | 0 | 0 | Y | 12974.91 | 0 | 0 | 12974.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 221 | 66 | 155 | 221 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0045-0000-L | IPCRP1 | IPCRP1 | 0045-0000 | EPOXY COATED REBAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0045-0000-R | IPCRP1 | IPCRP1 | 0045-0000 | EPOXY COATED REBAR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 400 | 0 | 0 | 400 | 0 | 400 | 4577.6 | 0 | N | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0046-0000-L | IPCRP1 | IPCRP1 | 0046-0000 | TOPSOIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0046-0000-R | IPCRP1 | IPCRP1 | 0046-0000 | TOPSOIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18500 | 0 | 0 | 18500 | 0 | 18500 | 0 | 0 | N | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0047-0000-L | IPCRP1 | IPCRP1 | 0047-0000 | SODDING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0047-0000-R | IPCRP1 | IPCRP1 | 0047-0000 | SODDING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4375 | 0 | 0 | 4375 | 0 | 4375 | 0 | 0 | N | 4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0047-1000-L | IPCRP1 | IPCRP1 | 0047-1000 | SODDING (Do not use) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 175 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0048-0000-L | IPCRP1 | IPCRP1 | 0048-0000 | 3ft-0W X 5ft-6in H SNGL BARRL FLT TOP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0048-0000-R | IPCRP1 | IPCRP1 | 0048-0000 | 3ft-0W X 5ft-6in H SNGL BARRL FLT TOP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1060000 | 0 | 0 | 1060000 | 0 | 1060000 | 672300 | 0 | N | 1060000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0048-1000-E | IPCRP1 | IPCRP1 | 0048-1000 | Install 3ft x 5ft - 6in Combined Sewer | N | E |  | NR | P | 24490.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 24490.95 | 0 | 0 | 24490.95 | 0 | 0 | 0 | Y | 24490.95 | 0 | 0 | 24490.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 212 | 134.46 | 0 | 134.46 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0048-1000-L | IPCRP1 | IPCRP1 | 0048-1000 | Install 3ft x 5ft - 6in Combined Sewer | N | L |  | NR | P | 84873.96 | 160553.04 | 160553.04 | 160553.04 | 160553.04 | 100 | 0 | 0 | 0 | 0.01 | Y | 160553.05 | Y | -75679.09 | 0 | 0 | 84873.96 | 0 | 0 | 160553.05 | Y | -75679.09 | 0 | 0 | 84873.96 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -160553.05 | 0 | 0 | 160553.05 | 0 | 0 | 0 | 0 | 0 | 0 | -160553.05 | 0 | 0 | 160553.05 | 160553.05 | 0 | 0 | 0 | 688 | 0 | 1265.5 | 1265.5 | 688 | 1265.5 | 0 | 1265.5 | HR | 212 | 134.46 | 0 | 134.46 | LF | 0 | 0 | 0 | 0.01 | Many MH do not belong here. Were charged here, but were for handling spoils - now coded to 0498-1010, Screening & Loading of Contam & Non-Contam Soils. TBD if we review & move.
Y | IPCRP1-0048-1000-S | IPCRP1 | IPCRP1 | 0048-1000 | Install 3ft x 5ft - 6in Combined Sewer | N | S |  | UNIT | A | 0 | 3582.84 | 3582.84 | 3582.84 | 3582.84 | 100 | 0 | 0 | 0 | 0 | N | 3582.84 | N | -3582.84 | 0 | 0 | 0 | 0 | 0 | 3582.84 | N | -3582.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3582.84 | 0 | 0 | 3582.84 | 0 | 0 | 0 | 0 | 0 | 0 | -3582.84 | 0 | 0 | 3582.84 | 3582.84 | 0 | 0 | 0 | 0 | 0 | 28.5 | 28.5 | 0 | 28.5 | 0 | 28.5 | NA | 212 | 134.46 | 0 | 134.46 | LF | 3582.84 | 0 | 3582.84 | 0
Y | IPCRP1-0048-1010-E | IPCRP1 | IPCRP1 | 0048-1010 | CIP Bends for 3 ft x 5 ft - 6 in Comb Sewer | N | E |  | NR | P | 1548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1548 | 0 | 0 | 1548 | 0 | 0 | 0 | Y | 1548 | 0 | 0 | 1548 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 41 | 24.35 | 0 | 24.35 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0048-1010-L | IPCRP1 | IPCRP1 | 0048-1010 | CIP Bends for 3 ft x 5 ft - 6 in Comb Sewer | N | L |  | NR | P | 19381.08 | 11820.79 | 11820.79 | 11820.79 | 11820.79 | 100 | 0 | 0 | 0 | 0 | Y | 11820.79 | Y | 7560.29 | 0 | 0 | 19381.08 | 0 | 0 | 11820.79 | Y | 7560.29 | 0 | 0 | 19381.08 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11820.79 | 0 | 0 | 11820.79 | 0 | 0 | 0 | 0 | 0 | 0 | -11820.79 | 0 | 0 | 11820.79 | 11820.79 | 0 | 0 | 0 | 160 | 0 | 83.5 | 83.5 | 160 | 83.5 | 0 | 83.5 | HR | 41 | 24.35 | 0 | 24.35 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0049-0000-L | IPCRP1 | IPCRP1 | 0049-0000 | 4ft-0W X 4ft-0H SNGL BARRL FLT TOP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0049-0000-R | IPCRP1 | IPCRP1 | 0049-0000 | 4ft-0W X 4ft-0H SNGL BARRL FLT TOP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 748800 | 0 | 0 | 748800 | 0 | 748800 | 938232.5 | 0 | N | 748800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0049-1000-E | IPCRP1 | IPCRP1 | 0049-1000 | Install 4ft x 4ft Combined Sewer | N | E |  | NR | P | 24384.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 24384.44 | 0 | 0 | 24384.44 | 0 | 0 | 0 | N | 24384.44 | 0 | 0 | 24384.44 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 144 | 180.5 | 0 | 180.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0049-1000-L | IPCRP1 | IPCRP1 | 0049-1000 | Install 4ft x 4ft Combined Sewer | N | L |  | NR | P | 79157.12 | 73559.12 | 73559.12 | 73559.12 | 73559.12 | 100 | 0 | 0 | 0 | 0 | Y | 73559.12 | Y | 5598 | 0 | 0 | 79157.12 | 0 | 0 | 73559.12 | Y | 5598 | 0 | 0 | 79157.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -73559.12 | 0 | 0 | 73559.12 | 0 | 0 | 0 | 0 | 0 | 0 | -73559.12 | 0 | 0 | 73559.12 | 73559.12 | 0 | 0 | 0 | 642.24 | 0 | 568 | 568 | 642.24 | 568 | 0 | 568 | HR | 144 | 180.5 | 0 | 180.5 | LF | 0 | 0 | 0 | 0 | Bobby & PMCM team agreed to resolved utility interference/relocation on E10th St by building a 2.5' x 6' box sewer x 30.50' Lg and getting paid under this item. See Zach D email dated 11/25/24
Y | IPCRP1-0049-1010-E | IPCRP1 | IPCRP1 | 0049-1010 | CIP Bends for 4ft x 4ft Combined Sewer | N | E |  | NR | P | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 258 | 0 | 0 | 258 | 0 | 0 | 0 | N | 258 | 0 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 6 | 49.85 | 0 | 49.85 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0049-1010-L | IPCRP1 | IPCRP1 | 0049-1010 | CIP Bends for 4ft x 4ft Combined Sewer | N | L |  | NR | P | 3406.64 | 57453.78 | 57453.78 | 57453.78 | 57453.78 | 100 | 0 | 0 | 0 | 0 | Y | 57453.78 | Y | -54047.14 | 0 | 0 | 3406.64 | 0 | 0 | 57453.78 | Y | -54047.14 | 0 | 0 | 3406.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -57453.78 | 0 | 0 | 57453.78 | 0 | 0 | 0 | 0 | 0 | 0 | -57453.78 | 0 | 0 | 57453.78 | 57453.78 | 0 | 0 | 0 | 28 | 0 | 441.5 | 441.5 | 28 | 441.5 | 0 | 441.5 | HR | 6 | 49.85 | 0 | 49.85 | LF | 0 | 0 | 0 | 0 | Bobby & PMCM team agreed to resolved utility interference/relocation on E10th St by building a 2.5' x 6' box sewer x 30.50' Lg and getting paid under this item. See Zach D email dated 11/25/24
Y | IPCRP1-0050-0000-L | IPCRP1 | IPCRP1 | 0050-0000 | 5ft-0W X 4ft-0H SNGL BARRL FLT TOP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0050-0000-R | IPCRP1 | IPCRP1 | 0050-0000 | 5ft-0W X 4ft-0H SNGL BARRL FLT TOP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2465100 | 0 | 0 | 2465100 | 0 | 2465100 | 2388076 | 0 | N | 2465100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2465100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0050-1000-E | IPCRP1 | IPCRP1 | 0050-1000 | Install 5ft x 4ft Comb Sewer | N | E |  | NR | P | 110733.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 110733.72 | 0 | 0 | 110733.72 | 0 | 0 | 0 | N | 110733.72 | 0 | 0 | 110733.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 297 | 287.72 | 0 | 287.72 | LF | 0 | 0 | 0 | 0 | Change PMF (Quantity) from 287.84 to 287.72 (matching DDC PTD quantity)
Y | IPCRP1-0050-1000-L | IPCRP1 | IPCRP1 | 0050-1000 | Install 5ft x 4ft Comb Sewer | N | L |  | NR | P | 355196.28 | 210691.73 | 210691.73 | 210691.73 | 210691.73 | 100 | 0 | 0 | 0 | 0 | Y | 210691.73 | Y | 144504.55 | 0 | 0 | 355196.28 | 0 | 0 | 210691.73 | Y | 144504.55 | 0 | 0 | 355196.28 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -210691.73 | 0 | 0 | 210691.73 | 0 | 0 | 0 | 0 | 0 | 0 | -210691.73 | 0 | 0 | 210691.73 | 210691.73 | 0 | 0 | 0 | 2752 | 0 | 1567.5 | 1567.5 | 2752 | 1567.5 | 0 | 1567.5 | HR | 297 | 287.72 | 0 | 287.72 | LF | 0 | 0 | 0 | 0 | Change PMF (MH) from 1,495.68 to 3,116.00, Change PMF (Labor) from $166,125.16 to $373,920.00
Y | IPCRP1-0050-1000-S | IPCRP1 | IPCRP1 | 0050-1000 | Install 5ft x 4ft Comb Sewer | N | S |  | UNIT | A | 0 | 1300.38 | 1300.38 | 1300.38 | 1300.38 | 100 | 0 | 0 | 0 | 0 | Y | 1300.38 | Y | -1300.38 | 0 | 0 | 0 | 0 | 0 | 1300.38 | Y | -1300.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1300.38 | 0 | 0 | 1300.38 | 0 | 0 | 0 | 0 | 0 | 0 | -1300.38 | 0 | 0 | 1300.38 | 1300.38 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 11.5 | -8.5 | 3 | NA | 297 | 287.72 | 0 | 287.72 | LF | 1300.38 | 0 | 1300.38 | 0
Y | IPCRP1-0050-1010-E | IPCRP1 | IPCRP1 | 0050-1010 | CIP Bends for 5ft x 4ft Combined Sewer | N | E |  | NR | P | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 516 | 0 | 0 | 516 | 0 | 0 | 0 | N | 516 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 10 | 29 | 0 | 29 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0050-1010-L | IPCRP1 | IPCRP1 | 0050-1010 | CIP Bends for 5ft x 4ft Combined Sewer | N | L |  | NR | P | 6813.27 | 22617.82 | 22617.82 | 22617.82 | 22617.82 | 100 | 0 | 0 | 0 | 0 | Y | 22617.82 | Y | -15804.55 | 0 | 0 | 6813.27 | 0 | 0 | 22617.82 | Y | -15804.55 | 0 | 0 | 6813.27 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22617.82 | 0 | 0 | 22617.82 | 0 | 0 | 0 | 0 | 0 | 0 | -22617.82 | 0 | 0 | 22617.82 | 22617.82 | 0 | 0 | 0 | 0 | 0 | 174 | 174 | 0 | 174 | 0 | 174 | HR | 10 | 29 | 0 | 29 | LF | 0 | 0 | 0 | 0 | Change PMF (Quantity) from 33.00 to 29.00 (matching CTD), Change PMF (Labor) from $25,890.00 to $22,617.82 (matching CTD)
Y | IPCRP1-0051-0000-L | IPCRP1 | IPCRP1 | 0051-0000 | 7ft-6inW X 6in-0H SNGL BARRL FLT TOP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0051-0000-R | IPCRP1 | IPCRP1 | 0051-0000 | 7ft-6inW X 6in-0H SNGL BARRL FLT TOP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3300000 | 0 | 0 | 3300000 | 0 | 3300000 | 2797200 | 0 | N | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0051-1000-C | IPCRP1 | IPCRP1 | 0051-1000 | Install 7ft 6in x 6ft Combined Sewer | N | C |  | UNIT | U | 0 | 6607.1 | 6607.1 | 6607.1 | 6607.1 | 100 | 0 | 0 | 0 | 0 | N | 6607.1 | N | -6607.1 | 0 | 0 | 0 | 0 | 0 | 6607.1 | N | -6607.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6607.1 | 0 | 0 | 6607.1 | 0 | 0 | 0 | 0 | 0 | 0 | -6607.1 | 0 | 0 | 6607.1 | 6607.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 330 | 279.72 | 66.08 | 345.8 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0051-1000-E | IPCRP1 | IPCRP1 | 0051-1000 | Install 7ft 6in x 6ft Combined Sewer | N | E |  | NR | P | 65825.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 65825.79 | 0 | 0 | 65825.79 | 0 | 0 | 0 | Y | 65825.79 | 0 | 0 | 65825.79 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2685.71 | 2685.71 | LF | 330 | 279.72 | 66.08 | 345.8 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0051-1000-L | IPCRP1 | IPCRP1 | 0051-1000 | Install 7ft 6in x 6ft Combined Sewer | N | L |  | NR | P | 226114.28 | 315410.03 | 315410.03 | 315410.03 | 315410.03 | 85.0932 | 0 | 0 | 0 | 55253.97 | Y | 370664 | Y | -144549.72 | 0 | 0 | 226114.28 | 0 | 0 | 370664 | Y | -144549.72 | 0 | 0 | 226114.28 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -370664 | 0 | 1418.76 | 370664 | 0 | 0 | 0 | 0 | 0 | 0 | -370664 | 0 | 0 | 370664 | 370664 | 0 | 0 | 0 | 1832 | 0 | 2766 | 2766 | 1832 | 2365.5 | 400.5 | 2766 | HR | 330 | 279.72 | 66.08 | 345.8 | LF | 0 | 0 | 0 | 55253.97
Y | IPCRP1-0051-1000-S | IPCRP1 | IPCRP1 | 0051-1000 | Install 7ft 6in x 6ft Combined Sewer | N | S |  | UNIT | A | 0 | 16880.3 | 16880.3 | 16880.3 | 16880.3 | 100 | 0 | 0 | 0 | 0 | Y | 16880.3 | Y | -16880.3 | 0 | 0 | 0 | 0 | 0 | 16880.3 | Y | -16880.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16880.3 | 0 | 0 | 16880.3 | 0 | 0 | 0 | 0 | 0 | 0 | -16880.3 | 0 | 0 | 16880.3 | 16880.3 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 137.5 | -129.5 | 8 | NA | 330 | 279.72 | 66.08 | 345.8 | LF | 16880.3 | 0 | 16880.3 | 0 | KMA CO
Y | IPCRP1-0051-1010-E | IPCRP1 | IPCRP1 | 0051-1010 | CIP Bends for 7 ft 6 in x 6ft Combined Sewer | N | E |  | NR | P | 2838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2838 | 0 | 0 | 2838 | 0 | 0 | 0 | Y | 2838 | 0 | 0 | 2838 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 30 | 30.81 | 39 | 69.81 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0051-1010-L | IPCRP1 | IPCRP1 | 0051-1010 | CIP Bends for 7 ft 6 in x 6ft Combined Sewer | N | L |  | NR | P | 38002.34 | 72582.39 | 72582.39 | 72582.39 | 72582.39 | 63.4339 | 0 | 0 | 0 | 41839.73 | Y | 114422.12 | Y | -76419.78 | 0 | 0 | 38002.34 | 0 | 0 | 114422.12 | Y | -76419.78 | 0 | 0 | 38002.34 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -114422.12 | 0 | 0 | 114422.12 | 0 | 0 | 0 | 0 | 0 | 0 | -114422.12 | 0 | 0 | 114422.12 | 114422.12 | 0 | 0 | 0 | 312 | 0 | 850 | 850 | 312 | 555.5 | 294.5 | 850 | HR | 30 | 30.81 | 39 | 69.81 | LF | 0 | 0 | 0 | 41839.73 | As per NM (8/21) PMF (Quan) = 157.80' + est 188' (147' PC + 41 CIP) = 345.8 LF
Y | IPCRP1-0051-1010-S | IPCRP1 | IPCRP1 | 0051-1010 | CIP Bends for 7 ft 6 in x 6ft Combined Sewer | N | S |  | UNIT | A | 0 | 563.44 | 563.44 | 563.44 | 563.44 | 100 | 0 | 0 | 0 | 0 | N | 563.44 | N | -563.44 | 0 | 0 | 0 | 0 | 0 | 563.44 | N | -563.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -563.44 | 0 | 0 | 563.44 | 0 | 0 | 0 | 0 | 0 | 0 | -563.44 | 0 | 0 | 563.44 | 563.44 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 0 | 4.5 | 0 | 4.5 | NA | 30 | 30.81 | 39 | 69.81 | LF | 563.44 | 0 | 563.44 | 0
Y | IPCRP1-0052-0000-L | IPCRP1 | IPCRP1 | 0052-0000 | 8 ft-0W X 4ft-0H SNGL BARRL FLT TP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0052-0000-R | IPCRP1 | IPCRP1 | 0052-0000 | 8 ft-0W X 4ft-0H SNGL BARRL FLT TP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1836800 | 0 | 0 | 1836800 | 0 | 1836800 | 2179232 | 0 | N | 1836800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0052-1000-E | IPCRP1 | IPCRP1 | 0052-1000 | Install 8ft x 4ft Combined Sewer | N | E |  | NR | P | 50318.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 50318.43 | 0 | 0 | 50318.43 | 0 | 0 | 0 | N | 50318.43 | 0 | 0 | 50318.43 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 224 | 265.76 | 0 | 265.76 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0052-1000-L | IPCRP1 | IPCRP1 | 0052-1000 | Install 8ft x 4ft Combined Sewer | N | L |  | NR | P | 182583.45 | 206152.84 | 206152.84 | 206152.84 | 206152.84 | 100 | 0 | 0 | 0 | 0 | Y | 206152.84 | Y | -23569.39 | 0 | 0 | 182583.45 | 0 | 0 | 206152.84 | Y | -23569.39 | 0 | 0 | 182583.45 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -206152.84 | 0 | 0 | 206152.84 | 0 | 0 | 0 | 0 | 0 | 0 | -206152.84 | 0 | 0 | 206152.84 | 206152.84 | 0 | 0 | 0 | 1480 | 0 | 1552.5 | 1552.5 | 1480 | 1552.5 | 0 | 1552.5 | HR | 224 | 265.76 | 0 | 265.76 | LF | 0 | 0 | 0 | 0 | Change PMF (MH) from 1,600.16 to 1,552.50 (matching CTD), Change PMF (Labor) from $212,493.20 to $206,154.19 (matching CTD)
Y | IPCRP1-0052-1000-S | IPCRP1 | IPCRP1 | 0052-1000 | Install 8ft x 4ft Combined Sewer | N | S |  | UNIT | A | 0 | 787.3 | 787.3 | 787.3 | 787.3 | 100 | 0 | 0 | 0 | 0 | Y | 787.3 | Y | -787.3 | 0 | 0 | 0 | 0 | 0 | 787.3 | Y | -787.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -787.3 | 0 | 0 | 787.3 | 0 | 0 | 0 | 0 | 0 | 0 | -787.3 | 0 | 0 | 787.3 | 787.3 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 7 | -3 | 4 | NA | 224 | 265.76 | 0 | 265.76 | LF | 787.3 | 0 | 787.3 | 0
Y | IPCRP1-0052-1010-E | IPCRP1 | IPCRP1 | 0052-1010 | CIP Bends for 8ft x 4ft Combined Sewer | N | E |  | NR | P | 1548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1548 | 0 | 0 | 1548 | 0 | 0 | 0 | Y | 1548 | 0 | 0 | 1548 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 15 | 33.91 | 0 | 33.91 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0052-1010-L | IPCRP1 | IPCRP1 | 0052-1010 | CIP Bends for 8ft x 4ft Combined Sewer | N | L |  | NR | P | 20969.16 | 40220.74 | 40220.74 | 40220.74 | 40220.74 | 100 | 0 | 0 | 0 | 0 | Y | 40220.74 | Y | -19251.58 | 0 | 0 | 20969.16 | 0 | 0 | 40220.74 | Y | -19251.58 | 0 | 0 | 20969.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -40220.74 | 0 | 0 | 40220.74 | 0 | 0 | 0 | 0 | 0 | 0 | -40220.74 | 0 | 0 | 40220.74 | 40220.74 | 0 | 0 | 0 | 172 | 0 | 311.5 | 311.5 | 172 | 311.5 | 0 | 311.5 | HR | 15 | 33.91 | 0 | 33.91 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0053-0000-L | IPCRP1 | IPCRP1 | 0053-0000 | 8ft-0W X 4ft-6in H SNGL BARRL FLT TOP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0053-0000-R | IPCRP1 | IPCRP1 | 0053-0000 | 8ft-0W X 4ft-6in H SNGL BARRL FLT TOP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1675800 | 0 | 0 | 1675800 | 0 | 1675800 | 1632575 | 0 | N | 1675800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0053-1000-E | IPCRP1 | IPCRP1 | 0053-1000 | Install 8 ft x 4ft 6in Combined Sewer | N | E |  | NR | P | 36402.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 36402.74 | 0 | 0 | 36402.74 | 0 | 0 | 0 | N | 36402.74 | 0 | 0 | 36402.74 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 126 | 122.75 | 0 | 122.75 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0053-1000-L | IPCRP1 | IPCRP1 | 0053-1000 | Install 8 ft x 4ft 6in Combined Sewer | N | L |  | NR | P | 118035.85 | 113875.13 | 113875.13 | 113875.13 | 113875.13 | 100 | 0 | 0 | 0 | 0 | Y | 113875.13 | Y | 4160.72 | 0 | 0 | 118035.85 | 0 | 0 | 113875.13 | Y | 4160.72 | 0 | 0 | 118035.85 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -113875.13 | 0 | 0 | 113875.13 | 0 | 0 | 0 | 0 | 0 | 0 | -113875.13 | 0 | 0 | 113875.13 | 113875.13 | 0 | 0 | 0 | 956 | 0 | 909.5 | 909.5 | 956 | 909.5 | 0 | 909.5 | HR | 126 | 122.75 | 0 | 122.75 | LF | 0 | 0 | 0 | 0 | Change PMF (MH) from 953.22 to 909.50 (matching CTD), Change PMF (Labor) from $119,875.13 to $113,875.13 (matching CTD)
Y | IPCRP1-0053-1000-S | IPCRP1 | IPCRP1 | 0053-1000 | Install 8 ft x 4ft 6in Combined Sewer | N | S |  | UNIT | A | 0 | 3262.92 | 3262.92 | 3262.92 | 3262.92 | 100 | 0 | 0 | 0 | 0 | Y | 3262.92 | Y | -3262.92 | 0 | 0 | 0 | 0 | 0 | 3262.92 | Y | -3262.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3262.92 | 0 | 0 | 3262.92 | 0 | 0 | 0 | 0 | 0 | 0 | -3262.92 | 0 | 0 | 3262.92 | 3262.92 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 24.5 | -22.5 | 2 | NA | 126 | 122.75 | 0 | 122.75 | LF | 3262.92 | 0 | 3262.92 | 0
Y | IPCRP1-0053-1010-E | IPCRP1 | IPCRP1 | 0053-1010 | CIP Bends for 8 ft x 4 ft 6 in Combined Sewer | N | E |  | NR | P | 1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1806 | 0 | 0 | 1806 | 0 | 0 | 0 | N | 1806 | 0 | 0 | 1806 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 16 | 17.05 | 0 | 17.05 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0053-1010-L | IPCRP1 | IPCRP1 | 0053-1010 | CIP Bends for 8 ft x 4 ft 6 in Combined Sewer | N | L |  | NR | P | 24375.79 | 25894.38 | 25894.38 | 25894.38 | 25894.38 | 100 | 0 | 0 | 0 | 0 | Y | 25894.38 | Y | -1518.59 | 0 | 0 | 24375.79 | 0 | 0 | 25894.38 | Y | -1518.59 | 0 | 0 | 24375.79 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25894.38 | 0 | 0 | 25894.38 | 0 | 0 | 0 | 0 | 0 | 0 | -25894.38 | 0 | 0 | 25894.38 | 25894.38 | 0 | 0 | 0 | 200 | 0 | 204 | 204 | 200 | 204 | 0 | 204 | HR | 16 | 17.05 | 0 | 17.05 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0054-0000-L | IPCRP1 | IPCRP1 | 0054-0000 | 8ft-0W X 5ft H SNGL BARRL FLT TOP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0054-0000-R | IPCRP1 | IPCRP1 | 0054-0000 | 8ft-0W X 5ft H SNGL BARRL FLT TOP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1990000 | 0 | 0 | 1990000 | 0 | 1990000 | 2030000 | 0 | N | 1990000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1990000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0054-1000-E | IPCRP1 | IPCRP1 | 0054-1000 | Install 8ft x 5ft Combined Sewer | N | E |  | NR | P | 52905.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 52905.27 | 0 | 0 | 52905.27 | 0 | 0 | 0 | Y | 52905.27 | 0 | 0 | 52905.27 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 199 | 203 | 0 | 203 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0054-1000-L | IPCRP1 | IPCRP1 | 0054-1000 | Install 8ft x 5ft Combined Sewer | N | L |  | NR | P | 173786.19 | 238806.53 | 238806.53 | 238806.53 | 238806.53 | 100 | 0 | 0 | 0 | 0 | Y | 238806.53 | Y | -65020.34 | 0 | 0 | 173786.19 | 0 | 0 | 238806.53 | Y | -65020.34 | 0 | 0 | 173786.19 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -238806.53 | 0 | 0 | 238806.53 | 0 | 0 | 0 | 0 | 0 | 0 | -238806.53 | 0 | 0 | 238806.53 | 238806.53 | 0 | 0 | 0 | 1408 | 0 | 1834 | 1834 | 1408 | 1834 | 0 | 1834 | HR | 199 | 203 | 0 | 203 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0054-1000-S | IPCRP1 | IPCRP1 | 0054-1000 | Install 8ft x 5ft Combined Sewer | N | S |  | UNIT | A | 0 | 6211.25 | 6211.25 | 6211.25 | 6211.25 | 100 | 0 | 0 | 0 | 0 | Y | 6211.25 | Y | -6211.25 | 0 | 0 | 0 | 0 | 0 | 6211.25 | Y | -6211.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6211.25 | 0 | 0 | 6211.25 | 0 | 0 | 0 | 0 | 0 | 0 | -6211.25 | 0 | 0 | 6211.25 | 6211.25 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 54 | -10 | 44 | NA | 199 | 203 | 0 | 203 | LF | 6211.25 | 0 | 6211.25 | 0
Y | IPCRP1-0054-1010-E | IPCRP1 | IPCRP1 | 0054-1010 | CIP Bends for 8ft x 5ft Combined Sewer | N | E |  | NR | P | 3612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 3612 | 0 | 0 | 3612 | 0 | 0 | 0 | N | 3612 | 0 | 0 | 3612 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 30 | 44.58 | 0 | 44.58 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0054-1010-L | IPCRP1 | IPCRP1 | 0054-1010 | CIP Bends for 8ft x 5ft Combined Sewer | N | L |  | NR | P | 48751.59 | 62223.03 | 62223.03 | 62223.03 | 62223.03 | 100 | 0 | 0 | 0 | 0 | Y | 62223.03 | Y | -13471.44 | 0 | 0 | 48751.59 | 0 | 0 | 62223.03 | Y | -13471.44 | 0 | 0 | 48751.59 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -62223.03 | 0 | 0 | 62223.03 | 0 | 0 | 0 | 0 | 0 | 0 | -62223.03 | 0 | 0 | 62223.03 | 62223.03 | 0 | 0 | 0 | 400 | 0 | 477.5 | 477.5 | 400 | 477.5 | 0 | 477.5 | HR | 30 | 44.58 | 0 | 44.58 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0055-0000-L | IPCRP1 | IPCRP1 | 0055-0000 | 9ft-0W X 4ft-6in H SNGL BARREL FLT TOP RC COMB SE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0055-0000-R | IPCRP1 | IPCRP1 | 0055-0000 | 9ft-0W X 4ft-6in H SNGL BARREL FLT TOP RC COMB SE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 688000 | 0 | 0 | 688000 | 0 | 688000 | 737680 | 0 | N | 688000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0055-1000-E | IPCRP1 | IPCRP1 | 0055-1000 | Install 9 ft x 4 ft 6 in Combined Sewer | N | E |  | NR | P | 22714.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 22714.22 | 0 | 0 | 22714.22 | 0 | 0 | 0 | N | 22714.22 | 0 | 0 | 22714.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 86 | 92.21 | 0 | 92.21 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0055-1000-L | IPCRP1 | IPCRP1 | 0055-1000 | Install 9 ft x 4 ft 6 in Combined Sewer | N | L |  | NR | P | 81451.73 | 130431.99 | 130431.99 | 130431.99 | 130431.99 | 100 | 0 | 0 | 0 | 0 | Y | 130431.99 | Y | -48980.26 | 0 | 0 | 81451.73 | 0 | 0 | 130431.99 | Y | -48980.26 | 0 | 0 | 81451.73 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130431.99 | 0 | 0 | 130431.99 | 0 | 0 | 0 | 0 | 0 | 0 | -130431.99 | 0 | 0 | 130431.99 | 130431.99 | 0 | 0 | 0 | 660 | 0 | 1063 | 1063 | 660 | 1063 | 0 | 1063 | HR | 86 | 92.21 | 0 | 92.21 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0055-1000-S | IPCRP1 | IPCRP1 | 0055-1000 | Install 9 ft x 4 ft 6 in Combined Sewer | N | S |  | UNIT | A | 0 | 3173.75 | 3173.75 | 3173.75 | 3173.75 | 100 | 0 | 0 | 0 | 0 | N | 3173.75 | N | -3173.75 | 0 | 0 | 0 | 0 | 0 | 3173.75 | N | -3173.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3173.75 | 0 | 0 | 3173.75 | 0 | 0 | 0 | 0 | 0 | 0 | -3173.75 | 0 | 0 | 3173.75 | 3173.75 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 0 | 31 | 0 | 31 | NA | 86 | 92.21 | 0 | 92.21 | LF | 3173.75 | 0 | 3173.75 | 0
Y | IPCRP1-0055-1010-L | IPCRP1 | IPCRP1 | 0055-1010 | CIP Bends for 9 ft by 4.5 ft comb sewer | N | L |  | UNIT | P | 0 | 3806.22 | 3806.22 | 3806.22 | 3806.22 | 100 | 0 | 0 | 0 | 0 | Y | 3806.22 | Y | -3806.22 | 0 | 0 | 0 | 0 | 0 | 3806.22 | Y | -3806.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3806.22 | 0 | 0 | 3806.22 | 0 | 0 | 0 | 0 | 0 | 0 | -3806.22 | 0 | 0 | 3806.22 | 3806.22 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 0 | 33 | 0 | 33 | HR | 0 | 11.25 | 0 | 11.25 | LF | 0 | 0 | 0 | 0 | Change PMF (MH) from 72.00 to 33.00 (matching CTD), Change PMF (Labor) from $9,359.77 to $3,806.22 (matching CTD)
Y | IPCRP1-0056-0000-L | IPCRP1 | IPCRP1 | 0056-0000 | 10ft-6iW X 5ft-0H SINGLE BARREL FLAT TOP RC COMB S | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0056-0000-R | IPCRP1 | IPCRP1 | 0056-0000 | 10ft-6iW X 5ft-0H SINGLE BARREL FLAT TOP RC COMB S | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1829000 | 0 | 0 | 1829000 | 0 | 1829000 | 1386146 | 0 | N | 1829000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1829000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0056-1000-E | IPCRP1 | IPCRP1 | 0056-1000 | Install 10 ft 6 in x 5 ft Combined Sewer | N | E |  | NR | P | 37692.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 37692.94 | 0 | 0 | 37692.94 | 0 | 0 | 0 | Y | 37692.94 | 0 | 0 | 37692.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 155 | 117.47 | 37.53 | 155 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0056-1000-L | IPCRP1 | IPCRP1 | 0056-1000 | Install 10 ft 6 in x 5 ft Combined Sewer | N | L |  | NR | P | 137715.81 | 156487.44 | 156487.44 | 156487.44 | 156487.44 | 86.9375 | 0 | 0 | 0 | 23512.56 | Y | 180000 | Y | -42284.19 | 0 | 0 | 137715.81 | 0 | 0 | 180000 | Y | -42284.19 | 0 | 0 | 137715.81 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -180000 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | -180000 | 0 | 0 | 180000 | 180000 | 0 | 0 | 0 | 1116 | 0 | 1352.09 | 1352.09 | 1116 | 1169.5 | 182.59 | 1352.09 | HR | 155 | 117.47 | 37.53 | 155 | LF | 0 | 0 | 0 | 23512.56
Y | IPCRP1-0056-1000-S | IPCRP1 | IPCRP1 | 0056-1000 | Install 10 ft 6 in x 5 ft Combined Sewer | N | S |  | UNIT | A | 0 | 8627.68 | 8627.68 | 8627.68 | 8627.68 | 100 | 0 | 0 | 0 | 0 | Y | 8627.68 | Y | -8627.68 | 0 | 0 | 0 | 0 | 0 | 8627.68 | Y | -8627.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8627.68 | 0 | 0 | 8627.68 | 0 | 0 | 0 | 0 | 0 | 0 | -8627.68 | 0 | 0 | 8627.68 | 8627.68 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 67.5 | -65.5 | 2 | NA | 155 | 117.47 | 37.53 | 155 | LF | 8627.68 | 0 | 8627.68 | 0
Y | IPCRP1-0056-1010-E | IPCRP1 | IPCRP1 | 0056-1010 | CIP Bends for 10 ft 6in x 5ft Combined Sewer | N | E |  | NR | P | 4644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 4644 | 0 | 0 | 4644 | 0 | 0 | 0 | N | 4644 | 0 | 0 | 4644 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 22 | 21.8 | 17.6 | 39.4 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0056-1010-L | IPCRP1 | IPCRP1 | 0056-1010 | CIP Bends for 10 ft 6in x 5ft Combined Sewer | N | L |  | NR | P | 60260.7 | 35499.71 | 35499.71 | 35499.71 | 35499.71 | 58.9102 | 0 | 0 | 0 | 24760.99 | Y | 60260.7 | Y | 0 | 0 | 0 | 60260.7 | 0 | 0 | 60260.7 | Y | 0 | 0 | 0 | 60260.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60260.7 | 0 | 0 | 60260.7 | 0 | 0 | 0 | 0 | 0 | 0 | -60260.7 | 0 | 0 | 60260.7 | 60260.7 | 0 | 0 | 0 | 0 | 0 | 496.01 | 496.01 | 0 | 264.5 | 231.51 | 496.01 | HR | 22 | 21.8 | 17.6 | 39.4 | LF | 0 | 0 | 0 | 24760.99
Y | IPCRP1-0056-1010-S | IPCRP1 | IPCRP1 | 0056-1010 | CIP Bends for 10 ft 6in x 5ft Combined Sewer | N | S |  | UNIT | A | 0 | 765.79 | 765.79 | 765.79 | 765.79 | 100 | 0 | 0 | 0 | 0 | N | 765.79 | N | -765.79 | 0 | 0 | 0 | 0 | 0 | 765.79 | N | -765.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -765.79 | 0 | 0 | 765.79 | 0 | 0 | 0 | 0 | 0 | 0 | -765.79 | 0 | 0 | 765.79 | 765.79 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 22 | 21.8 | 17.6 | 39.4 | LF | 765.79 | 0 | 765.79 | 0
Y | IPCRP1-0057-0000-L | IPCRP1 | IPCRP1 | 0057-0000 | 11ft-0W X 5 ft-0H SNGL BARRL FLT TOP RC COMB S | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0057-0000-R | IPCRP1 | IPCRP1 | 0057-0000 | 11ft-0W X 5 ft-0H SNGL BARRL FLT TOP RC COMB S | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3227100 | 0 | 0 | 3227100 | 0 | 3227100 | 3092250 | 0 | N | 3227100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3227100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0057-1000-C | IPCRP1 | IPCRP1 | 0057-1000 | Install 11ft x 5ft Combined Sewer | N | C |  | UNIT | U | 0 | 16869.94 | 16869.94 | 16869.94 | 16869.94 | 100 | 0 | 0 | 0 | 0 | N | 16869.94 | N | -16869.94 | 0 | 0 | 0 | 0 | 0 | 16869.94 | N | -16869.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16869.94 | 0 | 0 | 16869.94 | 0 | 0 | 0 | 0 | 0 | 0 | -16869.94 | 0 | 0 | 16869.94 | 16869.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 347 | 332.5 | 14.5 | 347 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0057-1000-E | IPCRP1 | IPCRP1 | 0057-1000 | Install 11ft x 5ft Combined Sewer | N | E |  | NR | P | 79017.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 79017.05 | 0 | 0 | 79017.05 | 0 | 0 | 0 | Y | 79017.05 | 0 | 0 | 79017.05 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 347 | 332.5 | 14.5 | 347 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0057-1000-L | IPCRP1 | IPCRP1 | 0057-1000 | Install 11ft x 5ft Combined Sewer | N | L |  | NR | P | 282414.12 | 448185.48 | 448185.48 | 448185.48 | 448185.48 | 96.5527 | 0 | 0 | 0 | 16001.75 | Y | 464187.23 | Y | -181773.11 | 0 | 0 | 282414.12 | 0 | 0 | 464187.23 | Y | -181773.11 | 0 | 0 | 282414.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -464187.23 | 17870.23 | -5187.66 | 464187.23 | 0 | 0 | 0 | 0 | 0 | 0 | -464187.23 | 0 | 0 | 464187.23 | 464187.23 | 0 | 0 | 0 | 2288.33 | 0 | 3470 | 3470 | 2288.33 | 3299.5 | 170.5 | 3470 | HR | 347 | 332.5 | 14.5 | 347 | LF | 0 | 0 | 0 | 16001.75
Y | IPCRP1-0057-1000-S | IPCRP1 | IPCRP1 | 0057-1000 | Install 11ft x 5ft Combined Sewer | N | S |  | UNIT | A | 0 | 23537.35 | 23537.35 | 23537.35 | 23537.35 | 181.4072 | 0 | 0 | 0 | -10562.48 | Y | 12974.87 | Y | -12974.87 | 0 | 0 | 0 | 0 | 0 | 12974.87 | Y | -12974.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12974.87 | 0 | 2031.33 | 12974.87 | 0 | 0 | 0 | 0 | 0 | 0 | -12974.87 | 0 | 0 | 12974.87 | 12974.87 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 170.5 | -167.5 | 3 | NA | 347 | 332.5 | 14.5 | 347 | LF | 23537.35 | 0 | 23537.35 | -10562.48
Y | IPCRP1-0057-1010-E | IPCRP1 | IPCRP1 | 0057-1010 | CIP Bends for 11ft x 5ft Combined Sewer | N | E |  | NR | P | 6192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 6192 | 0 | 0 | 6192 | 0 | 0 | 0 | N | 6192 | 0 | 0 | 6192 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 28 | 50.36 | 2.39 | 52.75 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0057-1010-L | IPCRP1 | IPCRP1 | 0057-1010 | CIP Bends for 11ft x 5ft Combined Sewer | N | L |  | NR | P | 79641.8 | 119949.81 | 119949.81 | 119949.81 | 119949.81 | 87.5258 | 0 | 0 | 0 | 17095.23 | Y | 137045.04 | Y | -57403.24 | 0 | 0 | 79641.8 | 0 | 0 | 137045.04 | Y | -57403.24 | 0 | 0 | 79641.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -137045.04 | -17870.23 | 28002.18 | 137045.04 | 0 | 0 | 0 | 0 | 0 | 0 | -137045.04 | 0 | 0 | 137045.04 | 137045.04 | 0 | 0 | 0 | 656 | 0 | 1030 | 1030 | 656 | 909.5 | 120.5 | 1030 | HR | 28 | 50.36 | 2.39 | 52.75 | LF | 0 | 0 | 0 | 17095.23
Y | IPCRP1-0057-1010-S | IPCRP1 | IPCRP1 | 0057-1010 | CIP Bends for 11ft x 5ft Combined Sewer | N | S |  | UNIT | A | 0 | 4154.84 | 4154.84 | 4154.84 | 4154.84 | 212.5499 | 0 | 0 | 0 | 0 | N | 1954.76 | N | -1954.76 | 0 | 0 | 0 | 0 | 0 | 1954.76 | N | -1954.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1954.76 | 1872.45 | 327.63 | 1954.76 | 0 | 0 | 0 | 0 | 1872.45 | 0 | -1954.76 | 0 | 0 | 1954.76 | 1954.76 | 0 | 0 | 0 | 0 | 0 | 15.5 | 15.5 | 0 | 15.5 | 0 | 15.5 | NA | 28 | 50.36 | 2.39 | 52.75 | LF | 4154.84 | 0 | 4154.84 | 0
Y | IPCRP1-0058-0000-L | IPCRP1 | IPCRP1 | 0058-0000 | 12 ft W X 4ft-6in H SNGL BARRL FLT TOP RC CS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0058-0000-R | IPCRP1 | IPCRP1 | 0058-0000 | 12 ft W X 4ft-6in H SNGL BARRL FLT TOP RC CS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9384000 | 0 | 0 | 9384000 | 0 | 9384000 | 9295680 | 0 | N | 9384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1000-C | IPCRP1 | IPCRP1 | 0058-1000 | Install 12 ft x 4ft 6in Combined Sewer | N | C |  | UNIT | U | 0 | 4943.69 | 4943.69 | 4920.26 | 4943.69 | 100 | 0 | 0 | 0 | -23.43 | Y | 4920.26 | Y | -4920.26 | 0 | 0 | 0 | 0 | 0 | 4920.26 | Y | -4920.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4920.26 | 0 | 0 | 4920.26 | 0 | 0 | 0 | 0 | 0 | 0 | -4920.26 | 0 | 0 | 4920.26 | 4920.26 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 816 | 808.32 | 0 | 808.32 | LF | 287.43 | 23.43 | 264 | -23.43
Y | IPCRP1-0058-1000-E | IPCRP1 | IPCRP1 | 0058-1000 | Install 12 ft x 4ft 6in Combined Sewer | N | E |  | NR | P | 371086.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 371086.79 | 0 | 0 | 371086.79 | 0 | 0 | 0 | Y | 371086.79 | 0 | 0 | 371086.79 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 816 | 808.32 | 0 | 808.32 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1000-L | IPCRP1 | IPCRP1 | 0058-1000 | Install 12 ft x 4ft 6in Combined Sewer | N | L |  | NR | P | 974869.56 | 961611.95 | 961611.95 | 961611.95 | 961611.95 | 100 | 0 | 0 | 0 | 0 | Y | 961611.95 | Y | 13257.61 | 0 | 0 | 974869.56 | 0 | 0 | 961611.95 | Y | 13257.61 | 0 | 0 | 974869.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -961611.95 | 0 | 0 | 961611.95 | 0 | 0 | 0 | 0 | 0 | 0 | -961611.95 | 0 | 0 | 961611.95 | 961611.95 | 0 | 0 | 0 | 7672 | 0 | 7417.5 | 7417.5 | 7672 | 7417.5 | 0 | 7417.5 | HR | 816 | 808.32 | 0 | 808.32 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1000-S | IPCRP1 | IPCRP1 | 0058-1000 | Install 12 ft x 4ft 6in Combined Sewer | N | S |  | UNIT | A | 0 | 30895.48 | 30895.48 | 30895.48 | 30895.48 | 100 | 0 | 0 | 0 | 0 | Y | 30895.48 | Y | -30895.48 | 0 | 0 | 0 | 0 | 0 | 30895.48 | Y | -30895.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30895.48 | 0 | 0 | 30895.48 | 0 | 0 | 0 | 0 | 0 | 0 | -30895.48 | 0 | 0 | 30895.48 | 30895.48 | 0 | 0 | 0 | 0 | 0 | 49 | 49 | 0 | 251.5 | -202.5 | 49 | NA | 816 | 808.32 | 0 | 808.32 | LF | 30895.48 | 0 | 30895.48 | 0
Y | IPCRP1-0058-1010-E | IPCRP1 | IPCRP1 | 0058-1010 | CIP Bends for 12ft x 4ft 6in Combined Sewer | N | E |  | NR | P | 13158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 13158 | 0 | 0 | 13158 | 0 | 0 | 0 | N | 13158 | 0 | 0 | 13158 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 74 | 103.79 | 0 | 103.79 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1010-L | IPCRP1 | IPCRP1 | 0058-1010 | CIP Bends for 12ft x 4ft 6in Combined Sewer | N | L |  | NR | P | 178502.58 | 163571.2 | 163571.2 | 163571.2 | 163571.2 | 100 | 0 | 0 | 0 | 0 | Y | 163571.2 | Y | 14931.38 | 0 | 0 | 178502.58 | 0 | 0 | 163571.2 | Y | 14931.38 | 0 | 0 | 178502.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -163571.2 | 0 | 0 | 163571.2 | 0 | 0 | 0 | 0 | 0 | 0 | -163571.2 | 0 | 0 | 163571.2 | 163571.2 | 0 | 0 | 0 | 1464 | 0 | 1283 | 1283 | 1464 | 1283 | 0 | 1283 | HR | 74 | 103.79 | 0 | 103.79 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1010-S | IPCRP1 | IPCRP1 | 0058-1010 | CIP Bends for 12ft x 4ft 6in Combined Sewer | N | S |  | UNIT | A | 0 | 2922.46 | 2922.46 | 2922.46 | 2922.46 | 100 | 0 | 0 | 0 | 0 | Y | 2922.46 | Y | -2922.46 | 0 | 0 | 0 | 0 | 0 | 2922.46 | Y | -2922.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2922.46 | 0 | 0 | 2922.46 | 0 | 0 | 0 | 0 | 0 | 0 | -2922.46 | 0 | 0 | 2922.46 | 2922.46 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 24 | -13 | 11 | NA | 74 | 103.79 | 0 | 103.79 | LF | 2922.46 | 0 | 2922.46 | 0
Y | IPCRP1-0058-1020-L | IPCRP1 | IPCRP1 | 0058-1020 | PM - Box Sewer, RCP Pipe, MH, CB (Coastal) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.6 | 0.4 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1020-M | IPCRP1 | IPCRP1 | 0058-1020 | PM - Box Sewer, RCP Pipe, MH, CB (Coastal) | N | M |  | NR | P | 4418340 | 5372333.83 | 5372333.83 | 4193493.56 | 5372333.83 | 96.4022 | 0 | 0 | 0 | -1022333.83 | Y | 4350000 | Y | 68340 | 0 | 0 | 4418340 | 0 | 0 | 4350000 | Y | 68340 | 0 | 0 | 4418340 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4350000 | 45020.8 | 0 | 4350000 | 0 | 0 | 0 | 73976.5 | 2696 | 0 | -4350000 | 0 | 0 | 4350000 | 4350000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 63294.21 | -1524.8 | 61769.41 | EA | 1 | 0.6 | 0.4 | 1 | LS | 5373983.83 | 1178840.27 | 4195143.56 | -1022333.83 | Coastal Pipeline ( $4,800,269.13) Change PMF (Mat) from $4,876,415.72 to $4,734,332.33
Y | IPCRP1-0058-1030-E | IPCRP1 | IPCRP1 | 0058-1030 | Demo of various size comb sewer & RCP pipe | N | E |  | NR | P | 370621.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 370621.84 | 0 | 0 | 370621.84 | 0 | 0 | 0 | Y | 370621.84 | 0 | 0 | 370621.84 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 3155 | 1437 | 563 | 2000 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1030-L | IPCRP1 | IPCRP1 | 0058-1030 | Demo of various size comb sewer & RCP pipe | N | L |  | NR | P | 997239.25 | 505946.3 | 505946.3 | 505946.3 | 505946.3 | 76.0264 | 0 | 0 | 0 | 159541.42 | Y | 665487.72 | Y | 331751.53 | 0 | 0 | 997239.25 | 0 | 0 | 665487.72 | Y | 331751.53 | 0 | 0 | 997239.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -665487.72 | 0 | 917.94 | 665487.72 | 0 | 0 | 0 | 0 | 0 | 0 | -665487.72 | 0 | 0 | 665487.72 | 665487.72 | 0 | 0 | 0 | 7592 | 0 | 5000 | 5000 | 7592 | 3800 | 1200 | 5000 | HR | 3155 | 1437 | 563 | 2000 | LF | 0 | 0 | 0 | 159541.42
Y | IPCRP1-0058-1030-M | IPCRP1 | IPCRP1 | 0058-1030 | Demo of various size comb sewer & RCP pipe | N | M |  | UNIT | U | 0 | 0 | -542.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 101 | 0 | 101 | 0 | 101 | NA | 3155 | 1437 | 563 | 2000 | LF | -542.4 | -542.4 | 0 | 0 | HOLBROOK PIPE @6,653.94
Y | IPCRP1-0058-1030-S | IPCRP1 | IPCRP1 | 0058-1030 | Demo of various size comb sewer & RCP pipe | N | S |  | UNIT | A | 0 | 26829.62 | 26829.62 | 26829.62 | 26829.62 | 106.1298 | 0 | 0 | 0 | -1549.62 | Y | 25280 | Y | -25280 | 0 | 0 | 0 | 0 | 0 | 25280 | Y | -25280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25280 | 1549.62 | 0 | 25280 | 0 | 0 | 0 | 0 | 1549.62 | 0 | -25280 | 0 | 0 | 25280 | 25280 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 134.5 | -132.5 | 2 | NA | 3155 | 1437 | 563 | 2000 | LF | 26829.62 | 0 | 26829.62 | -1549.62
Y | IPCRP1-0058-1040-E | IPCRP1 | IPCRP1 | 0058-1040 | Demo of exist regulators & chambers | N | E |  | NR | P | 78014.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 78014.46 | 0 | 0 | 78014.46 | 0 | 0 | 0 | Y | 78014.46 | 0 | 0 | 78014.46 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 7 | 5 | 1 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0058-1040-L | IPCRP1 | IPCRP1 | 0058-1040 | Demo of exist regulators & chambers | N | L |  | NR | P | 172962.94 | 38145.7 | 38145.7 | 38145.7 | 38145.7 | 38.1445 | 0 | 0 | 0 | 61857.5 | Y | 100003.2 | Y | 72959.74 | 0 | 0 | 172962.94 | 0 | 0 | 100003.2 | Y | 72959.74 | 0 | 0 | 172962.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100003.2 | 0 | 0 | 100003.2 | 0 | 0 | 0 | 0 | 0 | 0 | -100003.2 | 0 | 0 | 100003.2 | 100003.2 | 0 | 0 | 0 | 1344 | 0 | 735 | 735 | 1344 | 281 | 454 | 735 | HR | 7 | 5 | 1 | 6 | EA | 0 | 0 | 0 | 61857.5 | As / NM (10/16) we re-routed 1 pipe run to avoid demo of 1 exist chamber.
Y | IPCRP1-0058-1040-S | IPCRP1 | IPCRP1 | 0058-1040 | Demo of exist regulators & chambers | N | S |  | UNIT | A | 0 | 2637.89 | 2637.89 | 2637.89 | 2637.89 | 100 | 0 | 0 | 0 | 0 | Y | 2637.89 | Y | -2637.89 | 0 | 0 | 0 | 0 | 0 | 2637.89 | Y | -2637.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2637.89 | 0 | 0 | 2637.89 | 0 | 0 | 0 | 0 | 0 | 0 | -2637.89 | 0 | 0 | 2637.89 | 2637.89 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 22 | -12 | 10 | NA | 7 | 5 | 1 | 6 | EA | 2637.89 | 0 | 2637.89 | 0
Y | IPCRP1-0058-1050-C | IPCRP1 | IPCRP1 | 0058-1050 | Temp Bypass for Sewer Work | N | C |  | UNIT | U | 0 | 89109.3 | 89109.3 | 87945.73 | 89109.3 | 87.9457 | 0 | 0 | 0 | 10890.7 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 1782.07 | 100000 | 0 | 0 | 0 | 0 | 1782.08 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789.84 | -789.84 | 0 | NA | 0 | 17.2 | 1.8 | 19 | EA | 88289.88 | 1163.57 | 87126.31 | 10890.7
Y | IPCRP1-0058-1050-L | IPCRP1 | IPCRP1 | 0058-1050 | Temp Bypass for Sewer Work | N | L |  | UNIT | P | 0 | 842807.28 | 842807.28 | 842807.28 | 842807.28 | 87.7896 | 0 | 0 | 0 | 117223.7 | Y | 960030.98 | Y | -960030.98 | 0 | 0 | 0 | 0 | 0 | 960030.98 | Y | -960030.98 | 0 | 0 | -100005 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -960030.98 | 0 | 5350.31 | 960030.98 | 0 | 0 | 0 | 0 | 0 | 0 | -960030.98 | 0 | 0 | 960030.98 | 960030.98 | 0 | 0 | 0 | 750 | 0 | 6999.98 | 6999.98 | 750 | 6334.5 | 665.48 | 6999.98 | HR | 0 | 17.2 | 1.8 | 19 | EA | 0 | 0 | 0 | 117223.7 | Increased PMF qty by 1 in March'23. Missed in the bid. The purpose of adding this code will be to keep the construction of sewer work more accurate.
Y | IPCRP1-0058-1050-M | IPCRP1 | IPCRP1 | 0058-1050 | Temp Bypass for Sewer Work | N | M |  | UNIT | U | 0 | 62637.12 | 62637.12 | 62637.12 | 62637.12 | 62.6371 | 0 | 0 | 0 | 37362.88 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 4199.45 | 100000 | 0 | 0 | 0 | 0 | 3969.31 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 101 | 101 | 0 | 1706.77 | -1605.77 | 101 | NA | 0 | 17.2 | 1.8 | 19 | EA | 62528.91 | -108.21 | 62637.12 | 37362.88
Y | IPCRP1-0058-1050-S | IPCRP1 | IPCRP1 | 0058-1050 | Temp Bypass for Sewer Work | N | S |  | UNIT | A | 0 | 83430.78 | 83430.78 | 83430.78 | 83430.78 | 69.5256 | 0 | 0 | 0 | 36569.22 | Y | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -120000 | 774.81 | 196.58 | 120000 | 0 | 0 | 0 | 0 | 774.81 | 0 | -120000 | 0 | 0 | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 233 | -222 | 11 | NA | 0 | 17.2 | 1.8 | 19 | EA | 83430.78 | 0 | 83430.78 | 36569.22 | KMA CO's added. EN-TECH Corp
Y | IPCRP1-0059-0000-L | IPCRP1 | IPCRP1 | 0059-0000 | 12 R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0059-0000-R | IPCRP1 | IPCRP1 | 0059-0000 | 12 R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 806400 | 0 | 0 | 806400 | 0 | 806400 | 822500 | 0 | N | 806400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0059-1000-E | IPCRP1 | IPCRP1 | 0059-1000 | Install 12 RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 57268.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 57268.02 | 0 | 0 | 57268.02 | 0 | 0 | 0 | N | 57268.02 | 0 | 0 | 57268.02 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 288 | 293.75 | 0 | 293.75 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0059-1000-L | IPCRP1 | IPCRP1 | 0059-1000 | Install 12 RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 172015.16 | 113977.85 | 113977.85 | 113977.85 | 113977.85 | 100 | 0 | 0 | 0 | 0 | Y | 113977.85 | Y | 58037.31 | 0 | 0 | 172015.16 | 0 | 0 | 113977.85 | Y | 58037.31 | 0 | 0 | 172015.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -113977.85 | 0 | 0 | 113977.85 | 0 | 0 | 0 | 0 | 0 | 0 | -113977.85 | 0 | 0 | 113977.85 | 113977.85 | 0 | 0 | 0 | 1328 | 0 | 844 | 844 | 1328 | 844 | 0 | 844 | HR | 288 | 293.75 | 0 | 293.75 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0059-1000-S | IPCRP1 | IPCRP1 | 0059-1000 | Install 12 RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 244063.52 | 244063.52 | 161357.32 | 244063.52 | 66.1128 | 0 | 0 | 0 | 0 | Y | 244063.52 | Y | -244063.52 | 0 | 0 | 0 | 0 | 0 | 244063.52 | Y | -244063.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -244063.52 | 0 | 7450 | 244063.52 | 0 | 0 | 0 | 0 | 0 | 0 | -244063.52 | 0 | 0 | 244063.52 | 244063.52 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 104.99 | -103.99 | 1 | NA | 288 | 293.75 | 0 | 293.75 | LF | 244063.52 | 82706.2 | 161357.32 | 0 | 11 Enviro Video Inspection @$20k - Additional Clean & TV Shift in December 11 Enviro ($40,172) + En-Tech Infrastructure ($47,500) + KMA ($409.52)
Y | IPCRP1-0060-0000-L | IPCRP1 | IPCRP1 | 0060-0000 | 24 R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0060-0000-R | IPCRP1 | IPCRP1 | 0060-0000 | 24 R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1352000 | 0 | 0 | 1352000 | 0 | 1352000 | 1384708 | 0 | N | 1352000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0060-1000-C | IPCRP1 | IPCRP1 | 0060-1000 | Install 24 in RCP Comb Sewer on Conc Cradle | N | C |  | UNIT | U | 0 | 13385.28 | 13385.28 | 13385.28 | 13385.28 | 100 | 0 | 0 | 0 | 0 | N | 13385.28 | N | -13385.28 | 0 | 0 | 0 | 0 | 0 | 13385.28 | N | -13385.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13385.28 | 0 | 0 | 13385.28 | 0 | 0 | 0 | 0 | 0 | 0 | -13385.28 | 0 | 0 | 13385.28 | 13385.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 520 | 532.58 | 0 | 532.58 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0060-1000-E | IPCRP1 | IPCRP1 | 0060-1000 | Install 24 in RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 64374.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 64374.61 | 0 | 0 | 64374.61 | 0 | 0 | 0 | Y | 64374.61 | 0 | 0 | 64374.61 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 520 | 532.58 | 0 | 532.58 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0060-1000-L | IPCRP1 | IPCRP1 | 0060-1000 | Install 24 in RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 205959.2 | 286478.24 | 286478.24 | 286478.24 | 286478.24 | 100 | 0 | 0 | 0 | 0 | Y | 286478.24 | Y | -80519.04 | 0 | 0 | 205959.2 | 0 | 0 | 286478.24 | Y | -80519.04 | 0 | 0 | 205959.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -286478.24 | 0 | 0 | 286478.24 | 0 | 0 | 0 | 0 | 0 | 0 | -286478.24 | 0 | 0 | 286478.24 | 286478.24 | 0 | 0 | 0 | 1657.6 | 0 | 2117.5 | 2117.5 | 1657.6 | 2117.5 | 0 | 2117.5 | HR | 520 | 532.58 | 0 | 532.58 | LF | 0 | 0 | 0 | 0 | VS PMF Quantity is 568 LF. Nick M CTD quantity is 521.58 LF. Another 11 LF from 15-January-2023 bring total completed-to-date to 532.58
Y | IPCRP1-0060-1000-S | IPCRP1 | IPCRP1 | 0060-1000 | Install 24 in RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 27407.96 | 27407.96 | 27407.96 | 27407.96 | 100 | 0 | 0 | 0 | 0 | Y | 27407.96 | Y | -27407.96 | 0 | 0 | 0 | 0 | 0 | 27407.96 | Y | -27407.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27407.96 | 0 | 0 | 27407.96 | 0 | 0 | 0 | 0 | 0 | 0 | -27407.96 | 0 | 0 | 27407.96 | 27407.96 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 0 | 215 | 0 | 215 | NA | 520 | 532.58 | 0 | 532.58 | LF | 27407.96 | 0 | 27407.96 | 0
Y | IPCRP1-0060-1010-C | IPCRP1 | IPCRP1 | 0060-1010 | Cost Adjustment | N | C |  | NR | P | 742732.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 742732.36 | 0 | 0 | 742732.36 | 0 | 0 | 0 | Y | 742732.36 | 0 | 0 | 742732.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | Pick up
Y | IPCRP1-0060-1010-L | IPCRP1 | IPCRP1 | 0060-1010 | Cost Adjustment | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0061-0000-L | IPCRP1 | IPCRP1 | 0061-0000 | 30 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0061-0000-R | IPCRP1 | IPCRP1 | 0061-0000 | 30 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3009000 | 0 | 0 | 3009000 | 0 | 3009000 | 3033990 | 0 | N | 3009000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0061-1000-E | IPCRP1 | IPCRP1 | 0061-1000 | Install 30 in RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 111551.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 111551.32 | 0 | 0 | 111551.32 | 0 | 0 | 0 | Y | 111551.32 | 0 | 0 | 111551.32 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1003 | 1011.33 | 6.46 | 1017.79 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0061-1000-L | IPCRP1 | IPCRP1 | 0061-1000 | Install 30 in RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 358204.11 | 437916.36 | 437916.36 | 437916.36 | 437916.36 | 100 | 0 | 0 | 0 | 0.02 | Y | 437916.38 | Y | -79712.27 | 0 | 0 | 358204.11 | 0 | 0 | 437916.38 | Y | -79712.27 | 0 | 0 | 358204.11 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -437916.38 | 0 | 0 | 437916.38 | 0 | 0 | 0 | 0 | 0 | 0 | -437916.38 | 0 | 0 | 437916.38 | 437916.38 | 0 | 0 | 0 | 2891.2 | 0 | 3316 | 3316 | 2891.2 | 3316 | 0 | 3316 | HR | 1003 | 1011.33 | 6.46 | 1017.79 | LF | 0 | 0 | 0 | 0.02 | As per NM (2/6) our final installed quan is 1,017.79 LF. NM to speak with RC to get remaining 6.46 LF
Y | IPCRP1-0061-1000-S | IPCRP1 | IPCRP1 | 0061-1000 | Install 30 in RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 6235.19 | 6235.19 | 6235.19 | 6235.19 | 100 | 0 | 0 | 0 | 0 | Y | 6235.19 | Y | -6235.19 | 0 | 0 | 0 | 0 | 0 | 6235.19 | Y | -6235.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6235.19 | 0 | 0 | 6235.19 | 0 | 0 | 0 | 0 | 0 | 0 | -6235.19 | 0 | 0 | 6235.19 | 6235.19 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 50 | -42 | 8 | NA | 1003 | 1011.33 | 6.46 | 1017.79 | LF | 6235.19 | 0 | 6235.19 | 0 | KMA CO
Y | IPCRP1-0062-0000-L | IPCRP1 | IPCRP1 | 0062-0000 | 36 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0062-0000-R | IPCRP1 | IPCRP1 | 0062-0000 | 36 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5337000 | 0 | 0 | 5337000 | 0 | 5337000 | 5380875 | 0 | N | 5337000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5337000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0062-1000-C | IPCRP1 | IPCRP1 | 0062-1000 | Install 36 in RCP Comb Sewer on Conc Cradle | N | C |  | UNIT | U | 0 | 2522.84 | -1056.99 | -1056.99 | 2522.84 | -41.8968 | 0 | 0 | 0 | 0 | N | 2522.84 | N | -2522.84 | 0 | 0 | 0 | 0 | 0 | 2522.84 | N | -2522.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2522.84 | -3579.83 | 0 | 2522.84 | 0 | 0 | 0 | 0 | 0 | 0 | -2522.84 | 0 | 0 | 2522.84 | 2522.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1186 | 1195.75 | 0 | 1195.75 | LF | 0 | 3579.83 | -3579.83 | 0
Y | IPCRP1-0062-1000-E | IPCRP1 | IPCRP1 | 0062-1000 | Install 36 in RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 261850.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 261850.9 | 0 | 0 | 261850.9 | 0 | 0 | 0 | Y | 261850.9 | 0 | 0 | 261850.9 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 1186 | 1195.75 | 0 | 1195.75 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0062-1000-L | IPCRP1 | IPCRP1 | 0062-1000 | Install 36 in RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 800935.26 | 783079.27 | 783079.27 | 783079.27 | 783079.27 | 100.284 | 0 | 0 | 0 | -2218 | Y | 780861.27 | Y | 20073.99 | 0 | 0 | 800935.26 | 0 | 0 | 780861.27 | Y | 20073.99 | 0 | 0 | 800935.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -780861.27 | 0 | 2218 | 780861.27 | 0 | 0 | 0 | 0 | 0 | 0 | -780861.27 | 0 | 0 | 780861.27 | 780861.27 | 0 | 0 | 0 | 6257.52 | 0 | 5915.5 | 5915.5 | 6257.52 | 5931.5 | -16 | 5915.5 | HR | 1186 | 1195.75 | 0 | 1195.75 | LF | 0 | 0 | 0 | -2218
Y | IPCRP1-0062-1000-S | IPCRP1 | IPCRP1 | 0062-1000 | Install 36 in RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 68405.98 | 68405.98 | 68405.98 | 68405.98 | 100 | 0 | 0 | 0 | 0 | N | 68405.98 | N | -68405.98 | 0 | 0 | 0 | 0 | 0 | 68405.98 | N | -68405.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -68405.98 | 0 | 0 | 68405.98 | 0 | 0 | 0 | 0 | 0 | 0 | -68405.98 | 0 | 0 | 68405.98 | 68405.98 | 0 | 0 | 0 | 0 | 0 | 558.5 | 558.5 | 0 | 558.5 | 0 | 558.5 | NA | 1186 | 1195.75 | 0 | 1195.75 | LF | 68405.98 | 0 | 68405.98 | 0
Y | IPCRP1-0063-0000-L | IPCRP1 | IPCRP1 | 0063-0000 | 42 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0063-0000-R | IPCRP1 | IPCRP1 | 0063-0000 | 42 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3566400 | 0 | 0 | 3566400 | 0 | 3566400 | 3428016 | 0 | N | 3566400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3566400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0063-1000-E | IPCRP1 | IPCRP1 | 0063-1000 | Install 42 in RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 203626.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 203626.59 | 0 | 0 | 203626.59 | 0 | 0 | 0 | Y | 203626.59 | 0 | 0 | 203626.59 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 743 | 714.17 | 0 | 714.17 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0063-1000-L | IPCRP1 | IPCRP1 | 0063-1000 | Install 42 in RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 624637.47 | 345117.66 | 345117.66 | 345117.66 | 345117.66 | 99.8311 | 0 | 0 | 0 | 583.73 | Y | 345701.39 | Y | 278936.08 | 0 | 0 | 624637.47 | 0 | 0 | 345701.39 | Y | 278936.08 | 0 | 0 | 624637.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -345701.39 | -583.73 | 561.44 | 345701.39 | 0 | 0 | 0 | 0 | 0 | 0 | -345701.39 | 0 | 0 | 345701.39 | 345701.39 | 0 | 0 | 0 | 4832 | 0 | 2734.5 | 2734.5 | 4832 | 2730.5 | 4 | 2734.5 | HR | 743 | 714.17 | 0 | 714.17 | LF | 0 | 0 | 0 | 583.73
Y | IPCRP1-0063-1000-S | IPCRP1 | IPCRP1 | 0063-1000 | Install 42 in RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 16208.61 | 16208.61 | 16208.61 | 16208.61 | 100 | 0 | 0 | 0 | 0 | Y | 16208.61 | Y | -16208.61 | 0 | 0 | 0 | 0 | 0 | 16208.61 | Y | -16208.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16208.61 | 0 | 0 | 16208.61 | 0 | 0 | 0 | 0 | 0 | 0 | -16208.61 | 0 | 0 | 16208.61 | 16208.61 | 0 | 0 | 0 | 0 | 0 | 58.5 | 58.5 | 0 | 133.5 | -75 | 58.5 | NA | 743 | 714.17 | 0 | 714.17 | LF | 16208.61 | 0 | 16208.61 | 0 | KMA CO
Y | IPCRP1-0064-0000-L | IPCRP1 | IPCRP1 | 0064-0000 | 48 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0064-0000-R | IPCRP1 | IPCRP1 | 0064-0000 | 48 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2766000 | 0 | 0 | 2766000 | 0 | 2766000 | 2833020 | 0 | N | 2766000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2766000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0064-1000-E | IPCRP1 | IPCRP1 | 0064-1000 | Install 48 in RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 155863.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 155863.8 | 0 | 0 | 155863.8 | 0 | 0 | 0 | N | 155863.8 | 0 | 0 | 155863.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 461 | 472.17 | 0 | 472.17 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0064-1000-L | IPCRP1 | IPCRP1 | 0064-1000 | Install 48 in RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 468533.62 | 335677.99 | 335677.99 | 335677.99 | 335677.99 | 100 | 0 | 0 | 0 | 0.01 | Y | 335678 | Y | 132855.62 | 0 | 0 | 468533.62 | 0 | 0 | 335678 | Y | 132855.62 | 0 | 0 | 468533.62 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -335678 | 0 | 0 | 335678 | 0 | 0 | 0 | 0 | 0 | 0 | -335678 | 0 | 0 | 335678 | 335678 | 0 | 0 | 0 | 3616 | 0 | 2616 | 2616 | 3616 | 2616 | 0 | 2616 | HR | 461 | 472.17 | 0 | 472.17 | LF | 0 | 0 | 0 | 0.01 | Change PMF (Labor) from $271,224.56 to $271,189.61
Y | IPCRP1-0064-1000-S | IPCRP1 | IPCRP1 | 0064-1000 | Install 48 in RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 13430.17 | 13430.17 | 13430.17 | 13430.17 | 100 | 0 | 0 | 0 | 0 | Y | 13430.17 | Y | -13430.17 | 0 | 0 | 0 | 0 | 0 | 13430.17 | Y | -13430.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13430.17 | 0 | 0 | 13430.17 | 0 | 0 | 0 | 0 | 0 | 0 | -13430.17 | 0 | 0 | 13430.17 | 13430.17 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 111.5 | -55.5 | 56 | NA | 461 | 472.17 | 0 | 472.17 | LF | 13430.17 | 0 | 13430.17 | 0 | KMA CO
Y | IPCRP1-0065-0000-L | IPCRP1 | IPCRP1 | 0065-0000 | 54 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0065-0000-R | IPCRP1 | IPCRP1 | 0065-0000 | 54 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1772400 | 0 | 0 | 1772400 | 0 | 1772400 | 814800 | 0 | N | 1772400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1772400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0065-1000-C | IPCRP1 | IPCRP1 | 0065-1000 | Install 54 in RCP Comb Sewer on Conc Cradle | N | C |  | UNIT | U | 0 | 6926.06 | 6926.06 | 6926.06 | 6926.06 | 100 | 0 | 0 | 0 | 0 | N | 6926.06 | N | -6926.06 | 0 | 0 | 0 | 0 | 0 | 6926.06 | N | -6926.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6926.06 | 0 | 0 | 6926.06 | 0 | 0 | 0 | 0 | 0 | 0 | -6926.06 | 0 | 0 | 6926.06 | 6926.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 422 | 261.9 | 160.1 | 422 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0065-1000-E | IPCRP1 | IPCRP1 | 0065-1000 | Install 54 in RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 74710.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 74710.59 | 0 | 0 | 74710.59 | 0 | 0 | 0 | Y | 74710.59 | 0 | 0 | 74710.59 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 422 | 261.9 | 160.1 | 422 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0065-1000-L | IPCRP1 | IPCRP1 | 0065-1000 | Install 54 in RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 210849.52 | 254753.53 | 254753.53 | 254753.53 | 254753.53 | 79.6105 | 0 | 0 | 0 | 65246.47 | Y | 320000 | Y | -109150.48 | 0 | 0 | 210849.52 | 0 | 0 | 320000 | Y | -109150.48 | 0 | 0 | 210849.52 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -320000 | 0 | 78971.52 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | -320000 | 0 | 0 | 320000 | 320000 | 0 | 0 | 0 | 1640 | 0 | 2322.88 | 2322.88 | 1640 | 1825 | 497.88 | 2322.88 | HR | 422 | 261.9 | 160.1 | 422 | LF | 0 | 0 | 0 | 65246.47
Y | IPCRP1-0065-1000-S | IPCRP1 | IPCRP1 | 0065-1000 | Install 54 in RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 23918.8 | 23918.8 | 23918.8 | 23918.8 | 136.275 | 0 | 0 | 0 | 0 | N | 17551.86 | N | -17551.86 | 0 | 0 | 0 | 0 | 0 | 17551.86 | N | -17551.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17551.86 | 3680.34 | 2686.6 | 17551.86 | 0 | 0 | 0 | 0 | 3680.34 | 0 | -17551.86 | 0 | 0 | 17551.86 | 17551.86 | 0 | 0 | 0 | 0 | 0 | 139 | 139 | 0 | 139 | 0 | 139 | NA | 422 | 261.9 | 160.1 | 422 | LF | 23918.8 | 0 | 23918.8 | 0
Y | IPCRP1-0066-0000-L | IPCRP1 | IPCRP1 | 0066-0000 | 60 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0066-0000-R | IPCRP1 | IPCRP1 | 0066-0000 | 60 in R.C.P. CL IV COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1164500 | 0 | 0 | 1164500 | 0 | 1164500 | 1119195 | 0 | N | 1164500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0066-1000-E | IPCRP1 | IPCRP1 | 0066-1000 | Install 60 in RCP Comb Sewer on Conc Cradle | N | E |  | NR | P | 57046.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 57046.85 | 0 | 0 | 57046.85 | 0 | 0 | 0 | N | 57046.85 | 0 | 0 | 57046.85 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 137 | 131.67 | 0 | 131.67 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0066-1000-L | IPCRP1 | IPCRP1 | 0066-1000 | Install 60 in RCP Comb Sewer on Conc Cradle | N | L |  | NR | P | 171603.64 | 81387.98 | 81387.98 | 81387.98 | 81387.98 | 100 | 0 | 0 | 0 | 0 | Y | 81387.98 | Y | 90215.66 | 0 | 0 | 171603.64 | 0 | 0 | 81387.98 | Y | 90215.66 | 0 | 0 | 171603.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -81387.98 | 0 | 0 | 81387.98 | 0 | 0 | 0 | 0 | 0 | 0 | -81387.98 | 0 | 0 | 81387.98 | 81387.98 | 0 | 0 | 0 | 1324 | 0 | 623 | 623 | 1324 | 623 | 0 | 623 | HR | 137 | 131.67 | 0 | 131.67 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0066-1000-S | IPCRP1 | IPCRP1 | 0066-1000 | Install 60 in RCP Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 821.53 | 821.53 | 821.53 | 821.53 | 100 | 0 | 0 | 0 | 0 | N | 821.53 | N | -821.53 | 0 | 0 | 0 | 0 | 0 | 821.53 | N | -821.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -821.53 | 0 | 0 | 821.53 | 0 | 0 | 0 | 0 | 0 | 0 | -821.53 | 0 | 0 | 821.53 | 821.53 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 7 | NA | 137 | 131.67 | 0 | 131.67 | LF | 821.53 | 0 | 821.53 | 0
Y | IPCRP1-0067-0000-L | IPCRP1 | IPCRP1 | 0067-0000 | 36 in R.C.P. CL V COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0067-0000-R | IPCRP1 | IPCRP1 | 0067-0000 | 36 in R.C.P. CL V COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 324000 | 0 | 0 | 324000 | 0 | 324000 | 0 | 0 | N | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0067-1000-E | IPCRP1 | IPCRP1 | 0067-1000 | Install 36 in RCP (Cl v) Comb Sewer on Conc Cradle | N | E |  | NR | P | 58717.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 58717.63 | 0 | 0 | 58717.63 | 0 | 0 | 0 | Y | 58717.63 | 0 | 0 | 58717.63 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 216 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0067-1000-L | IPCRP1 | IPCRP1 | 0067-1000 | Install 36 in RCP (Cl v) Comb Sewer on Conc Cradle | N | L |  | NR | P | 188446.13 | 1252.29 | 1252.29 | 1252.29 | 1252.29 | 100.0016 | 0 | 0 | 0 | -0.02 | Y | 1252.27 | Y | 187193.86 | 0 | 0 | 188446.13 | 0 | 0 | 1252.27 | Y | 187193.86 | 0 | 0 | 188446.13 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1252.27 | 0 | -2218 | 1252.27 | 0 | 0 | 0 | 0 | 0 | 0 | -1252.27 | 0 | 0 | 1252.27 | 1252.27 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | HR | 216 | 0 | 0 | 0 | LF | 0 | 0 | 0 | -0.02
Y | IPCRP1-0067-1000-S | IPCRP1 | IPCRP1 | 0067-1000 | Install 36 in RCP (Cl v) Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 1621.3 | 1621.3 | 1621.3 | 1621.3 | 100 | 0 | 0 | 0 | 0 | Y | 1621.3 | Y | -1621.3 | 0 | 0 | 0 | 0 | 0 | 1621.3 | Y | -1621.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1621.3 | 0 | 0 | 1621.3 | 0 | 0 | 0 | 0 | 0 | 0 | -1621.3 | 0 | 0 | 1621.3 | 1621.3 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 14 | -4 | 10 | NA | 216 | 0 | 0 | 0 | LF | 1621.3 | 0 | 1621.3 | 0 | KMA CO
Y | IPCRP1-0068-0000-L | IPCRP1 | IPCRP1 | 0068-0000 | 36 in D.I.P. CL 56 COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0068-0000-R | IPCRP1 | IPCRP1 | 0068-0000 | 36 in D.I.P. CL 56 COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 81000 | 0 | 0 | 81000 | 0 | 81000 | 48000 | 0 | N | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0068-1000-E | IPCRP1 | IPCRP1 | 0068-1000 | Install 36 inDIP (Cl 56) Comb Sewer on Conc Cradle | N | E |  | NR | P | 18481.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 18481.39 | 0 | 0 | 18481.39 | 0 | 0 | 0 | Y | 18481.39 | 0 | 0 | 18481.39 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 54 | 32 | 0 | 32 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0068-1000-L | IPCRP1 | IPCRP1 | 0068-1000 | Install 36 inDIP (Cl 56) Comb Sewer on Conc Cradle | N | L |  | NR | P | 59455.15 | 57608.2 | 57608.2 | 57608.2 | 57608.2 | 100 | 0 | 0 | 0 | 0 | Y | 57608.2 | Y | 1846.95 | 0 | 0 | 59455.15 | 0 | 0 | 57608.2 | Y | 1846.95 | 0 | 0 | 59455.15 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -57608.2 | 0 | 0 | 57608.2 | 0 | 0 | 0 | 0 | 0 | 0 | -57608.2 | 0 | 0 | 57608.2 | 57608.2 | 0 | 0 | 0 | 482 | 0 | 439 | 439 | 482 | 439 | 0 | 439 | HR | 54 | 32 | 0 | 32 | LF | 0 | 0 | 0 | 0 | On Delancey St (sheet 334)
Y | IPCRP1-0069-0000-L | IPCRP1 | IPCRP1 | 0069-0000 | 42 in D.I.P. CL 56 COMB SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0069-0000-R | IPCRP1 | IPCRP1 | 0069-0000 | 42 in D.I.P. CL 56 COMB SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5010000 | 0 | 0 | 5010000 | 0 | 5010000 | 4927500 | 0 | N | 5010000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0069-1000-C | IPCRP1 | IPCRP1 | 0069-1000 | Install 42 i DIP (Cl 56) Comb Sewer on Conc Cradle | N | C |  | UNIT | U | 0 | 36967.77 | 36967.77 | 36967.77 | 36967.77 | 100 | 0 | 0 | 0 | 0 | N | 36967.77 | N | -36967.77 | 0 | 0 | 0 | 0 | 0 | 36967.77 | N | -36967.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36967.77 | 0 | 0 | 36967.77 | 0 | 0 | 0 | 0 | 0 | 0 | -36967.77 | 0 | 0 | 36967.77 | 36967.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 501 | 492.75 | 12 | 504.75 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0069-1000-E | IPCRP1 | IPCRP1 | 0069-1000 | Install 42 i DIP (Cl 56) Comb Sewer on Conc Cradle | N | E |  | NR | P | 241399.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 241399.17 | 0 | 0 | 241399.17 | 0 | 0 | 0 | Y | 241399.17 | 0 | 0 | 241399.17 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 501 | 492.75 | 12 | 504.75 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0069-1000-L | IPCRP1 | IPCRP1 | 0069-1000 | Install 42 i DIP (Cl 56) Comb Sewer on Conc Cradle | N | L |  | NR | P | 795354.92 | 890133.03 | 890133.03 | 890133.03 | 890133.03 | 97.6023 | 0 | 0 | 0 | 21866.97 | Y | 912000 | Y | -116645.08 | 0 | 0 | 795354.92 | 0 | 0 | 912000 | Y | -116645.08 | 0 | 0 | 795354.92 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -912000 | 0 | 0 | 912000 | 0 | 0 | 0 | 0 | 0 | 0 | -912000 | 0 | 0 | 912000 | 912000 | 0 | 0 | 0 | 6136 | 0 | 6530.97 | 6530.97 | 6136 | 6375 | 155.97 | 6530.97 | HR | 501 | 492.75 | 12 | 504.75 | LF | 0 | 0 | 0 | 21866.97 | As / NM (9/20) rework to sheeting is the reason for over budget. NM (9/20) 469.25' completed to date, app 12' left from Chamber #1 to MH-B1-02 in Receiving Pit
Y | IPCRP1-0069-1000-S | IPCRP1 | IPCRP1 | 0069-1000 | Install 42 i DIP (Cl 56) Comb Sewer on Conc Cradle | N | S |  | UNIT | A | 0 | 67561.3 | 67561.3 | 67561.3 | 67561.3 | 100 | 0 | 0 | 0 | 0 | N | 67561.3 | N | -67561.3 | 0 | 0 | 0 | 0 | 0 | 67561.3 | N | -67561.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -67561.3 | 0 | 0 | 67561.3 | 0 | 0 | 0 | 0 | 0 | 0 | -67561.3 | 0 | 0 | 67561.3 | 67561.3 | 0 | 0 | 0 | 0 | 0 | 586 | 586 | 0 | 586 | 0 | 586 | NA | 501 | 492.75 | 12 | 504.75 | LF | 67561.3 | 0 | 67561.3 | 0 | NM (9/20) 469.25' completed to date, app 12' left from Chamber #1 to MH-B1-02 in Receiving Pit
Y | IPCRP1-0070-0000-L | IPCRP1 | IPCRP1 | 0070-0000 | 42 in D.I.P. CL 56 COMB SEWER, ENCASED IN CONC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0070-0000-R | IPCRP1 | IPCRP1 | 0070-0000 | 42 in D.I.P. CL 56 COMB SEWER, ENCASED IN CONC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 363000 | 0 | 0 | 363000 | 0 | 363000 | 286875 | 0 | N | 363000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0070-1000-C | IPCRP1 | IPCRP1 | 0070-1000 | Install 42 inDIP (Cl 56) Comb Sewer Encased in Con | N | C |  | UNIT | U | 0 | 27367.26 | 27367.26 | 26924.93 | 27367.26 | 100 | 0 | 0 | 0 | -442.33 | Y | 26924.93 | Y | -26924.93 | 0 | 0 | 0 | 0 | 0 | 26924.93 | Y | -26924.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26924.93 | 0 | 0 | 26924.93 | 0 | 0 | 0 | 0 | 0 | 0 | -26924.93 | 0 | 0 | 26924.93 | 26924.93 | 0 | 0 | 0 | 0 | 0 | 86 | 86 | 0 | 86 | 0 | 86 | NA | 242 | 191.25 | 0 | 191.25 | LF | 22890.18 | 442.33 | 22447.85 | -442.33
Y | IPCRP1-0070-1000-E | IPCRP1 | IPCRP1 | 0070-1000 | Install 42 inDIP (Cl 56) Comb Sewer Encased in Con | N | E |  | NR | P | 37422.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 37422.15 | 0 | 0 | 37422.15 | 0 | 0 | 0 | Y | 37422.15 | 0 | 0 | 37422.15 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 242 | 191.25 | 0 | 191.25 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0070-1000-L | IPCRP1 | IPCRP1 | 0070-1000 | Install 42 inDIP (Cl 56) Comb Sewer Encased in Con | N | L |  | NR | P | 120532.83 | 176775.76 | 176775.76 | 176775.76 | 176775.76 | 100 | 0 | 0 | 0 | 0.01 | Y | 176775.77 | Y | -56242.94 | 0 | 0 | 120532.83 | 0 | 0 | 176775.77 | Y | -56242.94 | 0 | 0 | 120532.83 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -176775.77 | 0 | 0 | 176775.77 | 0 | 0 | 0 | 0 | 0 | 0 | -176775.77 | 0 | 0 | 176775.77 | 176775.77 | 0 | 0 | 0 | 976 | 0 | 1297 | 1297 | 976 | 1297 | 0 | 1297 | HR | 242 | 191.25 | 0 | 191.25 | LF | 0 | 0 | 0 | 0.01
Y | IPCRP1-0070-1000-S | IPCRP1 | IPCRP1 | 0070-1000 | Install 42 inDIP (Cl 56) Comb Sewer Encased in Con | N | S |  | UNIT | A | 0 | 11363.67 | 11363.67 | 11363.67 | 11363.67 | 100 | 0 | 0 | 0 | 0 | N | 11363.67 | N | -11363.67 | 0 | 0 | 0 | 0 | 0 | 11363.67 | N | -11363.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11363.67 | 0 | 0 | 11363.67 | 0 | 0 | 0 | 0 | 0 | 0 | -11363.67 | 0 | 0 | 11363.67 | 11363.67 | 0 | 0 | 0 | 0 | 0 | 90.5 | 90.5 | 0 | 90.5 | 0 | 90.5 | NA | 242 | 191.25 | 0 | 191.25 | LF | 11363.67 | 0 | 11363.67 | 0
Y | IPCRP1-0071-0000-L | IPCRP1 | IPCRP1 | 0071-0000 | 18 in D.I.P. CL 56 STORM SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0071-0000-R | IPCRP1 | IPCRP1 | 0071-0000 | 18 in D.I.P. CL 56 STORM SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 132000 | 0 | 0 | 132000 | 0 | 132000 | 54250 | 0 | N | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0071-1000-E | IPCRP1 | IPCRP1 | 0071-1000 | Install 18 inDIP (Cl 56) Storm Sewer on Conc Cradl | N | E |  | NR | P | 20179.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20179.31 | 0 | 0 | 20179.31 | 0 | 0 | 0 | Y | 20179.31 | 0 | 0 | 20179.31 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 264 | 212.2 | 51.8 | 264 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0071-1000-L | IPCRP1 | IPCRP1 | 0071-1000 | Install 18 inDIP (Cl 56) Storm Sewer on Conc Cradl | N | L |  | NR | P | 86534.36 | 63358.93 | 63358.93 | 63358.93 | 63358.93 | 62.2527 | 0 | 0 | 0 | 38418.09 | Y | 101777.02 | Y | -15242.66 | 0 | 0 | 86534.36 | 0 | 0 | 101777.02 | Y | -15242.66 | 0 | 0 | 86534.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -101777.02 | 0 | -21208 | 101777.02 | 0 | 0 | 0 | 0 | 0 | 0 | -101777.02 | 0 | 0 | 101777.02 | 101777.02 | 0 | 0 | 0 | 712 | 0 | 743.34 | 743.34 | 712 | 463 | 280.34 | 743.34 | HR | 264 | 212.2 | 51.8 | 264 | LF | 0 | 0 | 0 | 38418.09 | Gave Akela 131 LF of this pipe in Phase 1. Reduce Labor cost accordingly.
Y | IPCRP1-0071-1000-S | IPCRP1 | IPCRP1 | 0071-1000 | Install 18 inDIP (Cl 56) Storm Sewer on Conc Cradl | N | S |  | UNIT | A | 0 | 113843.72 | 113843.72 | 95326.22 | 113843.72 | 88.4181 | 0 | 0 | 0 | 0 | N | 107813 | N | -107813 | 0 | 0 | 0 | 0 | 0 | 107813 | N | -107813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -107813 | 0 | 655.27 | 107813 | 0 | 0 | 0 | 0 | 0 | 0 | -107813 | 0 | 0 | 107813 | 107813 | 0 | 0 | 0 | 0 | 0 | 131 | 131 | 0 | 151 | -20 | 131 | NA | 264 | 212.2 | 51.8 | 264 | LF | 113843.72 | 18517.5 | 95326.22 | 0 | Gave Akela 131 LF of this pipe in Phase 1. Reduce Labor cost accordingly. Akela completed 108.5LF in Phase 1
Y | IPCRP1-0072-0000-L | IPCRP1 | IPCRP1 | 0072-0000 | 24 in D.I.P. CL 56 STORM SEWER, ON CONC CRADLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0072-0000-R | IPCRP1 | IPCRP1 | 0072-0000 | 24 in D.I.P. CL 56 STORM SEWER, ON CONC CRADLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 154000 | 0 | 0 | 154000 | 0 | 154000 | 4500 | 0 | N | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0072-1000-E | IPCRP1 | IPCRP1 | 0072-1000 | Install 24 inDIP (Cl 56) Storm Sewer on Conc Cradl | N | E |  | NR | P | 13790.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 13790.35 | 0 | 0 | 13790.35 | 0 | 0 | 0 | Y | 13790.35 | 0 | 0 | 13790.35 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 180.94 | -180.94 | 0 | LS | 133 | 9 | 124 | 133 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0072-1000-L | IPCRP1 | IPCRP1 | 0072-1000 | Install 24 inDIP (Cl 56) Storm Sewer on Conc Cradl | N | L |  | NR | P | 54723.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49300 | Y | 49300 | Y | 5423.47 | 0 | 0 | 54723.47 | 0 | 0 | 49300 | Y | 5423.47 | 0 | 0 | 54723.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -49300 | 0 | 0 | 49300 | 0 | 0 | 0 | 0 | 0 | 0 | -49300 | 0 | 0 | 49300 | 49300 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 400 | 400 | HR | 133 | 9 | 124 | 133 | LF | 0 | 0 | 0 | 49300 | Gave Akela 13 LF of this pipe in Phase 1. Reduce Labor cost accordingly.
Y | IPCRP1-0072-1000-S | IPCRP1 | IPCRP1 | 0072-1000 | Install 24 inDIP (Cl 56) Storm Sewer on Conc Cradl | N | S |  | UNIT | A | 0 | 15054 | 15054 | 10422 | 15054 | 69.2308 | 0 | 0 | 0 | 0 | N | 15054 | N | -15054 | 0 | 0 | 0 | 0 | 0 | 15054 | N | -15054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15054 | 0 | 0 | 15054 | 0 | 0 | 0 | 0 | 0 | 0 | -15054 | 0 | 0 | 15054 | 15054 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 9 | 4 | 13 | NA | 133 | 9 | 124 | 133 | LF | 15054 | 4632 | 10422 | 0 | Gave Akela 13 LF of this pipe in Phase 1. Reduce Labor cost accordingly.
Y | IPCRP1-0072-1010-L | IPCRP1 | IPCRP1 | 0072-1010 | DIP for Sewer & Water, inc Fittings, Gt Valves, e | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.82 | 0.18 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0072-1010-M | IPCRP1 | IPCRP1 | 0072-1010 | DIP for Sewer & Water, inc Fittings, Gt Valves, e | N | M |  | NR | P | 804915 | 1308672.24 | 1308672.24 | 1183938.01 | 1308672.24 | 91.8908 | 0 | 0 | 0 | -20253.56 | Y | 1288418.68 | Y | -483503.68 | 0 | 0 | 804915 | 0 | 0 | 1288418.68 | Y | -483503.68 | 0 | 0 | 804915 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1288418.68 | 0 | 38220.26 | 1288418.68 | 0 | 0 | 0 | 0 | 13657.16 | 0 | -1288418.68 | 0 | 0 | 1288418.68 | 1288418.68 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8372.47 | -416 | 7956.47 | LF | 1 | 0.82 | 0.18 | 1 | LS | 1308293.45 | 124734.23 | 1183559.22 | -20253.56 | Initial purchase with Capital Supply (PO #0001, $789,667.44). To be purchased Gate Valve (app 40K) and Fittings (app 40K). The remainder of the commitment is for DIP work to feed trailers.
Y | IPCRP1-0073-0000-L | IPCRP1 | IPCRP1 | 0073-0000 | CHAMBER NO. 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0073-0000-R | IPCRP1 | IPCRP1 | 0073-0000 | CHAMBER NO. 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 350000 | 0 | 0 | 350000 | 0 | 350000 | 350000 | 0 | N | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0073-1000-C | IPCRP1 | IPCRP1 | 0073-1000 | Excavate & Sheet Pit for Chamber No. 1 (E 10th St | N | C |  | UNIT | U | 0 | 10494.54 | 10494.54 | 10494.54 | 10494.54 | 100 | 0 | 0 | 0 | 0 | N | 10494.54 | N | -10494.54 | 0 | 0 | 0 | 0 | 0 | 10494.54 | N | -10494.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10494.54 | 0 | 0 | 10494.54 | 0 | 0 | 0 | 0 | 0 | 0 | -10494.54 | 0 | 0 | 10494.54 | 10494.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 293 | 293 | 0 | 293 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0073-1000-E | IPCRP1 | IPCRP1 | 0073-1000 | Excavate & Sheet Pit for Chamber No. 1 (E 10th St | N | E |  | NR | P | 15497.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 15497.91 | 0 | 0 | 15497.91 | 0 | 0 | 0 | Y | 15497.91 | 0 | 0 | 15497.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 293 | 293 | 0 | 293 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0073-1000-L | IPCRP1 | IPCRP1 | 0073-1000 | Excavate & Sheet Pit for Chamber No. 1 (E 10th St | N | L |  | NR | P | 46688.75 | 56266.25 | 56266.25 | 56266.25 | 56266.25 | 100 | 0 | 0 | 0 | 0 | Y | 56266.25 | Y | -9577.5 | 0 | 0 | 46688.75 | 0 | 0 | 56266.25 | Y | -9577.5 | 0 | 0 | 46688.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -56266.25 | 0 | 0 | 56266.25 | 0 | 0 | 0 | 0 | 0 | 0 | -56266.25 | 0 | 0 | 56266.25 | 56266.25 | 0 | 0 | 0 | 360 | 0 | 415 | 415 | 360 | 415 | 0 | 415 | HR | 293 | 293 | 0 | 293 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0073-1000-S | IPCRP1 | IPCRP1 | 0073-1000 | Excavate & Sheet Pit for Chamber No. 1 (E 10th St | N | S |  | UNIT | A | 0 | 5307.17 | 5307.17 | 5307.17 | 5307.17 | 100 | 0 | 0 | 0 | 0 | N | 5307.17 | N | -5307.17 | 0 | 0 | 0 | 0 | 0 | 5307.17 | N | -5307.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5307.17 | 0 | 0 | 5307.17 | 0 | 0 | 0 | 0 | 0 | 0 | -5307.17 | 0 | 0 | 5307.17 | 5307.17 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 45 | 0 | 45 | NA | 293 | 293 | 0 | 293 | CY | 5307.17 | 0 | 5307.17 | 0
Y | IPCRP1-0073-1010-E | IPCRP1 | IPCRP1 | 0073-1010 | Construct Chamber No. 1 (E 10th St) | N | E |  | NR | P | 4642.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4642.24 | 0 | 0 | 4642.24 | 0 | 0 | 0 | Y | 4642.24 | 0 | 0 | 4642.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 1 | 0 | 1 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0073-1010-L | IPCRP1 | IPCRP1 | 0073-1010 | Construct Chamber No. 1 (E 10th St) | N | L |  | NR | P | 57309.55 | 134273.69 | 134273.69 | 134273.69 | 134273.69 | 100 | 0 | 0 | 0 | 0 | Y | 134273.69 | Y | -76964.14 | 0 | 0 | 57309.55 | 0 | 0 | 134273.69 | Y | -76964.14 | 0 | 0 | 57309.55 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -134273.69 | 0 | 0 | 134273.69 | 0 | 0 | 0 | 0 | 0 | 0 | -134273.69 | 0 | 0 | 134273.69 | 134273.69 | 0 | 0 | 0 | 480 | 0 | 983 | 983 | 480 | 983 | 0 | 983 | HR | 1 | 1 | 0 | 1 | LF | 0 | 0 | 0 | 0 | Chamber 1 (sht 468) in intersection of Ave D & E10th St
Y | IPCRP1-0073-1010-S | IPCRP1 | IPCRP1 | 0073-1010 | Construct Chamber No. 1 (E 10th St) | N | S |  | UNIT | A | 0 | 3106.68 | 3106.68 | 3106.68 | 3106.68 | 100 | 0 | 0 | 0 | 0 | N | 3106.68 | N | -3106.68 | 0 | 0 | 0 | 0 | 0 | 3106.68 | N | -3106.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3106.68 | 0 | 0 | 3106.68 | 0 | 0 | 0 | 0 | 0 | 0 | -3106.68 | 0 | 0 | 3106.68 | 3106.68 | 0 | 0 | 0 | 0 | 0 | 24.5 | 24.5 | 0 | 24.5 | 0 | 24.5 | NA | 1 | 1 | 0 | 1 | LF | 3106.68 | 0 | 3106.68 | 0
Y | IPCRP1-0073-1020-E | IPCRP1 | IPCRP1 | 0073-1020 | Install Chimneys at Chamber No. 1 (E 10th St) | N | E |  | NR | P | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 516 | 0 | 0 | 516 | 0 | 0 | 0 | Y | 516 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0073-1020-L | IPCRP1 | IPCRP1 | 0073-1020 | Install Chimneys at Chamber No. 1 (E 10th St) | N | L |  | NR | P | 9518.07 | 706.35 | 706.35 | 706.35 | 706.35 | 100 | 0 | 0 | 0 | 0 | Y | 706.35 | Y | 8811.72 | 0 | 0 | 9518.07 | 0 | 0 | 706.35 | Y | 8811.72 | 0 | 0 | 9518.07 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -706.35 | 0 | 0 | 706.35 | 0 | 0 | 0 | 0 | 0 | 0 | -706.35 | 0 | 0 | 706.35 | 706.35 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 | As / NM (9/30) - work is 100% complete
Y | IPCRP1-0074-0000-L | IPCRP1 | IPCRP1 | 0074-0000 | CHAMBER NO. 10A | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0074-0000-R | IPCRP1 | IPCRP1 | 0074-0000 | CHAMBER NO. 10A | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 75000 | 0 | 0 | 75000 | 0 | 75000 | 75000 | 0 | N | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0074-1000-C | IPCRP1 | IPCRP1 | 0074-1000 | Excavate & Sheet Pit for Chamber 10A (E10th St) | N | C |  | UNIT | U | 0 | 3060.34 | 3060.34 | 3060.34 | 3060.34 | 100 | 0 | 0 | 0 | 0 | N | 3060.34 | N | -3060.34 | 0 | 0 | 0 | 0 | 0 | 3060.34 | N | -3060.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3060.34 | 0 | 0 | 3060.34 | 0 | 0 | 0 | 0 | 0 | 0 | -3060.34 | 0 | 0 | 3060.34 | 3060.34 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 47 | 47 | 0 | 47 | CY | 1296 | 0 | 1296 | 0
Y | IPCRP1-0074-1000-E | IPCRP1 | IPCRP1 | 0074-1000 | Excavate & Sheet Pit for Chamber 10A (E10th St) | N | E |  | NR | P | 1530.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1530.91 | 0 | 0 | 1530.91 | 0 | 0 | 0 | Y | 1530.91 | 0 | 0 | 1530.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 47 | 47 | 0 | 47 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0074-1000-L | IPCRP1 | IPCRP1 | 0074-1000 | Excavate & Sheet Pit for Chamber 10A (E10th St) | N | L |  | NR | P | 5441.36 | 39531.83 | 39531.83 | 39531.83 | 39531.83 | 100 | 0 | 0 | 0 | 0 | Y | 39531.83 | Y | -34090.47 | 0 | 0 | 5441.36 | 0 | 0 | 39531.83 | Y | -34090.47 | 0 | 0 | 5441.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39531.83 | 0 | 0 | 39531.83 | 0 | 0 | 0 | 0 | 0 | 0 | -39531.83 | 0 | 0 | 39531.83 | 39531.83 | 0 | 0 | 0 | 44 | 0 | 279 | 279 | 44 | 279 | 0 | 279 | HR | 47 | 47 | 0 | 47 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0074-1000-S | IPCRP1 | IPCRP1 | 0074-1000 | Excavate & Sheet Pit for Chamber 10A (E10th St) | N | S |  | UNIT | A | 0 | 4438.11 | 4438.11 | 4438.11 | 4438.11 | 100 | 0 | 0 | 0 | 0 | N | 4438.11 | N | -4438.11 | 0 | 0 | 0 | 0 | 0 | 4438.11 | N | -4438.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4438.11 | 0 | 0 | 4438.11 | 0 | 0 | 0 | 0 | 0 | 0 | -4438.11 | 0 | 0 | 4438.11 | 4438.11 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 35 | 0 | 35 | NA | 47 | 47 | 0 | 47 | CY | 4438.11 | 0 | 4438.11 | 0
Y | IPCRP1-0074-1010-E | IPCRP1 | IPCRP1 | 0074-1010 | Construct Chamber 10A (E 10th St) | N | E |  | NR | P | 1161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1161 | 0 | 0 | 1161 | 0 | 0 | 0 | Y | 1161 | 0 | 0 | 1161 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1 | 0.99 | 0.01 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0074-1010-L | IPCRP1 | IPCRP1 | 0074-1010 | Construct Chamber 10A (E 10th St) | N | L |  | NR | P | 18535 | 34611.62 | 34611.62 | 34611.62 | 34611.62 | 88.8238 | 0 | 0 | 0 | 4355 | Y | 38966.62 | Y | -20431.62 | 0 | 0 | 18535 | 0 | 0 | 38966.62 | Y | -20431.62 | 0 | 0 | 18535 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -38966.62 | 0 | 0 | 38966.62 | 0 | 0 | 0 | 0 | 0 | 0 | -38966.62 | 0 | 0 | 38966.62 | 38966.62 | 0 | 0 | 0 | 152 | 0 | 300 | 300 | 152 | 266.5 | 33.5 | 300 | HR | 1 | 0.99 | 0.01 | 1 | EA | 0 | 0 | 0 | 4355
Y | IPCRP1-0074-1010-S | IPCRP1 | IPCRP1 | 0074-1010 | Construct Chamber 10A (E 10th St) | N | S |  | UNIT | A | 0 | 250.2 | 250.2 | 250.2 | 250.2 | 100 | 0 | 0 | 0 | 0 | N | 250.2 | N | -250.2 | 0 | 0 | 0 | 0 | 0 | 250.2 | N | -250.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250.2 | 0 | 0 | 250.2 | 0 | 0 | 0 | 0 | 0 | 0 | -250.2 | 0 | 0 | 250.2 | 250.2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 1 | 0.99 | 0.01 | 1 | EA | 250.2 | 0 | 250.2 | 0
Y | IPCRP1-0075-0000-L | IPCRP1 | IPCRP1 | 0075-0000 | CHAMBER NO. 10B | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0075-0000-R | IPCRP1 | IPCRP1 | 0075-0000 | CHAMBER NO. 10B | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 90000 | 0 | 0 | 90000 | 0 | 90000 | 0 | 0 | N | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0075-1000-C | IPCRP1 | IPCRP1 | 0075-1000 | Excavate & Sheet Pit for Chamber 10B (E10th St) | N | C |  | UNIT | U | 0 | 2487.45 | 2487.45 | 2429.41 | 2487.45 | 97.6667 | 0 | 0 | 0 | 0 | N | 2487.45 | N | -2487.45 | 0 | 0 | 0 | 0 | 0 | 2487.45 | N | -2487.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2487.45 | 0 | 0 | 2487.45 | 0 | 0 | 0 | 0 | 0 | 0 | -2487.45 | 0 | 0 | 2487.45 | 2487.45 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 54 | 40.5 | 13.5 | 54 | CY | 712.04 | 58.04 | 654 | 0
Y | IPCRP1-0075-1000-E | IPCRP1 | IPCRP1 | 0075-1000 | Excavate & Sheet Pit for Chamber 10B (E10th St) | N | E |  | NR | P | 1530.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1530.91 | 0 | 0 | 1530.91 | 0 | 0 | 0 | Y | 1530.91 | 0 | 0 | 1530.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 54 | 40.5 | 13.5 | 54 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0075-1000-L | IPCRP1 | IPCRP1 | 0075-1000 | Excavate & Sheet Pit for Chamber 10B (E10th St) | N | L |  | NR | P | 5441.36 | 31589.24 | 31589.24 | 31589.24 | 31589.24 | 63.0139 | 0 | 0 | 0 | 18541.34 | Y | 50130.58 | Y | -44689.22 | 0 | 0 | 5441.36 | 0 | 0 | 50130.58 | Y | -44689.22 | 0 | 0 | 5441.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50130.58 | 0 | 0 | 50130.58 | 0 | 0 | 0 | 0 | 0 | 0 | -50130.58 | 0 | 0 | 50130.58 | 50130.58 | 0 | 0 | 0 | 44 | 0 | 350 | 350 | 44 | 225.5 | 124.5 | 350 | HR | 54 | 40.5 | 13.5 | 54 | CY | 0 | 0 | 0 | 18541.34 | Backfill remains
Y | IPCRP1-0075-1000-S | IPCRP1 | IPCRP1 | 0075-1000 | Excavate & Sheet Pit for Chamber 10B (E10th St) | N | S |  | UNIT | A | 0 | 4644.3 | 4644.3 | 4644.3 | 4644.3 | 100 | 0 | 0 | 0 | 0 | N | 4644.3 | N | -4644.3 | 0 | 0 | 0 | 0 | 0 | 4644.3 | N | -4644.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4644.3 | 0 | 0 | 4644.3 | 0 | 0 | 0 | 0 | 0 | 0 | -4644.3 | 0 | 0 | 4644.3 | 4644.3 | 0 | 0 | 0 | 0 | 0 | 37 | 37 | 0 | 37 | 0 | 37 | NA | 54 | 40.5 | 13.5 | 54 | CY | 4644.3 | 0 | 4644.3 | 0
Y | IPCRP1-0075-1010-E | IPCRP1 | IPCRP1 | 0075-1010 | Construct Chamber 10B (E 10th St) | N | E |  | NR | P | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1419 | 0 | 0 | 1419 | 0 | 0 | 0 | Y | 1419 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SH | 1 | 0.66 | 0.34 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0075-1010-L | IPCRP1 | IPCRP1 | 0075-1010 | Construct Chamber 10B (E 10th St) | N | L |  | NR | P | 22471 | 20816.7 | 20816.7 | 20816.7 | 20816.7 | 77.2495 | 0 | 0 | 0 | 6130.67 | Y | 26947.37 | Y | -4476.37 | 0 | 0 | 22471 | 0 | 0 | 26947.37 | Y | -4476.37 | 0 | 0 | 22471 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26947.37 | 0 | 0 | 26947.37 | 0 | 0 | 0 | 0 | 0 | 0 | -26947.37 | 0 | 0 | 26947.37 | 26947.37 | 0 | 0 | 0 | 184 | 0 | 200 | 200 | 184 | 154.5 | 45.5 | 200 | HR | 1 | 0.66 | 0.34 | 1 | EA | 0 | 0 | 0 | 6130.67 | Chamber 10B (sht 446) is on SB FDR SR, just S of the existing E10th St bridge
Y | IPCRP1-0075-1010-S | IPCRP1 | IPCRP1 | 0075-1010 | Construct Chamber 10B (E 10th St) | N | S |  | UNIT | A | 0 | 1240.84 | 1240.84 | 1240.84 | 1240.84 | 100 | 0 | 0 | 0 | 0 | N | 1240.84 | N | -1240.84 | 0 | 0 | 0 | 0 | 0 | 1240.84 | N | -1240.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1240.84 | 0 | 0 | 1240.84 | 0 | 0 | 0 | 0 | 0 | 0 | -1240.84 | 0 | 0 | 1240.84 | 1240.84 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 10 | NA | 1 | 0.66 | 0.34 | 1 | EA | 1240.84 | 0 | 1240.84 | 0
Y | IPCRP1-0076-0000-L | IPCRP1 | IPCRP1 | 0076-0000 | REGULATOR CHAMBER NO M-25 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0076-0000-R | IPCRP1 | IPCRP1 | 0076-0000 | REGULATOR CHAMBER NO M-25 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750000 | 0 | 0 | 750000 | 0 | 750000 | 750000 | 0 | N | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1000-E | IPCRP1 | IPCRP1 | 0076-1000 | Excavate & Sheet Pit for Reg Chamber M-25 | N | E |  | NR | P | 20897.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20897.91 | 0 | 0 | 20897.91 | 0 | 0 | 0 | Y | 20897.91 | 0 | 0 | 20897.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 355 | 355 | 0 | 355 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1000-L | IPCRP1 | IPCRP1 | 0076-1000 | Excavate & Sheet Pit for Reg Chamber M-25 | N | L |  | NR | P | 43607.4 | 26045.69 | 26045.69 | 26045.69 | 26045.69 | 100 | 0 | 0 | 0 | 0 | Y | 26045.69 | Y | 17561.71 | 0 | 0 | 43607.4 | 0 | 0 | 26045.69 | Y | 17561.71 | 0 | 0 | 43607.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26045.69 | 0 | 0 | 26045.69 | 0 | 0 | 0 | 0 | 0 | 0 | -26045.69 | 0 | 0 | 26045.69 | 26045.69 | 0 | 0 | 0 | 336 | 0 | 181.5 | 181.5 | 336 | 181.5 | 0 | 181.5 | HR | 355 | 355 | 0 | 355 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1000-S | IPCRP1 | IPCRP1 | 0076-1000 | Excavate & Sheet Pit for Reg Chamber M-25 | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 355 | 355 | 0 | 355 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1010-E | IPCRP1 | IPCRP1 | 0076-1010 | Construct Reg Chamber M-25 | N | E |  | NR | P | 3612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3612 | 0 | 0 | 3612 | 0 | 0 | 0 | Y | 3612 | 0 | 0 | 3612 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1010-L | IPCRP1 | IPCRP1 | 0076-1010 | Construct Reg Chamber M-25 | N | L |  | NR | P | 63334.33 | 103165.46 | 103165.46 | 103165.46 | 103165.46 | 100 | 0 | 0 | 0 | 0 | Y | 103165.46 | Y | -39831.13 | 0 | 0 | 63334.33 | 0 | 0 | 103165.46 | Y | -39831.13 | 0 | 0 | 63334.33 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -103165.46 | 0 | 0 | 103165.46 | 0 | 0 | 0 | 0 | 0 | 0 | -103165.46 | 0 | 0 | 103165.46 | 103165.46 | 0 | 0 | 0 | 528 | 0 | 792.5 | 792.5 | 528 | 792.5 | 0 | 792.5 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1010-S | IPCRP1 | IPCRP1 | 0076-1010 | Construct Reg Chamber M-25 | N | S |  | UNIT | A | 0 | 307.14 | 307.14 | 307.14 | 307.14 | 100 | 0 | 0 | 0 | 0 | N | 307.14 | N | -307.14 | 0 | 0 | 0 | 0 | 0 | 307.14 | N | -307.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -307.14 | 0 | 0 | 307.14 | 0 | 0 | 0 | 0 | 0 | 0 | -307.14 | 0 | 0 | 307.14 | 307.14 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 0 | 3 | NA | 1 | 1 | 0 | 1 | EA | 307.14 | 0 | 307.14 | 0
Y | IPCRP1-0076-1020-E | IPCRP1 | IPCRP1 | 0076-1020 | Install Chimneys at Reg Chamber M-25 | N | E |  | NR | P | 2064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2064 | 0 | 0 | 2064 | 0 | 0 | 0 | Y | 2064 | 0 | 0 | 2064 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 3 | 3 | 0 | 3 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1020-L | IPCRP1 | IPCRP1 | 0076-1020 | Install Chimneys at Reg Chamber M-25 | N | L |  | NR | P | 34368.59 | 32322.19 | 32322.19 | 32322.19 | 32322.19 | 100 | 0 | 0 | 0 | 0 | Y | 32322.19 | Y | 2046.4 | 0 | 0 | 34368.59 | 0 | 0 | 32322.19 | Y | 2046.4 | 0 | 0 | 34368.59 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32322.19 | 0 | 0 | 32322.19 | 0 | 0 | 0 | 0 | 0 | 0 | -32322.19 | 0 | 0 | 32322.19 | 32322.19 | 0 | 0 | 0 | 284 | 0 | 263 | 263 | 284 | 263 | 0 | 263 | HR | 3 | 3 | 0 | 3 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1030-E | IPCRP1 | IPCRP1 | 0076-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-25 | N | E |  | NR | P | 2131.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2131.47 | 0 | 0 | 2131.47 | 0 | 0 | 0 | Y | 2131.47 | 0 | 0 | 2131.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0076-1030-L | IPCRP1 | IPCRP1 | 0076-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-25 | N | L |  | NR | P | 17215.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 17215.76 | 0 | 0 | 17215.76 | 0 | 0 | 0 | N | 17215.76 | 0 | 0 | 17215.76 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0077-0000-L | IPCRP1 | IPCRP1 | 0077-0000 | REGULATOR CHAMBER NO M-26 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0077-0000-R | IPCRP1 | IPCRP1 | 0077-0000 | REGULATOR CHAMBER NO M-26 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200000 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | N | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0077-1000-E | IPCRP1 | IPCRP1 | 0077-1000 | Excavate & Sheet Pit for Reg Chamber M-26 | N | E |  | NR | P | 26663.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 26663.88 | 0 | 0 | 26663.88 | 0 | 0 | 0 | N | 26663.88 | 0 | 0 | 26663.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | TN | 520 | 520 | 0 | 520 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0077-1000-L | IPCRP1 | IPCRP1 | 0077-1000 | Excavate & Sheet Pit for Reg Chamber M-26 | N | L |  | NR | P | 58143.21 | 37788.57 | 37788.57 | 37788.57 | 37788.57 | 100 | 0 | 0 | 0 | 0 | Y | 37788.57 | Y | 20354.64 | 0 | 0 | 58143.21 | 0 | 0 | 37788.57 | Y | 20354.64 | 0 | 0 | 58143.21 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37788.57 | 0 | 0 | 37788.57 | 0 | 0 | 0 | 0 | 0 | 0 | -37788.57 | 0 | 0 | 37788.57 | 37788.57 | 0 | 0 | 0 | 448 | 0 | 240 | 240 | 448 | 240 | 0 | 240 | HR | 520 | 520 | 0 | 520 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0077-1000-S | IPCRP1 | IPCRP1 | 0077-1000 | Excavate & Sheet Pit for Reg Chamber M-26 | N | S |  | UNIT | A | 0 | 960 | 960 | 960 | 960 | 100 | 0 | 0 | 0 | 0 | N | 960 | N | -960 | 0 | 0 | 0 | 0 | 0 | 960 | N | -960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -960 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | -960 | 0 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 520 | 520 | 0 | 520 | CY | 960 | 0 | 960 | 0 | KMA CO
Y | IPCRP1-0077-1010-E | IPCRP1 | IPCRP1 | 0077-1010 | Construct Reg Chamber M-26 | N | E |  | NR | P | 6966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6966 | 0 | 0 | 6966 | 0 | 0 | 0 | Y | 6966 | 0 | 0 | 6966 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | TN | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0077-1010-L | IPCRP1 | IPCRP1 | 0077-1010 | Construct Reg Chamber M-26 | N | L |  | NR | P | 114502 | 186269.41 | 186269.41 | 186269.41 | 186269.41 | 100 | 0 | 0 | 0 | 0 | Y | 186269.41 | Y | -71767.41 | 0 | 0 | 114502 | 0 | 0 | 186269.41 | Y | -71767.41 | 0 | 0 | 114502 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -186269.41 | 0 | 0 | 186269.41 | 0 | 0 | 0 | 0 | 0 | 0 | -186269.41 | 0 | 0 | 186269.41 | 186269.41 | 0 | 0 | 0 | 944 | 0 | 1429 | 1429 | 944 | 1429 | 0 | 1429 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 | Change PMF (Labor) from $186,371.19 to $186,269.41 (matching CTD)
Y | IPCRP1-0077-1020-E | IPCRP1 | IPCRP1 | 0077-1020 | Install Chimneys at Reg Chamber M-26 | N | E |  | NR | P | 3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3354 | 0 | 0 | 3354 | 0 | 0 | 0 | Y | 3354 | 0 | 0 | 3354 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0 | As / Nick (7/23) chimney & castings 100% complete
Y | IPCRP1-0077-1020-L | IPCRP1 | IPCRP1 | 0077-1020 | Install Chimneys at Reg Chamber M-26 | N | L |  | NR | P | 56929 | 32056.22 | 32056.22 | 32056.22 | 32056.22 | 100 | 0 | 0 | 0 | 0 | Y | 32056.22 | Y | 24872.78 | 0 | 0 | 56929 | 0 | 0 | 32056.22 | Y | 24872.78 | 0 | 0 | 56929 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32056.22 | 0 | 0 | 32056.22 | 0 | 0 | 0 | 0 | 0 | 0 | -32056.22 | 0 | 0 | 32056.22 | 32056.22 | 0 | 0 | 0 | 472 | 0 | 262 | 262 | 472 | 262 | 0 | 262 | HR | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0 | As / Nick (7/23) chimney & castings 100% complete
Y | IPCRP1-0077-1030-E | IPCRP1 | IPCRP1 | 0077-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-26 | N | E |  | NR | P | 2647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2647 | 0 | 0 | 2647 | 0 | 0 | 0 | Y | 2647 | 0 | 0 | 2647 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0077-1030-L | IPCRP1 | IPCRP1 | 0077-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-26 | N | L |  | NR | P | 25088 | 14249.74 | 14249.74 | 14249.74 | 14249.74 | 100 | 0 | 0 | 0 | 0 | Y | 14249.74 | Y | 10838.26 | 0 | 0 | 25088 | 0 | 0 | 14249.74 | Y | 10838.26 | 0 | 0 | 25088 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14249.74 | 0 | 0 | 14249.74 | 0 | 0 | 0 | 0 | 0 | 0 | -14249.74 | 0 | 0 | 14249.74 | 14249.74 | 0 | 0 | 0 | 200 | 0 | 108.5 | 108.5 | 200 | 108.5 | 0 | 108.5 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0078-0000-L | IPCRP1 | IPCRP1 | 0078-0000 | REGULATOR CHAMBER NO M-28 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0078-0000-R | IPCRP1 | IPCRP1 | 0078-0000 | REGULATOR CHAMBER NO M-28 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 600000 | 0 | 0 | 600000 | 0 | 600000 | 600000 | 0 | N | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0078-1000-E | IPCRP1 | IPCRP1 | 0078-1000 | Excavate & Sheet Pit for Reg Chamber M-28 | N | E |  | NR | P | 9731.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 9731.94 | 0 | 0 | 9731.94 | 0 | 0 | 0 | N | 9731.94 | 0 | 0 | 9731.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 186 | 186 | 0 | 186 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0078-1000-L | IPCRP1 | IPCRP1 | 0078-1000 | Excavate & Sheet Pit for Reg Chamber M-28 | N | L |  | NR | P | 34069.41 | 6144.92 | 6144.92 | 6144.92 | 6144.92 | 100 | 0 | 0 | 0 | 0 | Y | 6144.92 | Y | 27924.49 | 0 | 0 | 34069.41 | 0 | 0 | 6144.92 | Y | 27924.49 | 0 | 0 | 34069.41 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6144.92 | 0 | 0 | 6144.92 | 0 | 0 | 0 | 0 | 0 | 0 | -6144.92 | 0 | 0 | 6144.92 | 6144.92 | 0 | 0 | 0 | 256 | 0 | 46 | 46 | 256 | 46 | 0 | 46 | HR | 186 | 186 | 0 | 186 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0078-1010-E | IPCRP1 | IPCRP1 | 0078-1010 | Construct Reg Chamber M-28 | N | E |  | NR | P | 2580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2580 | 0 | 0 | 2580 | 0 | 0 | 0 | Y | 2580 | 0 | 0 | 2580 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0078-1010-L | IPCRP1 | IPCRP1 | 0078-1010 | Construct Reg Chamber M-28 | N | L |  | NR | P | 42652 | 97891.64 | 97891.64 | 97891.64 | 97891.64 | 100 | 0 | 0 | 0 | 0 | Y | 97891.64 | Y | -55239.64 | 0 | 0 | 42652 | 0 | 0 | 97891.64 | Y | -55239.64 | 0 | 0 | 42652 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -97891.64 | 0 | 0 | 97891.64 | 0 | 0 | 0 | 0 | 0 | 0 | -97891.64 | 0 | 0 | 97891.64 | 97891.64 | 0 | 0 | 0 | 352 | 0 | 728 | 728 | 352 | 728 | 0 | 728 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0078-1010-S | IPCRP1 | IPCRP1 | 0078-1010 | Construct Reg Chamber M-28 | N | S |  | UNIT | A | 0 | 233.7 | 233.7 | 233.7 | 233.7 | 100 | 0 | 0 | 0 | 0 | N | 233.7 | N | -233.7 | 0 | 0 | 0 | 0 | 0 | 233.7 | N | -233.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -233.7 | 0 | 0 | 233.7 | 0 | 0 | 0 | 0 | 0 | 0 | -233.7 | 0 | 0 | 233.7 | 233.7 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 1 | 1 | 0 | 1 | EA | 233.7 | 0 | 233.7 | 0
Y | IPCRP1-0078-1020-E | IPCRP1 | IPCRP1 | 0078-1020 | Install Chimneys at Reg Chamber M-28 | N | E |  | NR | P | 1548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1548 | 0 | 0 | 1548 | 0 | 0 | 0 | N | 1548 | 0 | 0 | 1548 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0078-1020-L | IPCRP1 | IPCRP1 | 0078-1020 | Install Chimneys at Reg Chamber M-28 | N | L |  | NR | P | 26497 | 33225.81 | 33225.81 | 33225.81 | 33225.81 | 100 | 0 | 0 | 0 | 0 | Y | 33225.81 | Y | -6728.81 | 0 | 0 | 26497 | 0 | 0 | 33225.81 | Y | -6728.81 | 0 | 0 | 26497 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -33225.81 | 0 | 0 | 33225.81 | 0 | 0 | 0 | 0 | 0 | 0 | -33225.81 | 0 | 0 | 33225.81 | 33225.81 | 0 | 0 | 0 | 220 | 0 | 239.5 | 239.5 | 220 | 239.5 | 0 | 239.5 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0 | Holding back 15mh/ea for install frames & covers. As / Nick (7/23) castings not complete yet
Y | IPCRP1-0078-1030-E | IPCRP1 | IPCRP1 | 0078-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-28 | N | E |  | NR | P | 1615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1615 | 0 | 0 | 1615 | 0 | 0 | 0 | N | 1615 | 0 | 0 | 1615 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0078-1030-L | IPCRP1 | IPCRP1 | 0078-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-28 | N | L |  | NR | P | 9344 | 258.26 | 258.26 | 258.26 | 258.26 | 100 | 0 | 0 | 0 | 0 | Y | 258.26 | Y | 9085.74 | 0 | 0 | 9344 | 0 | 0 | 258.26 | Y | 9085.74 | 0 | 0 | 9344 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -258.26 | 0 | 0 | 258.26 | 0 | 0 | 0 | 0 | 0 | 0 | -258.26 | 0 | 0 | 258.26 | 258.26 | 0 | 0 | 0 | 72 | 0 | 2 | 2 | 72 | 2 | 0 | 2 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 | Change PMF (MH) from 72.00 to 2.00 (matching CTD), Change PMF (Labor) from $9,344.00 to $258.26 (matching CTD)
Y | IPCRP1-0079-0000-L | IPCRP1 | IPCRP1 | 0079-0000 | REGULATOR CHAMBER NO M-29 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0079-0000-R | IPCRP1 | IPCRP1 | 0079-0000 | REGULATOR CHAMBER NO M-29 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200000 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | N | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0079-1000-E | IPCRP1 | IPCRP1 | 0079-1000 | Excavate & Sheet Pit for Reg Chamber M-29 | N | E |  | NR | P | 34829.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 34829.85 | 0 | 0 | 34829.85 | 0 | 0 | 0 | Y | 34829.85 | 0 | 0 | 34829.85 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 654 | 654 | 0 | 654 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0079-1000-L | IPCRP1 | IPCRP1 | 0079-1000 | Excavate & Sheet Pit for Reg Chamber M-29 | N | L |  | NR | P | 77814.58 | 29997.15 | 29997.15 | 29997.15 | 29997.15 | 100 | 0 | 0 | 0 | 0 | Y | 29997.15 | Y | 47817.43 | 0 | 0 | 77814.58 | 0 | 0 | 29997.15 | Y | 47817.43 | 0 | 0 | 77814.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -29997.15 | 0 | 0 | 29997.15 | 0 | 0 | 0 | 0 | 0 | 0 | -29997.15 | 0 | 0 | 29997.15 | 29997.15 | 0 | 0 | 0 | 600 | 0 | 201.5 | 201.5 | 600 | 201.5 | 0 | 201.5 | HR | 654 | 654 | 0 | 654 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0079-1000-S | IPCRP1 | IPCRP1 | 0079-1000 | Excavate & Sheet Pit for Reg Chamber M-29 | N | S |  | UNIT | A | 0 | 2084.24 | 2084.24 | 2084.24 | 2084.24 | 100 | 0 | 0 | 0 | 0 | N | 2084.24 | N | -2084.24 | 0 | 0 | 0 | 0 | 0 | 2084.24 | N | -2084.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2084.24 | 0 | 0 | 2084.24 | 0 | 0 | 0 | 0 | 0 | 0 | -2084.24 | 0 | 0 | 2084.24 | 2084.24 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 16 | -8 | 8 | NA | 654 | 654 | 0 | 654 | CY | 2084.24 | 0 | 2084.24 | 0
Y | IPCRP1-0079-1010-E | IPCRP1 | IPCRP1 | 0079-1010 | Construct Reg Chamber M-29 | N | E |  | NR | P | 5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5934 | 0 | 0 | 5934 | 0 | 0 | 0 | Y | 5934 | 0 | 0 | 5934 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0079-1010-L | IPCRP1 | IPCRP1 | 0079-1010 | Construct Reg Chamber M-29 | N | L |  | NR | P | 98758 | 184734 | 184734 | 184734 | 184734 | 100 | 0 | 0 | 0 | 0 | Y | 184734 | Y | -85976 | 0 | 0 | 98758 | 0 | 0 | 184734 | Y | -85976 | 0 | 0 | 98758 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -184734 | 0 | 0 | 184734 | 0 | 0 | 0 | 0 | 0 | 0 | -184734 | 0 | 0 | 184734 | 184734 | 0 | 0 | 0 | 816 | 0 | 1434 | 1434 | 816 | 1434 | 0 | 1434 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0079-1020-E | IPCRP1 | IPCRP1 | 0079-1020 | Install Chimneys at Reg Chamber M-29 | N | E |  | NR | P | 2193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2193 | 0 | 0 | 2193 | 0 | 0 | 0 | Y | 2193 | 0 | 0 | 2193 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 5 | 5 | 0 | 5 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0079-1020-L | IPCRP1 | IPCRP1 | 0079-1020 | Install Chimneys at Reg Chamber M-29 | N | L |  | NR | P | 37983 | 31972.88 | 31972.88 | 31972.88 | 31972.88 | 100 | 0 | 0 | 0 | 0 | Y | 31972.88 | Y | 6010.12 | 0 | 0 | 37983 | 0 | 0 | 31972.88 | Y | 6010.12 | 0 | 0 | 37983 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31972.88 | 0 | 0 | 31972.88 | 0 | 0 | 0 | 0 | 0 | 0 | -31972.88 | 0 | 0 | 31972.88 | 31972.88 | 0 | 0 | 0 | 316 | 0 | 231.5 | 231.5 | 316 | 231.5 | 0 | 231.5 | HR | 5 | 5 | 0 | 5 | EA | 0 | 0 | 0 | 0 | Change PMF (MH) from 210.00 to 231.50 (matching CTD), Change PMF (Labor) from $27,001.80 to $31,972.88 (matching CTD) As / Nick (7/23) castings not complete yet
Y | IPCRP1-0079-1030-E | IPCRP1 | IPCRP1 | 0079-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-29 | N | E |  | NR | P | 2131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2131 | 0 | 0 | 2131 | 0 | 0 | 0 | Y | 2131 | 0 | 0 | 2131 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0079-1030-L | IPCRP1 | IPCRP1 | 0079-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-29 | N | L |  | NR | P | 17216 | 20051.04 | 20051.04 | 20051.04 | 20051.04 | 100 | 0 | 0 | 0 | 0 | Y | 20051.04 | Y | -2835.04 | 0 | 0 | 17216 | 0 | 0 | 20051.04 | Y | -2835.04 | 0 | 0 | 17216 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20051.04 | 0 | 0 | 20051.04 | 0 | 0 | 0 | 0 | 0 | 0 | -20051.04 | 0 | 0 | 20051.04 | 20051.04 | 0 | 0 | 0 | 136 | 0 | 155.5 | 155.5 | 136 | 155.5 | 0 | 155.5 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-0000-L | IPCRP1 | IPCRP1 | 0080-0000 | REGULATOR CHAMBER NO M-30 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-0000-R | IPCRP1 | IPCRP1 | 0080-0000 | REGULATOR CHAMBER NO M-30 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200000 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | N | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1000-E | IPCRP1 | IPCRP1 | 0080-1000 | Excavate & Sheet Pit for Reg Chamber M-30 | N | E |  | NR | P | 20897.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 20897.91 | 0 | 0 | 20897.91 | 0 | 0 | 0 | N | 20897.91 | 0 | 0 | 20897.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 347 | 347 | 0 | 347 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1000-L | IPCRP1 | IPCRP1 | 0080-1000 | Excavate & Sheet Pit for Reg Chamber M-30 | N | L |  | NR | P | 46688.75 | 37665.04 | 37665.04 | 37665.04 | 37665.04 | 100 | 0 | 0 | 0 | 0 | Y | 37665.04 | Y | 9023.71 | 0 | 0 | 46688.75 | 0 | 0 | 37665.04 | Y | 9023.71 | 0 | 0 | 46688.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37665.04 | 0 | 0 | 37665.04 | 0 | 0 | 0 | 0 | 0 | 0 | -37665.04 | 0 | 0 | 37665.04 | 37665.04 | 0 | 0 | 0 | 360 | 0 | 300 | 300 | 360 | 300 | 0 | 300 | HR | 347 | 347 | 0 | 347 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1010-E | IPCRP1 | IPCRP1 | 0080-1010 | Construct Reg Chamber M-30 | N | E |  | NR | P | 5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5934 | 0 | 0 | 5934 | 0 | 0 | 0 | Y | 5934 | 0 | 0 | 5934 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1010-L | IPCRP1 | IPCRP1 | 0080-1010 | Construct Reg Chamber M-30 | N | L |  | NR | P | 98758 | 167731.83 | 167731.83 | 167731.83 | 167731.83 | 100 | 0 | 0 | 0 | 0 | Y | 167731.83 | Y | -68973.83 | 0 | 0 | 98758 | 0 | 0 | 167731.83 | Y | -68973.83 | 0 | 0 | 98758 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -167731.83 | 0 | 0 | 167731.83 | 0 | 0 | 0 | 0 | 0 | 0 | -167731.83 | 0 | 0 | 167731.83 | 167731.83 | 0 | 0 | 0 | 816 | 0 | 1292 | 1292 | 816 | 1292 | 0 | 1292 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1010-S | IPCRP1 | IPCRP1 | 0080-1010 | Construct Reg Chamber M-30 | N | S |  | UNIT | A | 0 | 720 | 720 | 720 | 720 | 100 | 0 | 0 | 0 | 0 | N | 720 | N | -720 | 0 | 0 | 0 | 0 | 0 | 720 | N | -720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -720 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | -720 | 0 | 0 | 720 | 720 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 1 | 1 | 0 | 1 | EA | 720 | 0 | 720 | 0
Y | IPCRP1-0080-1020-E | IPCRP1 | IPCRP1 | 0080-1020 | Install Chimneys at Reg Chamber M-30 | N | E |  | NR | P | 2193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2193 | 0 | 0 | 2193 | 0 | 0 | 0 | Y | 2193 | 0 | 0 | 2193 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 5 | 5 | 0 | 5 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1020-L | IPCRP1 | IPCRP1 | 0080-1020 | Install Chimneys at Reg Chamber M-30 | N | L |  | NR | P | 37983 | 16571.74 | 16571.74 | 16571.74 | 16571.74 | 100 | 0 | 0 | 0 | 0 | Y | 16571.74 | Y | 21411.26 | 0 | 0 | 37983 | 0 | 0 | 16571.74 | Y | 21411.26 | 0 | 0 | 37983 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16571.74 | 0 | 0 | 16571.74 | 0 | 0 | 0 | 0 | 0 | 0 | -16571.74 | 0 | 0 | 16571.74 | 16571.74 | 0 | 0 | 0 | 316 | 0 | 127 | 127 | 316 | 127 | 0 | 127 | HR | 5 | 5 | 0 | 5 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1030-E | IPCRP1 | IPCRP1 | 0080-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-30 | N | E |  | NR | P | 2211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2211 | 0 | 0 | 2211 | 0 | 0 | 0 | Y | 2211 | 0 | 0 | 2211 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0080-1030-L | IPCRP1 | IPCRP1 | 0080-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-30 | N | L |  | NR | P | 18423 | 13149.68 | 13149.68 | 13149.68 | 13149.68 | 100 | 0 | 0 | 0 | 0 | Y | 13149.68 | Y | 5273.32 | 0 | 0 | 18423 | 0 | 0 | 13149.68 | Y | 5273.32 | 0 | 0 | 18423 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13149.68 | 0 | 0 | 13149.68 | 0 | 0 | 0 | 0 | 0 | 0 | -13149.68 | 0 | 0 | 13149.68 | 13149.68 | 0 | 0 | 0 | 145.8 | 0 | 98.5 | 98.5 | 145.8 | 98.5 | 0 | 98.5 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0081-0000-L | IPCRP1 | IPCRP1 | 0081-0000 | REGULATOR CHAMBER NO M-31 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0081-0000-R | IPCRP1 | IPCRP1 | 0081-0000 | REGULATOR CHAMBER NO M-31 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 600000 | 0 | 0 | 600000 | 0 | 600000 | 600000 | 0 | N | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0081-1000-E | IPCRP1 | IPCRP1 | 0081-1000 | Excavate & Sheet Pit for Reg Chamber M-31 | N | E |  | NR | P | 9731.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 9731.94 | 0 | 0 | 9731.94 | 0 | 0 | 0 | Y | 9731.94 | 0 | 0 | 9731.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | TN | 243 | 243 | 0 | 243 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0081-1000-L | IPCRP1 | IPCRP1 | 0081-1000 | Excavate & Sheet Pit for Reg Chamber M-31 | N | L |  | NR | P | 34069.41 | 28974.9 | 28974.9 | 28974.9 | 28974.9 | 100 | 0 | 0 | 0 | 0 | Y | 28974.9 | Y | 5094.51 | 0 | 0 | 34069.41 | 0 | 0 | 28974.9 | Y | 5094.51 | 0 | 0 | 34069.41 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28974.9 | 0 | 0 | 28974.9 | 0 | 0 | 0 | 0 | 0 | 0 | -28974.9 | 0 | 0 | 28974.9 | 28974.9 | 0 | 0 | 0 | 256 | 0 | 229 | 229 | 256 | 229 | 0 | 229 | HR | 243 | 243 | 0 | 243 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0081-1000-S | IPCRP1 | IPCRP1 | 0081-1000 | Excavate & Sheet Pit for Reg Chamber M-31 | N | S |  | UNIT | A | 0 | 1756.66 | 1756.66 | 1756.66 | 1756.66 | 100 | 0 | 0 | 0 | 0 | N | 1756.66 | N | -1756.66 | 0 | 0 | 0 | 0 | 0 | 1756.66 | N | -1756.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1756.66 | 0 | 0 | 1756.66 | 0 | 0 | 0 | 0 | 0 | 0 | -1756.66 | 0 | 0 | 1756.66 | 1756.66 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 14 | 0 | 14 | NA | 243 | 243 | 0 | 243 | CY | 1756.66 | 0 | 1756.66 | 0
Y | IPCRP1-0081-1010-E | IPCRP1 | IPCRP1 | 0081-1010 | Construct Reg Chamber M-31 | N | E |  | NR | P | 2580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2580 | 0 | 0 | 2580 | 0 | 0 | 0 | Y | 2580 | 0 | 0 | 2580 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0081-1010-L | IPCRP1 | IPCRP1 | 0081-1010 | Construct Reg Chamber M-31 | N | L |  | NR | P | 42652 | 103648.4 | 103648.4 | 103648.4 | 103648.4 | 100 | 0 | 0 | 0 | 0 | Y | 103648.4 | Y | -60996.4 | 0 | 0 | 42652 | 0 | 0 | 103648.4 | Y | -60996.4 | 0 | 0 | 42652 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -103648.4 | 0 | 0 | 103648.4 | 0 | 0 | 0 | 0 | 0 | 0 | -103648.4 | 0 | 0 | 103648.4 | 103648.4 | 0 | 0 | 0 | 352 | 0 | 772.5 | 772.5 | 352 | 772.5 | 0 | 772.5 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0081-1010-S | IPCRP1 | IPCRP1 | 0081-1010 | Construct Reg Chamber M-31 | N | S |  | UNIT | A | 0 | 3419.03 | 3419.03 | 3419.03 | 3419.03 | 100 | 0 | 0 | 0 | 0 | Y | 3419.03 | Y | -3419.03 | 0 | 0 | 0 | 0 | 0 | 3419.03 | Y | -3419.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3419.03 | 0 | 0 | 3419.03 | 0 | 0 | 0 | 0 | 0 | 0 | -3419.03 | 0 | 0 | 3419.03 | 3419.03 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 27.5 | -20.5 | 7 | NA | 1 | 1 | 0 | 1 | EA | 3419.03 | 0 | 3419.03 | 0
Y | IPCRP1-0081-1020-E | IPCRP1 | IPCRP1 | 0081-1020 | Install Chimneys at Reg Chamber M-31 | N | E |  | NR | P | 1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1613 | 0 | 0 | 1613 | 0 | 0 | 0 | Y | 1613 | 0 | 0 | 1613 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2 | 1.8 | 0.2 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0081-1020-L | IPCRP1 | IPCRP1 | 0081-1020 | Install Chimneys at Reg Chamber M-31 | N | L |  | NR | P | 28304 | 27828.5 | 27828.5 | 27828.5 | 27828.5 | 98.32 | 0 | 0 | 0 | 475.5 | N | 28304 | N | 0 | 0 | 0 | 28304 | 0 | 0 | 28304 | N | 0 | 0 | 0 | 28304 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28304 | 0 | 0 | 28304 | 0 | 0 | 0 | 0 | 0 | 0 | -28304 | 0 | 0 | 28304 | 28304 | 0 | 0 | 0 | 236 | 0 | 236 | 236 | 236 | 193.5 | 42.5 | 236 | HR | 2 | 1.8 | 0.2 | 2 | EA | 0 | 0 | 0 | 475.5 | As / NM (6/16/25) chimneys done, , but still need to be install castings
Y | IPCRP1-0081-1020-S | IPCRP1 | IPCRP1 | 0081-1020 | Install Chimneys at Reg Chamber M-31 | N | S |  | UNIT | A | 0 | 747.52 | 747.52 | 747.52 | 747.52 | 100 | 0 | 0 | 0 | 0 | N | 747.52 | N | -747.52 | 0 | 0 | 0 | 0 | 0 | 747.52 | N | -747.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -747.52 | 0 | 0 | 747.52 | 0 | 0 | 0 | 0 | 0 | 0 | -747.52 | 0 | 0 | 747.52 | 747.52 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 2 | 1.8 | 0.2 | 2 | EA | 747.52 | 0 | 747.52 | 0
Y | IPCRP1-0081-1030-E | IPCRP1 | IPCRP1 | 0081-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-31 | N | E |  | NR | P | 1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1744 | 0 | 0 | 1744 | 0 | 0 | 0 | Y | 1744 | 0 | 0 | 1744 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0081-1030-L | IPCRP1 | IPCRP1 | 0081-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-31 | N | L |  | NR | P | 11312 | 12526.71 | 12526.71 | 12526.71 | 12526.71 | 100 | 0 | 0 | 0 | 0 | Y | 12526.71 | Y | -1214.71 | 0 | 0 | 11312 | 0 | 0 | 12526.71 | Y | -1214.71 | 0 | 0 | 11312 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12526.71 | 0 | 0 | 12526.71 | 0 | 0 | 0 | 0 | 0 | 0 | -12526.71 | 0 | 0 | 12526.71 | 12526.71 | 0 | 0 | 0 | 88 | 0 | 96 | 96 | 88 | 96 | 0 | 96 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0082-0000-L | IPCRP1 | IPCRP1 | 0082-0000 | REGULATOR CHAMBER NO M-32 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0082-0000-R | IPCRP1 | IPCRP1 | 0082-0000 | REGULATOR CHAMBER NO M-32 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200000 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | N | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0082-1000-C | IPCRP1 | IPCRP1 | 0082-1000 | Excavate & Sheet Pit for Reg Chamber M-32 | N | C |  | UNIT | U | 0 | 18499.26 | 18499.26 | 18499.26 | 18499.26 | 100 | 0 | 0 | 0 | 0 | N | 18499.26 | N | -18499.26 | 0 | 0 | 0 | 0 | 0 | 18499.26 | N | -18499.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18499.26 | 0 | 0 | 18499.26 | 0 | 0 | 0 | 0 | 0 | 0 | -18499.26 | 0 | 0 | 18499.26 | 18499.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 430 | 430 | 0 | 430 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0082-1000-E | IPCRP1 | IPCRP1 | 0082-1000 | Excavate & Sheet Pit for Reg Chamber M-32 | N | E |  | NR | P | 24263.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 24263.88 | 0 | 0 | 24263.88 | 0 | 0 | 0 | Y | 24263.88 | 0 | 0 | 24263.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 430 | 430 | 0 | 430 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0082-1000-L | IPCRP1 | IPCRP1 | 0082-1000 | Excavate & Sheet Pit for Reg Chamber M-32 | N | L |  | NR | P | 62251.67 | 80169.15 | 80169.15 | 80169.15 | 80169.15 | 100 | 0 | 0 | 0 | 0 | Y | 80169.15 | Y | -17917.48 | 0 | 0 | 62251.67 | 0 | 0 | 80169.15 | Y | -17917.48 | 0 | 0 | 62251.67 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -80169.15 | 0 | 0 | 80169.15 | 0 | 0 | 0 | 0 | 0 | 0 | -80169.15 | 0 | 0 | 80169.15 | 80169.15 | 0 | 0 | 0 | 480 | 0 | 590 | 590 | 480 | 590 | 0 | 590 | HR | 430 | 430 | 0 | 430 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0082-1000-S | IPCRP1 | IPCRP1 | 0082-1000 | Excavate & Sheet Pit for Reg Chamber M-32 | N | S |  | UNIT | A | 0 | 6950.22 | 6950.22 | 6950.22 | 6950.22 | 100 | 0 | 0 | 0 | 0 | N | 6950.22 | N | -6950.22 | 0 | 0 | 0 | 0 | 0 | 6950.22 | N | -6950.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6950.22 | 0 | 0 | 6950.22 | 0 | 0 | 0 | 0 | 0 | 0 | -6950.22 | 0 | 0 | 6950.22 | 6950.22 | 0 | 0 | 0 | 0 | 0 | 61 | 61 | 0 | 61 | 0 | 61 | NA | 430 | 430 | 0 | 430 | CY | 6950.22 | 0 | 6950.22 | 0
Y | IPCRP1-0082-1010-E | IPCRP1 | IPCRP1 | 0082-1010 | Construct Reg Chamber M-32 | N | E |  | NR | P | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6450 | 0 | 0 | 6450 | 0 | 0 | 0 | Y | 6450 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0082-1010-L | IPCRP1 | IPCRP1 | 0082-1010 | Construct Reg Chamber M-32 | N | L |  | NR | P | 108276 | 246060.93 | 246060.93 | 246060.93 | 246060.93 | 100 | 0 | 0 | 0 | 0.01 | Y | 246060.94 | Y | -137784.94 | 0 | 0 | 108276 | 0 | 0 | 246060.94 | Y | -137784.94 | 0 | 0 | 108276 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -246060.94 | 0 | 0 | 246060.94 | 0 | 0 | 0 | 0 | 0 | 0 | -246060.94 | 0 | 0 | 246060.94 | 246060.94 | 0 | 0 | 0 | 896 | 0 | 1864.5 | 1864.5 | 896 | 1864.5 | 0 | 1864.5 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0.01
Y | IPCRP1-0082-1010-S | IPCRP1 | IPCRP1 | 0082-1010 | Construct Reg Chamber M-32 | N | S |  | UNIT | A | 0 | 2324.51 | 2324.51 | 2324.51 | 2324.51 | 100 | 0 | 0 | 0 | 0 | N | 2324.51 | N | -2324.51 | 0 | 0 | 0 | 0 | 0 | 2324.51 | N | -2324.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2324.51 | 0 | 0 | 2324.51 | 0 | 0 | 0 | 0 | 0 | 0 | -2324.51 | 0 | 0 | 2324.51 | 2324.51 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 20 | 0 | 20 | NA | 1 | 1 | 0 | 1 | EA | 2324.51 | 0 | 2324.51 | 0
Y | IPCRP1-0082-1020-E | IPCRP1 | IPCRP1 | 0082-1020 | Install Chimneys at Reg Chamber M-32 | N | E |  | NR | P | 2193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2193 | 0 | 0 | 2193 | 0 | 0 | 0 | Y | 2193 | 0 | 0 | 2193 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LB | 4 | 1.25 | 2.75 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0082-1020-L | IPCRP1 | IPCRP1 | 0082-1020 | Install Chimneys at Reg Chamber M-32 | N | L |  | NR | P | 37983 | 28819.26 | 28819.26 | 28819.26 | 28819.26 | 75.8741 | 0 | 0 | 0 | 9163.74 | N | 37983 | N | 0 | 0 | 0 | 37983 | 0 | 0 | 37983 | N | 0 | 0 | 0 | 37983 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37983 | 0 | 0 | 37983 | 0 | 0 | 0 | 0 | 0 | 0 | -37983 | 0 | 0 | 37983 | 37983 | 0 | 0 | 0 | 316 | 0 | 316 | 316 | 316 | 225 | 91 | 316 | HR | 4 | 1.25 | 2.75 | 4 | EA | 0 | 0 | 0 | 9163.74
Y | IPCRP1-0082-1030-E | IPCRP1 | IPCRP1 | 0082-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-32 | N | E |  | NR | P | 1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1711 | 0 | 0 | 1711 | 0 | 0 | 0 | Y | 1711 | 0 | 0 | 1711 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0082-1030-L | IPCRP1 | IPCRP1 | 0082-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-32 | N | L |  | NR | P | 18448 | 15723.61 | 15723.61 | 15723.61 | 15723.61 | 100 | 0 | 0 | 0 | 0 | Y | 15723.61 | Y | 2724.39 | 0 | 0 | 18448 | 0 | 0 | 15723.61 | Y | 2724.39 | 0 | 0 | 18448 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15723.61 | 0 | 0 | 15723.61 | 0 | 0 | 0 | 0 | 0 | 0 | -15723.61 | 0 | 0 | 15723.61 | 15723.61 | 0 | 0 | 0 | 148 | 0 | 109 | 109 | 148 | 109 | 0 | 109 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0083-0000-L | IPCRP1 | IPCRP1 | 0083-0000 | REGULATOR CHAMBER NO M-33 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0083-0000-R | IPCRP1 | IPCRP1 | 0083-0000 | REGULATOR CHAMBER NO M-33 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 900000 | 0 | 0 | 900000 | 0 | 900000 | 0 | 0 | N | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1000-C | IPCRP1 | IPCRP1 | 0083-1000 | Excavate & Sheet Pit for Reg Chamber M-33 | N | C |  | UNIT | U | 0 | 6826.39 | 6826.39 | 6826.39 | 6826.39 | 100 | 0 | 0 | 0 | 0 | N | 6826.39 | N | -6826.39 | 0 | 0 | 0 | 0 | 0 | 6826.39 | N | -6826.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6826.39 | 0 | 0 | 6826.39 | 0 | 0 | 0 | 0 | 0 | 0 | -6826.39 | 0 | 0 | 6826.39 | 6826.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 368 | 381 | 0 | 381 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1000-E | IPCRP1 | IPCRP1 | 0083-1000 | Excavate & Sheet Pit for Reg Chamber M-33 | N | E |  | NR | P | 18197.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 18197.91 | 0 | 0 | 18197.91 | 0 | 0 | 0 | Y | 18197.91 | 0 | 0 | 18197.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 368 | 381 | 0 | 381 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1000-L | IPCRP1 | IPCRP1 | 0083-1000 | Excavate & Sheet Pit for Reg Chamber M-33 | N | L |  | NR | P | 46688.75 | 65008.91 | 65008.91 | 65008.91 | 65008.91 | 100 | 0 | 0 | 0 | 0 | Y | 65008.91 | Y | -18320.16 | 0 | 0 | 46688.75 | 0 | 0 | 65008.91 | Y | -18320.16 | 0 | 0 | 46688.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -65008.91 | 0 | 5925.98 | 65008.91 | 0 | 0 | 0 | 0 | 0 | 0 | -65008.91 | 0 | 0 | 65008.91 | 65008.91 | 0 | 0 | 0 | 360 | 0 | 443.5 | 443.5 | 360 | 481 | -37.5 | 443.5 | HR | 368 | 381 | 0 | 381 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1000-S | IPCRP1 | IPCRP1 | 0083-1000 | Excavate & Sheet Pit for Reg Chamber M-33 | N | S |  | UNIT | A | 0 | 6062.33 | 6062.33 | 6062.33 | 6062.33 | 100 | 0 | 0 | 0 | 0 | N | 6062.33 | N | -6062.33 | 0 | 0 | 0 | 0 | 0 | 6062.33 | N | -6062.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6062.33 | 0 | 0 | 6062.33 | 0 | 0 | 0 | 0 | 0 | 0 | -6062.33 | 0 | 0 | 6062.33 | 6062.33 | 0 | 0 | 0 | 0 | 0 | 47.5 | 47.5 | 0 | 47.5 | 0 | 47.5 | NA | 368 | 381 | 0 | 381 | CY | 6062.33 | 0 | 6062.33 | 0
Y | IPCRP1-0083-1010-E | IPCRP1 | IPCRP1 | 0083-1010 | Construct Reg Chamber M-33 | N | E |  | NR | P | 5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5934 | 0 | 0 | 5934 | 0 | 0 | 0 | Y | 5934 | 0 | 0 | 5934 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1010-L | IPCRP1 | IPCRP1 | 0083-1010 | Construct Reg Chamber M-33 | N | L |  | NR | P | 100404 | 181839.89 | 181839.89 | 181839.89 | 181839.89 | 100 | 0 | 0 | 0 | 0 | Y | 181839.89 | Y | -81435.89 | 0 | 0 | 100404 | 0 | 0 | 181839.89 | Y | -81435.89 | 0 | 0 | 100404 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -181839.89 | 0 | 0 | 181839.89 | 0 | 0 | 0 | 0 | 0 | 0 | -181839.89 | 0 | 0 | 181839.89 | 181839.89 | 0 | 0 | 0 | 832 | 0 | 1365 | 1365 | 832 | 1365 | 0 | 1365 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1010-S | IPCRP1 | IPCRP1 | 0083-1010 | Construct Reg Chamber M-33 | N | S |  | UNIT | A | 0 | 3386.33 | 3386.33 | 3386.33 | 3386.33 | 100 | 0 | 0 | 0 | 0 | Y | 3386.33 | Y | -3386.33 | 0 | 0 | 0 | 0 | 0 | 3386.33 | Y | -3386.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3386.33 | 0 | 655.27 | 3386.33 | 0 | 0 | 0 | 0 | 0 | 0 | -3386.33 | 0 | 0 | 3386.33 | 3386.33 | 0 | 0 | 0 | 0 | 0 | 21.5 | 21.5 | 0 | 21.5 | 0 | 21.5 | NA | 1 | 1 | 0 | 1 | EA | 3386.33 | 0 | 3386.33 | 0
Y | IPCRP1-0083-1020-E | IPCRP1 | IPCRP1 | 0083-1020 | Install Chimneys at Reg Chamber M-33 | N | E |  | NR | P | 1903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1903 | 0 | 0 | 1903 | 0 | 0 | 0 | Y | 1903 | 0 | 0 | 1903 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 5 | 3.55 | 1.45 | 5 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1020-L | IPCRP1 | IPCRP1 | 0083-1020 | Install Chimneys at Reg Chamber M-33 | N | L |  | NR | P | 33143 | 47013.22 | 47013.22 | 47013.22 | 47013.22 | 94.0264 | 0 | 0 | 0 | 2986.78 | Y | 50000 | Y | -16857 | 0 | 0 | 33143 | 0 | 0 | 50000 | Y | -16857 | 0 | 0 | 33143 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 7034.8 | 25224.01 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 276 | 0 | 369.66 | 369.66 | 276 | 348.5 | 21.16 | 369.66 | HR | 5 | 3.55 | 1.45 | 5 | EA | 0 | 0 | 0 | 2986.78
N | IPCRP1-0083-1020-S | IPCRP1 | IPCRP1 | 0083-1020 | Install Chimneys at Reg Chamber M-33 | N | S |  | UNIT | A | 0 | 520.38 | 520.38 | 520.38 | 520.38 | 100 | 0 | 0 | 0 | 0 | N | 520.38 | N | -520.38 | 0 | 0 | 0 | 0 | 0 | 520.38 | N | -520.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -520.38 | 258.27 | 262.11 | 520.38 | 0 | 0 | 0 | 0 | 258.27 | 0 | -520.38 | 0 | 0 | 520.38 | 520.38 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | NA | 5 | 3.55 | 1.45 | 5 | EA | 520.38 | 0 | 520.38 | 0
Y | IPCRP1-0083-1030-E | IPCRP1 | IPCRP1 | 0083-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-33 | N | E |  | NR | P | 2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2002 | 0 | 0 | 2002 | 0 | 0 | 0 | Y | 2002 | 0 | 0 | 2002 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 2 | 1.75 | 0.25 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0083-1030-L | IPCRP1 | IPCRP1 | 0083-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-33 | N | L |  | NR | P | 15248 | 10179.56 | 10179.56 | 10179.56 | 10179.56 | 66.76 | 0 | 0 | 0 | 5068.44 | N | 15248 | N | 0 | 0 | 0 | 15248 | 0 | 0 | 15248 | N | 0 | 0 | 0 | 15248 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15248 | 0 | 0 | 15248 | 0 | 0 | 0 | 0 | 0 | 0 | -15248 | 0 | 0 | 15248 | 15248 | 0 | 0 | 0 | 120 | 0 | 120 | 120 | 120 | 75 | 45 | 120 | HR | 2 | 1.75 | 0.25 | 2 | EA | 0 | 0 | 0 | 5068.44
Y | IPCRP1-0084-0000-L | IPCRP1 | IPCRP1 | 0084-0000 | REGULATOR CHAMBER NO M-34 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0084-0000-R | IPCRP1 | IPCRP1 | 0084-0000 | REGULATOR CHAMBER NO M-34 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200000 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | N | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0084-1000-E | IPCRP1 | IPCRP1 | 0084-1000 | Excavate & Sheet Pit for Reg Chamber M-34 | N | E |  | NR | P | 24263.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 24263.88 | 0 | 0 | 24263.88 | 0 | 0 | 0 | Y | 24263.88 | 0 | 0 | 24263.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SH | 455 | 455 | 0 | 455 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0084-1000-L | IPCRP1 | IPCRP1 | 0084-1000 | Excavate & Sheet Pit for Reg Chamber M-34 | N | L |  | NR | P | 62251.67 | 37968.49 | 37968.49 | 37968.49 | 37968.49 | 101.8291 | 0 | 0 | 0 | -682 | Y | 37286.49 | Y | 24965.18 | 0 | 0 | 62251.67 | 0 | 0 | 37286.49 | Y | 24965.18 | 0 | 0 | 62251.67 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37286.49 | 682 | 0 | 37286.49 | 0 | 0 | 0 | 0 | 0 | 0 | -37286.49 | 0 | 0 | 37286.49 | 37286.49 | 0 | 0 | 0 | 480 | 0 | 283.5 | 283.5 | 480 | 294 | -10.5 | 283.5 | HR | 455 | 455 | 0 | 455 | CY | 0 | 0 | 0 | -682
Y | IPCRP1-0084-1000-S | IPCRP1 | IPCRP1 | 0084-1000 | Excavate & Sheet Pit for Reg Chamber M-34 | N | S |  | UNIT | A | 0 | 3942.82 | 3942.82 | 3942.82 | 3942.82 | 100 | 0 | 0 | 0 | 0 | Y | 3942.82 | Y | -3942.82 | 0 | 0 | 0 | 0 | 0 | 3942.82 | Y | -3942.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3942.82 | 0 | 0 | 3942.82 | 0 | 0 | 0 | 0 | 0 | 0 | -3942.82 | 0 | 0 | 3942.82 | 3942.82 | 0 | 0 | 0 | 0 | 0 | 29.5 | 29.5 | 0 | 31.5 | -2 | 29.5 | NA | 455 | 455 | 0 | 455 | CY | 3942.82 | 0 | 3942.82 | 0
Y | IPCRP1-0084-1005-L | IPCRP1 | IPCRP1 | 0084-1005 | Excav Haz Mat Inside Chamber M-34 Area | N | L |  | UNIT | P | 0 | 10264.86 | 10264.86 | 10264.86 | 10264.86 | 100 | 0 | 0 | 0 | 0 | Y | 10264.86 | Y | -10264.86 | 0 | 0 | 0 | 0 | 0 | 10264.86 | Y | -10264.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10264.86 | 0 | 0 | 10264.86 | 0 | 0 | 0 | 0 | 0 | 0 | -10264.86 | 0 | 0 | 10264.86 | 10264.86 | 0 | 0 | 0 | 0 | 0 | 79 | 79 | 0 | 79 | 0 | 79 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0084-1005-S | IPCRP1 | IPCRP1 | 0084-1005 | Excav Haz Mat Inside Chamber M-34 Area | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0084-1010-E | IPCRP1 | IPCRP1 | 0084-1010 | Construct Reg Chamber M-34 | N | E |  | NR | P | 6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6708 | 0 | 0 | 6708 | 0 | 0 | 0 | Y | 6708 | 0 | 0 | 6708 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0084-1010-L | IPCRP1 | IPCRP1 | 0084-1010 | Construct Reg Chamber M-34 | N | L |  | NR | P | 112212 | 195888.87 | 195888.87 | 195888.87 | 195888.87 | 100 | 0 | 0 | 0 | 0.01 | Y | 195888.88 | Y | -83676.88 | 0 | 0 | 112212 | 0 | 0 | 195888.88 | Y | -83676.88 | 0 | 0 | 112212 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -195888.88 | 0 | 0 | 195888.88 | 0 | 0 | 0 | 0 | 0 | 0 | -195888.88 | 0 | 0 | 195888.88 | 195888.88 | 0 | 0 | 0 | 928 | 0 | 1466.5 | 1466.5 | 928 | 1466.5 | 0 | 1466.5 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0.01
Y | IPCRP1-0084-1010-S | IPCRP1 | IPCRP1 | 0084-1010 | Construct Reg Chamber M-34 | N | S |  | UNIT | A | 0 | 498.35 | 498.35 | 498.35 | 498.35 | 100 | 0 | 0 | 0 | 0 | N | 498.35 | N | -498.35 | 0 | 0 | 0 | 0 | 0 | 498.35 | N | -498.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -498.35 | 0 | 0 | 498.35 | 0 | 0 | 0 | 0 | 0 | 0 | -498.35 | 0 | 0 | 498.35 | 498.35 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 1 | 1 | 0 | 1 | EA | 498.35 | 0 | 498.35 | 0
Y | IPCRP1-0084-1020-E | IPCRP1 | IPCRP1 | 0084-1020 | Install Chimneys at Reg Chamber M-34 | N | E |  | NR | P | 2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2548 | 0 | 0 | 2548 | 0 | 0 | 0 | Y | 2548 | 0 | 0 | 2548 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 6 | 5 | 1 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0084-1020-L | IPCRP1 | IPCRP1 | 0084-1020 | Install Chimneys at Reg Chamber M-34 | N | L |  | NR | P | 44218 | 59650.41 | 59650.41 | 59650.41 | 59650.41 | 82.8747 | 0 | 0 | 0 | 12326.25 | Y | 71976.66 | Y | -27758.66 | 0 | 0 | 44218 | 0 | 0 | 71976.66 | Y | -27758.66 | 0 | 0 | 44218 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -71976.66 | 0 | 0 | 71976.66 | 0 | 0 | 0 | 0 | 0 | 0 | -71976.66 | 0 | 0 | 71976.66 | 71976.66 | 0 | 0 | 0 | 368 | 0 | 540 | 540 | 368 | 453.5 | 86.5 | 540 | HR | 6 | 5 | 1 | 6 | EA | 0 | 0 | 0 | 12326.25
Y | IPCRP1-0084-1020-S | IPCRP1 | IPCRP1 | 0084-1020 | Install Chimneys at Reg Chamber M-34 | N | S |  | UNIT | A | 0 | 125.1 | 125.1 | 125.1 | 125.1 | 100 | 0 | 0 | 0 | 0 | N | 125.1 | N | -125.1 | 0 | 0 | 0 | 0 | 0 | 125.1 | N | -125.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -125.1 | 0 | 0 | 125.1 | 0 | 0 | 0 | 0 | 0 | 0 | -125.1 | 0 | 0 | 125.1 | 125.1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 6 | 5 | 1 | 6 | EA | 125.1 | 0 | 125.1 | 0
Y | IPCRP1-0084-1030-E | IPCRP1 | IPCRP1 | 0084-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-34 | N | E |  | NR | P | 2389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2389 | 0 | 0 | 2389 | 0 | 0 | 0 | Y | 2389 | 0 | 0 | 2389 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0084-1030-L | IPCRP1 | IPCRP1 | 0084-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-34 | N | L |  | NR | P | 21152 | 24724.94 | 24724.94 | 24724.94 | 24724.94 | 100 | 0 | 0 | 0 | 0 | Y | 24724.94 | Y | -3572.94 | 0 | 0 | 21152 | 0 | 0 | 24724.94 | Y | -3572.94 | 0 | 0 | 21152 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24724.94 | 0 | 0 | 24724.94 | 0 | 0 | 0 | 0 | 0 | 0 | -24724.94 | 0 | 0 | 24724.94 | 24724.94 | 0 | 0 | 0 | 168 | 0 | 187 | 187 | 168 | 187 | 0 | 187 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-0000-L | IPCRP1 | IPCRP1 | 0085-0000 | REGULATOR CHAMBER NO M-35 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-0000-R | IPCRP1 | IPCRP1 | 0085-0000 | REGULATOR CHAMBER NO M-35 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 1500000 | 1500000 | 0 | N | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1000-C | IPCRP1 | IPCRP1 | 0085-1000 | Excavate & Sheet Pit for Reg Chamber M-35 | N | C |  | UNIT | U | 0 | 5426.41 | 5426.41 | 5426.41 | 5426.41 | 100 | 0 | 0 | 0 | 0 | N | 5426.41 | N | -5426.41 | 0 | 0 | 0 | 0 | 0 | 5426.41 | N | -5426.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5426.41 | 0 | 0 | 5426.41 | 0 | 0 | 0 | 0 | 0 | 0 | -5426.41 | 0 | 0 | 5426.41 | 5426.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 520 | 520 | 0 | 520 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1000-E | IPCRP1 | IPCRP1 | 0085-1000 | Excavate & Sheet Pit for Reg Chamber M-35 | N | E |  | NR | P | 26663.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 26663.88 | 0 | 0 | 26663.88 | 0 | 0 | 0 | Y | 26663.88 | 0 | 0 | 26663.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 520 | 520 | 0 | 520 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1000-L | IPCRP1 | IPCRP1 | 0085-1000 | Excavate & Sheet Pit for Reg Chamber M-35 | N | L |  | NR | P | 58143.21 | 68788.69 | 68788.69 | 68788.69 | 68788.69 | 100 | 0 | 0 | 0 | 0 | Y | 68788.69 | Y | -10645.48 | 0 | 0 | 58143.21 | 0 | 0 | 68788.69 | Y | -10645.48 | 0 | 0 | 58143.21 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -68788.69 | 0 | 0 | 68788.69 | 0 | 0 | 0 | 0 | 0 | 0 | -68788.69 | 0 | 0 | 68788.69 | 68788.69 | 0 | 0 | 0 | 448 | 0 | 513.5 | 513.5 | 448 | 513.5 | 0 | 513.5 | HR | 520 | 520 | 0 | 520 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1000-S | IPCRP1 | IPCRP1 | 0085-1000 | Excavate & Sheet Pit for Reg Chamber M-35 | N | S |  | UNIT | A | 0 | 3321.47 | 3321.47 | 3321.47 | 3321.47 | 100 | 0 | 0 | 0 | 0 | N | 3321.47 | N | -3321.47 | 0 | 0 | 0 | 0 | 0 | 3321.47 | N | -3321.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3321.47 | 0 | 0 | 3321.47 | 0 | 0 | 0 | 0 | 0 | 0 | -3321.47 | 0 | 0 | 3321.47 | 3321.47 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 26 | 0 | 26 | NA | 520 | 520 | 0 | 520 | CY | 3321.47 | 0 | 3321.47 | 0
Y | IPCRP1-0085-1010-E | IPCRP1 | IPCRP1 | 0085-1010 | Construct Reg Chamber M-35 | N | E |  | NR | P | 7482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 7482 | 0 | 0 | 7482 | 0 | 0 | 0 | Y | 7482 | 0 | 0 | 7482 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1010-L | IPCRP1 | IPCRP1 | 0085-1010 | Construct Reg Chamber M-35 | N | L |  | NR | P | 124020 | 220936.07 | 220936.07 | 220936.07 | 220936.07 | 100 | 0 | 0 | 0 | -0.01 | Y | 220936.06 | Y | -96916.06 | 0 | 0 | 124020 | 0 | 0 | 220936.06 | Y | -96916.06 | 0 | 0 | 124020 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -220936.06 | 0 | 0 | 220936.06 | 0 | 0 | 0 | 0 | 0 | 0 | -220936.06 | 0 | 0 | 220936.06 | 220936.06 | 0 | 0 | 0 | 1024 | 0 | 1751 | 1751 | 1024 | 1751 | 0 | 1751 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | -0.01
Y | IPCRP1-0085-1010-S | IPCRP1 | IPCRP1 | 0085-1010 | Construct Reg Chamber M-35 | N | S |  | UNIT | A | 0 | 449.49 | 449.49 | 449.49 | 449.49 | 100 | 0 | 0 | 0 | 0 | N | 449.49 | N | -449.49 | 0 | 0 | 0 | 0 | 0 | 449.49 | N | -449.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -449.49 | 0 | 0 | 449.49 | 0 | 0 | 0 | 0 | 0 | 0 | -449.49 | 0 | 0 | 449.49 | 449.49 | 0 | 0 | 0 | 0 | 0 | 3.5 | 3.5 | 0 | 3.5 | 0 | 3.5 | NA | 1 | 1 | 0 | 1 | EA | 449.49 | 0 | 449.49 | 0
Y | IPCRP1-0085-1020-E | IPCRP1 | IPCRP1 | 0085-1020 | Install Chimneys at Reg Chamber M-35 | N | E |  | NR | P | 2580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2580 | 0 | 0 | 2580 | 0 | 0 | 0 | Y | 2580 | 0 | 0 | 2580 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1020-L | IPCRP1 | IPCRP1 | 0085-1020 | Install Chimneys at Reg Chamber M-35 | N | L |  | NR | P | 45121 | 57079.77 | 57079.77 | 57079.77 | 57079.77 | 100 | 0 | 0 | 0 | 0 | Y | 57079.77 | Y | -11958.77 | 0 | 0 | 45121 | 0 | 0 | 57079.77 | Y | -11958.77 | 0 | 0 | 45121 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -57079.77 | 0 | 0 | 57079.77 | 0 | 0 | 0 | 0 | 0 | 0 | -57079.77 | 0 | 0 | 57079.77 | 57079.77 | 0 | 0 | 0 | 376 | 0 | 413 | 413 | 376 | 413 | 0 | 413 | HR | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1020-S | IPCRP1 | IPCRP1 | 0085-1020 | Install Chimneys at Reg Chamber M-35 | N | S |  | UNIT | A | 0 | 815.48 | 815.48 | 815.48 | 815.48 | 100 | 0 | 0 | 0 | 0 | N | 815.48 | N | -815.48 | 0 | 0 | 0 | 0 | 0 | 815.48 | N | -815.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -815.48 | 0 | 0 | 815.48 | 0 | 0 | 0 | 0 | 0 | 0 | -815.48 | 0 | 0 | 815.48 | 815.48 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | NA | 6 | 6 | 0 | 6 | EA | 815.48 | 0 | 815.48 | 0
Y | IPCRP1-0085-1030-E | IPCRP1 | IPCRP1 | 0085-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-35 | N | E |  | NR | P | 2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2222 | 0 | 0 | 2222 | 0 | 0 | 0 | Y | 2222 | 0 | 0 | 2222 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | BX | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1030-L | IPCRP1 | IPCRP1 | 0085-1030 | Install Pontoon Gates, Stop Planks/ Guides, M-35 | N | L |  | NR | P | 18593 | 14450.56 | 14450.56 | 14450.56 | 14450.56 | 77.7204 | 0 | 0 | 0 | 4142.44 | N | 18593 | N | 0 | 0 | 0 | 18593 | 0 | 0 | 18593 | N | 0 | 0 | 0 | 18593 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18593 | 0 | 0 | 18593 | 0 | 0 | 0 | 0 | 0 | 0 | -18593 | 0 | 0 | 18593 | 18593 | 0 | 0 | 0 | 147.2 | 0 | 147.2 | 147.2 | 147.2 | 119.5 | 27.7 | 147.2 | HR | 2 | 2 | 0 | 2 | EA | 0 | 0 | 0 | 4142.44
Y | IPCRP1-0085-1040-L | IPCRP1 | IPCRP1 | 0085-1040 | PM - Pontoon (Tide) Gates for Reg Chambers | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 17 | 17 | 0 | 17 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1040-M | IPCRP1 | IPCRP1 | 0085-1040 | PM - Pontoon (Tide) Gates for Reg Chambers | N | M |  | NR | P | 340000 | 357451.14 | 357451.14 | 357152.94 | 357451.14 | 99.9166 | 0 | 0 | 0 | 0 | Y | 357451.14 | Y | -17451.14 | 0 | 0 | 340000 | 0 | 0 | 357451.14 | Y | -17451.14 | 0 | 0 | 340000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -357451.14 | 0 | 0 | 357451.14 | 0 | 0 | 0 | 0 | 0 | 0 | -357451.14 | 0 | 0 | 357451.14 | 357451.14 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 19 | -2 | 17 | LF | 17 | 17 | 0 | 17 | EA | 357451.14 | 298.2 | 357152.94 | 0 | Rodney Hunt commitment under this code is $353,793
Y | IPCRP1-0085-1050-L | IPCRP1 | IPCRP1 | 0085-1050 | PM - Stop Plank Guides for Reg Chambers | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 313 | 313 | 0 | 313 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1050-M | IPCRP1 | IPCRP1 | 0085-1050 | PM - Stop Plank Guides for Reg Chambers | N | M |  | NR | P | 39125 | 132395.51 | 132395.51 | 122675.5 | 132395.51 | 92.6584 | 0 | 0 | 0 | 0 | Y | 132395.51 | Y | -93270.51 | 0 | 0 | 39125 | 0 | 0 | 132395.51 | Y | -93270.51 | 0 | 0 | 39125 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -132395.51 | 0 | 0 | 132395.51 | 0 | 0 | 0 | 0 | 0 | 0 | -132395.51 | 0 | 0 | 132395.51 | 132395.51 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 53 | -53 | 0 | EA | 313 | 313 | 0 | 313 | LF | 132395.51 | 9720.01 | 122675.5 | 0 | CAMPBELL FOUNDRY @$40,042.80
Y | IPCRP1-0085-1060-L | IPCRP1 | IPCRP1 | 0085-1060 | PM - Timber Stop Logs for Reg Chambers | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 758 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Note on all Chamber contract drawings state "Stop Logs not included in this contract, to be procured separately". Removing PMF, as we do not furnish these.
Y | IPCRP1-0085-1060-M | IPCRP1 | IPCRP1 | 0085-1060 | PM - Timber Stop Logs for Reg Chambers | N | M |  | NR | P | 41249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 41249 | 0 | 0 | 41249 | 0 | 0 | 0 | Y | 41249 | 0 | 0 | 41249 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 758 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1070-L | IPCRP1 | IPCRP1 | 0085-1070 | PM - Slide Gates for Reg Chambers (all sizes) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0085-1070-M | IPCRP1 | IPCRP1 | 0085-1070 | PM - Slide Gates for Reg Chambers (all sizes) | N | M |  | NR | P | 83000 | 34734.06 | 34734.06 | 34734.06 | 34734.06 | 100 | 0 | 0 | 0 | 0 | Y | 34734.06 | Y | 48265.94 | 0 | 0 | 83000 | 0 | 0 | 34734.06 | Y | 48265.94 | 0 | 0 | 83000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -34734.06 | 0 | 1800 | 34734.06 | 0 | 0 | 0 | 0 | 0 | 0 | -34734.06 | 0 | 0 | 34734.06 | 34734.06 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9 | -9 | 0 | SF | 6 | 6 | 0 | 6 | EA | 34734.06 | 0 | 34734.06 | 0 | RODNEY HUNT Base PO@$373,977.00
Y | IPCRP1-0086-0000-L | IPCRP1 | IPCRP1 | 0086-0000 | STAND 6ft-0 DIA PC MANHOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0086-0000-R | IPCRP1 | IPCRP1 | 0086-0000 | STAND 6ft-0 DIA PC MANHOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 480000 | 0 | 0 | 480000 | 0 | 480000 | 480000 | 0 | N | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0086-1000-E | IPCRP1 | IPCRP1 | 0086-1000 | Construct 6ft-0 Dia PC Manholes | N | E |  | NR | P | 19919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 19919 | 0 | 0 | 19919 | 0 | 0 | 0 | Y | 19919 | 0 | 0 | 19919 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 12 | 11.6 | 0.4 | 12 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0086-1000-L | IPCRP1 | IPCRP1 | 0086-1000 | Construct 6ft-0 Dia PC Manholes | N | L |  | NR | P | 98789 | 97746.33 | 97746.33 | 97746.33 | 97746.33 | 91.3517 | 0 | 0 | 0 | 9253.67 | Y | 107000 | Y | -8211 | 0 | 0 | 98789 | 0 | 0 | 107000 | Y | -8211 | 0 | 0 | 98789 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -107000 | 0 | 0 | 107000 | 0 | 0 | 0 | 0 | 0 | 0 | -107000 | 0 | 0 | 107000 | 107000 | 0 | 0 | 0 | 816 | 0 | 816 | 816 | 816 | 747.5 | 68.5 | 816 | HR | 12 | 11.6 | 0.4 | 12 | EA | 0 | 0 | 0 | 9253.67
Y | IPCRP1-0086-1000-S | IPCRP1 | IPCRP1 | 0086-1000 | Construct 6ft-0 Dia PC Manholes | N | S |  | UNIT | A | 0 | 1377.35 | 1377.35 | 1377.35 | 1377.35 | 100 | 0 | 0 | 0 | 0 | N | 1377.35 | N | -1377.35 | 0 | 0 | 0 | 0 | 0 | 1377.35 | N | -1377.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1377.35 | 0 | 0 | 1377.35 | 0 | 0 | 0 | 0 | 0 | 0 | -1377.35 | 0 | 0 | 1377.35 | 1377.35 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 11 | 0 | 11 | NA | 12 | 11.6 | 0.4 | 12 | EA | 1377.35 | 0 | 1377.35 | 0
Y | IPCRP1-0087-0000-L | IPCRP1 | IPCRP1 | 0087-0000 | STAND 8 ft-0 DIA PC MANHOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0087-0000-R | IPCRP1 | IPCRP1 | 0087-0000 | STAND 8 ft-0 DIA PC MANHOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 375000 | 0 | 0 | 375000 | 0 | 375000 | 450000 | 0 | N | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0087-1000-C | IPCRP1 | IPCRP1 | 0087-1000 | Construct 8 ft-0 Dia PC Manholes | N | C |  | UNIT | U | 0 | 4986.7 | 4986.7 | 4986.7 | 4986.7 | 100 | 0 | 0 | 0 | 0 | N | 4986.7 | N | -4986.7 | 0 | 0 | 0 | 0 | 0 | 4986.7 | N | -4986.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4986.7 | 0 | 0 | 4986.7 | 0 | 0 | 0 | 0 | 0 | 0 | -4986.7 | 0 | 0 | 4986.7 | 4986.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 5 | 5.9 | 0.1 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0087-1000-E | IPCRP1 | IPCRP1 | 0087-1000 | Construct 8 ft-0 Dia PC Manholes | N | E |  | NR | P | 23580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 23580 | 0 | 0 | 23580 | 0 | 0 | 0 | N | 23580 | 0 | 0 | 23580 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 5 | 5.9 | 0.1 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0087-1000-L | IPCRP1 | IPCRP1 | 0087-1000 | Construct 8 ft-0 Dia PC Manholes | N | L |  | NR | P | 86045 | 277954.1 | 277954.1 | 277954.1 | 277954.1 | 96.2983 | 0 | 0 | 0 | 10684.4 | Y | 288638.5 | Y | -202593.5 | 0 | 0 | 86045 | 0 | 0 | 288638.5 | Y | -202593.5 | 0 | 0 | 86045 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -288638.5 | 0 | 0 | 288638.5 | 0 | 0 | 0 | 0 | 0 | 0 | -288638.5 | 0 | 0 | 288638.5 | 288638.5 | 0 | 0 | 0 | 680 | 0 | 2220 | 2220 | 680 | 2191.5 | 28.5 | 2220 | HR | 5 | 5.9 | 0.1 | 6 | EA | 0 | 0 | 0 | 10684.4 | As / NM (9/30) - we have 2 F&C left to set to grade
Y | IPCRP1-0088-0000-L | IPCRP1 | IPCRP1 | 0088-0000 | DIVERSION CHAMBER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0088-0000-R | IPCRP1 | IPCRP1 | 0088-0000 | DIVERSION CHAMBER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2240000 | 0 | 0 | 2240000 | 0 | 2240000 | 2240000 | 0 | N | 2240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0088-1000-C | IPCRP1 | IPCRP1 | 0088-1000 | Excavate & Sheet Pit for Diversion Chamber | N | C |  | UNIT | U | 0 | 15224.15 | 15224.15 | 15224.14 | 15224.15 | 99.9999 | 0 | 0 | 0 | 0 | Y | 15224.15 | Y | -15224.15 | 0 | 0 | 0 | 0 | 0 | 15224.15 | Y | -15224.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15224.15 | 0 | 0 | 15224.15 | 0 | 0 | 0 | 0 | 0 | 0 | -15224.15 | 0 | 0 | 15224.15 | 15224.15 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 1000 | 0 | 1000 | NA | 1152 | 1240.5 | 7.5 | 1248 | CY | 7774.77 | 0.01 | 7774.76 | 0
Y | IPCRP1-0088-1000-E | IPCRP1 | IPCRP1 | 0088-1000 | Excavate & Sheet Pit for Diversion Chamber | N | E |  | NR | P | 18370.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 18370.8 | 0 | 0 | 18370.8 | 0 | 0 | 0 | Y | 18370.8 | 0 | 0 | 18370.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1152 | 1240.5 | 7.5 | 1248 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0088-1000-L | IPCRP1 | IPCRP1 | 0088-1000 | Excavate & Sheet Pit for Diversion Chamber | N | L |  | NR | P | 65296.24 | 104757.37 | 104757.37 | 104757.37 | 104757.37 | 97.9041 | 0 | 0 | 0 | 2242.63 | Y | 107000 | Y | -41703.76 | 0 | 0 | 65296.24 | 0 | 0 | 107000 | Y | -41703.76 | 0 | 0 | 65296.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -107000 | 0 | 5929.97 | 107000 | 0 | 0 | 0 | 0 | 0 | 0 | -107000 | 0 | 0 | 107000 | 107000 | 0 | 0 | 0 | 528 | 0 | 779.74 | 779.74 | 528 | 763.5 | 16.24 | 779.74 | HR | 1152 | 1240.5 | 7.5 | 1248 | CY | 0 | 0 | 0 | 2242.63 | Added 1 DC not shown on plans (MH-G01A) to connect new 3'x5.5' box sewer to exist 6'x4.6' sewer. Add 96cy. 1,152 / 12ea = 96 CY per location As/ MN (9/30) H01 left to excavate, H07 left to backfill. Claim 75%/25%
Y | IPCRP1-0088-1000-S | IPCRP1 | IPCRP1 | 0088-1000 | Excavate & Sheet Pit for Diversion Chamber | N | S |  | UNIT | A | 0 | 7028.48 | 7028.48 | 7028.48 | 7028.48 | 107.9322 | 0 | 0 | 0 | -516.54 | Y | 6511.94 | Y | -6511.94 | 0 | 0 | 0 | 0 | 0 | 6511.94 | Y | -6511.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6511.94 | 516.54 | 0 | 6511.94 | 0 | 0 | 0 | 0 | 516.54 | 0 | -6511.94 | 0 | 0 | 6511.94 | 6511.94 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 53 | -21 | 32 | NA | 1152 | 1240.5 | 7.5 | 1248 | CY | 7028.48 | 0 | 7028.48 | -516.54
Y | IPCRP1-0088-1010-E | IPCRP1 | IPCRP1 | 0088-1010 | Construct Diversion Chamber | N | E |  | NR | P | 33851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 33851 | 0 | 0 | 33851 | 0 | 0 | 0 | Y | 33851 | 0 | 0 | 33851 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SH | 12 | 12.46 | 0.54 | 13 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0088-1010-L | IPCRP1 | IPCRP1 | 0088-1010 | Construct Diversion Chamber | N | L |  | NR | P | 311332 | 430044.27 | 430044.27 | 430044.27 | 430044.27 | 97.6792 | 0 | 0 | 0 | 10217.72 | Y | 440261.99 | Y | -128929.99 | 0 | 0 | 311332 | 0 | 0 | 440261.99 | Y | -128929.99 | 0 | 0 | 311332 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -440261.99 | 1741.76 | 37603.99 | 440261.99 | 0 | 0 | 0 | 0 | 0 | 0 | -440261.99 | 0 | 0 | 440261.99 | 440261.99 | 0 | 0 | 0 | 2544 | 0 | 3380.01 | 3380.01 | 2544 | 3313.5 | 66.51 | 3380.01 | HR | 12 | 12.46 | 0.54 | 13 | EA | 0 | 0 | 0 | 10217.72 | Nick M (3/20) we have built 8ea DC to date. We are holding back 15% for setting castings to final elevation. Added 1 DC not shown on plans (MH-G01A) to connect new 3'x5.5' box sewer to exist 6'x4.6' sewer. Add 1.00ea
Y | IPCRP1-0088-1010-S | IPCRP1 | IPCRP1 | 0088-1010 | Construct Diversion Chamber | N | S |  | UNIT | A | 0 | 3114.01 | 3114.01 | 3114.01 | 3114.01 | 106.6329 | 0 | 0 | 0 | -193.7 | Y | 2920.31 | Y | -2920.31 | 0 | 0 | 0 | 0 | 0 | 2920.31 | Y | -2920.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2920.31 | 193.7 | 0 | 2920.31 | 0 | 0 | 0 | 0 | 193.7 | 0 | -2920.31 | 0 | 0 | 2920.31 | 2920.31 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 24 | -16 | 8 | NA | 12 | 12.46 | 0.54 | 13 | EA | 3114.01 | 0 | 3114.01 | -193.7
Y | IPCRP1-0088-1020-C | IPCRP1 | IPCRP1 | 0088-1020 | Excavate & Sheet Pits for Junct Chamb D01 & G01 | N | C |  | UNIT | U | 0 | 6472.7 | 6472.7 | 6449.62 | 6472.7 | 100 | 0 | 0 | 0 | -23.08 | Y | 6449.62 | Y | -6449.62 | 0 | 0 | 0 | 0 | 0 | 6449.62 | Y | -6449.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6449.62 | 0 | 0 | 6449.62 | 0 | 0 | 0 | 0 | 0 | 0 | -6449.62 | 0 | 0 | 6449.62 | 6449.62 | 0 | 0 | 0 | 0 | 0 | 1303 | 1303 | 0 | 1303 | 0 | 1303 | NA | 552 | 552 | 0 | 552 | CY | 2944.02 | 23.08 | 2920.94 | -23.08
Y | IPCRP1-0088-1020-E | IPCRP1 | IPCRP1 | 0088-1020 | Excavate & Sheet Pits for Junct Chamb D01 & G01 | N | E |  | NR | P | 32796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 32796 | 0 | 0 | 32796 | 0 | 0 | 0 | Y | 32796 | 0 | 0 | 32796 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 552 | 552 | 0 | 552 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0088-1020-L | IPCRP1 | IPCRP1 | 0088-1020 | Excavate & Sheet Pits for Junct Chamb D01 & G01 | N | L |  | NR | P | 93378 | 61175.79 | 61175.79 | 61175.79 | 61175.79 | 100 | 0 | 0 | 0 | 0 | Y | 61175.79 | Y | 32202.21 | 0 | 0 | 93378 | 0 | 0 | 61175.79 | Y | 32202.21 | 0 | 0 | 93378 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -61175.79 | 0 | 0 | 61175.79 | 0 | 0 | 0 | 0 | 0 | 0 | -61175.79 | 0 | 0 | 61175.79 | 61175.79 | 0 | 0 | 0 | 720 | 0 | 465 | 465 | 720 | 465 | 0 | 465 | HR | 552 | 552 | 0 | 552 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0088-1020-S | IPCRP1 | IPCRP1 | 0088-1020 | Excavate & Sheet Pits for Junct Chamb D01 & G01 | N | S |  | UNIT | A | 0 | 3491.33 | 3491.33 | 3491.33 | 3491.33 | 100 | 0 | 0 | 0 | 0 | Y | 3491.33 | Y | -3491.33 | 0 | 0 | 0 | 0 | 0 | 3491.33 | Y | -3491.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3491.33 | 0 | 131.05 | 3491.33 | 0 | 0 | 0 | 0 | 0 | 0 | -3491.33 | 0 | 0 | 3491.33 | 3491.33 | 0 | 0 | 0 | 0 | 0 | 26.5 | 26.5 | 0 | 26.5 | 0 | 26.5 | NA | 552 | 552 | 0 | 552 | CY | 3491.33 | 0 | 3491.33 | 0
Y | IPCRP1-0088-1030-E | IPCRP1 | IPCRP1 | 0088-1030 | Constuct Junction Chambers, D01 & G01 | N | E |  | NR | P | 10320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 10320 | 0 | 0 | 10320 | 0 | 0 | 0 | Y | 10320 | 0 | 0 | 10320 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 2 | 1.75 | 0.25 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0088-1030-L | IPCRP1 | IPCRP1 | 0088-1030 | Constuct Junction Chambers, D01 & G01 | N | L |  | NR | P | 135439 | 289518.43 | 289518.43 | 289518.43 | 289518.43 | 97.3929 | 0 | 0 | 0 | 7750.01 | Y | 297268.44 | Y | -161829.44 | 0 | 0 | 135439 | 0 | 0 | 297268.44 | Y | -161829.44 | 0 | 0 | 135439 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -297268.44 | 0 | 0 | 297268.44 | 0 | 0 | 0 | 0 | 0 | 0 | -297268.44 | 0 | 0 | 297268.44 | 297268.44 | 0 | 0 | 0 | 1128 | 0 | 2200 | 2200 | 1128 | 2169 | 31 | 2200 | HR | 2 | 1.75 | 0.25 | 2 | EA | 0 | 0 | 0 | 7750.01 | As / NM (6/16/25) 99% done. Casting left to install at G01
Y | IPCRP1-0089-0000-L | IPCRP1 | IPCRP1 | 0089-0000 | CLEANOUT MANHOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0089-0000-R | IPCRP1 | IPCRP1 | 0089-0000 | CLEANOUT MANHOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 325000 | 0 | 0 | 325000 | 0 | 325000 | 425000 | 0 | N | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0090-0000-L | IPCRP1 | IPCRP1 | 0090-0000 | SPECIAL MH B-14 ON EXIST & NEW SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0090-0000-R | IPCRP1 | IPCRP1 | 0090-0000 | SPECIAL MH B-14 ON EXIST & NEW SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25000 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | N | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0091-0000-L | IPCRP1 | IPCRP1 | 0091-0000 | STAND MH TYPE A-2 ON 24 in R.C.P. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0091-0000-R | IPCRP1 | IPCRP1 | 0091-0000 | STAND MH TYPE A-2 ON 24 in R.C.P. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50000 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | N | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0092-0000-L | IPCRP1 | IPCRP1 | 0092-0000 | STAND MH TYPE B-2 ON 30 in R.C.P. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0092-0000-R | IPCRP1 | IPCRP1 | 0092-0000 | STAND MH TYPE B-2 ON 30 in R.C.P. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25000 | 0 | 0 | 25000 | 0 | 25000 | 25000 | 0 | N | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0093-0000-L | IPCRP1 | IPCRP1 | 0093-0000 | STAND MH TYPE C-1 ON 36 in R.C.P. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0093-0000-R | IPCRP1 | IPCRP1 | 0093-0000 | STAND MH TYPE C-1 ON 36 in R.C.P. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 28000 | 0 | 0 | 28000 | 0 | 28000 | 28000 | 0 | N | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0094-0000-L | IPCRP1 | IPCRP1 | 0094-0000 | STAND MH TYPE C-1 ON 42 in D.I.P. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0094-0000-R | IPCRP1 | IPCRP1 | 0094-0000 | STAND MH TYPE C-1 ON 42 in D.I.P. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 15000 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0095-0000-L | IPCRP1 | IPCRP1 | 0095-0000 | STAND MH TYPE C-2 ON 36 in R.C.P. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0095-0000-R | IPCRP1 | IPCRP1 | 0095-0000 | STAND MH TYPE C-2 ON 36 in R.C.P. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35000 | 0 | 0 | 35000 | 0 | 35000 | 35000 | 0 | N | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0096-0000-L | IPCRP1 | IPCRP1 | 0096-0000 | STAND MH TYPE C-2 ON 48 in WIDE F.T.R.C. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0096-0000-R | IPCRP1 | IPCRP1 | 0096-0000 | STAND MH TYPE C-2 ON 48 in WIDE F.T.R.C. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35000 | 0 | 0 | 35000 | 0 | 35000 | 105000 | 0 | N | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0097-0000-L | IPCRP1 | IPCRP1 | 0097-0000 | STAND MH TYPE C-2 ON 60 in WIDE F.T.R.C. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0097-0000-R | IPCRP1 | IPCRP1 | 0097-0000 | STAND MH TYPE C-2 ON 60 in WIDE F.T.R.C. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35000 | 0 | 0 | 35000 | 0 | 35000 | 35000 | 0 | N | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0098-0000-L | IPCRP1 | IPCRP1 | 0098-0000 | STAND MH TYPE D-2 ON 84 in WIDE F.T.R.C. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0098-0000-R | IPCRP1 | IPCRP1 | 0098-0000 | STAND MH TYPE D-2 ON 84 in WIDE F.T.R.C. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35000 | 0 | 0 | 35000 | 0 | 35000 | 0 | 0 | N | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0099-0000-L | IPCRP1 | IPCRP1 | 0099-0000 | STAND MH TYPE D-2 ON 96 in WIDE F.T.R.C. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0099-0000-R | IPCRP1 | IPCRP1 | 0099-0000 | STAND MH TYPE D-2 ON 96 in WIDE F.T.R.C. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 75000 | 0 | 0 | 75000 | 0 | 75000 | 75000 | 0 | N | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0100-0000-L | IPCRP1 | IPCRP1 | 0100-0000 | STAND MH TYPE E-2 ON 120 in WIDE F.T.R.C. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0100-0000-R | IPCRP1 | IPCRP1 | 0100-0000 | STAND MH TYPE E-2 ON 120 in WIDE F.T.R.C. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0101-0000-L | IPCRP1 | IPCRP1 | 0101-0000 | STAND MH TYPE E-2 ON 132 in WIDE F.T.R.C. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0101-0000-R | IPCRP1 | IPCRP1 | 0101-0000 | STAND MH TYPE E-2 ON 132 in WIDE F.T.R.C. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0102-0000-L | IPCRP1 | IPCRP1 | 0102-0000 | STAND MH TYPE E-2 ON 144 in WIDE F.T.R.C. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0102-0000-R | IPCRP1 | IPCRP1 | 0102-0000 | STAND MH TYPE E-2 ON 144 in WIDE F.T.R.C. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 120000 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0102-1000-E | IPCRP1 | IPCRP1 | 0102-1000 | Install Cleanout, Special & All Stand Type MH | N | E |  | NR | P | 45266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 45266 | 0 | 0 | 45266 | 0 | 0 | 0 | Y | 45266 | 0 | 0 | 45266 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 34 | 18.9 | 4.1 | 23 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0102-1000-L | IPCRP1 | IPCRP1 | 0102-1000 | Install Cleanout, Special & All Stand Type MH | N | L |  | NR | P | 219166 | 235927.7 | 235927.7 | 235927.7 | 235927.7 | 90.6158 | 0 | 0 | 0 | 24432.64 | Y | 260360.34 | Y | -41194.34 | 0 | 0 | 219166 | 0 | 0 | 260360.34 | Y | -41194.34 | 0 | 0 | 219166 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -260360.34 | 0 | 20828.13 | 260360.34 | 0 | 0 | 0 | 0 | 0 | 0 | -260360.34 | 0 | 0 | 260360.34 | 260360.34 | 0 | 0 | 0 | 1804 | 0 | 2069.96 | 2069.96 | 1804 | 1835 | 234.96 | 2069.96 | HR | 34 | 18.9 | 4.1 | 23 | EA | 0 | 0 | 0 | 24432.64 | 3. Add 2ea Type C-2 MH at E10th St, as/ ZD-BS exchange to avoid utility interference by installing 4'x4' Sewer in lieu of 42" DIP, with MH at each end. Thru 8/31/25, Akela QTD = 16ea, IPC QTD = 16ea, DDC QTD = 32ea. 1. Quantity increased by 31ea (from 13ea to 44ea) for Cleanout Manholes, increasing overall cc quantity from 34 to 65ea. Subcontractor (Akela) will be doing 44 cleanout manholes, cost to be included in Akela cost code (0832-1000). 2. Cost included above are for remaining 21ea self-performed Special, and Standard Type MH. 3. Add 2ea Type C-2 MH at E10th St, as/ ZD-BS exchange to avoid utility interference by installing 4'x4' Sewer in lieu of 42" DIP, with MH at each end. 4. Thru 9/30/24, Akela QTD = 3ea, IPC QTD = 7ea, DDC QTD = 10ea.
Y | IPCRP1-0102-1000-S | IPCRP1 | IPCRP1 | 0102-1000 | Install Cleanout, Special & All Stand Type MH | N | S |  | UNIT | A | 0 | 1215.53 | 1215.53 | 1215.53 | 1215.53 | 100 | 0 | 0 | 0 | 0 | N | 1215.53 | N | -1215.53 | 0 | 0 | 0 | 0 | 0 | 1215.53 | N | -1215.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1215.53 | 0 | 0 | 1215.53 | 0 | 0 | 0 | 0 | 0 | 0 | -1215.53 | 0 | 0 | 1215.53 | 1215.53 | 0 | 0 | 0 | 0 | 0 | 9.5 | 9.5 | 0 | 9.5 | 0 | 9.5 | NA | 34 | 18.9 | 4.1 | 23 | EA | 1215.53 | 0 | 1215.53 | 0
Y | IPCRP1-0103-0000-L | IPCRP1 | IPCRP1 | 0103-0000 | RECONST EXIST MH ON EXIST SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0103-0000-R | IPCRP1 | IPCRP1 | 0103-0000 | RECONST EXIST MH ON EXIST SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 90000 | 0 | 0 | 90000 | 0 | 90000 | 0 | 0 | N | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0103-1000-E | IPCRP1 | IPCRP1 | 0103-1000 | RECONST EXIST MH ON EXIST SEWER | N | E |  | NR | P | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | Y | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 18 | 0 | 18 | 18 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0103-1000-L | IPCRP1 | IPCRP1 | 0103-1000 | RECONST EXIST MH ON EXIST SEWER | N | L |  | NR | P | 47155.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47155.26 | N | 47155.26 | N | 0 | 0 | 0 | 47155.26 | 0 | 0 | 47155.26 | N | 0 | 0 | 0 | 47155.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -47155.26 | 0 | 0 | 47155.26 | 0 | 0 | 0 | 0 | 0 | 0 | -47155.26 | 0 | 0 | 47155.26 | 47155.26 | 0 | 0 | 0 | 432 | 0 | 432 | 432 | 432 | 0 | 432 | 432 | HR | 18 | 0 | 18 | 18 | EA | 0 | 0 | 0 | 47155.26
Y | IPCRP1-0104-0000-L | IPCRP1 | IPCRP1 | 0104-0000 | SPECIAL DEEP DROP-PIPE MH NO. 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0104-0000-R | IPCRP1 | IPCRP1 | 0104-0000 | SPECIAL DEEP DROP-PIPE MH NO. 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 960000 | 0 | 0 | 960000 | 0 | 960000 | 840000 | 0 | N | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0104-1000-E | IPCRP1 | IPCRP1 | 0104-1000 | Exc/Install Riser/Backfill at Spec Deep Drop-Pipe | N | E |  | NR | P | 50188.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 50188.8 | 0 | 0 | 50188.8 | 0 | 0 | 0 | Y | 50188.8 | 0 | 0 | 50188.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 8 | 6.7 | 1.3 | 8 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0104-1000-L | IPCRP1 | IPCRP1 | 0104-1000 | Exc/Install Riser/Backfill at Spec Deep Drop-Pipe | N | L |  | NR | P | 174123.33 | 11953.25 | 11953.25 | 11953.25 | 11953.25 | 91.1477 | 0 | 0 | 0 | 1160.9 | Y | 13114.15 | Y | 161009.18 | 0 | 0 | 174123.33 | 0 | 0 | 13114.15 | Y | 161009.18 | 0 | 0 | 174123.33 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13114.15 | 0 | 0 | 13114.15 | 0 | 0 | 0 | 0 | 0 | 0 | -13114.15 | 0 | 0 | 13114.15 | 13114.15 | 0 | 0 | 0 | 1408 | 0 | 110 | 110 | 1408 | 94 | 16 | 110 | HR | 8 | 6.7 | 1.3 | 8 | EA | 0 | 0 | 0 | 1160.9 | D05, E06, F08, F09, F10, G04, H08, H11
Y | IPCRP1-0104-1010-E | IPCRP1 | IPCRP1 | 0104-1010 | Construct Chamber Spec Deep Drop-Pipe MH No. 2 | N | E |  | NR | P | 17681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 17681 | 0 | 0 | 17681 | 0 | 0 | 0 | Y | 17681 | 0 | 0 | 17681 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 8 | 5.49 | 2.51 | 8 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0104-1010-L | IPCRP1 | IPCRP1 | 0104-1010 | Construct Chamber Spec Deep Drop-Pipe MH No. 2 | N | L |  | NR | P | 95981 | 77959.03 | 77959.03 | 77959.03 | 77959.03 | 74.8964 | 0 | 0 | 0 | 26130.07 | Y | 104089.1 | Y | -8108.1 | 0 | 0 | 95981 | 0 | 0 | 104089.1 | Y | -8108.1 | 0 | 0 | 95981 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -104089.1 | 0 | 0 | 104089.1 | 0 | 0 | 0 | 0 | 0 | 0 | -104089.1 | 0 | 0 | 104089.1 | 104089.1 | 0 | 0 | 0 | 768 | 0 | 800 | 800 | 768 | 598.5 | 201.5 | 800 | HR | 8 | 5.49 | 2.51 | 8 | EA | 0 | 0 | 0 | 26130.07 | D05, E06, F08, F09, F10, G04, H08, H11 drop-in pipe work will start after Akela installs drainage pipes.
Y | IPCRP1-0104-1010-S | IPCRP1 | IPCRP1 | 0104-1010 | Construct Chamber Spec Deep Drop-Pipe MH No. 2 | N | S |  | UNIT | A | 0 | 985.52 | 985.52 | 985.52 | 985.52 | 100 | 0 | 0 | 0 | 0 | N | 985.52 | N | -985.52 | 0 | 0 | 0 | 0 | 0 | 985.52 | N | -985.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -985.52 | 0 | 0 | 985.52 | 0 | 0 | 0 | 0 | 0 | 0 | -985.52 | 0 | 0 | 985.52 | 985.52 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 8 | 5.49 | 2.51 | 8 | EA | 985.52 | 0 | 985.52 | 0
Y | IPCRP1-0105-0000-L | IPCRP1 | IPCRP1 | 0105-0000 | STAND DROP-PIPE MH TYPE 2 ON 42 in R.C.P. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0105-0000-R | IPCRP1 | IPCRP1 | 0105-0000 | STAND DROP-PIPE MH TYPE 2 ON 42 in R.C.P. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 160000 | 0 | 0 | 160000 | 0 | 160000 | 160000 | 0 | N | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0106-0000-L | IPCRP1 | IPCRP1 | 0106-0000 | STAND DROP-PIPE MH TYPE 2 ON 54 in R.C.P. SEWER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0106-0000-R | IPCRP1 | IPCRP1 | 0106-0000 | STAND DROP-PIPE MH TYPE 2 ON 54 in R.C.P. SEWER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300000 | 0 | 0 | 300000 | 0 | 300000 | 0 | 0 | N | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0106-1000-E | IPCRP1 | IPCRP1 | 0106-1000 | Exc, Inst Drop-Pipe MH Type 2 on RCP Sewer w/ Cas | N | E |  | NR | P | 25784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 25784 | 0 | 0 | 25784 | 0 | 0 | 0 | Y | 25784 | 0 | 0 | 25784 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 5 | 3.05 | 1.95 | 5 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0106-1000-L | IPCRP1 | IPCRP1 | 0106-1000 | Exc, Inst Drop-Pipe MH Type 2 on RCP Sewer w/ Cas | N | L |  | NR | P | 120026 | 39774.27 | 39774.27 | 39774.27 | 39774.27 | 33.138 | 0 | 0 | 0 | 80251.73 | N | 120026 | N | 0 | 0 | 0 | 120026 | 0 | 0 | 120026 | N | 0 | 0 | 0 | 120026 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -120026 | 0 | 7826.69 | 120026 | 0 | 0 | 0 | 0 | 0 | 0 | -120026 | 0 | 0 | 120026 | 120026 | 0 | 0 | 0 | 952 | 0 | 952 | 952 | 952 | 307.5 | 644.5 | 952 | HR | 5 | 3.05 | 1.95 | 5 | EA | 0 | 0 | 0 | 80251.73 | 2ea on 42in RCP, 3ea on 54in RCP
Y | IPCRP1-0107-0000-L | IPCRP1 | IPCRP1 | 0107-0000 | SPECIAL CB | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0107-0000-R | IPCRP1 | IPCRP1 | 0107-0000 | SPECIAL CB | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15000 | 0 | 0 | 15000 | 0 | 15000 | 15000 | 0 | N | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0108-0000-L | IPCRP1 | IPCRP1 | 0108-0000 | STAND CB, TYPE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0108-0000-R | IPCRP1 | IPCRP1 | 0108-0000 | STAND CB, TYPE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 105000 | 0 | 0 | 105000 | 0 | 105000 | 15000 | 0 | N | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0109-0000-L | IPCRP1 | IPCRP1 | 0109-0000 | STAND CB, TYPE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0109-0000-R | IPCRP1 | IPCRP1 | 0109-0000 | STAND CB, TYPE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 60000 | 0 | 0 | 60000 | 0 | 60000 | 30000 | 0 | N | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0109-1000-E | IPCRP1 | IPCRP1 | 0109-1000 | Install CB Type 1, 2, Spec, w/ Casting | N | E |  | NR | P | 5533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5533 | 0 | 0 | 5533 | 0 | 0 | 0 | Y | 5533 | 0 | 0 | 5533 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 12 | 4 | 8 | 12 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0109-1000-L | IPCRP1 | IPCRP1 | 0109-1000 | Install CB Type 1, 2, Spec, w/ Casting | N | L |  | NR | P | 36648 | 9089.78 | 9089.78 | 9089.78 | 9089.78 | 24.8029 | 0 | 0 | 0 | 27558.22 | N | 36648 | N | 0 | 0 | 0 | 36648 | 0 | 0 | 36648 | N | 0 | 0 | 0 | 36648 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36648 | 0 | 0 | 36648 | 0 | 0 | 0 | 0 | 0 | 0 | -36648 | 0 | 0 | 36648 | 36648 | 0 | 0 | 0 | 308.96 | 0 | 308.96 | 308.96 | 308.96 | 62 | 246.96 | 308.96 | HR | 12 | 4 | 8 | 12 | EA | 0 | 0 | 0 | 27558.22
Y | IPCRP1-0109-1000-S | IPCRP1 | IPCRP1 | 0109-1000 | Install CB Type 1, 2, Spec, w/ Casting | N | S |  | UNIT | A | 0 | 2308.41 | 2308.41 | 2308.41 | 2308.41 | 100 | 0 | 0 | 0 | 0 | Y | 2308.41 | Y | -2308.41 | 0 | 0 | 0 | 0 | 0 | 2308.41 | Y | -2308.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2308.41 | 0 | 0 | 2308.41 | 0 | 0 | 0 | 0 | 0 | 0 | -2308.41 | 0 | 0 | 2308.41 | 2308.41 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 19 | -11 | 8 | NA | 12 | 4 | 8 | 12 | EA | 2308.41 | 0 | 2308.41 | 0
Y | IPCRP1-0110-0000-L | IPCRP1 | IPCRP1 | 0110-0000 | OUTFALL STRUCT NO. 020 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0110-0000-R | IPCRP1 | IPCRP1 | 0110-0000 | OUTFALL STRUCT NO. 020 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0111-0000-L | IPCRP1 | IPCRP1 | 0111-0000 | OUTFALL STRUCT NO. 028 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0111-0000-R | IPCRP1 | IPCRP1 | 0111-0000 | OUTFALL STRUCT NO. 028 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0112-0000-L | IPCRP1 | IPCRP1 | 0112-0000 | OUTFALL STRUCT NO. 053 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0112-0000-R | IPCRP1 | IPCRP1 | 0112-0000 | OUTFALL STRUCT NO. 053 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300000 | 0 | 0 | 300000 | 0 | 300000 | 0 | 0 | N | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0113-0000-L | IPCRP1 | IPCRP1 | 0113-0000 | OUTFALL STRUCT NO. 054 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0113-0000-R | IPCRP1 | IPCRP1 | 0113-0000 | OUTFALL STRUCT NO. 054 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300000 | 0 | 0 | 300000 | 0 | 300000 | 300000 | 0 | N | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0114-0000-L | IPCRP1 | IPCRP1 | 0114-0000 | OUTFALL STRUCT NO. 055 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0114-0000-R | IPCRP1 | IPCRP1 | 0114-0000 | OUTFALL STRUCT NO. 055 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 150000 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | N | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0115-0000-L | IPCRP1 | IPCRP1 | 0115-0000 | OUTFALL STRUCT NO. 056 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0115-0000-R | IPCRP1 | IPCRP1 | 0115-0000 | OUTFALL STRUCT NO. 056 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 0 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0116-0000-L | IPCRP1 | IPCRP1 | 0116-0000 | OUTFALL STRUCT NO. 057 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0116-0000-R | IPCRP1 | IPCRP1 | 0116-0000 | OUTFALL STRUCT NO. 057 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0117-0000-L | IPCRP1 | IPCRP1 | 0117-0000 | OUTFALL STRUCT NO. 058 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0117-0000-R | IPCRP1 | IPCRP1 | 0117-0000 | OUTFALL STRUCT NO. 058 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0118-0000-L | IPCRP1 | IPCRP1 | 0118-0000 | OUTFALL STRUCT NO. 059 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0118-0000-R | IPCRP1 | IPCRP1 | 0118-0000 | OUTFALL STRUCT NO. 059 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0119-0000-L | IPCRP1 | IPCRP1 | 0119-0000 | OUTFALL STRUCT NO. 060 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0119-0000-R | IPCRP1 | IPCRP1 | 0119-0000 | OUTFALL STRUCT NO. 060 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 200000 | 0 | 0 | 200000 | 0 | 200000 | 200000 | 0 | N | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0119-1000-E | IPCRP1 | IPCRP1 | 0119-1000 | Install/Remove Cofferdam Sheeting at Embayments | N | E |  | NR | P | 154407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 154407 | 0 | 0 | 154407 | 0 | 0 | 0 | Y | 154407 | 0 | 0 | 154407 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 10 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0119-1000-L | IPCRP1 | IPCRP1 | 0119-1000 | Install/Remove Cofferdam Sheeting at Embayments | N | L |  | NR | P | 424322 | 273253.02 | 273253.02 | 273253.02 | 273253.02 | 48.7952 | 0 | 0 | 0 | 286746.98 | Y | 560000 | Y | -135678 | 0 | 0 | 424322 | 0 | 0 | 560000 | Y | -135678 | 0 | 0 | 424322 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -560000 | 0 | 0 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | -560000 | 0 | 0 | 560000 | 560000 | 0 | 0 | 0 | 3264 | 0 | 4011.07 | 4011.07 | 3264 | 1976.5 | 2034.57 | 4011.07 | HR | 10 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 286746.98
Y | IPCRP1-0119-1000-S | IPCRP1 | IPCRP1 | 0119-1000 | Install/Remove Cofferdam Sheeting at Embayments | N | S |  | UNIT | A | 0 | 2218.97 | 2218.97 | 2218.97 | 2218.97 | 100 | 0 | 0 | 0 | 0 | N | 2218.97 | N | -2218.97 | 0 | 0 | 0 | 0 | 0 | 2218.97 | N | -2218.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2218.97 | 0 | 0 | 2218.97 | 0 | 0 | 0 | 0 | 0 | 0 | -2218.97 | 0 | 0 | 2218.97 | 2218.97 | 0 | 0 | 0 | 0 | 0 | 17.5 | 17.5 | 0 | 17.5 | 0 | 17.5 | NA | 10 | 2 | 2 | 4 | EA | 2218.97 | 0 | 2218.97 | 0
Y | IPCRP1-0119-1005-L | IPCRP1 | IPCRP1 | 0119-1005 | Install/Remove Cofferdam Sheeting at Outfalls | N | L |  | UNIT | P | 0 | 1633077.53 | 1633077.53 | 1633077.53 | 1633077.53 | 64.8042 | 0 | 0 | 0 | 886940.58 | Y | 2520018.11 | Y | -2520018.11 | 0 | 0 | 0 | 0 | 0 | 2520018.11 | Y | -2520018.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2520018.11 | 88340.11 | 33815.09 | 2520018.11 | 0 | 0 | 0 | 0 | 0 | 0 | -2520018.11 | 0 | 0 | 2520018.11 | 2520018.11 | 0 | 0 | 0 | 0 | 0 | 17914.35 | 17914.35 | 0 | 11510.8 | 6403.55 | 17914.35 | HR | 0 | 8 | 2 | 10 | EA | 0 | 0 | 0 | 886940.58
Y | IPCRP1-0119-1005-S | IPCRP1 | IPCRP1 | 0119-1005 | Install/Remove Cofferdam Sheeting at Outfalls | N | S |  | UNIT | A | 0 | 12079.53 | 12079.53 | 12079.53 | 12079.53 | 113.9776 | 0 | 0 | 0 | -1481.37 | Y | 10598.16 | Y | -10598.16 | 0 | 0 | 0 | 0 | 0 | 10598.16 | Y | -10598.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10598.16 | 1355.91 | 0 | 10598.16 | 0 | 0 | 0 | 0 | 1355.91 | 0 | -10598.16 | 0 | 0 | 10598.16 | 10598.16 | 0 | 0 | 0 | 0 | 0 | 25.5 | 25.5 | 0 | 92 | -66.5 | 25.5 | NA | 0 | 8 | 2 | 10 | EA | 12079.53 | 0 | 12079.53 | -1481.37 | Change PMF (Sub) from $2,923.21 to $6,246.61 (matching Commitment)
Y | IPCRP1-0119-1010-E | IPCRP1 | IPCRP1 | 0119-1010 | CIP Portion at Outfalls (all) | N | E |  | NR | P | 19456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 19456 | 0 | 0 | 19456 | 0 | 0 | 0 | Y | 19456 | 0 | 0 | 19456 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 10 | 7.75 | 2.25 | 10 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0119-1010-L | IPCRP1 | IPCRP1 | 0119-1010 | CIP Portion at Outfalls (all) | N | L |  | NR | P | 204328 | 32951.37 | 32951.37 | 32951.37 | 32951.37 | 32.2559 | 0 | 0 | 0 | 69204.81 | Y | 102156.18 | Y | 102171.82 | 0 | 0 | 204328 | 0 | 0 | 102156.18 | Y | 102171.82 | 0 | 0 | 204328 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -102156.18 | 0 | 0 | 102156.18 | 0 | 0 | 0 | 0 | 0 | 0 | -102156.18 | 0 | 0 | 102156.18 | 102156.18 | 0 | 0 | 0 | 1680 | 0 | 839.96 | 839.96 | 1680 | 251 | 588.96 | 839.96 | HR | 10 | 7.75 | 2.25 | 10 | EA | 0 | 0 | 0 | 69204.81 | $0.00 cost incurred to do the first 5 CIP portions of Outfalls. All costs are for the quantity after this.
Y | IPCRP1-0119-1015-L | IPCRP1 | IPCRP1 | 0119-1015 | Excavate Inside Cofferdams | N | L |  | UNIT | P | 0 | 107420.44 | 107420.44 | 107420.44 | 107420.44 | 82.6311 | 0 | 0 | 0 | 22579.56 | Y | 130000 | Y | -130000 | 0 | 0 | 0 | 0 | 0 | 130000 | Y | -130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130000 | 24724.82 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | -130000 | 0 | 0 | 130000 | 130000 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 848.5 | 151.5 | 1000 | HR | 0 | 7 | 3 | 10 | EA | 0 | 0 | 0 | 22579.56 | This is based on a 6man crew x 2 days to excavate each cofferdam
Y | IPCRP1-0119-1015-S | IPCRP1 | IPCRP1 | 0119-1015 | Excavate Inside Cofferdams | N | S |  | UNIT | A | 0 | 7837.56 | 7837.56 | 7837.56 | 7837.56 | 248.5305 | 0 | 0 | 0 | 0 | N | 3153.56 | N | -3153.56 | 0 | 0 | 0 | 0 | 0 | 3153.56 | N | -3153.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3153.56 | 3680.34 | 0 | 3153.56 | 0 | 0 | 0 | 0 | 3680.34 | 0 | -3153.56 | 0 | 0 | 3153.56 | 3153.56 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 33 | -8 | 25 | NA | 0 | 7 | 3 | 10 | EA | 7837.56 | 0 | 7837.56 | 0
Y | IPCRP1-0119-1020-C | IPCRP1 | IPCRP1 | 0119-1020 | CM – Steel Sheeting for Cofferdams (All Types) | N | C |  | NR | P | 213120 | 158811.27 | 158811.27 | 158011.68 | 158811.27 | 99.4965 | 0 | 0 | 0 | 0 | Y | 158811.27 | Y | 54308.73 | 0 | 0 | 213120 | 0 | 0 | 158811.27 | Y | 54308.73 | 0 | 0 | 213120 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -158811.27 | 0 | 0 | 158811.27 | 0 | 0 | 0 | 0 | 0 | 0 | -158811.27 | 0 | 0 | 158811.27 | 158811.27 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4127 | 405.74 | 4532.74 | EA | 590400 | 301040 | 98960 | 400000 | LB | 158811.27 | 799.59 | 158011.68 | 0
Y | IPCRP1-0119-1020-L | IPCRP1 | IPCRP1 | 0119-1020 | CM – Steel Sheeting for Cofferdams (All Types) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 590400 | 301040 | 98960 | 400000 | LB | 0 | 0 | 0 | 0 | 16 sheet piles delivered on 8/7/23 completed cofferdam set. Claiming 85% as of 7-31-23 to cover additional cost when we cannot re-use the materials.
Y | IPCRP1-0119-1020-M | IPCRP1 | IPCRP1 | 0119-1020 | CM – Steel Sheeting for Cofferdams (All Types) | N | M |  | UNIT | U | 0 | 635931.1 | 635931.1 | 598664.72 | 635931.1 | 94.1399 | 0 | 0 | 0 | 0 | Y | 635931.1 | Y | -635931.1 | 0 | 0 | 0 | 0 | 0 | 635931.1 | Y | -635931.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -635931.1 | 0 | 0 | 635931.1 | 0 | 0 | 0 | 0 | 0 | 0 | -635931.1 | 0 | 0 | 635931.1 | 635931.1 | 0 | 0 | 0 | 0 | 0 | 515259 | 515259 | 0 | 515259 | 0 | 515259 | NA | 590400 | 301040 | 98960 | 400000 | LB | 635931.1 | 37266.38 | 598664.72 | 0
Y | IPCRP1-0119-1030-L | IPCRP1 | IPCRP1 | 0119-1030 | Cofferdam Dewatering | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-0120-0000-L | IPCRP1 | IPCRP1 | 0120-0000 | MODIFY EXIST TYPE 2 CB | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0120-0000-R | IPCRP1 | IPCRP1 | 0120-0000 | MODIFY EXIST TYPE 2 CB | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15000 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | N | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0120-0000-S | IPCRP1 | IPCRP1 | 0120-0000 | MODIFY EXIST TYPE 2 CB | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0120-1000-E | IPCRP1 | IPCRP1 | 0120-1000 | Modify Exist Type 2 Catch Basin | N | E |  | NR | P | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 306 | 0 | 0 | 306 | 0 | 0 | 0 | Y | 306 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2 | 0.66 | 1.34 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0120-1000-L | IPCRP1 | IPCRP1 | 0120-1000 | Modify Exist Type 2 Catch Basin | N | L |  | NR | P | 2740 | 2746.69 | 2746.69 | 2746.69 | 2746.69 | 32.6982 | 0 | 0 | 0 | 5653.44 | Y | 8400.13 | Y | -5660.13 | 0 | 0 | 2740 | 0 | 0 | 8400.13 | Y | -5660.13 | 0 | 0 | 2740 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8400.13 | 0 | 0 | 8400.13 | 0 | 0 | 0 | 0 | 0 | 0 | -8400.13 | 0 | 0 | 8400.13 | 8400.13 | 0 | 0 | 0 | 24 | 0 | 60 | 60 | 24 | 21 | 39 | 60 | HR | 2 | 0.66 | 1.34 | 2 | EA | 0 | 0 | 0 | 5653.44 | As / NM (9/30) not sure where 2nd CB is. 1st CB is on FDR & connects to new CB on E10th (sht 446). Andrew submitting for pay in Sep PP
Y | IPCRP1-0120-1000-S | IPCRP1 | IPCRP1 | 0120-1000 | Modify Exist Type 2 Catch Basin | N | S |  | UNIT | A | 0 | 622.93 | 622.93 | 622.93 | 622.93 | 100 | 0 | 0 | 0 | 0 | N | 622.93 | N | -622.93 | 0 | 0 | 0 | 0 | 0 | 622.93 | N | -622.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -622.93 | 0 | 0 | 622.93 | 0 | 0 | 0 | 0 | 0 | 0 | -622.93 | 0 | 0 | 622.93 | 622.93 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | NA | 2 | 0.66 | 1.34 | 2 | EA | 622.93 | 0 | 622.93 | 0
Y | IPCRP1-0121-0000-L | IPCRP1 | IPCRP1 | 0121-0000 | MODIFY EXIST DROP-PIPE MH NO. 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0121-0000-R | IPCRP1 | IPCRP1 | 0121-0000 | MODIFY EXIST DROP-PIPE MH NO. 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0121-1000-C | IPCRP1 | IPCRP1 | 0121-1000 | Excav, Sheet, Mod Exist Drop Pipe MH 2, Backfill | N | C |  | UNIT | U | 0 | 12089.18 | 12089.18 | 12089.18 | 12089.18 | 100 | 0 | 0 | 0 | 0 | Y | 12089.18 | Y | -12089.18 | 0 | 0 | 0 | 0 | 0 | 12089.18 | Y | -12089.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12089.18 | 0 | 0 | 12089.18 | 0 | 0 | 0 | 0 | 0 | 0 | -12089.18 | 0 | 0 | 12089.18 | 12089.18 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 1 | 1 | 0 | 1 | EA | 3750 | 0 | 3750 | 0 | matching to CTD $ Change PMF (Consum) from $12,421.99 to $12,089.18, matching CTD.
Y | IPCRP1-0121-1000-E | IPCRP1 | IPCRP1 | 0121-1000 | Excav, Sheet, Mod Exist Drop Pipe MH 2, Backfill | N | E |  | NR | P | 20343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20343 | 0 | 0 | 20343 | 0 | 0 | 0 | Y | 20343 | 0 | 0 | 20343 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0121-1000-L | IPCRP1 | IPCRP1 | 0121-1000 | Excav, Sheet, Mod Exist Drop Pipe MH 2, Backfill | N | L |  | NR | P | 68097 | 192622.8 | 192622.8 | 192622.8 | 192622.8 | 100 | 0 | 0 | 0 | 0 | Y | 192622.8 | Y | -124525.8 | 0 | 0 | 68097 | 0 | 0 | 192622.8 | Y | -124525.8 | 0 | 0 | 68097 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -192622.8 | 0 | 0 | 192622.8 | 0 | 0 | 0 | 0 | 0 | 0 | -192622.8 | 0 | 0 | 192622.8 | 192622.8 | 0 | 0 | 0 | 536 | 0 | 1460 | 1460 | 536 | 1460 | 0 | 1460 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0121-1000-S | IPCRP1 | IPCRP1 | 0121-1000 | Excav, Sheet, Mod Exist Drop Pipe MH 2, Backfill | N | S |  | UNIT | A | 0 | 18693.44 | 18693.44 | 18693.44 | 18693.44 | 100 | 0 | 0 | 0 | 0 | Y | 18693.44 | Y | -18693.44 | 0 | 0 | 0 | 0 | 0 | 18693.44 | Y | -18693.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18693.44 | 0 | 0 | 18693.44 | 0 | 0 | 0 | 0 | 0 | 0 | -18693.44 | 0 | 0 | 18693.44 | 18693.44 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 28 | 0 | 28 | NA | 1 | 1 | 0 | 1 | EA | 18693.44 | 0 | 18693.44 | 0
Y | IPCRP1-0121-1010-C | IPCRP1 | IPCRP1 | 0121-1010 | Stainless Steel Gratings/Railings | N | C |  | UNIT | U | 0 | 2088.21 | 2088.21 | 2088.21 | 2088.21 | 100 | 0 | 0 | 0 | 0 | N | 2088.21 | N | -2088.21 | 0 | 0 | 0 | 0 | 0 | 2088.21 | N | -2088.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2088.21 | 0 | 0 | 2088.21 | 0 | 0 | 0 | 0 | 0 | 0 | -2088.21 | 0 | 0 | 2088.21 | 2088.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0121-1010-L | IPCRP1 | IPCRP1 | 0121-1010 | Stainless Steel Gratings/Railings | N | L |  | UNIT | P | 0 | -0.37 | -0.37 | -0.37 | -0.37 | 0 | 0 | 0 | 0 | 0.37 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0.37
Y | IPCRP1-0121-1010-M | IPCRP1 | IPCRP1 | 0121-1010 | Stainless Steel Gratings/Railings | N | M |  | UNIT | U | 0 | 25326.64 | 25326.64 | 25326.64 | 25326.64 | 100 | 0 | 0 | 0 | 0 | Y | 25326.64 | Y | -25326.64 | 0 | 0 | 0 | 0 | 0 | 25326.64 | Y | -25326.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25326.64 | 0 | 0 | 25326.64 | 0 | 0 | 0 | 0 | 0 | 0 | -25326.64 | 0 | 0 | 25326.64 | 25326.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -6 | 0 | LS | 1 | 1 | 0 | 1 | LS | 25326.64 | 0 | 25326.64 | 0
Y | IPCRP1-0121-1010-S | IPCRP1 | IPCRP1 | 0121-1010 | Stainless Steel Gratings/Railings | N | S |  | NR | A | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | Y | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0122-0000-L | IPCRP1 | IPCRP1 | 0122-0000 | 12 DIP BASIN CONNECTION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0122-0000-R | IPCRP1 | IPCRP1 | 0122-0000 | 12 DIP BASIN CONNECTION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 350250 | 0 | 0 | 350250 | 0 | 350250 | 164709 | 0 | N | 350250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0122-1000-E | IPCRP1 | IPCRP1 | 0122-1000 | Install 12 DIP Basin Connection | N | E |  | NR | P | 15702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 15702 | 0 | 0 | 15702 | 0 | 0 | 0 | Y | 15702 | 0 | 0 | 15702 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 467 | 221.17 | 245.83 | 467 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0122-1000-L | IPCRP1 | IPCRP1 | 0122-1000 | Install 12 DIP Basin Connection | N | L |  | NR | P | 82451 | 9773.31 | 9773.31 | 9773.31 | 9773.31 | 11.8535 | 0 | 0 | 0 | 72677.69 | N | 82451 | N | 0 | 0 | 0 | 82451 | 0 | 0 | 82451 | N | 0 | 0 | 0 | 82451 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -82451 | 0 | 0 | 82451 | 0 | 0 | 0 | 0 | 0 | 0 | -82451 | 0 | 0 | 82451 | 82451 | 0 | 0 | 0 | 656 | 0 | 656 | 656 | 656 | 62.5 | 593.5 | 656 | HR | 467 | 221.17 | 245.83 | 467 | LF | 0 | 0 | 0 | 72677.69 | null
Y | IPCRP1-0122-1000-S | IPCRP1 | IPCRP1 | 0122-1000 | Install 12 DIP Basin Connection | N | S |  | UNIT | A | 0 | 559.31 | 559.31 | 559.31 | 559.31 | 100 | 0 | 0 | 0 | 0 | N | 559.31 | N | -559.31 | 0 | 0 | 0 | 0 | 0 | 559.31 | N | -559.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -559.31 | 0 | 0 | 559.31 | 0 | 0 | 0 | 0 | 0 | 0 | -559.31 | 0 | 0 | 559.31 | 559.31 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 0 | 4.5 | 0 | 4.5 | NA | 467 | 221.17 | 245.83 | 467 | LF | 559.31 | 0 | 559.31 | 0
Y | IPCRP1-0123-0000-L | IPCRP1 | IPCRP1 | 0123-0000 | SAWING CONCRETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0123-0000-R | IPCRP1 | IPCRP1 | 0123-0000 | SAWING CONCRETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 4386.7 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0123-1000-L | IPCRP1 | IPCRP1 | 0123-1000 | SAWING CONCRETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 500 | 438.67 | 61.33 | 500 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0123-1000-S | IPCRP1 | IPCRP1 | 0123-1000 | SAWING CONCRETE | N | S |  | NR | A | 1560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560 | N | 1560 | N | 0 | 0 | 0 | 1560 | 0 | 0 | 1560 | N | 0 | 0 | 0 | 1560 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1560 | 0 | 0 | 1560 | 0 | 0 | 0 | 0 | 0 | 0 | -1560 | 0 | 0 | 1560 | 1560 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 500 | 438.67 | 61.33 | 500 | LF | 0 | 0 | 0 | 1560
Y | IPCRP1-0124-0000-L | IPCRP1 | IPCRP1 | 0124-0000 | SEWER CLEANING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0124-0000-R | IPCRP1 | IPCRP1 | 0124-0000 | SEWER CLEANING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1250 | 0 | 0 | 1250 | 0 | 1250 | 0 | 0 | N | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0124-1000-L | IPCRP1 | IPCRP1 | 0124-1000 | SEWER CLEANING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 50 | 0 | 50 | 50 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0124-1000-S | IPCRP1 | IPCRP1 | 0124-1000 | SEWER CLEANING | N | S |  | NR | A | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | N | 1000 | N | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | N | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 50 | 0 | 50 | 50 | LF | 0 | 0 | 0 | 1000
Y | IPCRP1-0125-0000-L | IPCRP1 | IPCRP1 | 0125-0000 | SHOTCRETE FOR REPAIR WORK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CF | 0 | 0 | 0 | 0
Y | IPCRP1-0125-0000-R | IPCRP1 | IPCRP1 | 0125-0000 | SHOTCRETE FOR REPAIR WORK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 84500 | 0 | 0 | 84500 | 0 | 84500 | 223270 | 0 | N | 84500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CF | 0 | 0 | 0 | 0
Y | IPCRP1-0125-1000-L | IPCRP1 | IPCRP1 | 0125-1000 | SHOTCRETE FOR REPAIR WORK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 130 | 376.4 | 0 | 376.4 | CF | 0 | 0 | 0 | 0
Y | IPCRP1-0125-1000-S | IPCRP1 | IPCRP1 | 0125-1000 | SHOTCRETE FOR REPAIR WORK | N | S |  | NR | A | 83570.01 | 142857.41 | 142857.41 | 142857.41 | 142857.41 | 100 | 0 | 0 | 0 | 0 | Y | 142857.41 | Y | -59287.4 | 0 | 0 | 83570.01 | 0 | 0 | 142857.41 | Y | -59287.4 | 0 | 0 | 83570.01 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -142857.41 | 0 | 0 | 142857.41 | 0 | 0 | 0 | 0 | 0 | 0 | -142857.41 | 0 | 0 | 142857.41 | 142857.41 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 378.4 | -169.03 | 209.37 | LF | 130 | 376.4 | 0 | 376.4 | CF | 142857.41 | 0 | 142857.41 | 0 | EN-TECH CORP @$52,289.30 SCO sent to Entech. As / AT (9/30) not executed yet, so can't reduce commitment.
Y | IPCRP1-0126-0000-L | IPCRP1 | IPCRP1 | 0126-0000 | ABANDON BASINS & INLETS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0126-0000-R | IPCRP1 | IPCRP1 | 0126-0000 | ABANDON BASINS & INLETS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4000 | 0 | 0 | 4000 | 0 | 4000 | 0 | 0 | N | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0126-1000-E | IPCRP1 | IPCRP1 | 0126-1000 | ABANDON BASINS & INLETS | N | E |  | NR | P | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0126-1000-L | IPCRP1 | IPCRP1 | 0126-1000 | ABANDON BASINS & INLETS | N | L |  | NR | P | 1972.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972.54 | N | 1972.54 | N | 0 | 0 | 0 | 1972.54 | 0 | 0 | 1972.54 | N | 0 | 0 | 0 | 1972.54 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1972.54 | 0 | 0 | 1972.54 | 0 | 0 | 0 | 0 | 0 | 0 | -1972.54 | 0 | 0 | 1972.54 | 1972.54 | 0 | 0 | 0 | 16 | 0 | 16 | 16 | 16 | 0 | 16 | 16 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 1972.54
Y | IPCRP1-0126-1000-S | IPCRP1 | IPCRP1 | 0126-1000 | ABANDON BASINS & INLETS | N | S |  | UNIT | A | 0 | 124.29 | 124.29 | 124.29 | 124.29 | 100 | 0 | 0 | 0 | 0 | N | 124.29 | N | -124.29 | 0 | 0 | 0 | 0 | 0 | 124.29 | N | -124.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -124.29 | 0 | 0 | 124.29 | 0 | 0 | 0 | 0 | 0 | 0 | -124.29 | 0 | 0 | 124.29 | 124.29 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 2 | 0 | 2 | 2 | EA | 124.29 | 0 | 124.29 | 0
Y | IPCRP1-0127-0000-L | IPCRP1 | IPCRP1 | 0127-0000 | STEEL H-PILES (HP 12X53) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0127-0000-R | IPCRP1 | IPCRP1 | 0127-0000 | STEEL H-PILES (HP 12X53) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 304500 | 0 | 0 | 304500 | 0 | 304500 | 289239 | 0 | N | 304500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0128-0000-L | IPCRP1 | IPCRP1 | 0128-0000 | STEEL H-PILES (HP 12X84) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0128-0000-R | IPCRP1 | IPCRP1 | 0128-0000 | STEEL H-PILES (HP 12X84) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3106800 | 0 | 0 | 3106800 | 0 | 3106800 | 1997568.9 | 0 | N | 3106800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3106800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0129-0000-L | IPCRP1 | IPCRP1 | 0129-0000 | STEEL H-PILES (HP 14X73) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0129-0000-R | IPCRP1 | IPCRP1 | 0129-0000 | STEEL H-PILES (HP 14X73) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 56000 | 0 | 0 | 56000 | 0 | 56000 | 82800 | 0 | N | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0129-1000-L | IPCRP1 | IPCRP1 | 0129-1000 | BUILDING PILE SUB (TBD) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 560 | 828 | 1650 | 2478 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0129-1000-S | IPCRP1 | IPCRP1 | 0129-1000 | BUILDING PILE SUB (TBD) | N | S |  | UNIT | A | 47538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 47528 | 0 | 0 | 47538 | 0 | 0 | 10 | Y | 47528 | 0 | 0 | 47538 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 560 | 828 | 1650 | 2478 | LF | 0 | 0 | 0 | 10 | PM Forecast should match budget = $47,538.00 (VS, Mon 2/14/2022 3:58 PM)
Y | IPCRP1-0130-0000-L | IPCRP1 | IPCRP1 | 0130-0000 | PREDRILLING HOLES FOR PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0130-0000-R | IPCRP1 | IPCRP1 | 0130-0000 | PREDRILLING HOLES FOR PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1775000 | 0 | 0 | 1775000 | 0 | 1775000 | 758250 | 0 | N | 1775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0131-0000-L | IPCRP1 | IPCRP1 | 0131-0000 | SPLICES FOR STEEL H-PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0131-0000-R | IPCRP1 | IPCRP1 | 0131-0000 | SPLICES FOR STEEL H-PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 215000 | 0 | 0 | 215000 | 0 | 215000 | 2000 | 0 | N | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0132-0000-L | IPCRP1 | IPCRP1 | 0132-0000 | FURN EQUIP FOR DRIVING PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0132-0000-R | IPCRP1 | IPCRP1 | 0132-0000 | FURN EQUIP FOR DRIVING PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 22500000 | 0 | 0 | 22500000 | 0 | 22500000 | 16875000 | 0 | N | 22500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0133-0000-L | IPCRP1 | IPCRP1 | 0133-0000 | DYNAMIC PILE TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0133-0000-R | IPCRP1 | IPCRP1 | 0133-0000 | DYNAMIC PILE TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 135000 | 0 | 0 | 135000 | 0 | 135000 | 82500 | 0 | N | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0133-1000-L | IPCRP1 | IPCRP1 | 0133-1000 | Bridge & Structure Pile Sub (TBD) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0133-1000-S | IPCRP1 | IPCRP1 | 0133-1000 | Bridge & Structure Pile Sub (TBD) | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | We reverted PMF back to $0 after CMiC displays $47,538.00 as PMF.
Y | IPCRP1-0134-0000-L | IPCRP1 | IPCRP1 | 0134-0000 | FURN EQUIP FOR INSTALL MICROPILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0134-0000-R | IPCRP1 | IPCRP1 | 0134-0000 | FURN EQUIP FOR INSTALL MICROPILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7500000 | 0 | 0 | 7500000 | 0 | 7500000 | 5625000 | 0 | N | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0135-0000-L | IPCRP1 | IPCRP1 | 0135-0000 | STATIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0135-0000-R | IPCRP1 | IPCRP1 | 0135-0000 | STATIC PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 180000 | 0 | 0 | 180000 | 0 | 180000 | 240000 | 0 | N | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0136-0000-L | IPCRP1 | IPCRP1 | 0136-0000 | REMOVAL OF PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0136-0000-R | IPCRP1 | IPCRP1 | 0136-0000 | REMOVAL OF PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 80000 | 0 | 0 | 80000 | 0 | 80000 | 251300 | 0 | N | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0137-0000-L | IPCRP1 | IPCRP1 | 0137-0000 | MICROPILES (DESIGN PROVIDED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0137-0000-R | IPCRP1 | IPCRP1 | 0137-0000 | MICROPILES (DESIGN PROVIDED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9400000 | 0 | 0 | 9400000 | 0 | 9400000 | 5013285 | 0 | N | 9400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0137-1000-C | IPCRP1 | IPCRP1 | 0137-1000 | Micropiles Support | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0137-1000-L | IPCRP1 | IPCRP1 | 0137-1000 | Micropiles Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0137-1000-S | IPCRP1 | IPCRP1 | 0137-1000 | Micropiles Support | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0138-0000-L | IPCRP1 | IPCRP1 | 0138-0000 | PERMANENT CASING FOR MICROPILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0138-0000-R | IPCRP1 | IPCRP1 | 0138-0000 | PERMANENT CASING FOR MICROPILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3825000 | 0 | 0 | 3825000 | 0 | 3825000 | 2149207.5 | 0 | N | 3825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0138-1000-L | IPCRP1 | IPCRP1 | 0138-1000 | Furnish 12.75 Inch Dia MP Casing to Keller | N | L |  | UNIT | P | 0 | 2940.02 | 2940.02 | 2940.02 | 2940.02 | 100 | 0 | 0 | 0 | 0 | Y | 2940.02 | Y | -2940.02 | 0 | 0 | 0 | 0 | 0 | 2940.02 | Y | -2940.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2940.02 | 0 | 0 | 2940.02 | 0 | 0 | 0 | 0 | 0 | 0 | -2940.02 | 0 | 0 | 2940.02 | 2940.02 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 24 | 0 | 24 | HR | 0 | 1880 | 0 | 1880 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0138-1000-M | IPCRP1 | IPCRP1 | 0138-1000 | Furnish 12.75 Inch Dia MP Casing to Keller | N | M |  | UNIT | U | 0 | 114800 | 114800 | 114800 | 114800 | 100 | 0 | 0 | 0 | 0 | N | 114800 | N | -114800 | 0 | 0 | 0 | 0 | 0 | 114800 | N | -114800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -114800 | 0 | 0 | 114800 | 0 | 0 | 0 | 0 | 0 | 0 | -114800 | 0 | 0 | 114800 | 114800 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 0 | 40 | NA | 0 | 1880 | 0 | 1880 | LF | 114800 | 0 | 114800 | 0 | Skyline PO#3217 (line 29) 40ea = 1880 LF as per LS email 7/23/24. Raw material, then shipped to GMS for fabrication then shipped to GMS for fabrication, and coded to 0000-0062, and leaving it there.
Y | IPCRP1-0139-0000-L | IPCRP1 | IPCRP1 | 0139-0000 | TEMP STEEL SHEETING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0139-0000-R | IPCRP1 | IPCRP1 | 0139-0000 | TEMP STEEL SHEETING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 104850 | 0 | 0 | 104850 | 0 | 104850 | 101700 | 0 | N | 104850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0139-1000-E | IPCRP1 | IPCRP1 | 0139-1000 | Haul Temp Sheeting On/Off Site | N | E |  | NR | P | 9634.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 9634.18 | 0 | 0 | 9634.18 | 0 | 0 | 0 | Y | 9634.18 | 0 | 0 | 9634.18 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 315200 | 0 | 315200 | 315200 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0139-1000-L | IPCRP1 | IPCRP1 | 0139-1000 | Haul Temp Sheeting On/Off Site | N | L |  | NR | P | 14826.1 | 1354.82 | 1354.82 | 1354.82 | 1354.82 | 9.1381 | 0 | 0 | 0 | 13471.28 | N | 14826.1 | N | 0 | 0 | 0 | 14826.1 | 0 | 0 | 14826.1 | N | 0 | 0 | 0 | 14826.1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14826.1 | 0 | 0 | 14826.1 | 0 | 0 | 0 | 0 | 0 | 0 | -14826.1 | 0 | 0 | 14826.1 | 14826.1 | 0 | 0 | 0 | 192 | 0 | 122.93 | 122.93 | 192 | 11 | 111.93 | 122.93 | HR | 315200 | 0 | 315200 | 315200 | LB | 0 | 0 | 0 | 13471.28
Y | IPCRP1-0139-1010-L | IPCRP1 | IPCRP1 | 0139-1010 | PM - Furn Temporary St Sheeting | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5610 | 5610 | 0 | 5610 | SF | 0 | 0 | 0 | 0 | H-Piles along ERH property line. Payment included in PCO to accelerate at DSB. If we are not able to remove entitled to recovery costs.
Y | IPCRP1-0139-1010-M | IPCRP1 | IPCRP1 | 0139-1010 | PM - Furn Temporary St Sheeting | N | M |  | NR | P | 56541 | 97324.12 | 97324.12 | 96131.92 | 97324.12 | 97.9921 | 0 | 0 | 0 | 777.63 | Y | 98101.75 | Y | -41560.75 | 0 | 0 | 56541 | 0 | 0 | 98101.75 | Y | -41560.75 | 0 | 0 | 56541 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -98101.75 | 0 | 0 | 98101.75 | 0 | 0 | 0 | 0 | 0 | 0 | -98101.75 | 0 | 0 | 98101.75 | 98101.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1249.24 | 0 | 1249.24 | SF | 5610 | 5610 | 0 | 5610 | SF | 98101.75 | 1192.2 | 96909.55 | 777.63
Y | IPCRP1-0139-1020-E | IPCRP1 | IPCRP1 | 0139-1020 | Mob/Demob Temp St Sheeting Crew (CLOSED) | N | E |  | NR | P | 24457.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 24457.58 | 0 | 0 | 24457.58 | 0 | 0 | 0 | Y | 24457.58 | 0 | 0 | 24457.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 6 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0139-1020-L | IPCRP1 | IPCRP1 | 0139-1020 | Mob/Demob Temp St Sheeting Crew (CLOSED) | N | L |  | NR | P | 56494.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 56494.9 | 0 | 0 | 56494.9 | 0 | 0 | 0 | Y | 56494.9 | 0 | 0 | 56494.9 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 0 | 0 | 0 | HR | 6 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | Mob #1 - install temp sheeting at Delancey St West Ramp along ERH property.
Y | IPCRP1-0139-1030-E | IPCRP1 | IPCRP1 | 0139-1030 | Install Temporary St Sheeting | N | E |  | NR | P | 46237.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 46237.85 | 0 | 0 | 46237.85 | 0 | 0 | 0 | Y | 46237.85 | 0 | 0 | 46237.85 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LB | 20970 | 20340 | 630 | 20970 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0139-1030-L | IPCRP1 | IPCRP1 | 0139-1030 | Install Temporary St Sheeting | N | L |  | NR | P | 95057.05 | 219872.33 | 219872.33 | 219872.33 | 219872.33 | 90.8563 | 0 | 0 | 0 | 22127.67 | Y | 242000 | Y | -146942.95 | 0 | 0 | 95057.05 | 0 | 0 | 242000 | Y | -146942.95 | 0 | 0 | 95057.05 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -242000 | 0 | 0 | 242000 | 0 | 0 | 0 | 0 | 0 | 0 | -242000 | 0 | 0 | 242000 | 242000 | 0 | 0 | 0 | 1029 | 0 | 1702.18 | 1702.18 | 1029 | 1547 | 155.18 | 1702.18 | HR | 20970 | 20340 | 630 | 20970 | SF | 0 | 0 | 0 | 22127.67
Y | IPCRP1-0139-1030-S | IPCRP1 | IPCRP1 | 0139-1030 | Install Temporary St Sheeting | N | S |  | UNIT | A | 0 | 9759.4 | 9759.4 | 9759.4 | 9759.4 | 100 | 0 | 0 | 0 | 0 | Y | 9759.4 | Y | -9759.4 | 0 | 0 | 0 | 0 | 0 | 9759.4 | Y | -9759.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9759.4 | 0 | 0 | 9759.4 | 0 | 0 | 0 | 0 | 0 | 0 | -9759.4 | 0 | 0 | 9759.4 | 9759.4 | 0 | 0 | 0 | 0 | 0 | 84.5 | 84.5 | 0 | 86.5 | -2 | 84.5 | NA | 20970 | 20340 | 630 | 20970 | SF | 9759.4 | 0 | 9759.4 | 0
Y | IPCRP1-0140-0000-L | IPCRP1 | IPCRP1 | 0140-0000 | FILL TYPE RETAINING WALL (> 18FT. - 24FT.) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0140-0000-R | IPCRP1 | IPCRP1 | 0140-0000 | FILL TYPE RETAINING WALL (> 18FT. - 24FT.) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 53600 | 0 | 0 | 53600 | 0 | 53600 | 0 | 0 | N | 53600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0140-1000-L | IPCRP1 | IPCRP1 | 0140-1000 | Install MSE Wall | N | L |  | NR | P | 11275.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | Y | 100 | Y | 11175.76 | 0 | 0 | 11275.76 | 0 | 0 | 100 | Y | 11175.76 | 0 | 0 | 11275.76 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | -100 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 112 | 0 | 1 | 1 | 112 | 0 | 1 | 1 | HR | 2680 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 100 | Origiially used inside Ramps at DSB & E10th St. Deleted via RFI
Y | IPCRP1-0140-1010-L | IPCRP1 | IPCRP1 | 0140-1010 | Furn MSE Wall | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0.01 | HR | 2680 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0140-1010-M | IPCRP1 | IPCRP1 | 0140-1010 | Furn MSE Wall | N | M |  | NR | P | 51249.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 1 | Y | 51248.64 | 0 | 0 | 51249.64 | 0 | 0 | 1 | Y | 51248.64 | 0 | 0 | 51249.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2680 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 1
Y | IPCRP1-0141-0000-L | IPCRP1 | IPCRP1 | 0141-0000 | CONC FOR STRUCTURES, CL MP (MASS PLACEMENT) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0141-0000-R | IPCRP1 | IPCRP1 | 0141-0000 | CONC FOR STRUCTURES, CL MP (MASS PLACEMENT) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 126000 | 0 | 0 | 126000 | 0 | 126000 | 105060 | 0 | N | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0141-1000-L | IPCRP1 | IPCRP1 | 0141-1000 | Install & Strip Formwork | N | L |  | NR | P | 141792.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 141792.37 | 0 | 0 | 141792.37 | 0 | 0 | 0 | Y | 141792.37 | 0 | 0 | 141792.37 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | HR | 2999.99 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0141-1010-C | IPCRP1 | IPCRP1 | 0141-1010 | Place Concrete | N | C |  | NR | P | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1155 | 0 | 0 | 1155 | 0 | 0 | 0 | N | 1155 | 0 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 167 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0141-1010-E | IPCRP1 | IPCRP1 | 0141-1010 | Place Concrete | N | E |  | NR | P | 13590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 13590 | 0 | 0 | 13590 | 0 | 0 | 0 | N | 13590 | 0 | 0 | 13590 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 167 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0141-1010-L | IPCRP1 | IPCRP1 | 0141-1010 | Place Concrete | N | L |  | NR | P | 43627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 43627 | 0 | 0 | 43627 | 0 | 0 | 0 | Y | 43627 | 0 | 0 | 43627 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417.25 | 0 | 0 | 0 | 417.25 | 0 | 0 | 0 | HR | 167 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0141-1020-C | IPCRP1 | IPCRP1 | 0141-1020 | Furn Formwork | N | C |  | NR | P | 14699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 14699 | 0 | 0 | 14699 | 0 | 0 | 0 | N | 14699 | 0 | 0 | 14699 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 3000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0141-1020-L | IPCRP1 | IPCRP1 | 0141-1020 | Furn Formwork | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0141-1030-L | IPCRP1 | IPCRP1 | 0141-1030 | Thermal Control Plan | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0141-1030-S | IPCRP1 | IPCRP1 | 0141-1030 | Thermal Control Plan | N | S |  | NR | P | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 26400 | 0 | 0 | 26400 | 0 | 0 | 0 | Y | 26400 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0141-1040-L | IPCRP1 | IPCRP1 | 0141-1040 | Structural Concrete | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-0141-1040-S | IPCRP1 | IPCRP1 | 0141-1040 | Structural Concrete | N | S |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | J . D'Annunzio & Sons, Inc.
Y | IPCRP1-0142-0000-L | IPCRP1 | IPCRP1 | 0142-0000 | FOOTING CONC, CL HP | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0142-0000-R | IPCRP1 | IPCRP1 | 0142-0000 | FOOTING CONC, CL HP | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1921200 | 0 | 0 | 1921200 | 0 | 1921200 | 605910 | 0 | N | 1921200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1921200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0142-1000-L | IPCRP1 | IPCRP1 | 0142-1000 | Install & Strip Formwork | N | L |  | NR | P | 930422.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 930422.4 | 0 | 0 | 930422.4 | 0 | 0 | 0 | Y | 930422.4 | 0 | 0 | 930422.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7680 | 0 | 0 | 0 | 7680 | 0 | 0 | 0 | HR | 25055 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0142-1010-C | IPCRP1 | IPCRP1 | 0142-1010 | Place Concrete | N | C |  | NR | P | 17611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 17611 | 0 | 0 | 17611 | 0 | 0 | 0 | N | 17611 | 0 | 0 | 17611 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 3065 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0142-1010-E | IPCRP1 | IPCRP1 | 0142-1010 | Place Concrete | N | E |  | NR | P | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | N | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 3065 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0142-1010-L | IPCRP1 | IPCRP1 | 0142-1010 | Place Concrete | N | L |  | NR | P | 772934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 772934 | 0 | 0 | 772934 | 0 | 0 | 0 | Y | 772934 | 0 | 0 | 772934 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7360 | 0 | 0 | 0 | 7360 | 0 | 0 | 0 | HR | 3065 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0142-1020-C | IPCRP1 | IPCRP1 | 0142-1020 | Furn Formwork | N | C |  | NR | P | 122759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 122759 | 0 | 0 | 122759 | 0 | 0 | 0 | N | 122759 | 0 | 0 | 122759 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 3202 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0142-1020-L | IPCRP1 | IPCRP1 | 0142-1020 | Furn Formwork | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3202 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0143-0000-L | IPCRP1 | IPCRP1 | 0143-0000 | CONC FOR STRUCTURES, CL HP | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0143-0000-R | IPCRP1 | IPCRP1 | 0143-0000 | CONC FOR STRUCTURES, CL HP | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3918000 | 0 | 0 | 3918000 | 0 | 3918000 | 1043508 | 0 | N | 3918000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3918000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0143-1000-L | IPCRP1 | IPCRP1 | 0143-1000 | Install & Strip Formwork | N | L |  | NR | P | 3407153.95 | 1372.98 | 1372.98 | 1372.98 | 1372.98 | 10.5614 | 0 | 0 | 0 | 11627.02 | Y | 13000 | Y | 3394153.95 | 0 | 0 | 3407153.95 | 0 | 0 | 13000 | Y | 3394153.95 | 0 | 0 | 3407153.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 28835 | 0 | 100 | 100 | 28835 | 9.5 | 90.5 | 100 | HR | 86505 | 12.05 | 257.95 | 270 | SF | 0 | 0 | 0 | 11627.02 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0143-1010-C | IPCRP1 | IPCRP1 | 0143-1010 | Place Concrete | N | C |  | NR | P | 17958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 17958 | 0 | 0 | 17958 | 0 | 0 | 0 | Y | 17958 | 0 | 0 | 17958 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 3390 | 1.26 | 3.74 | 5 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0143-1010-E | IPCRP1 | IPCRP1 | 0143-1010 | Place Concrete | N | E |  | NR | P | 158833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 158833 | 0 | 0 | 158833 | 0 | 0 | 0 | Y | 158833 | 0 | 0 | 158833 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 3390 | 1.26 | 3.74 | 5 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0143-1010-L | IPCRP1 | IPCRP1 | 0143-1010 | Place Concrete | N | L |  | NR | P | 759524 | 2288.94 | 2288.94 | 2288.94 | 2288.94 | 176.0723 | 0 | 0 | 0 | -988.94 | Y | 1300 | Y | 758224 | 0 | 0 | 759524 | 0 | 0 | 1300 | Y | 758224 | 0 | 0 | 759524 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1300 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | -1300 | 0 | 0 | 1300 | 1300 | 0 | 0 | 0 | 7118 | 0 | 10 | 10 | 7118 | 19 | -9 | 10 | HR | 3390 | 1.26 | 3.74 | 5 | CY | 0 | 0 | 0 | -988.94 | 2. Self-perform budget for est 5cy/270sf of ful depth conc repair at Houston St work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
N | IPCRP1-0143-1010-S | IPCRP1 | IPCRP1 | 0143-1010 | Place Concrete | N | S |  | UNIT | A | 0 | 720.79 | 720.79 | 720.79 | 720.79 | 100 | 0 | 0 | 0 | 0 | N | 720.79 | N | -720.79 | 0 | 0 | 0 | 0 | 0 | 720.79 | N | -720.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -720.79 | 0 | 720.79 | 720.79 | 0 | 0 | 0 | 0 | 0 | 0 | -720.79 | 0 | 0 | 720.79 | 720.79 | 0 | 0 | 0 | 0 | 0 | 5.5 | 5.5 | 0 | 0 | 5.5 | 5.5 | NA | 3390 | 1.26 | 3.74 | 5 | CY | 720.79 | 0 | 720.79 | 0
Y | IPCRP1-0143-1020-C | IPCRP1 | IPCRP1 | 0143-1020 | Furn Formwork | N | C |  | NR | P | 282559.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 282549.93 | 0 | 0 | 282559.93 | 0 | 0 | 10 | Y | 282549.93 | 0 | 0 | 282559.93 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 86505 | 0 | 270 | 270 | SF | 0 | 0 | 0 | 10 | I don’t expect us to charge anything here work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0143-1020-L | IPCRP1 | IPCRP1 | 0143-1020 | Furn Formwork | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 86505 | 0 | 270 | 270 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0144-0000-L | IPCRP1 | IPCRP1 | 0144-0000 | EPOXY COATED ST FABRIC REINFORCEMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0144-0000-R | IPCRP1 | IPCRP1 | 0144-0000 | EPOXY COATED ST FABRIC REINFORCEMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9000 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | N | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0145-0000-L | IPCRP1 | IPCRP1 | 0145-0000 | EPOXY COATED REBAR FOR STRUCTURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0145-0000-R | IPCRP1 | IPCRP1 | 0145-0000 | EPOXY COATED REBAR FOR STRUCTURES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1970566 | 0 | 0 | 1970566 | 0 | 1970566 | 704982.98 | 0 | N | 1970566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1970566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0146-0000-L | IPCRP1 | IPCRP1 | 0146-0000 | STUD SHEAR CONNECTORS FOR BRIDGES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0146-0000-R | IPCRP1 | IPCRP1 | 0146-0000 | STUD SHEAR CONNECTORS FOR BRIDGES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 76320 | 0 | 0 | 76320 | 0 | 76320 | 73520 | 0 | N | 76320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0146-1000-L | IPCRP1 | IPCRP1 | 0146-1000 | Shear Stud Connectors for Bridges | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4764 | 3676 | 1088 | 4764 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0146-1000-S | IPCRP1 | IPCRP1 | 0146-1000 | Shear Stud Connectors for Bridges | N | S |  | NR | A | 45258 | 36252 | 36252 | 34922 | 36252 | 96.3312 | 0 | 0 | 0 | 0 | Y | 36252 | Y | 9006 | 0 | 0 | 45258 | 0 | 0 | 36252 | Y | 9006 | 0 | 0 | 45258 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36252 | 0 | 0 | 36252 | 0 | 0 | 0 | 0 | 0 | 0 | -36252 | 0 | 0 | 36252 | 36252 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3676 | 1088 | 4764 | LS | 4764 | 3676 | 1088 | 4764 | EA | 36252 | 1330 | 34922 | 0 | need to write SCO to JA Equipment for delta (+698ea) btwn IPC takeoff 4,514ea) & EE (3,816ea), as Subcontract was written to EE. Do after work completed, so only done once. J. ANTHONY EQUIPMENT CO., INC. @$36,252 (Total $224,252.00) PMF DSB (1,176) + CHB (2,640) + E10th (est 2 x 21 x 19FB = 798) = 4,514ea
Y | IPCRP1-0147-0000-L | IPCRP1 | IPCRP1 | 0147-0000 | SS SLAB W/ INTEGRAL WS, BTM FW REQD, TYPE 9 FRICT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0147-0000-R | IPCRP1 | IPCRP1 | 0147-0000 | SS SLAB W/ INTEGRAL WS, BTM FW REQD, TYPE 9 FRICT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1161000 | 0 | 0 | 1161000 | 0 | 1161000 | 632407.5 | 0 | N | 1161000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1000-E | IPCRP1 | IPCRP1 | 0147-1000 | Install & Strip Deck Formwork | N | E |  | NR | P | 36800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 36800 | 0 | 0 | 36800 | 0 | 0 | 0 | N | 36800 | 0 | 0 | 36800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 13320 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0147-1000-L | IPCRP1 | IPCRP1 | 0147-1000 | Install & Strip Deck Formwork | N | L |  | NR | P | 699786.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 699786.96 | 0 | 0 | 699786.96 | 0 | 0 | 0 | Y | 699786.96 | 0 | 0 | 699786.96 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5152 | 0 | 0 | 0 | 5152 | 0 | 0 | 0 | HR | 13320 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1020-E | IPCRP1 | IPCRP1 | 0147-1020 | Install & Strip Parapet Formwork | N | E |  | NR | P | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 3200 | 0 | 0 | 3200 | 0 | 0 | 0 | N | 3200 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 4000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1020-L | IPCRP1 | IPCRP1 | 0147-1020 | Install & Strip Parapet Formwork | N | L |  | NR | P | 52935.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 52935.84 | 0 | 0 | 52935.84 | 0 | 0 | 0 | Y | 52935.84 | 0 | 0 | 52935.84 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0147-1021-C | IPCRP1 | IPCRP1 | 0147-1021 | Bridge OH Bracket & Decking, Install-Remove | N | C |  | UNIT | U | 0 | 23692.69 | 23692.69 | 14722.51 | 23692.69 | 62.1395 | 0 | 0 | 0 | 0 | Y | 23692.69 | Y | -23692.69 | 0 | 0 | 0 | 0 | 0 | 23692.69 | Y | -23692.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23692.69 | 0 | 0 | 23692.69 | 0 | 0 | 0 | 0 | 0 | 0 | -23692.69 | 0 | 0 | 23692.69 | 23692.69 | 0 | 0 | 0 | 0 | 0 | 5529.09 | 5529.09 | 0 | 1355.69 | 4173.4 | 5529.09 | NA | 0 | 636 | 404 | 1040 | LF | 23692.69 | 8970.18 | 14722.51 | 0
Y | IPCRP1-0147-1021-L | IPCRP1 | IPCRP1 | 0147-1021 | Bridge OH Bracket & Decking, Install-Remove | N | L |  | UNIT | P | 0 | 99701.31 | 99701.31 | 99701.31 | 99701.31 | 38.3467 | 0 | 0 | 0 | 160298.69 | Y | 260000 | Y | -260000 | 0 | 0 | 0 | 0 | 0 | 260000 | Y | -260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -260000 | 0 | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | -260000 | 0 | 0 | 260000 | 260000 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 752 | 1248 | 2000 | HR | 0 | 636 | 404 | 1040 | LF | 0 | 0 | 0 | 160298.69 | DSB (2 x 210), CHB (2 x 160), E10St (2 x 150). Claim 60% install, 40% remove.
Y | IPCRP1-0147-1030-E | IPCRP1 | IPCRP1 | 0147-1030 | Set Up Screed | N | E |  | NR | P | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 6600 | 0 | 0 | 6600 | 0 | 0 | 0 | N | 6600 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 3 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1030-L | IPCRP1 | IPCRP1 | 0147-1030 | Set Up Screed | N | L |  | NR | P | 18531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 18531 | 0 | 0 | 18531 | 0 | 0 | 0 | Y | 18531 | 0 | 0 | 18531 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | HR | 3 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0147-1040-C | IPCRP1 | IPCRP1 | 0147-1040 | Place Concrete | N | C |  | NR | P | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 2280 | 0 | 0 | 2280 | 0 | 0 | 0 | N | 2280 | 0 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 836 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0147-1040-E | IPCRP1 | IPCRP1 | 0147-1040 | Place Concrete | N | E |  | NR | P | 30300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 30300 | 0 | 0 | 30300 | 0 | 0 | 0 | N | 30300 | 0 | 0 | 30300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 836 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1040-L | IPCRP1 | IPCRP1 | 0147-1040 | Place Concrete | N | L |  | NR | P | 203590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 203590 | 0 | 0 | 203590 | 0 | 0 | 0 | Y | 203590 | 0 | 0 | 203590 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 0 | 0 | 0 | 1836 | 0 | 0 | 0 | HR | 836 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1050-C | IPCRP1 | IPCRP1 | 0147-1050 | F&I SIP Formwork - Sub | N | C |  | UNIT | U | 0 | 21045.9 | 21045.9 | 19958 | 21045.9 | 94.8308 | 0 | 0 | 0 | 0 | Y | 21045.9 | Y | -21045.9 | 0 | 0 | 0 | 0 | 0 | 21045.9 | Y | -21045.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21045.9 | 0 | 0 | 21045.9 | 0 | 0 | 0 | 0 | 0 | 0 | -21045.9 | 0 | 0 | 21045.9 | 21045.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | -84 | 0 | NA | 1100 | 0 | 0 | 0 | SY | 13345.9 | 1087.9 | 12258 | 0
Y | IPCRP1-0147-1050-L | IPCRP1 | IPCRP1 | 0147-1050 | F&I SIP Formwork - Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1100 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1050-S | IPCRP1 | IPCRP1 | 0147-1050 | F&I SIP Formwork - Sub | N | S |  | NR | P | 136950 | 188000 | 188000 | 142880 | 188000 | 76 | 0 | 0 | 0 | 0 | Y | 188000 | Y | -51050 | 0 | 0 | 136950 | 0 | 0 | 188000 | Y | -51050 | 0 | 0 | 136950 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -188000 | 0 | 0 | 188000 | 0 | 0 | 0 | 0 | 0 | 0 | -188000 | 0 | 0 | 188000 | 188000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.52 | -1.52 | 0 | MO | 1100 | 0 | 0 | 0 | SY | 188000 | 45120 | 142880 | 0 | J. ANTHONY EQUIPMENT CO., INC. @$188,000 (Total $224,252.00)
Y | IPCRP1-0147-1060-C | IPCRP1 | IPCRP1 | 0147-1060 | Furn Formwork | N | C |  | NR | P | 94290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 94290 | 0 | 0 | 94290 | 0 | 0 | 0 | N | 94290 | 0 | 0 | 94290 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 13320 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0147-1060-L | IPCRP1 | IPCRP1 | 0147-1060 | Furn Formwork | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 13320 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0147-1070-L | IPCRP1 | IPCRP1 | 0147-1070 | Structural Concrete Sub (D’Annunzio) | N | L |  | UNIT | P | 0 | 33547.84 | 33547.84 | 33547.84 | 33547.84 | 99.9941 | 0 | 0 | 0 | 1.98 | Y | 33549.82 | Y | -33549.82 | 0 | 0 | 0 | 0 | 0 | 33549.82 | Y | -33549.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -33549.82 | 0 | 0 | 33549.82 | 0 | 0 | 0 | 0 | 0 | 0 | -33549.82 | 0 | 0 | 33549.82 | 33549.82 | 0 | 0 | 0 | 0 | 0 | 253 | 253 | 0 | 253 | 0 | 253 | HR | 1 | 0.35 | 0.65 | 1 | LS | 0 | 0 | 0 | 1.98
Y | IPCRP1-0147-1070-S | IPCRP1 | IPCRP1 | 0147-1070 | Structural Concrete Sub (D’Annunzio) | N | S |  | UNIT | A | 0 | 15383771.32 | 15383771.32 | 5198125.06 | 15383771.32 | 34.6183 | 0 | 0 | 0 | -368209 | Y | 15015562.32 | Y | -15015562.32 | 0 | 0 | 0 | 0 | 0 | 15015562.32 | Y | -15015562.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15015562.32 | 0 | 0 | 15015562.32 | 0 | 0 | 0 | 0 | 125264.22 | 0 | -15015562.32 | 0 | 0 | 15015562.32 | 15015562.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10897.24 | -10897.24 | 0 | NA | 1 | 0.35 | 0.65 | 1 | LS | 15383771.32 | 10185646.26 | 5198125.06 | -368209 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0148-0000-L | IPCRP1 | IPCRP1 | 0148-0000 | STRUCT APP SLAB W/ INTEGRAL WS, TYPE 1 FRICTION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0148-0000-R | IPCRP1 | IPCRP1 | 0148-0000 | STRUCT APP SLAB W/ INTEGRAL WS, TYPE 1 FRICTION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 49320 | 0 | 0 | 49320 | 0 | 49320 | 24548.4 | 0 | N | 49320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0148-1000-L | IPCRP1 | IPCRP1 | 0148-1000 | Install & Strip Formwork - App Slabs | N | L |  | NR | P | 959.45 | 3230.1 | 3230.1 | 3230.1 | 3230.1 | 30.2729 | 0 | 0 | 0 | 7439.83 | Y | 10669.93 | Y | -9710.48 | 0 | 0 | 959.45 | 0 | 0 | 10669.93 | Y | -9710.48 | 0 | 0 | 959.45 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10669.93 | 0 | 0 | 10669.93 | 0 | 0 | 0 | 0 | 0 | 0 | -10669.93 | 0 | 0 | 10669.93 | 10669.93 | 0 | 0 | 0 | 8.12 | 0 | 80 | 80 | 8.12 | 25.5 | 54.5 | 80 | HR | 72.46 | 155.8 | 368.2 | 524 | SF | 0 | 0 | 0 | 7439.83 | 50% item self-performed (Flood Gates), 50% item included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0148-1010-C | IPCRP1 | IPCRP1 | 0148-1010 | Place Concrete - App Slabs | N | C |  | NR | P | 95.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 95.7 | 0 | 0 | 95.7 | 0 | 0 | 0 | N | 95.7 | 0 | 0 | 95.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 28.99 | 8.74 | 78.63 | 87.37 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0148-1010-E | IPCRP1 | IPCRP1 | 0148-1010 | Place Concrete - App Slabs | N | E |  | NR | P | 6105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 6105 | 0 | 0 | 6105 | 0 | 0 | 0 | N | 6105 | 0 | 0 | 6105 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 28.99 | 8.74 | 78.63 | 87.37 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0148-1010-L | IPCRP1 | IPCRP1 | 0148-1010 | Place Concrete - App Slabs | N | L |  | NR | P | 24520 | 8731.35 | 8731.35 | 8731.35 | 8731.35 | 17.4511 | 0 | 0 | 0 | 41301.76 | Y | 50033.11 | Y | -25513.11 | 0 | 0 | 24520 | 0 | 0 | 50033.11 | Y | -25513.11 | 0 | 0 | 24520 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50033.11 | 0 | 0 | 50033.11 | 0 | 0 | 0 | 0 | 0 | 0 | -50033.11 | 0 | 0 | 50033.11 | 50033.11 | 0 | 0 | 0 | 210.51 | 0 | 415.3 | 415.3 | 210.51 | 71.5 | 343.8 | 415.3 | HR | 28.99 | 8.74 | 78.63 | 87.37 | CY | 0 | 0 | 0 | 41301.76 | 2. As / SS (10/3) DT takeoff for IPC FG App Slabs used to update PMF. Including JDA App slabs for Bridges there will be a 7% underrun of EE quantity 50% item self-performed (Flood Gates), 50% item included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0148-1020-C | IPCRP1 | IPCRP1 | 0148-1020 | Furn Formwork | N | C |  | NR | P | 394.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 394.47 | 0 | 0 | 394.47 | 0 | 0 | 0 | N | 394.47 | 0 | 0 | 394.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 72.46 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Note worth tracking, made PMF = $0.00 as per VS
Y | IPCRP1-0148-1020-L | IPCRP1 | IPCRP1 | 0148-1020 | Furn Formwork | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 72.46 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0149-0000-L | IPCRP1 | IPCRP1 | 0149-0000 | WINTER SURF TREATMENT - SS SLAB & APP SLAB | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0149-0000-R | IPCRP1 | IPCRP1 | 0149-0000 | WINTER SURF TREATMENT - SS SLAB & APP SLAB | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 55700 | 0 | 0 | 55700 | 0 | 55700 | 0 | 0 | N | 55700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0149-1000-C | IPCRP1 | IPCRP1 | 0149-1000 | WINTER SURF TREATMENT - SS SLAB & APP SLAB | N | C |  | NR | P | 1306.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1306.56 | 0 | 0 | 1306.56 | 0 | 0 | 0 | Y | 1306.56 | 0 | 0 | 1306.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1114 | 0 | 370 | 370 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0149-1000-E | IPCRP1 | IPCRP1 | 0149-1000 | WINTER SURF TREATMENT - SS SLAB & APP SLAB | N | E |  | NR | P | 21018.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 21018.75 | 0 | 0 | 21018.75 | 0 | 0 | 0 | Y | 21018.75 | 0 | 0 | 21018.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1114 | 0 | 370 | 370 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0149-1000-L | IPCRP1 | IPCRP1 | 0149-1000 | WINTER SURF TREATMENT - SS SLAB & APP SLAB | N | L |  | NR | P | 146686.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48895 | Y | 48895 | Y | 97791.5 | 0 | 0 | 146686.5 | 0 | 0 | 48895 | Y | 97791.5 | 0 | 0 | 146686.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -48895 | 0 | 0 | 48895 | 0 | 0 | 0 | 0 | 0 | 0 | -48895 | 0 | 0 | 48895 | 48895 | 0 | 0 | 0 | 1345.2 | 0 | 448.41 | 448.41 | 1345.2 | 0 | 448.41 | 448.41 | HR | 1114 | 0 | 370 | 370 | SY | 0 | 0 | 0 | 48895
Y | IPCRP1-0149-1010-L | IPCRP1 | IPCRP1 | 0149-1010 | Operators for Winter Conc for Deck & App Slabs | N | L |  | NR | P | 66118.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22040 | Y | 22040 | Y | 44078.5 | 0 | 0 | 66118.5 | 0 | 0 | 22040 | Y | 44078.5 | 0 | 0 | 66118.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22040 | 0 | 0 | 22040 | 0 | 0 | 0 | 0 | 0 | 0 | -22040 | 0 | 0 | 22040 | 22040 | 0 | 0 | 0 | 504 | 0 | 168 | 168 | 504 | 0 | 168 | 168 | HR | 21 | 0 | 7 | 7 | HR | 0 | 0 | 0 | 22040 | DSB & CHB completed, item not used, reduced by 2/3.
Y | IPCRP1-0150-0000-L | IPCRP1 | IPCRP1 | 0150-0000 | PROT SEALING OF STRUCT CONCRETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0150-0000-R | IPCRP1 | IPCRP1 | 0150-0000 | PROT SEALING OF STRUCT CONCRETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 462294 | 0 | 0 | 462294 | 0 | 462294 | 113312.7 | 0 | N | 462294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0150-1000-L | IPCRP1 | IPCRP1 | 0150-1000 | Prot Seal of Struct Concrete | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 154098 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0150-1000-S | IPCRP1 | IPCRP1 | 0150-1000 | Prot Seal of Struct Concrete | N | S |  | NR | P | 462294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 462294 | 0 | 0 | 462294 | 0 | 0 | 0 | N | 462294 | 0 | 0 | 462294 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 154098 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work included in Sheet Applied Waterproofing Membrane Sub (D-Star), cost code 0178-1000
Y | IPCRP1-0151-0000-L | IPCRP1 | IPCRP1 | 0151-0000 | PROT SEAL CONC ON NEW BRIDGE DECKS & OVERLAYS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0151-0000-R | IPCRP1 | IPCRP1 | 0151-0000 | PROT SEAL CONC ON NEW BRIDGE DECKS & OVERLAYS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 23120 | 0 | 0 | 23120 | 0 | 23120 | 11924.8 | 0 | N | 23120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0151-1000-L | IPCRP1 | IPCRP1 | 0151-1000 | Protect Seal Conc on New Bridge Decks & Overlays | N | L |  | UNIT | P | 0 | -0.63 | -0.63 | -0.63 | -0.63 | 0 | 0 | 0 | 0 | 0.63 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 23120 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0.63
Y | IPCRP1-0151-1000-S | IPCRP1 | IPCRP1 | 0151-1000 | Protect Seal Conc on New Bridge Decks & Overlays | N | S |  | NR | P | 23120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 23120 | 0 | 0 | 23120 | 0 | 0 | 0 | N | 23120 | 0 | 0 | 23120 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 23120 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work included in Sheet Applied Waterproofing Membrane Sub (D-Star), cost code 0178-1000
Y | IPCRP1-0152-0000-L | IPCRP1 | IPCRP1 | 0152-0000 | ANTI-GRAFFITI PROTECTION COATING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0152-0000-R | IPCRP1 | IPCRP1 | 0152-0000 | ANTI-GRAFFITI PROTECTION COATING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 78750 | 0 | 0 | 78750 | 0 | 78750 | 88245 | 0 | N | 78750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0152-1000-L | IPCRP1 | IPCRP1 | 0152-1000 | ANTI-GRAFFITI PROTECTION COATING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1750 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0152-1000-S | IPCRP1 | IPCRP1 | 0152-1000 | ANTI-GRAFFITI PROTECTION COATING | N | S |  | NR | P | 74999.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 74999.93 | 0 | 0 | 74999.93 | 0 | 0 | 0 | N | 74999.93 | 0 | 0 | 74999.93 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1750 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | Work included in painting/lead abatement sub (Crossroads JV) cc: 0717-1090.
Y | IPCRP1-0153-0000-L | IPCRP1 | IPCRP1 | 0153-0000 | REM OF STONE MASONRY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0153-0000-R | IPCRP1 | IPCRP1 | 0153-0000 | REM OF STONE MASONRY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 108250 | 0 | 0 | 108250 | 0 | 108250 | 107214 | 0 | N | 108250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0154-0000-L | IPCRP1 | IPCRP1 | 0154-0000 | PS CONC I-BEAM (AASHTO TYPE 1 GIRDER) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0154-0000-R | IPCRP1 | IPCRP1 | 0154-0000 | PS CONC I-BEAM (AASHTO TYPE 1 GIRDER) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 386400 | 0 | 0 | 386400 | 0 | 386400 | 386946 | 0 | N | 386400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0155-0000-L | IPCRP1 | IPCRP1 | 0155-0000 | PS CONC I-BEAM (AASHTO TYPE 5 GIRDER) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0155-0000-R | IPCRP1 | IPCRP1 | 0155-0000 | PS CONC I-BEAM (AASHTO TYPE 5 GIRDER) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 21749200 | 0 | 0 | 21749200 | 0 | 21749200 | 0 | 0 | N | 21749200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21749200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0156-0000-L | IPCRP1 | IPCRP1 | 0156-0000 | PS HOLLOW SLAB UNITS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0156-0000-R | IPCRP1 | IPCRP1 | 0156-0000 | PS HOLLOW SLAB UNITS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 698000 | 0 | 0 | 698000 | 0 | 698000 | 1275589.19 | 0 | N | 698000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0157-0000-L | IPCRP1 | IPCRP1 | 0157-0000 | BRIDGE HANGER ASSEMBLIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0157-0000-R | IPCRP1 | IPCRP1 | 0157-0000 | BRIDGE HANGER ASSEMBLIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7750000 | 0 | 0 | 7750000 | 0 | 7750000 | 5704542.56 | 0 | N | 7750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0158-0000-L | IPCRP1 | IPCRP1 | 0158-0000 | STRUCT STEEL (TYPE 1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0158-0000-R | IPCRP1 | IPCRP1 | 0158-0000 | STRUCT STEEL (TYPE 1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7750000 | 0 | 0 | 7750000 | 0 | 7750000 | 7175310.8 | 0 | N | 7750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0159-0000-L | IPCRP1 | IPCRP1 | 0159-0000 | STRUCT STEEL (TYPE 2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0159-0000-R | IPCRP1 | IPCRP1 | 0159-0000 | STRUCT STEEL (TYPE 2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25000000 | 0 | 0 | 25000000 | 0 | 25000000 | 20154800.33 | 0 | N | 25000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0159-1000-C | IPCRP1 | IPCRP1 | 0159-1000 | Structural Steel Subcontractor (ASW) | N | C |  | UNIT | U | 0 | 2911076 | 2911076 | 420076 | 2911076 | 155.5399 | 0 | 0 | 0 | -2641000 | Y | 270076 | Y | -270076 | 0 | 0 | 0 | 0 | 0 | 270076 | Y | -270076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -270076 | 0 | 150000 | 270076 | 0 | 0 | 0 | 0 | 2641000 | 0 | -270076 | 0 | 0 | 270076 | 270076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | -150000 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 2641000 | 2491000 | 150000 | -2641000
Y | IPCRP1-0159-1000-L | IPCRP1 | IPCRP1 | 0159-1000 | Structural Steel Subcontractor (ASW) | N | L |  | UNIT | P | 0 | 4179.33 | 4179.33 | 4179.33 | 4179.33 | 100 | 0 | 0 | 0 | 0 | Y | 4179.33 | Y | -4179.33 | 0 | 0 | 0 | 0 | 0 | 4179.33 | Y | -4179.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4179.33 | 0 | 0 | 4179.33 | 0 | 0 | 0 | 0 | 0 | 0 | -4179.33 | 0 | 0 | 4179.33 | 4179.33 | 0 | 0 | 0 | 0 | 0 | 35.5 | 35.5 | 0 | 35.5 | 0 | 35.5 | HR | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0159-1000-S | IPCRP1 | IPCRP1 | 0159-1000 | Structural Steel Subcontractor (ASW) | N | S |  | NR | A | 32126283 | 57783502.79 | 57783502.79 | 35111678.03 | 57783502.79 | 63.2071 | 0 | 0 | 0 | -2233333.33 | Y | 55550169.46 | Y | -23423886.46 | 0 | 0 | 32126283 | 0 | 0 | 55550169.46 | Y | -23423886.46 | 0 | 0 | 32126283 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -55550169.46 | 0 | 0 | 55550169.46 | 0 | 0 | 0 | 133333.33 | 0 | 0 | -55550169.46 | 0 | 0 | 55550169.46 | 55550169.46 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4388.76 | 21204.45 | 25593.21 | LS | 1 | 0.65 | 0.35 | 1 | LS | 57783502.79 | 22671824.76 | 35111678.03 | -2233333.33 | ASW Base Contract 29.5M. CO #1 (139K) due to relocated temp bridge location w/ added span. IPC decided to change the location of temporary bridge to minimize the delays in schedule and additional costs.
Y | IPCRP1-0160-0000-L | IPCRP1 | IPCRP1 | 0160-0000 | NON-GUIDED PTFE SLIDING BEARINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0160-0000-R | IPCRP1 | IPCRP1 | 0160-0000 | NON-GUIDED PTFE SLIDING BEARINGS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1813500 | 0 | 0 | 1813500 | 0 | 1813500 | 976500 | 0 | N | 1813500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0160-1000-L | IPCRP1 | IPCRP1 | 0160-1000 | NON-GUIDED PTFE SLIDING BEARINGS | N | L |  | UNIT | P | 0 | 273809.18 | 273809.18 | 273809.18 | 273809.18 | 48.8387 | 0 | 0 | 0 | 286830.82 | Y | 560640 | Y | -560640 | 0 | 0 | 0 | 0 | 0 | 560640 | Y | -560640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -560640 | 0 | 0 | 560640 | 0 | 0 | 0 | 0 | 0 | 0 | -560640 | 0 | 0 | 560640 | 560640 | 0 | 0 | 0 | 0 | 0 | 4672 | 4672 | 0 | 2189.5 | 2482.5 | 4672 | HR | 1209 | 651 | 558 | 1209 | EA | 0 | 0 | 0 | 286830.82 | Drill (for 3/4 in bolt) 5,000ea x production rate: 2men x 4/hr x 7hr = 28/day, say 30ea/day 167 days, Grout (for 3/4in bolt), 5,000ea x production rate: 2men x 6/hr x 7hr = 42/day, say 40ea/day, 125 days, 292 days x 8hr x 2 men = 4,672 hrs @ $120/hr = $560,640.00
Y | IPCRP1-0160-1000-M | IPCRP1 | IPCRP1 | 0160-1000 | NON-GUIDED PTFE SLIDING BEARINGS | N | M |  | NR | P | 1209000 | 2428932.66 | 2428932.66 | 1550259.17 | 2428932.66 | 63.8247 | 0 | 0 | 0 | 0 | Y | 2428932.66 | Y | -1219932.66 | 0 | 0 | 1209000 | 0 | 0 | 2428932.66 | Y | -1219932.66 | 0 | 0 | 1209000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2428932.66 | 0 | 0 | 2428932.66 | 0 | 0 | 0 | 0 | 0 | 0 | -2428932.66 | 0 | 0 | 2428932.66 | 2428932.66 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1550068.51 | -1550068.51 | 0 | LS | 1209 | 651 | 558 | 1209 | EA | 2428932.66 | 878673.49 | 1550259.17 | 0
Y | IPCRP1-0161-0000-L | IPCRP1 | IPCRP1 | 0161-0000 | TYPE M.R. EXPAN BEARINGS (226-450 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0161-0000-R | IPCRP1 | IPCRP1 | 0161-0000 | TYPE M.R. EXPAN BEARINGS (226-450 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 20000 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0162-0000-L | IPCRP1 | IPCRP1 | 0162-0000 | TYPE M.R. EXPAN BEARINGS (451-675 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0162-0000-R | IPCRP1 | IPCRP1 | 0162-0000 | TYPE M.R. EXPAN BEARINGS (451-675 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0163-0000-L | IPCRP1 | IPCRP1 | 0163-0000 | TYPE M.R. FIXED BEARINGS (226-450 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0163-0000-R | IPCRP1 | IPCRP1 | 0163-0000 | TYPE M.R. FIXED BEARINGS (226-450 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 20000 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0164-0000-L | IPCRP1 | IPCRP1 | 0164-0000 | TYPE M.R. FIXED BEARINGS (451-675 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0164-0000-R | IPCRP1 | IPCRP1 | 0164-0000 | TYPE M.R. FIXED BEARINGS (451-675 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0165-0000-L | IPCRP1 | IPCRP1 | 0165-0000 | TYPE E.P. BEARINGS (ALL LOAD RANGES) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0165-0000-R | IPCRP1 | IPCRP1 | 0165-0000 | TYPE E.P. BEARINGS (ALL LOAD RANGES) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 228300 | 0 | 0 | 228300 | 0 | 228300 | 4200 | 0 | N | 228300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0165-1000-L | IPCRP1 | IPCRP1 | 0165-1000 | TYPE EP Bearings (All Load Ranges) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 761 | 840 | 0 | 840 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0165-1000-M | IPCRP1 | IPCRP1 | 0165-1000 | TYPE EP Bearings (All Load Ranges) | N | M |  | UNIT | U | 0 | 500989.5 | 500989.5 | 496004.4 | 500989.5 | 99.0049 | 0 | 0 | 0 | 0 | Y | 500989.5 | Y | -500989.5 | 0 | 0 | 0 | 0 | 0 | 500989.5 | Y | -500989.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -500989.5 | 0 | 0 | 500989.5 | 0 | 0 | 0 | 0 | 0 | 0 | -500989.5 | 0 | 0 | 500989.5 | 500989.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7934.48 | -7934.48 | 0 | NA | 761 | 840 | 0 | 840 | EA | 500989.5 | 4985.1 | 496004.4 | 0 | DSB has F&D all BP for project. Phase 1 installed (298ea - VECP, 106ea - Type EL, 14ea - Type EP). Phase 2 at P-Park. D.S. Brown has fabricated and delivered all bearings for the project. Phase 1 installation is 100% complete, with remaining bearings stored at P-Park. Assuming this code applies to all bearings, regardless of VE or base contract work Phase 1 Installations: VE: 298 Bearings Base EL: 106 Bearings Base EP: 14 Bearings.
Y | IPCRP1-0165-1000-S | IPCRP1 | IPCRP1 | 0165-1000 | TYPE EP Bearings (All Load Ranges) | N | S |  | NR | A | 319834.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 319834.45 | 0 | 0 | 319834.45 | 0 | 0 | 0 | Y | 319834.45 | 0 | 0 | 319834.45 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 761 | 840 | 0 | 840 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0166-0000-L | IPCRP1 | IPCRP1 | 0166-0000 | TYPE E.L. BEARINGS (0-55 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0166-0000-R | IPCRP1 | IPCRP1 | 0166-0000 | TYPE E.L. BEARINGS (0-55 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18000 | 0 | 0 | 18000 | 0 | 18000 | 13000 | 0 | N | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0167-0000-L | IPCRP1 | IPCRP1 | 0167-0000 | TYPE E.L. BEARINGS (56-111 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0167-0000-R | IPCRP1 | IPCRP1 | 0167-0000 | TYPE E.L. BEARINGS (56-111 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 121000 | 0 | 0 | 121000 | 0 | 121000 | 36500 | 0 | N | 121000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0168-0000-L | IPCRP1 | IPCRP1 | 0168-0000 | TYPE E.L. BEARINGS (112-168 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0168-0000-R | IPCRP1 | IPCRP1 | 0168-0000 | TYPE E.L. BEARINGS (112-168 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 368000 | 0 | 0 | 368000 | 0 | 368000 | 0 | 0 | N | 368000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0169-0000-L | IPCRP1 | IPCRP1 | 0169-0000 | TYPE E.L. BEARINGS (169-225 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0169-0000-R | IPCRP1 | IPCRP1 | 0169-0000 | TYPE E.L. BEARINGS (169-225 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 159000 | 0 | 0 | 159000 | 0 | 159000 | 9500 | 0 | N | 159000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0170-0000-L | IPCRP1 | IPCRP1 | 0170-0000 | TYPE E.L. BEARINGS (+225 KIPS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0170-0000-R | IPCRP1 | IPCRP1 | 0170-0000 | TYPE E.L. BEARINGS (+225 KIPS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0171-0000-L | IPCRP1 | IPCRP1 | 0171-0000 | ARMORLESS BRIDGE JOINT SYSTEM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0171-0000-R | IPCRP1 | IPCRP1 | 0171-0000 | ARMORLESS BRIDGE JOINT SYSTEM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 36600 | 0 | 0 | 36600 | 0 | 36600 | 18498 | 0 | N | 36600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0171-1000-L | IPCRP1 | IPCRP1 | 0171-1000 | ARMORLESS BRIDGE JOINT SYSTEM | N | L |  | NR | P | 30574.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 30574.56 | 0 | 0 | 30574.56 | 0 | 0 | 0 | Y | 30574.56 | 0 | 0 | 30574.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 200 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0171-1000-M | IPCRP1 | IPCRP1 | 0171-1000 | ARMORLESS BRIDGE JOINT SYSTEM | N | M |  | NR | P | 12440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 12440 | 0 | 0 | 12440 | 0 | 0 | 0 | N | 12440 | 0 | 0 | 12440 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 200 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0172-0000-L | IPCRP1 | IPCRP1 | 0172-0000 | METAL HANDRAIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0172-0000-R | IPCRP1 | IPCRP1 | 0172-0000 | METAL HANDRAIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1077000 | 0 | 0 | 1077000 | 0 | 1077000 | 0 | 0 | N | 1077000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0173-0000-L | IPCRP1 | IPCRP1 | 0173-0000 | VERTICAL FACED CONC PARAPET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0173-0000-R | IPCRP1 | IPCRP1 | 0173-0000 | VERTICAL FACED CONC PARAPET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1365700 | 0 | 0 | 1365700 | 0 | 1365700 | 399819 | 0 | N | 1365700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1365700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0173-1000-E | IPCRP1 | IPCRP1 | 0173-1000 | Install & Strip Formwork | N | E |  | NR | P | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | N | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 27314 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0173-1000-L | IPCRP1 | IPCRP1 | 0173-1000 | Install & Strip Formwork | N | L |  | NR | P | 330849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 330849 | 0 | 0 | 330849 | 0 | 0 | 0 | Y | 330849 | 0 | 0 | 330849 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | HR | 27314 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0173-1010-C | IPCRP1 | IPCRP1 | 0173-1010 | Place Concrete | N | C |  | NR | P | 1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1518 | 0 | 0 | 1518 | 0 | 0 | 0 | N | 1518 | 0 | 0 | 1518 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 506 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0173-1010-E | IPCRP1 | IPCRP1 | 0173-1010 | Place Concrete | N | E |  | NR | P | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | N | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 506 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0173-1010-L | IPCRP1 | IPCRP1 | 0173-1010 | Place Concrete | N | L |  | NR | P | 85666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 85666 | 0 | 0 | 85666 | 0 | 0 | 0 | Y | 85666 | 0 | 0 | 85666 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795.6 | 0 | 0 | 0 | 795.6 | 0 | 0 | 0 | HR | 506 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0173-1020-C | IPCRP1 | IPCRP1 | 0173-1020 | Furn Formwork | N | C |  | NR | P | 98140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 98140 | 0 | 0 | 98140 | 0 | 0 | 0 | N | 98140 | 0 | 0 | 98140 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SH | 27314 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0173-1020-L | IPCRP1 | IPCRP1 | 0173-1020 | Furn Formwork | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 27314 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0174-0000-L | IPCRP1 | IPCRP1 | 0174-0000 | REM OF STRUCT CONCRETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0174-0000-R | IPCRP1 | IPCRP1 | 0174-0000 | REM OF STRUCT CONCRETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 133000 | 0 | 0 | 133000 | 0 | 133000 | 172396 | 0 | N | 133000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0174-1000-L | IPCRP1 | IPCRP1 | 0174-1000 | Removal of Struct Concrete (Self Perform) | N | L |  | UNIT | P | 0 | 112.21 | 112.21 | 112.21 | 112.21 | 1.1221 | 0 | 0 | 0 | 9887.79 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 112.21 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 1 | 74 | 75 | HR | 0 | 0 | 5 | 5 | CY | 0 | 0 | 0 | 9887.79 | This work scope was originally included in Gateways subcontract, but we will be self-performing.
Y | IPCRP1-0175-0000-L | IPCRP1 | IPCRP1 | 0175-0000 | REM STRUCT CONC - REPLACE W/ CL D CONC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0175-0000-R | IPCRP1 | IPCRP1 | 0175-0000 | REM STRUCT CONC - REPLACE W/ CL D CONC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 742440 | 0 | 0 | 742440 | 0 | 742440 | 7353.6 | 0 | N | 742440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0176-0000-L | IPCRP1 | IPCRP1 | 0176-0000 | REM STRUCT CONC - REPLACE W/ V&O PATCH MAT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0176-0000-R | IPCRP1 | IPCRP1 | 0176-0000 | REM STRUCT CONC - REPLACE W/ V&O PATCH MAT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 227200 | 0 | 0 | 227200 | 0 | 227200 | 15776 | 0 | N | 227200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0176-1000-L | IPCRP1 | IPCRP1 | 0176-1000 | Rem Conc, Replace w/ V&O or Class D Conc | N | L |  | UNIT | P | 0 | 58003.87 | 58003.87 | 58003.87 | 58003.87 | 48.3366 | 0 | 0 | 0 | 61996.13 | Y | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -120000 | 140.8 | -112.21 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | -120000 | 0 | 0 | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 942.07 | 942.07 | 0 | 490 | 452.07 | 942.07 | HR | 1 | 159.88 | 40.12 | 200 | SF | 0 | 0 | 0 | 61996.13 | Providence bid budget was $223,790
Y | IPCRP1-0176-1000-S | IPCRP1 | IPCRP1 | 0176-1000 | Rem Conc, Replace w/ V&O or Class D Conc | N | S |  | NR | A | 875941 | 779.27 | 779.27 | 779.27 | 779.27 | 100 | 0 | 0 | 0 | 0 | Y | 779.27 | Y | 875161.73 | 0 | 0 | 875941 | 0 | 0 | 779.27 | Y | 875161.73 | 0 | 0 | 875941 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -779.27 | 0 | 524.21 | 779.27 | 0 | 0 | 0 | 0 | 0 | 0 | -779.27 | 0 | 0 | 779.27 | 779.27 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | -1 | 1 | NA | 1 | 159.88 | 40.12 | 200 | SF | 779.27 | 0 | 779.27 | 0 | Originally gave to Providence Const for $1,839,977. Eliminated entire scope from their subcontract due to lack of quantity, and left 800 SF in for IPC to self perform.
Y | IPCRP1-0177-0000-L | IPCRP1 | IPCRP1 | 0177-0000 | D&G BOLTS OR REBAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0177-0000-R | IPCRP1 | IPCRP1 | 0177-0000 | D&G BOLTS OR REBAR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1058750 | 0 | 0 | 1058750 | 0 | 1058750 | 1480900 | 0 | N | 1058750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0177-1000-C | IPCRP1 | IPCRP1 | 0177-1000 | D&G BOLTS OR REBAR | N | C |  | UNIT | U | 0 | 63093.97 | 63093.97 | 59533.46 | 63093.97 | 29.7667 | 0 | 0 | 0 | 136906.03 | Y | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200000 | 0 | -2216.04 | 200000 | 0 | 0 | 0 | -2216.04 | 0 | 0 | -200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947 | -1947 | 0 | LS | 12143 | 6975 | 5168 | 12143 | EA | 63093.97 | 3560.51 | 59533.46 | 136906.03
Y | IPCRP1-0177-1000-L | IPCRP1 | IPCRP1 | 0177-1000 | D&G BOLTS OR REBAR | N | L |  | UNIT | P | 0 | 337312.37 | 337312.37 | 337312.37 | 337312.37 | 37.0982 | 0 | 0 | 0 | 571929.35 | Y | 909241.72 | Y | -909241.72 | 0 | 0 | 0 | 0 | 0 | 909241.72 | Y | -909241.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -909241.72 | 0 | 0 | 909241.72 | 0 | 0 | 0 | 0 | 0 | 0 | -909241.72 | 0 | 0 | 909241.72 | 909241.72 | 0 | 0 | 0 | 0 | 0 | 7000.1 | 7000.1 | 0 | 2920.5 | 4079.6 | 7000.1 | HR | 12143 | 6975 | 5168 | 12143 | EA | 0 | 0 | 0 | 571929.35 | DDC removed 60.00 ea under seq #1770, and will add back in under seq #51670 in Sept CO payment. As of Nov 2025 DDC paid seq #1770 (3,781.25 ea) + seq #1771 (961.75ea) + seq#51670 (1,958.00ea) = 6,701.00 ea
Y | IPCRP1-0177-1000-M | IPCRP1 | IPCRP1 | 0177-1000 | D&G BOLTS OR REBAR | N | M |  | UNIT | U | 0 | 124861.29 | 124861.29 | 106295.57 | 124861.29 | 53.1478 | 0 | 0 | 0 | 75138.71 | Y | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200000 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4708 | -4708 | 0 | LS | 12143 | 6975 | 5168 | 12143 | EA | 124861.29 | 18565.72 | 106295.57 | 75138.71
Y | IPCRP1-0177-1000-S | IPCRP1 | IPCRP1 | 0177-1000 | D&G BOLTS OR REBAR | N | S |  | NR | A | 2981206.07 | 955840 | 955840 | 532015 | 955840 | 46.2622 | 0 | 0 | 0 | 194160 | Y | 1150000 | Y | 1831206.07 | 0 | 0 | 2981206.07 | 0 | 0 | 1150000 | Y | 1831206.07 | 0 | 0 | 2981206.07 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1150000 | 0 | 0 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 | -1150000 | 0 | 0 | 1150000 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2975.78 | -2975.78 | 0 | NA | 12143 | 6975 | 5168 | 12143 | EA | 955840 | 423825 | 532015 | 194160
Y | IPCRP1-0178-0000-L | IPCRP1 | IPCRP1 | 0178-0000 | SHEET APPLIED WATERPROOF MEMBRANE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0178-0000-R | IPCRP1 | IPCRP1 | 0178-0000 | SHEET APPLIED WATERPROOF MEMBRANE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 894360 | 0 | 0 | 894360 | 0 | 894360 | 429473.55 | 0 | N | 894360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0178-1000-L | IPCRP1 | IPCRP1 | 0178-1000 | Sheet Applied Waterproofing Membrane Sub (D-Star) | N | L |  | UNIT | P | 0 | 580.03 | 580.03 | 580.03 | 580.03 | 100 | 0 | 0 | 0 | 0 | Y | 580.03 | Y | -580.03 | 0 | 0 | 0 | 0 | 0 | 580.03 | Y | -580.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -580.03 | 0 | 0 | 580.03 | 0 | 0 | 0 | 0 | 0 | 0 | -580.03 | 0 | 0 | 580.03 | 580.03 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | HR | 1 | 0.43 | 0.57 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0178-1000-S | IPCRP1 | IPCRP1 | 0178-1000 | Sheet Applied Waterproofing Membrane Sub (D-Star) | N | S |  | NR | P | 894360 | 1902957.4 | 1902957.4 | 838627.07 | 1902957.4 | 44.0697 | 0 | 0 | 0 | 0 | Y | 1902957.4 | Y | -1008597.4 | 0 | 0 | 894360 | 0 | 0 | 1902957.4 | Y | -1008597.4 | 0 | 0 | 894360 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1902957.4 | 0 | 24022.44 | 1902957.4 | 0 | 0 | 0 | 0 | 0 | 0 | -1902957.4 | 0 | 0 | 1902957.4 | 1902957.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 176193.42 | 0 | 176193.42 | EA | 1 | 0.43 | 0.57 | 1 | LS | 1902957.4 | 1064330.33 | 838627.07 | 0 | D-Star Waterproofers Base Contract @$1.9M
Y | IPCRP1-0179-0000-L | IPCRP1 | IPCRP1 | 0179-0000 | CLEARING & GRUBBING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0179-0000-R | IPCRP1 | IPCRP1 | 0179-0000 | CLEARING & GRUBBING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 70625 | 0 | 0 | 70625 | 0 | 70625 | 67112.75 | 0 | N | 70625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0179-1000-L | IPCRP1 | IPCRP1 | 0179-1000 | CLEARING & GRUBBING | N | L |  | UNIT | P | 0 | 46828.18 | 46828.18 | 46828.18 | 46828.18 | 100 | 0 | 0 | 0 | 0 | Y | 46828.18 | Y | -46828.18 | 0 | 0 | 0 | 0 | 0 | 46828.18 | Y | -46828.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -46828.18 | 0 | 0 | 46828.18 | 0 | 0 | 0 | 0 | 0 | 0 | -46828.18 | 0 | 0 | 46828.18 | 46828.18 | 0 | 0 | 0 | 0 | 0 | 393 | 393 | 0 | 393 | 0 | 393 | HR | 2825 | 2684.51 | 0 | 2684.51 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0179-1000-S | IPCRP1 | IPCRP1 | 0179-1000 | CLEARING & GRUBBING | N | S |  | NR | A | 56500 | 476.74 | 476.74 | 476.74 | 476.74 | 100 | 0 | 0 | 0 | 0 | Y | 476.74 | Y | 56023.26 | 0 | 0 | 56500 | 0 | 0 | 476.74 | Y | 56023.26 | 0 | 0 | 56500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -476.74 | 0 | 0 | 476.74 | 0 | 0 | 0 | 0 | 0 | 0 | -476.74 | 0 | 0 | 476.74 | 476.74 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | -4 | 0 | EA | 2825 | 2684.51 | 0 | 2684.51 | SY | 476.74 | 0 | 476.74 | 0
Y | IPCRP1-0180-0000-L | IPCRP1 | IPCRP1 | 0180-0000 | UNCLASSIFIED EXCAVATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0180-0000-R | IPCRP1 | IPCRP1 | 0180-0000 | UNCLASSIFIED EXCAVATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 968082.5 | 0 | 0 | 968082.5 | 0 | 968082.5 | 346248.5 | 0 | N | 968082.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968082.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0180-1000-E | IPCRP1 | IPCRP1 | 0180-1000 | Unclassified Ex - Self Perform/ All Other Subs | N | E |  | NR | P | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | N | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 19361.3 | 5982.49 | 13378.81 | 19361.3 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0180-1000-L | IPCRP1 | IPCRP1 | 0180-1000 | Unclassified Ex - Self Perform/ All Other Subs | N | L |  | NR | P | 225076.5 | 456631.84 | 456631.84 | 456631.84 | 456631.84 | 90.8573 | 0 | 0 | 0 | 45949.44 | Y | 502581.28 | Y | -277504.78 | 0 | 0 | 225076.5 | 0 | 0 | 502581.28 | Y | -277504.78 | 0 | 0 | 225076.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -502581.28 | 0 | 0 | 502581.28 | 0 | 0 | 0 | 0 | 0 | 0 | -502581.28 | 0 | 0 | 502581.28 | 502581.28 | 0 | 0 | 0 | 4000 | 0 | 3880 | 3880 | 4000 | 3571 | 309 | 3880 | HR | 19361.3 | 5982.49 | 13378.81 | 19361.3 | CY | 0 | 0 | 0 | 45949.44 | DDC quantity thru Aug 24 (9,168.03cy). Akela quantity thru Aug (5,402.33cy). IPC QTD therefore is 3,765.70cy. 2. CTD Quantity is overall QTD paid by DDC. Production rate & costs are not reflecting this quantity but rather the IPC self-performed quantity, which is DDC - Akela = IPC quantity.v
Y | IPCRP1-0180-1000-S | IPCRP1 | IPCRP1 | 0180-1000 | Unclassified Ex - Self Perform/ All Other Subs | N | S |  | UNIT | A | 0 | 44408.61 | 44408.61 | 44408.61 | 44408.61 | 101.8026 | 0 | 0 | 0 | -786.32 | Y | 43622.29 | Y | -43622.29 | 0 | 0 | 0 | 0 | 0 | 43622.29 | Y | -43622.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -43622.29 | 0 | 786.32 | 43622.29 | 0 | 0 | 0 | 0 | 0 | 0 | -43622.29 | 0 | 0 | 43622.29 | 43622.29 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 347 | -339 | 8 | NA | 19361.3 | 5982.49 | 13378.81 | 19361.3 | CY | 44408.61 | 0 | 44408.61 | -786.32
Y | IPCRP1-0181-0000-L | IPCRP1 | IPCRP1 | 0181-0000 | HAND EXCAV AROUND STRUCT & UTILITIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0181-0000-R | IPCRP1 | IPCRP1 | 0181-0000 | HAND EXCAV AROUND STRUCT & UTILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 575200 | 0 | 0 | 575200 | 0 | 575200 | 0 | 0 | N | 575200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0181-1000-E | IPCRP1 | IPCRP1 | 0181-1000 | HAND EXCAV AROUND STRUCT & UTILITIES | N | E |  | NR | P | 76539.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 76539.7 | 0 | 0 | 76539.7 | 0 | 0 | 0 | Y | 76539.7 | 0 | 0 | 76539.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1438 | 0 | 1438 | 1438 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0181-1000-L | IPCRP1 | IPCRP1 | 0181-1000 | HAND EXCAV AROUND STRUCT & UTILITIES | N | L |  | NR | P | 458499.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458499.77 | N | 458499.77 | N | 0 | 0 | 0 | 458499.77 | 0 | 0 | 458499.77 | N | 0 | 0 | 0 | 458499.77 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -458499.77 | 0 | 0 | 458499.77 | 0 | 0 | 0 | 0 | 0 | 0 | -458499.77 | 0 | 0 | 458499.77 | 458499.77 | 0 | 0 | 0 | 4170.2 | 0 | 4170.2 | 4170.2 | 4170.2 | 0 | 4170.2 | 4170.2 | HR | 1438 | 0 | 1438 | 1438 | CY | 0 | 0 | 0 | 458499.77
Y | IPCRP1-0182-0000-L | IPCRP1 | IPCRP1 | 0182-0000 | STRIP PVMNT SURFACE (ASPH CONC) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0182-0000-R | IPCRP1 | IPCRP1 | 0182-0000 | STRIP PVMNT SURFACE (ASPH CONC) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 93350 | 0 | 0 | 93350 | 0 | 93350 | 0 | 0 | N | 93350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0182-1000-L | IPCRP1 | IPCRP1 | 0182-1000 | STRIP PVMNT SURFACE (ASPH CONC) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3734 | 0 | 3734 | 3734 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0182-1000-S | IPCRP1 | IPCRP1 | 0182-1000 | STRIP PVMNT SURFACE (ASPH CONC) | N | S |  | NR | A | 75128.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75128.08 | N | 75128.08 | N | 0 | 0 | 0 | 75128.08 | 0 | 0 | 75128.08 | N | 0 | 0 | 0 | 75128.08 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -75128.08 | 0 | 0 | 75128.08 | 0 | 0 | 0 | 0 | 0 | 0 | -75128.08 | 0 | 0 | 75128.08 | 75128.08 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 3734 | 0 | 3734 | 3734 | SY | 0 | 0 | 0 | 75128.08
Y | IPCRP1-0183-0000-L | IPCRP1 | IPCRP1 | 0183-0000 | STRIP PVMNT SURFACE (ASPH CONC - SHARED PATH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0183-0000-R | IPCRP1 | IPCRP1 | 0183-0000 | STRIP PVMNT SURFACE (ASPH CONC - SHARED PATH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30350 | 0 | 0 | 30350 | 0 | 30350 | 0 | 0 | N | 30350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0183-1000-L | IPCRP1 | IPCRP1 | 0183-1000 | Strip Pvmnt Surface (Asph Conc, Shared Path) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1214 | 0 | 1214 | 1214 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0183-1000-S | IPCRP1 | IPCRP1 | 0183-1000 | Strip Pvmnt Surface (Asph Conc, Shared Path) | N | S |  | NR | A | 24425.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24425.68 | N | 24425.68 | N | 0 | 0 | 0 | 24425.68 | 0 | 0 | 24425.68 | N | 0 | 0 | 0 | 24425.68 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24425.68 | 0 | 0 | 24425.68 | 0 | 0 | 0 | 0 | 0 | 0 | -24425.68 | 0 | 0 | 24425.68 | 24425.68 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1214 | 0 | 1214 | 1214 | SY | 0 | 0 | 0 | 24425.68
Y | IPCRP1-0184-0000-L | IPCRP1 | IPCRP1 | 0184-0000 | STRIP PVMNT SURFACE (COBBLESTONE - DEL TO YARD) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0184-0000-R | IPCRP1 | IPCRP1 | 0184-0000 | STRIP PVMNT SURFACE (COBBLESTONE - DEL TO YARD) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 33900 | 0 | 0 | 33900 | 0 | 33900 | 0 | 0 | N | 33900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0184-1000-L | IPCRP1 | IPCRP1 | 0184-1000 | Strip Pvmnt Surface (Cobblestone, Del to Yard) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 678 | 0 | 678 | 678 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0184-1000-S | IPCRP1 | IPCRP1 | 0184-1000 | Strip Pvmnt Surface (Cobblestone, Del to Yard) | N | S |  | NR | A | 28482.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28482.78 | N | 28482.78 | N | 0 | 0 | 0 | 28482.78 | 0 | 0 | 28482.78 | N | 0 | 0 | 0 | 28482.78 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28482.78 | 0 | 0 | 28482.78 | 0 | 0 | 0 | 0 | 0 | 0 | -28482.78 | 0 | 0 | 28482.78 | 28482.78 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 678 | 0 | 678 | 678 | SY | 0 | 0 | 0 | 28482.78
Y | IPCRP1-0185-0000-L | IPCRP1 | IPCRP1 | 0185-0000 | GRANITE BLOCK SW, SAND JT, SALVAGED BLOCK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0185-0000-R | IPCRP1 | IPCRP1 | 0185-0000 | GRANITE BLOCK SW, SAND JT, SALVAGED BLOCK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19375 | 0 | 0 | 19375 | 0 | 19375 | 0 | 0 | N | 19375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0185-1000-L | IPCRP1 | IPCRP1 | 0185-1000 | Granite Block SW, Sand Jt (Salvaged Block) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 155 | 0 | 155 | 155 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0185-1000-S | IPCRP1 | IPCRP1 | 0185-1000 | Granite Block SW, Sand Jt (Salvaged Block) | N | S |  | NR | A | 19522.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19522.25 | N | 19522.25 | N | 0 | 0 | 0 | 19522.25 | 0 | 0 | 19522.25 | N | 0 | 0 | 0 | 19522.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19522.25 | 0 | 0 | 19522.25 | 0 | 0 | 0 | 0 | 0 | 0 | -19522.25 | 0 | 0 | 19522.25 | 19522.25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 155 | 0 | 155 | 155 | SY | 0 | 0 | 0 | 19522.25
Y | IPCRP1-0186-0000-L | IPCRP1 | IPCRP1 | 0186-0000 | PICKET FENCE REMOVED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0186-0000-R | IPCRP1 | IPCRP1 | 0186-0000 | PICKET FENCE REMOVED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 37300 | 0 | 0 | 37300 | 0 | 37300 | 18782.4 | 0 | N | 37300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0186-1000-L | IPCRP1 | IPCRP1 | 0186-1000 | PICKET FENCE REMOVED | N | L |  | NR | P | 30095.14 | 29078.78 | 29078.78 | 29078.78 | 29078.78 | 48.3367 | 0 | 0 | 0 | 31080 | Y | 60158.78 | Y | -30063.64 | 0 | 0 | 30095.14 | 0 | 0 | 60158.78 | Y | -30063.64 | 0 | 0 | 30095.14 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60158.78 | 0 | 0 | 60158.78 | 0 | 0 | 0 | 0 | 0 | 0 | -60158.78 | 0 | 0 | 60158.78 | 60158.78 | 0 | 0 | 0 | 298.4 | 0 | 560 | 560 | 298.4 | 280 | 280 | 560 | HR | 3730 | 1878.24 | 1851.76 | 3730 | LF | 0 | 0 | 0 | 31080
Y | IPCRP1-0187-0000-L | IPCRP1 | IPCRP1 | 0187-0000 | BROKEN STONE BALLAST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0187-0000-R | IPCRP1 | IPCRP1 | 0187-0000 | BROKEN STONE BALLAST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 45000 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | N | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0187-1000-E | IPCRP1 | IPCRP1 | 0187-1000 | BROKEN STONE BALLAST | N | E |  | NR | P | 2340.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2340.78 | 0 | 0 | 2340.78 | 0 | 0 | 0 | Y | 2340.78 | 0 | 0 | 2340.78 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 300 | 0 | 300 | 300 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0187-1000-L | IPCRP1 | IPCRP1 | 0187-1000 | BROKEN STONE BALLAST | N | L |  | NR | P | 16161.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16161.47 | N | 16161.47 | N | 0 | 0 | 0 | 16161.47 | 0 | 0 | 16161.47 | N | 0 | 0 | 0 | 16161.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16161.47 | 0 | 0 | 16161.47 | 0 | 0 | 0 | 0 | 0 | 0 | -16161.47 | 0 | 0 | 16161.47 | 16161.47 | 0 | 0 | 0 | 144 | 0 | 144 | 144 | 144 | 0 | 144 | 144 | HR | 300 | 0 | 300 | 300 | CY | 0 | 0 | 0 | 16161.47
Y | IPCRP1-0188-0000-L | IPCRP1 | IPCRP1 | 0188-0000 | ADDITIONAL HARDWARE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0188-0000-R | IPCRP1 | IPCRP1 | 0188-0000 | ADDITIONAL HARDWARE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10875 | 0 | 0 | 10875 | 0 | 10875 | 0 | 0 | N | 10875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0188-1000-L | IPCRP1 | IPCRP1 | 0188-1000 | ADDITIONAL HARDWARE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4350 | 0 | 4350 | 4350 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0188-1000-M | IPCRP1 | IPCRP1 | 0188-1000 | ADDITIONAL HARDWARE | N | M |  | NR | P | 10875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10875 | N | 10875 | N | 0 | 0 | 0 | 10875 | 0 | 0 | 10875 | N | 0 | 0 | 0 | 10875 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10875 | 0 | 0 | 10875 | 0 | 0 | 0 | 0 | 0 | 0 | -10875 | 0 | 0 | 10875 | 10875 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 4350 | 0 | 4350 | 4350 | LB | 0 | 0 | 0 | 10875
Y | IPCRP1-0189-0000-L | IPCRP1 | IPCRP1 | 0189-0000 | REM EXIST FIRE ALARM POST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0189-0000-R | IPCRP1 | IPCRP1 | 0189-0000 | REM EXIST FIRE ALARM POST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6000 | 0 | 0 | 6000 | 0 | 6000 | 1000 | 0 | N | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0190-0000-L | IPCRP1 | IPCRP1 | 0190-0000 | F&I FIRE ALARM POST & SUBBASE (STD DWG #141) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0190-0000-R | IPCRP1 | IPCRP1 | 0190-0000 | F&I FIRE ALARM POST & SUBBASE (STD DWG #141) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 80000 | 0 | 0 | 80000 | 0 | 80000 | 1600 | 0 | N | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0191-0000-L | IPCRP1 | IPCRP1 | 0191-0000 | F&I 4-PAIR FIRE ALARM CABLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0191-0000-R | IPCRP1 | IPCRP1 | 0191-0000 | F&I 4-PAIR FIRE ALARM CABLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2500 | 0 | 0 | 2500 | 0 | 2500 | 0 | 0 | N | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0192-0000-L | IPCRP1 | IPCRP1 | 0192-0000 | F&I FIRE DEPT SLOT MH TYPE A W/ F&C (#140, 144S 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0192-0000-R | IPCRP1 | IPCRP1 | 0192-0000 | F&I FIRE DEPT SLOT MH TYPE A W/ F&C (#140, 144S 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 17000 | 0 | 0 | 17000 | 0 | 17000 | 8500 | 0 | N | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0193-0000-L | IPCRP1 | IPCRP1 | 0193-0000 | F&I FIRE DEPT 16 WIRE TERM BOX & TERM FIRE ALARM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0193-0000-R | IPCRP1 | IPCRP1 | 0193-0000 | F&I FIRE DEPT 16 WIRE TERM BOX & TERM FIRE ALARM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2400 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | N | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0194-0000-L | IPCRP1 | IPCRP1 | 0194-0000 | F&I 4 PVC COND, SCH 40, UL 651 (W/ PVMNT EXC) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0194-0000-R | IPCRP1 | IPCRP1 | 0194-0000 | F&I 4 PVC COND, SCH 40, UL 651 (W/ PVMNT EXC) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5500 | 0 | 0 | 5500 | 0 | 5500 | 2625 | 0 | N | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0195-0000-L | IPCRP1 | IPCRP1 | 0195-0000 | F&I 4 90 DEGREE PVC WIDE BEND, SCH 40 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0195-0000-R | IPCRP1 | IPCRP1 | 0195-0000 | F&I 4 90 DEGREE PVC WIDE BEND, SCH 40 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 600 | 0 | 0 | 600 | 0 | 600 | 540 | 0 | N | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0196-0000-L | IPCRP1 | IPCRP1 | 0196-0000 | F&I FIRE ALARM PEDESTAL BUMPERS (STD DWG #168) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0196-0000-R | IPCRP1 | IPCRP1 | 0196-0000 | F&I FIRE ALARM PEDESTAL BUMPERS (STD DWG #168) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 150 | 0 | 0 | 150 | 0 | 150 | 0 | 0 | N | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0197-0000-L | IPCRP1 | IPCRP1 | 0197-0000 | REM EXIST FDNY MANHOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0197-0000-R | IPCRP1 | IPCRP1 | 0197-0000 | REM EXIST FDNY MANHOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9000 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | N | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0198-0000-L | IPCRP1 | IPCRP1 | 0198-0000 | TEMPORARY SIGNS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0198-0000-R | IPCRP1 | IPCRP1 | 0198-0000 | TEMPORARY SIGNS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0199-0000-L | IPCRP1 | IPCRP1 | 0199-0000 | REM & DISP CONCRETE BARRIERS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0199-0000-R | IPCRP1 | IPCRP1 | 0199-0000 | REM & DISP CONCRETE BARRIERS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19675 | 0 | 0 | 19675 | 0 | 19675 | 26287.5 | 0 | N | 19675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0199-1000-E | IPCRP1 | IPCRP1 | 0199-1000 | REM & DISP CONCRETE BARRIERS | N | E |  | NR | P | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 787 | 1051.5 | 0 | 1051.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0199-1000-L | IPCRP1 | IPCRP1 | 0199-1000 | REM & DISP CONCRETE BARRIERS | N | L |  | NR | P | 5548.76 | 43524.08 | 43524.08 | 43524.08 | 43524.08 | 100 | 0 | 0 | 0 | 0 | Y | 43524.08 | Y | -37975.32 | 0 | 0 | 5548.76 | 0 | 0 | 43524.08 | Y | -37975.32 | 0 | 0 | 5548.76 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -43524.08 | 0 | 0 | 43524.08 | 0 | 0 | 0 | 0 | 0 | 0 | -43524.08 | 0 | 0 | 43524.08 | 43524.08 | 0 | 0 | 0 | 48 | 0 | 342 | 342 | 48 | 342 | 0 | 342 | HR | 787 | 1051.5 | 0 | 1051.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0199-1000-S | IPCRP1 | IPCRP1 | 0199-1000 | REM & DISP CONCRETE BARRIERS | N | S |  | UNIT | A | 0 | 516.39 | 516.39 | 516.39 | 516.39 | 100 | 0 | 0 | 0 | 0 | N | 516.39 | N | -516.39 | 0 | 0 | 0 | 0 | 0 | 516.39 | N | -516.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -516.39 | 0 | 0 | 516.39 | 0 | 0 | 0 | 0 | 0 | 0 | -516.39 | 0 | 0 | 516.39 | 516.39 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 787 | 1051.5 | 0 | 1051.5 | LF | 516.39 | 0 | 516.39 | 0
Y | IPCRP1-0199-1010-L | IPCRP1 | IPCRP1 | 0199-1010 | Flatbed Trucking (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0199-1010-S | IPCRP1 | IPCRP1 | 0199-1010 | Flatbed Trucking (CLOSED) | N | S |  | NR | A | 5560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5560 | 0 | 0 | 5560 | 0 | 0 | 0 | Y | 5560 | 0 | 0 | 5560 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 4 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0200-0000-L | IPCRP1 | IPCRP1 | 0200-0000 | LIGHTED TIMBER BARRICADES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0200-0000-R | IPCRP1 | IPCRP1 | 0200-0000 | LIGHTED TIMBER BARRICADES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16800 | 0 | 0 | 16800 | 0 | 16800 | 0 | 0 | N | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0201-0000-L | IPCRP1 | IPCRP1 | 0201-0000 | BEAM TYPE GUIDE RAIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0201-0000-R | IPCRP1 | IPCRP1 | 0201-0000 | BEAM TYPE GUIDE RAIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11250 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | N | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0202-0000-L | IPCRP1 | IPCRP1 | 0202-0000 | REM EXIST GUIDE RAIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0202-0000-R | IPCRP1 | IPCRP1 | 0202-0000 | REM EXIST GUIDE RAIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 1050 | 0 | N | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0203-0000-L | IPCRP1 | IPCRP1 | 0203-0000 | PRECAST CONC WHEEL STOPS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0203-0000-R | IPCRP1 | IPCRP1 | 0203-0000 | PRECAST CONC WHEEL STOPS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 18500 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0203-1000-E | IPCRP1 | IPCRP1 | 0203-1000 | Inst PC Conc Wheel Stops | N | E |  | NR | P | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1600 | 0 | 0 | 1600 | 0 | 0 | 0 | Y | 1600 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 40 | 37 | 0 | 37 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0203-1000-L | IPCRP1 | IPCRP1 | 0203-1000 | Inst PC Conc Wheel Stops | N | L |  | NR | P | 8756.12 | 6026.93 | 6026.93 | 6026.93 | 6026.93 | 100 | 0 | 0 | 0 | 0 | Y | 6026.93 | Y | 2729.19 | 0 | 0 | 8756.12 | 0 | 0 | 6026.93 | Y | 2729.19 | 0 | 0 | 8756.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6026.93 | 0 | 0 | 6026.93 | 0 | 0 | 0 | 0 | 0 | 0 | -6026.93 | 0 | 0 | 6026.93 | 6026.93 | 0 | 0 | 0 | 80 | 0 | 56 | 56 | 80 | 56 | 0 | 56 | HR | 40 | 37 | 0 | 37 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0203-1010-L | IPCRP1 | IPCRP1 | 0203-1010 | Furn PC Conc Wheel Stops | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 40 | 39 | 0 | 39 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0203-1010-M | IPCRP1 | IPCRP1 | 0203-1010 | Furn PC Conc Wheel Stops | N | M |  | NR | P | 9200 | 10000 | 10000 | 10000 | 10000 | 100 | 0 | 0 | 0 | 0 | Y | 10000 | Y | -800 | 0 | 0 | 9200 | 0 | 0 | 10000 | Y | -800 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1533.15 | 0 | 1533.15 | NA | 40 | 39 | 0 | 39 | EA | 10000 | 0 | 10000 | 0
Y | IPCRP1-0204-0000-L | IPCRP1 | IPCRP1 | 0204-0000 | CHAIN LINK FENCE, 8ft-0 HIGH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0204-0000-R | IPCRP1 | IPCRP1 | 0204-0000 | CHAIN LINK FENCE, 8ft-0 HIGH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 312900 | 0 | 0 | 312900 | 0 | 312900 | 110243 | 0 | N | 312900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0205-0000-L | IPCRP1 | IPCRP1 | 0205-0000 | ST PICKET FENCE W/WELDED WIRE MESH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0205-0000-R | IPCRP1 | IPCRP1 | 0205-0000 | ST PICKET FENCE W/WELDED WIRE MESH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2224000 | 0 | 0 | 2224000 | 0 | 2224000 | 0 | 0 | N | 2224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0206-0000-L | IPCRP1 | IPCRP1 | 0206-0000 | CLF GATE FOR 8ft HIGH FENCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0206-0000-R | IPCRP1 | IPCRP1 | 0206-0000 | CLF GATE FOR 8ft HIGH FENCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11000 | 0 | 0 | 11000 | 0 | 11000 | 11000 | 0 | N | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0207-0000-L | IPCRP1 | IPCRP1 | 0207-0000 | REM & DISP EXIST CLF | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0207-0000-R | IPCRP1 | IPCRP1 | 0207-0000 | REM & DISP EXIST CLF | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11830 | 0 | 0 | 11830 | 0 | 11830 | 8757.5 | 0 | N | 11830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0208-0000-L | IPCRP1 | IPCRP1 | 0208-0000 | STRUCT REPAIR & ADJUST UTILITY STRUCT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0208-0000-R | IPCRP1 | IPCRP1 | 0208-0000 | STRUCT REPAIR & ADJUST UTILITY STRUCT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 180 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0208-1000-E | IPCRP1 | IPCRP1 | 0208-1000 | Struct Repair & Adjust Utility Structures | N | E |  | NR | P | 474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 474 | 0 | 0 | 474 | 0 | 0 | 0 | Y | 474 | 0 | 0 | 474 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 8 | 0.12 | 7.88 | 8 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0208-1000-L | IPCRP1 | IPCRP1 | 0208-1000 | Struct Repair & Adjust Utility Structures | N | L |  | NR | P | 8931.83 | 659.02 | 659.02 | 659.02 | 659.02 | 7.3783 | 0 | 0 | 0 | 8272.81 | N | 8931.83 | N | 0 | 0 | 0 | 8931.83 | 0 | 0 | 8931.83 | N | 0 | 0 | 0 | 8931.83 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8931.83 | 0 | 0 | 8931.83 | 0 | 0 | 0 | 0 | 0 | 0 | -8931.83 | 0 | 0 | 8931.83 | 8931.83 | 0 | 0 | 0 | 72 | 0 | 72 | 72 | 72 | 6 | 66 | 72 | HR | 8 | 0.12 | 7.88 | 8 | CY | 0 | 0 | 0 | 8272.81
Y | IPCRP1-0209-0000-L | IPCRP1 | IPCRP1 | 0209-0000 | ENGINEERs FIELD OFFICE (COASTAL RESILIENCY) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0209-0000-R | IPCRP1 | IPCRP1 | 0209-0000 | ENGINEERs FIELD OFFICE (COASTAL RESILIENCY) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 14100000 | 0 | 0 | 14100000 | 0 | 14100000 | 10446000 | 0 | N | 14100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14100000 | 0 | 0.23 | -0.23 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0209-1000-C | IPCRP1 | IPCRP1 | 0209-1000 | Engineers Field Office - Set Up | N | C |  | NR | P | 1025497 | 69426.01 | 69426.01 | 62124.7 | 69426.01 | 62.1247 | 0 | 0 | 0 | 30573.99 | Y | 100000 | Y | 925497 | 0 | 0 | 1025497 | 0 | 0 | 100000 | Y | 925497 | 0 | 0 | 1025497 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2659 | -2659 | 0 | NA | 1 | 1 | 0 | 1 | LS | 29792.97 | 7301.31 | 22491.66 | 30573.99
Y | IPCRP1-0209-1000-L | IPCRP1 | IPCRP1 | 0209-1000 | Engineers Field Office - Set Up | N | L |  | UNIT | P | 0 | 4816.07 | 4816.07 | 4816.07 | 4816.07 | 100 | 0 | 0 | 0 | 0 | Y | 4816.07 | Y | -4816.07 | 0 | 0 | 0 | 0 | 0 | 4816.07 | Y | -4816.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4816.07 | 0 | 0 | 4816.07 | 0 | 0 | 0 | 0 | 0 | 0 | -4816.07 | 0 | 0 | 4816.07 | 4816.07 | 0 | 0 | 0 | 0 | 0 | 27.5 | 27.5 | 0 | 27.5 | 0 | 27.5 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0209-1000-S | IPCRP1 | IPCRP1 | 0209-1000 | Engineers Field Office - Set Up | N | S |  | UNIT | A | 0 | 605534.09 | 605534.09 | 551030.85 | 605534.09 | 90.9991 | 0 | 0 | 0 | 0 | Y | 605534.09 | Y | -605534.09 | 0 | 0 | 0 | 0 | 0 | 605534.09 | Y | -605534.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -605534.09 | 0 | 0 | 605534.09 | 0 | 0 | 0 | 0 | 0 | 0 | -605534.09 | 0 | 0 | 605534.09 | 605534.09 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 4335.56 | -4299.56 | 36 | NA | 1 | 1 | 0 | 1 | LS | 605534.09 | 54503.24 | 551030.85 | 0 | ALL POINTS COMMUNICATIONS INC @$740,350.00; CASSONE LEASING, INC @$31,628.19
Y | IPCRP1-0209-1010-C | IPCRP1 | IPCRP1 | 0209-1010 | Engineers Field Office - Monthly Cost | N | C |  | NR | P | 6040156 | 2781546.11 | 2781546.11 | 2781546.11 | 2781546.11 | 77.2652 | 0 | 0 | 0 | 818453.89 | Y | 3600000 | Y | 2440156 | 0 | 0 | 6040156 | 0 | 0 | 3600000 | Y | 2440156 | 0 | 0 | 6040156 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3600000 | 67393.92 | 20777.67 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | -3600000 | 0 | 0 | 3600000 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 332.25 | -285.44 | 46.81 | NA | 71 | 54 | 17 | 71 | MO | 37251.02 | -22742.93 | 59993.95 | 818453.89 | 6 yr (180 Maiden Lane+ = 72 months. Lease starts on 9/24/21, use Oct 2021 as Month #1.
Y | IPCRP1-0209-1010-L | IPCRP1 | IPCRP1 | 0209-1010 | Engineers Field Office - Monthly Cost | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 71 | 54 | 17 | 71 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0209-1010-S | IPCRP1 | IPCRP1 | 0209-1010 | Engineers Field Office - Monthly Cost | N | S |  | UNIT | A | 0 | 671382.64 | 671382.64 | 531257.02 | 671382.64 | 79.1288 | 0 | 0 | 0 | 0 | Y | 671382.64 | Y | -671382.64 | 0 | 0 | 0 | 0 | 0 | 671382.64 | Y | -671382.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -671382.64 | 4679.45 | 6253.83 | 671382.64 | 0 | 0 | 0 | 0 | 0 | 0 | -671382.64 | 0 | 0 | 671382.64 | 671382.64 | 0 | 0 | 0 | 0 | 0 | 181 | 181 | 0 | 9940.98 | -9759.98 | 181 | NA | 71 | 54 | 17 | 71 | MO | 671382.64 | 140125.62 | 531257.02 | 0
Y | IPCRP1-0210-0000-L | IPCRP1 | IPCRP1 | 0210-0000 | LINE & GRADE SURVEYS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0210-0000-R | IPCRP1 | IPCRP1 | 0210-0000 | LINE & GRADE SURVEYS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000000 | 0 | 0 | 30000000 | 0 | 30000000 | 18731507.63 | 0 | N | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0210-1000-C | IPCRP1 | IPCRP1 | 0210-1000 | LINE & GRADE SURVEYS | N | C |  | UNIT | U | 0 | 121332.46 | 121332.46 | 121332.46 | 121332.46 | 100 | 0 | 0 | 0 | 0 | Y | 121332.46 | Y | -121332.46 | 0 | 0 | 0 | 0 | 0 | 121332.46 | Y | -121332.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -121332.46 | 0 | 0 | 121332.46 | 0 | 0 | 0 | 0 | 0 | 0 | -121332.46 | 0 | 0 | 121332.46 | 121332.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 60 | 54 | 18 | 72 | MO | 0 | -17000 | 17000 | 0
Y | IPCRP1-0210-1000-L | IPCRP1 | IPCRP1 | 0210-1000 | LINE & GRADE SURVEYS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 54 | 18 | 72 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0210-1000-S | IPCRP1 | IPCRP1 | 0210-1000 | LINE & GRADE SURVEYS | N | S |  | NR | A | 7805899 | 10191025.4 | 10191025.4 | 7387261.04 | 10191025.4 | 73.2863 | 0 | 0 | 0 | -111025.4 | Y | 10080000 | Y | -2274101 | 0 | 0 | 7805899 | 0 | 0 | 10080000 | Y | -2274101 | 0 | 0 | 7805899 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10080000 | 0 | 0 | 10080000 | 0 | 0 | 0 | 4357.5 | 200000 | 0 | -10080000 | 0 | 0 | 10080000 | 10080000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5423.99 | 1992.99 | 7416.98 | NA | 60 | 54 | 18 | 72 | MO | 10191025.4 | 2803764.36 | 7387261.04 | -111025.4 | AQUA SURVEY INC. @$17K; 50 STATES ENGINEERING CORP. @$6M + $1,540 (CO)
Y | IPCRP1-0211-0000-L | IPCRP1 | IPCRP1 | 0211-0000 | DIGITAL PHOTOGRAPHS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0211-0000-R | IPCRP1 | IPCRP1 | 0211-0000 | DIGITAL PHOTOGRAPHS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 630000 | 0 | 0 | 630000 | 0 | 630000 | 19320 | 0 | N | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630000 | 0 | 1281 | -1281 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0211-1000-L | IPCRP1 | IPCRP1 | 0211-1000 | DIGITAL PHOTOGRAPHS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 63000 | 1932 | 0 | 1932 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0211-1000-S | IPCRP1 | IPCRP1 | 0211-1000 | DIGITAL PHOTOGRAPHS | N | S |  | NR | A | 598500 | 106645 | 106645 | 64428.1 | 106645 | 60.4136 | 0 | 0 | 0 | 0 | Y | 106645 | Y | 491855 | 0 | 0 | 598500 | 0 | 0 | 106645 | Y | 491855 | 0 | 0 | 598500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -106645 | 0 | 0 | 106645 | 0 | 0 | 0 | 0 | 0 | 0 | -106645 | 0 | 0 | 106645 | 106645 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7126 | 58274.3 | 65400.3 | NA | 63000 | 1932 | 0 | 1932 | ST | 106645 | 42216.9 | 64428.1 | 0 | BERNSTEIN Base @$568,495.00 + CO @$9,000
Y | IPCRP1-0212-0000-L | IPCRP1 | IPCRP1 | 0212-0000 | THERMO REFLECT PVMNT MARKINGS (4 WIDE) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0212-0000-R | IPCRP1 | IPCRP1 | 0212-0000 | THERMO REFLECT PVMNT MARKINGS (4 WIDE) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31112 | 0 | 0 | 31112 | 0 | 31112 | 7921.55 | 0 | N | 31112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0213-0000-L | IPCRP1 | IPCRP1 | 0213-0000 | CLEAN DRAIN STRUCTURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0213-0000-R | IPCRP1 | IPCRP1 | 0213-0000 | CLEAN DRAIN STRUCTURES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3750 | 0 | 0 | 3750 | 0 | 3750 | 750 | 0 | N | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0213-1000-L | IPCRP1 | IPCRP1 | 0213-1000 | CLEAN DRAIN STRUCTURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5 | 1 | 4 | 5 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0213-1000-S | IPCRP1 | IPCRP1 | 0213-1000 | CLEAN DRAIN STRUCTURES | N | S |  | NR | A | 3204.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3204.93 | N | 3204.93 | N | 0 | 0 | 0 | 3204.93 | 0 | 0 | 3204.93 | N | 0 | 0 | 0 | 3204.93 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3204.93 | 0 | 0 | 3204.93 | 0 | 0 | 0 | 0 | 0 | 0 | -3204.93 | 0 | 0 | 3204.93 | 3204.93 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 5 | 1 | 4 | 5 | EA | 0 | 0 | 0 | 3204.93
Y | IPCRP1-0214-0000-L | IPCRP1 | IPCRP1 | 0214-0000 | REM EXIST LANE MARKINGS (4 WIDE) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0214-0000-R | IPCRP1 | IPCRP1 | 0214-0000 | REM EXIST LANE MARKINGS (4 WIDE) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31317 | 0 | 0 | 31317 | 0 | 31317 | 3738.5 | 0 | N | 31317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0215-0000-L | IPCRP1 | IPCRP1 | 0215-0000 | SAWCUTTING EXIST PVMNT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0215-0000-R | IPCRP1 | IPCRP1 | 0215-0000 | SAWCUTTING EXIST PVMNT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 75425 | 0 | 0 | 75425 | 0 | 75425 | 16523.7 | 0 | N | 75425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0215-1000-E | IPCRP1 | IPCRP1 | 0215-1000 | Sawcuting Exist Pvmnt | N | E |  | NR | P | 22117.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 22117.5 | 0 | 0 | 22117.5 | 0 | 0 | 0 | Y | 22117.5 | 0 | 0 | 22117.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 15085 | 3304.74 | 11780.26 | 15085 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0215-1000-L | IPCRP1 | IPCRP1 | 0215-1000 | Sawcuting Exist Pvmnt | N | L |  | NR | P | 41152.11 | 14049.44 | 14049.44 | 14049.44 | 14049.44 | 34.1403 | 0 | 0 | 0 | 27102.67 | N | 41152.11 | N | 0 | 0 | 0 | 41152.11 | 0 | 0 | 41152.11 | N | 0 | 0 | 0 | 41152.11 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -41152.11 | 873.9 | 0 | 41152.11 | 0 | 0 | 0 | 0 | 0 | 0 | -41152.11 | 0 | 0 | 41152.11 | 41152.11 | 0 | 0 | 0 | 400 | 0 | 400 | 400 | 400 | 136 | 264 | 400 | HR | 15085 | 3304.74 | 11780.26 | 15085 | LF | 0 | 0 | 0 | 27102.67
Y | IPCRP1-0215-1000-S | IPCRP1 | IPCRP1 | 0215-1000 | Sawcuting Exist Pvmnt | N | S |  | UNIT | A | 0 | 982.16 | 982.16 | 982.16 | 982.16 | 100 | 0 | 0 | 0 | 0 | N | 982.16 | N | -982.16 | 0 | 0 | 0 | 0 | 0 | 982.16 | N | -982.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -982.16 | 0 | 0 | 982.16 | 0 | 0 | 0 | 0 | 0 | 0 | -982.16 | 0 | 0 | 982.16 | 982.16 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 15085 | 3304.74 | 11780.26 | 15085 | LF | 982.16 | 0 | 982.16 | 0
Y | IPCRP1-0216-0000-L | IPCRP1 | IPCRP1 | 0216-0000 | CONC BARRIER, HALF SECTION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0216-0000-R | IPCRP1 | IPCRP1 | 0216-0000 | CONC BARRIER, HALF SECTION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 49000 | 0 | 0 | 49000 | 0 | 49000 | 0 | 0 | N | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0216-1000-E | IPCRP1 | IPCRP1 | 0216-1000 | Inst Half Section Conc Barrier | N | E |  | NR | P | 3569.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3569.5 | 0 | 0 | 3569.5 | 0 | 0 | 0 | Y | 3569.5 | 0 | 0 | 3569.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 245 | 0 | 87 | 87 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0216-1000-L | IPCRP1 | IPCRP1 | 0216-1000 | Inst Half Section Conc Barrier | N | L |  | NR | P | 16659.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16659.82 | Y | 16659.82 | Y | 0 | 0 | 0 | 16659.82 | 0 | 0 | 16659.82 | Y | 0 | 0 | 0 | 16659.82 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16659.82 | 0 | 0 | 16659.82 | 0 | 0 | 0 | 0 | 0 | 0 | -16659.82 | 0 | 0 | 16659.82 | 16659.82 | 0 | 0 | 0 | 144 | 0 | 144 | 144 | 144 | 0 | 144 | 144 | HR | 245 | 0 | 87 | 87 | LF | 0 | 0 | 0 | 16659.82
Y | IPCRP1-0216-1010-L | IPCRP1 | IPCRP1 | 0216-1010 | PM - Half Section PC Conc Barrier | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 245 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | All PC Barrier (full sections) coded to cc: 0252-1020
Y | IPCRP1-0216-1010-M | IPCRP1 | IPCRP1 | 0216-1010 | PM - Half Section PC Conc Barrier | N | M |  | NR | P | 24867.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 24867.5 | 0 | 0 | 24867.5 | 0 | 0 | 0 | N | 24867.5 | 0 | 0 | 24867.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 245 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | All PC Barrier (full sections) coded to cc: 0252-1020
Y | IPCRP1-0217-0000-L | IPCRP1 | IPCRP1 | 0217-0000 | SUBBASE COURSE, SELECT GRAN MATERIAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0217-0000-R | IPCRP1 | IPCRP1 | 0217-0000 | SUBBASE COURSE, SELECT GRAN MATERIAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 296500 | 0 | 0 | 296500 | 0 | 296500 | 153050 | 0 | N | 296500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0217-1000-E | IPCRP1 | IPCRP1 | 0217-1000 | Inst Subbase Course, Select Gran Material | N | E |  | NR | P | 10408.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 10408.8 | 0 | 0 | 10408.8 | 0 | 0 | 0 | Y | 10408.8 | 0 | 0 | 10408.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1186 | 612.2 | 573.8 | 1186 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0217-1000-L | IPCRP1 | IPCRP1 | 0217-1000 | Inst Subbase Course, Select Gran Material | N | L |  | NR | P | 58847.94 | 59405.84 | 59405.84 | 59405.84 | 59405.84 | 43.1992 | 0 | 0 | 0 | 78110.28 | Y | 137516.12 | Y | -78668.18 | 0 | 0 | 58847.94 | 0 | 0 | 137516.12 | Y | -78668.18 | 0 | 0 | 58847.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -137516.12 | 0 | 0 | 137516.12 | 0 | 0 | 0 | 0 | 0 | 0 | -137516.12 | 0 | 0 | 137516.12 | 137516.12 | 0 | 0 | 0 | 512 | 0 | 1100 | 1100 | 512 | 475 | 625 | 1100 | HR | 1186 | 612.2 | 573.8 | 1186 | CY | 0 | 0 | 0 | 78110.28
Y | IPCRP1-0217-1000-S | IPCRP1 | IPCRP1 | 0217-1000 | Inst Subbase Course, Select Gran Material | N | S |  | UNIT | A | 0 | 8939.04 | 8939.04 | 8939.04 | 8939.04 | 100 | 0 | 0 | 0 | 0 | N | 8939.04 | N | -8939.04 | 0 | 0 | 0 | 0 | 0 | 8939.04 | N | -8939.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8939.04 | 0 | 0 | 8939.04 | 0 | 0 | 0 | 0 | 0 | 0 | -8939.04 | 0 | 0 | 8939.04 | 8939.04 | 0 | 0 | 0 | 0 | 0 | 71 | 71 | 0 | 71 | 0 | 71 | NA | 1186 | 612.2 | 573.8 | 1186 | CY | 8939.04 | 0 | 8939.04 | 0
Y | IPCRP1-0218-0000-L | IPCRP1 | IPCRP1 | 0218-0000 | PLASTIC FILTER FABRIC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0218-0000-R | IPCRP1 | IPCRP1 | 0218-0000 | PLASTIC FILTER FABRIC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10000 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | N | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0218-1000-C | IPCRP1 | IPCRP1 | 0218-1000 | Plastic Filter Fabric | N | C |  | NR | P | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2475 | Y | 2475 | Y | 0 | 0 | 0 | 2475 | 0 | 0 | 2475 | Y | 0 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2475 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | -2475 | 0 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1501 | 0 | 1501 | SF | 1000 | 0 | 1000 | 1000 | SY | 0 | 0 | 0 | 2475
Y | IPCRP1-0218-1000-L | IPCRP1 | IPCRP1 | 0218-1000 | Plastic Filter Fabric | N | L |  | NR | P | 6584.34 | -1.38 | -1.38 | -1.38 | -1.38 | -0.020959 | 0 | 0 | 0 | 6585.72 | Y | 6584.34 | Y | 0 | 0 | 0 | 6584.34 | 0 | 0 | 6584.34 | Y | 0 | 0 | 0 | 6584.34 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6584.34 | 0 | 0 | 6584.34 | 0 | 0 | 0 | 0 | 0 | 0 | -6584.34 | 0 | 0 | 6584.34 | 6584.34 | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 64 | 0 | 64 | 64 | HR | 1000 | 0 | 1000 | 1000 | SY | 0 | 0 | 0 | 6585.72
Y | IPCRP1-0218-1000-S | IPCRP1 | IPCRP1 | 0218-1000 | Plastic Filter Fabric | N | S |  | UNIT | A | 0 | 124.59 | 124.59 | 124.59 | 124.59 | 100 | 0 | 0 | 0 | 0 | N | 124.59 | N | -124.59 | 0 | 0 | 0 | 0 | 0 | 124.59 | N | -124.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -124.59 | 0 | 0 | 124.59 | 0 | 0 | 0 | 0 | 0 | 0 | -124.59 | 0 | 0 | 124.59 | 124.59 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 1000 | 0 | 1000 | 1000 | SY | 124.59 | 0 | 124.59 | 0
Y | IPCRP1-0219-0000-L | IPCRP1 | IPCRP1 | 0219-0000 | MAINT & PROT OF TRAFFIC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0219-0000-R | IPCRP1 | IPCRP1 | 0219-0000 | MAINT & PROT OF TRAFFIC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50000000 | 0 | 0 | 50000000 | 0 | 50000000 | 31499524.71 | 0 | N | 50000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1000-C | IPCRP1 | IPCRP1 | 0219-1000 | Furn MPT Materials | N | C |  | NR | P | 1260743 | 1753803.14 | 1753803.14 | 1676890.43 | 1753803.14 | 83.8445 | 0 | 0 | 0 | 246196.86 | Y | 2000000 | Y | -739257 | 0 | 0 | 1260743 | 0 | 0 | 2000000 | Y | -739257 | 0 | 0 | 1260743 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2000000 | 4937.37 | 1219.87 | 2000000 | 0 | 0 | 0 | 4937.37 | 2522.85 | 0 | -2000000 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 99331.78 | -6652.98 | 92678.8 | CY | 1 | 0.75 | 0.25 | 1 | LS | 1753864.21 | 76912.71 | 1676951.5 | 246196.86 | Traffic Lane, PowerPak. All cost in Labor category should be transferred to 0219-1020-Labor code
Y | IPCRP1-0219-1000-L | IPCRP1 | IPCRP1 | 0219-1000 | Furn MPT Materials | N | L |  | NR | P | 2430.52 | -1858.65 | -1858.65 | -1858.65 | -1858.65 | 100 | 0 | 0 | 0 | 0 | Y | -1858.65 | Y | 4289.17 | 0 | 0 | 2430.52 | 0 | 0 | -1858.65 | Y | 4289.17 | 0 | 0 | 2430.52 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 1858.65 | 0 | 0 | -1858.65 | 0 | 0 | 0 | 0 | 0 | 0 | 1858.65 | 0 | 0 | -1858.65 | -1858.65 | 0 | 0 | 0 | 24 | 0 | 2 | 2 | 24 | 2 | 0 | 2 | HR | 1 | 0.75 | 0.25 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1000-S | IPCRP1 | IPCRP1 | 0219-1000 | Furn MPT Materials | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 79 | 0 | 0 | 79 | 79 | NA | 1 | 0.75 | 0.25 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1010-C | IPCRP1 | IPCRP1 | 0219-1010 | Movable Barrier | N | C |  | UNIT | U | 0 | 1694334.33 | 1694334.33 | 35210.18 | 1694334.33 | 2.0956 | 0 | 0 | 0 | -14175.32 | Y | 1680159.01 | Y | -1680159.01 | 0 | 0 | 0 | 0 | 0 | 1680159.01 | Y | -1680159.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1680159.01 | 17964.38 | 17245.8 | 1680159.01 | 0 | 0 | 0 | 5095.14 | 35210.18 | 0 | -1680159.01 | 0 | 0 | 1680159.01 | 1680159.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283 | -2283 | 0 | LS | 1 | 0 | 1 | 1 | LS | 1694334.33 | 1659124.15 | 35210.18 | -14175.32
Y | IPCRP1-0219-1010-E | IPCRP1 | IPCRP1 | 0219-1010 | Movable Barrier | N | E |  | NR | P | 53000 | 49832.04 | 49832.04 | 0 | 49832.04 | 0 | 0 | 0 | 0 | 0 | Y | 49832.04 | Y | 3167.96 | 0 | 0 | 53000 | 0 | 0 | 49832.04 | Y | 3167.96 | 0 | 0 | 53000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -49832.04 | 0 | 0 | 49832.04 | 0 | 0 | 0 | 0 | 0 | 0 | -49832.04 | 0 | 0 | 49832.04 | 49832.04 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 327 | 327 | CY | 1 | 0 | 1 | 1 | LS | 49832.04 | 49832.04 | 0 | 0
Y | IPCRP1-0219-1010-L | IPCRP1 | IPCRP1 | 0219-1010 | Movable Barrier | N | L |  | NR | P | 52233.9 | -36.19 | -36.19 | -36.19 | -36.19 | -0.069285 | 0 | 0 | 0 | 52270.09 | N | 52233.9 | N | 0 | 0 | 0 | 52233.9 | 0 | 0 | 52233.9 | N | 0 | 0 | 0 | 52233.9 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -52233.9 | 0 | 0 | 52233.9 | 0 | 0 | 0 | 0 | 0 | 0 | -52233.9 | 0 | 0 | 52233.9 | 52233.9 | 0 | 0 | 0 | 480 | 0 | 480 | 480 | 480 | 0 | 480 | 480 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 52270.09
Y | IPCRP1-0219-1010-S | IPCRP1 | IPCRP1 | 0219-1010 | Movable Barrier | N | S |  | NR | A | 1087500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1087500 | 0 | 0 | 1087500 | 0 | 0 | 0 | Y | 1087500 | 0 | 0 | 1087500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1020-C | IPCRP1 | IPCRP1 | 0219-1020 | Haul & Maintain MPT - all shifts (D, N, WE) | N | C |  | NR | P | 197225 | 74623.09 | 74623.09 | 70893.51 | 74623.09 | 70.8935 | 0 | 0 | 0 | 25376.91 | Y | 100000 | Y | 97225 | 0 | 0 | 197225 | 0 | 0 | 100000 | Y | 97225 | 0 | 0 | 197225 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 4402.91 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 266 | -266 | 0 | CH | 1628 | 1126 | 502 | 1628 | SH | 60783.74 | 3729.58 | 57054.16 | 25376.91
Y | IPCRP1-0219-1020-E | IPCRP1 | IPCRP1 | 0219-1020 | Haul & Maintain MPT - all shifts (D, N, WE) | N | E |  | NR | P | 692960 | -521.81 | -1959.75 | -521.81 | -521.81 | 0 | 0 | 0 | 0 | 521.81 | Y | 0 | Y | 692960 | 0 | 0 | 692960 | 0 | 0 | 0 | Y | 692960 | 0 | 0 | 692960 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 31 | -9 | 22 | CH | 1628 | 1126 | 502 | 1628 | SH | -1959.75 | -1437.94 | -521.81 | 521.81 | Curry Supply PO # IPCRP1-0106 will be removed from there and this note will be deleted afterward. Angie is working with Selin & CMiC. SSD base contract @$400K, HSP base contract @$700K
Y | IPCRP1-0219-1020-L | IPCRP1 | IPCRP1 | 0219-1020 | Haul & Maintain MPT - all shifts (D, N, WE) | N | L |  | NR | P | 6226111 | 4385781.08 | 4385781.08 | 4385781.08 | 4385781.08 | 74.3353 | 0 | 0 | 0 | 1514218.92 | Y | 5900000 | Y | 326111 | 0 | 0 | 6226111 | 0 | 0 | 5900000 | Y | 326111 | 0 | 0 | 6226111 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5900000 | 59962.55 | 51791.35 | 5900000 | 0 | 0 | 0 | 0 | 0 | 0 | -5900000 | 0 | 0 | 5900000 | 5900000 | 0 | 0 | 0 | 49888 | 0 | 52183.93 | 52183.93 | 49888 | 38914 | 13269.93 | 52183.93 | HR | 1628 | 1126 | 502 | 1628 | SH | 0 | 0 | 0 | 1514218.92 | Curry Supply PO # IPCRP1-0106 will be removed from there and this note will be deleted afterward. Angie is working with Selin & CMiC. SSD base contract @$400K, HSP base contract @$700K
Y | IPCRP1-0219-1020-S | IPCRP1 | IPCRP1 | 0219-1020 | Haul & Maintain MPT - all shifts (D, N, WE) | N | S |  | UNIT | A | 0 | 2167538.54 | 2167538.54 | 1203721.87 | 2167538.54 | 41.8149 | 0 | 0 | 0 | 711154.9 | Y | 2878693.44 | Y | -2878693.44 | 0 | 0 | 0 | 0 | 0 | 2878693.44 | Y | -2878693.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2878693.44 | 42420.72 | 12974.29 | 2878693.44 | 0 | 0 | 0 | 0 | -162386.77 | 0 | -2878693.44 | 0 | 0 | 2878693.44 | 2878693.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5017167.42 | -5017167.42 | 0 | NA | 1628 | 1126 | 502 | 1628 | SH | 2167538.54 | 963816.67 | 1203721.87 | 711154.9 | Curry Supply PO # IPCRP1-0106 will be removed from there and this note will be deleted afterward. Angie is working with Selin & CMiC. SSD base contract @$400K, HSP base contract @$700K
Y | IPCRP1-0219-1040-L | IPCRP1 | IPCRP1 | 0219-1040 | F&I Temp Conc Barrier (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 300 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1040-S | IPCRP1 | IPCRP1 | 0219-1040 | F&I Temp Conc Barrier (CLOSED) | N | S |  | NR | A | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 75000 | 0 | 0 | 75000 | 0 | 0 | 0 | Y | 75000 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CH | 300 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1050-L | IPCRP1 | IPCRP1 | 0219-1050 | Hydroseed Surcharge Areas (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 667492 | 0 | 10 | 10 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1050-S | IPCRP1 | IPCRP1 | 0219-1050 | Hydroseed Surcharge Areas (CLOSED) | N | S |  | NR | A | 66749.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 66739.2 | 0 | 0 | 66749.2 | 0 | 0 | 10 | Y | 66739.2 | 0 | 0 | 66749.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 667492 | 0 | 10 | 10 | SF | 0 | 0 | 0 | 10
Y | IPCRP1-0219-1060-C | IPCRP1 | IPCRP1 | 0219-1060 | Temp Asphalt | N | C |  | NR | P | 220681.05 | 599307.54 | 599307.54 | 515105.63 | 599307.54 | 80.3306 | 0 | 0 | 0 | 41925 | Y | 641232.54 | Y | -420551.49 | 0 | 0 | 220681.05 | 0 | 0 | 641232.54 | Y | -420551.49 | 0 | 0 | 220681.05 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -641232.54 | 0 | 0 | 641232.54 | 0 | 0 | 0 | 0 | 0 | 0 | -641232.54 | 0 | 0 | 641232.54 | 641232.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 291222.98 | 0 | 291222.98 | LF | 5779.4 | 8130.63 | 1869.37 | 10000 | TN | 599307.54 | 84201.91 | 515105.63 | 41925 | GREEN ASPHALT CO LLC @$75K (2/23/22)
Y | IPCRP1-0219-1060-L | IPCRP1 | IPCRP1 | 0219-1060 | Temp Asphalt | N | L |  | UNIT | P | 0 | 24.01 | 24.01 | 24.01 | 24.01 | 100 | 0 | 0 | 0 | 0 | Y | 24.01 | Y | -24.01 | 0 | 0 | 0 | 0 | 0 | 24.01 | Y | -24.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24.01 | 0 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 | -24.01 | 0 | 0 | 24.01 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5779.4 | 8130.63 | 1869.37 | 10000 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1060-M | IPCRP1 | IPCRP1 | 0219-1060 | Temp Asphalt | N | M |  | NR | P | 191850.39 | 93469.06 | 93469.06 | 72162.95 | 93469.06 | 255.2879 | 0 | 0 | 0 | -65201.78 | Y | 28267.28 | Y | 163583.11 | 0 | 0 | 191850.39 | 0 | 0 | 28267.28 | Y | 163583.11 | 0 | 0 | 191850.39 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28267.28 | 48440.6 | 0 | 28267.28 | 0 | 0 | 0 | 72471.93 | 0 | 0 | -28267.28 | 0 | 0 | 28267.28 | 28267.28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1246.35 | -404 | 842.35 | CY | 5779.4 | 8130.63 | 1869.37 | 10000 | TN | 93469.06 | 21306.11 | 72162.95 | -65201.78
Y | IPCRP1-0219-1060-S | IPCRP1 | IPCRP1 | 0219-1060 | Temp Asphalt | N | S |  | NR | A | 26250 | 382.59 | 382.59 | 382.59 | 382.59 | 100 | 0 | 0 | 0 | 0 | Y | 382.59 | Y | 25867.41 | 0 | 0 | 26250 | 0 | 0 | 382.59 | Y | 25867.41 | 0 | 0 | 26250 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -382.59 | 0 | 0 | 382.59 | 0 | 0 | 0 | 0 | 0 | 0 | -382.59 | 0 | 0 | 382.59 | 382.59 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3 | -3 | 0 | CY | 5779.4 | 8130.63 | 1869.37 | 10000 | TN | 382.59 | 0 | 382.59 | 0
Y | IPCRP1-0219-1070-L | IPCRP1 | IPCRP1 | 0219-1070 | Crossing Guards (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8792 | 1072 | 0 | 1072 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-0219-1070-S | IPCRP1 | IPCRP1 | 0219-1070 | Crossing Guards (CLOSED) | N | S |  | NR | P | 384650 | 32509 | 32509 | 32509 | 32509 | 100 | 0 | 0 | 0 | 0 | Y | 32509 | Y | 352141 | 0 | 0 | 384650 | 0 | 0 | 32509 | Y | 352141 | 0 | 0 | 384650 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32509 | 0 | 0 | 32509 | 0 | 0 | 0 | 0 | 0 | 0 | -32509 | 0 | 0 | 32509 | 32509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118 | -1118 | 0 | HR | 8792 | 1072 | 0 | 1072 | HR | 32509 | 0 | 32509 | 0 | PERRY ONAH @$300K
Y | IPCRP1-0220-0000-L | IPCRP1 | IPCRP1 | 0220-0000 | GRIND EXIST ASPH CONC WEARING COURSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0220-0000-R | IPCRP1 | IPCRP1 | 0220-0000 | GRIND EXIST ASPH CONC WEARING COURSE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 32200 | 0 | 0 | 32200 | 0 | 32200 | 17466.75 | 0 | N | 32200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0220-1000-L | IPCRP1 | IPCRP1 | 0220-1000 | GRIND EXIST ASPH CONC WEARING COURSE | N | L |  | UNIT | P | 0 | 10586.96 | 10586.96 | 10586.96 | 10586.96 | 35.8558 | 0 | 0 | 0 | 18939.52 | Y | 29526.48 | Y | -29526.48 | 0 | 0 | 0 | 0 | 0 | 29526.48 | Y | -29526.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -29526.48 | 0 | 0 | 29526.48 | 0 | 0 | 0 | 0 | 0 | 0 | -29526.48 | 0 | 0 | 29526.48 | 29526.48 | 0 | 0 | 0 | 0 | 0 | 227.3 | 227.3 | 0 | 81.5 | 145.8 | 227.3 | HR | 184 | 99.81 | 84.19 | 184 | CY | 0 | 0 | 0 | 18939.52
Y | IPCRP1-0220-1000-S | IPCRP1 | IPCRP1 | 0220-1000 | GRIND EXIST ASPH CONC WEARING COURSE | N | S |  | NR | A | 29526.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 29526.48 | 0 | 0 | 29526.48 | 0 | 0 | 0 | Y | 29526.48 | 0 | 0 | 29526.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 184 | 99.81 | 84.19 | 184 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0221-0000-L | IPCRP1 | IPCRP1 | 0221-0000 | REM EXIST TRAFFIC & STREET NAME SIGNS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0221-0000-R | IPCRP1 | IPCRP1 | 0221-0000 | REM EXIST TRAFFIC & STREET NAME SIGNS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9750 | 0 | 0 | 9750 | 0 | 9750 | 3450 | 0 | N | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0222-0000-L | IPCRP1 | IPCRP1 | 0222-0000 | REM EXIST TRAFFIC & STREET NAME SIGN POSTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0222-0000-R | IPCRP1 | IPCRP1 | 0222-0000 | REM EXIST TRAFFIC & STREET NAME SIGN POSTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9730 | 0 | 0 | 9730 | 0 | 9730 | 840 | 0 | N | 9730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0223-0000-L | IPCRP1 | IPCRP1 | 0223-0000 | FURN NEW NON-REFLECT TRAFFIC SIGNS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0223-0000-R | IPCRP1 | IPCRP1 | 0223-0000 | FURN NEW NON-REFLECT TRAFFIC SIGNS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1400 | 0 | 0 | 1400 | 0 | 1400 | 0 | 0 | N | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0224-0000-L | IPCRP1 | IPCRP1 | 0224-0000 | FURN NEW TRAFFIC SIGN POSTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0224-0000-R | IPCRP1 | IPCRP1 | 0224-0000 | FURN NEW TRAFFIC SIGN POSTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4695 | 0 | 0 | 4695 | 0 | 4695 | 1380 | 0 | N | 4695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0225-0000-L | IPCRP1 | IPCRP1 | 0225-0000 | FURN NEW REFLECT TRAFFIC SIGNS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0225-0000-R | IPCRP1 | IPCRP1 | 0225-0000 | FURN NEW REFLECT TRAFFIC SIGNS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8100 | 0 | 0 | 8100 | 0 | 8100 | 1750 | 0 | N | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0226-0000-L | IPCRP1 | IPCRP1 | 0226-0000 | INSTALL TRAFFIC SIGNS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0226-0000-R | IPCRP1 | IPCRP1 | 0226-0000 | INSTALL TRAFFIC SIGNS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6840 | 0 | 0 | 6840 | 0 | 6840 | 2100 | 0 | N | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0227-0000-L | IPCRP1 | IPCRP1 | 0227-0000 | INSTALL TRAFFIC SIGN POSTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0227-0000-R | IPCRP1 | IPCRP1 | 0227-0000 | INSTALL TRAFFIC SIGN POSTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31300 | 0 | 0 | 31300 | 0 | 31300 | 9200 | 0 | N | 31300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0228-0000-L | IPCRP1 | IPCRP1 | 0228-0000 | ALLOWANCE - TRAFFIC ENFORCEMENT AGENTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0228-0000-R | IPCRP1 | IPCRP1 | 0228-0000 | ALLOWANCE - TRAFFIC ENFORCEMENT AGENTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 976084 | 0 | 0 | 976084 | 0 | 976084 | 795835.52 | 0 | N | 976084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 976084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0228-1000-C | IPCRP1 | IPCRP1 | 0228-1000 | ALLOWANCE - TRAFFIC ENFORCEMENT AGENTS | N | C |  | NR | P | 976084 | 795835.58 | 795835.58 | 795835.58 | 795835.58 | 81.5335 | 0 | 0 | 0 | 180248.42 | N | 976084 | N | 0 | 0 | 0 | 976084 | 0 | 0 | 976084 | N | 0 | 0 | 0 | 976084 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -976084 | 0 | 0 | 976084 | 0 | 0 | 0 | 0 | 0 | 0 | -976084 | 0 | 0 | 976084 | 976084 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | LF | 1 | 0.82 | 0.18 | 1 | FP | 0 | 0 | 0 | 180248.42
Y | IPCRP1-0228-1000-L | IPCRP1 | IPCRP1 | 0228-1000 | ALLOWANCE - TRAFFIC ENFORCEMENT AGENTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.82 | 0.18 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0229-0000-L | IPCRP1 | IPCRP1 | 0229-0000 | FURN NEW STREET NAME SIGNS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0229-0000-R | IPCRP1 | IPCRP1 | 0229-0000 | FURN NEW STREET NAME SIGNS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1100 | 0 | 0 | 1100 | 0 | 1100 | 0 | 0 | N | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0230-0000-L | IPCRP1 | IPCRP1 | 0230-0000 | FURN NEW STREET NAME SIGN POSTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0230-0000-R | IPCRP1 | IPCRP1 | 0230-0000 | FURN NEW STREET NAME SIGN POSTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0231-0000-L | IPCRP1 | IPCRP1 | 0231-0000 | INSTALL STREET NAME SIGNS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0231-0000-R | IPCRP1 | IPCRP1 | 0231-0000 | INSTALL STREET NAME SIGNS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1100 | 0 | 0 | 1100 | 0 | 1100 | 0 | 0 | N | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0232-0000-L | IPCRP1 | IPCRP1 | 0232-0000 | INSTALL STREET NAME SIGN POSTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0232-0000-R | IPCRP1 | IPCRP1 | 0232-0000 | INSTALL STREET NAME SIGN POSTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0233-0000-L | IPCRP1 | IPCRP1 | 0233-0000 | PLASTIC BARRELS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0233-0000-R | IPCRP1 | IPCRP1 | 0233-0000 | PLASTIC BARRELS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25000 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | N | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0234-0000-L | IPCRP1 | IPCRP1 | 0234-0000 | REFLECT CRACK MEMBRANE (18 WIDE) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0234-0000-R | IPCRP1 | IPCRP1 | 0234-0000 | REFLECT CRACK MEMBRANE (18 WIDE) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 34392 | 0 | 0 | 34392 | 0 | 34392 | 9918.2 | 0 | N | 34392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0235-0000-L | IPCRP1 | IPCRP1 | 0235-0000 | AUDIO & VIDEO DOCUMENTATION SURVEY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0235-0000-R | IPCRP1 | IPCRP1 | 0235-0000 | AUDIO & VIDEO DOCUMENTATION SURVEY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | -1 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0235-1000-L | IPCRP1 | IPCRP1 | 0235-1000 | AUDIO & VIDEO DOCUMENTATION SURVEY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0235-1000-S | IPCRP1 | IPCRP1 | 0235-1000 | AUDIO & VIDEO DOCUMENTATION SURVEY | N | S |  | NR | A | 4500 | 4500 | 4500 | 4500 | 4500 | 100 | 0 | 0 | 0 | 0 | N | 4500 | N | 0 | 0 | 0 | 4500 | 0 | 0 | 4500 | N | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4500 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | -4500 | 0 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 1 | LF | 1 | 1 | 0 | 1 | LS | 4500 | 0 | 4500 | 0
Y | IPCRP1-0236-0000-L | IPCRP1 | IPCRP1 | 0236-0000 | F&D 6 DI RESTRAINED JT PIPE, CL 56 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0236-0000-R | IPCRP1 | IPCRP1 | 0236-0000 | F&D 6 DI RESTRAINED JT PIPE, CL 56 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6240 | 0 | 0 | 6240 | 0 | 6240 | 2080 | 0 | N | 6240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0237-0000-L | IPCRP1 | IPCRP1 | 0237-0000 | F&D 12 DI RESTRAINED JT PIPE, CL 56 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0237-0000-R | IPCRP1 | IPCRP1 | 0237-0000 | F&D 12 DI RESTRAINED JT PIPE, CL 56 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 162750 | 0 | 0 | 162750 | 0 | 162750 | 185560.5 | 0 | N | 162750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0238-0000-L | IPCRP1 | IPCRP1 | 0238-0000 | LAYING 6 DI PIPE & FITTINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0238-0000-R | IPCRP1 | IPCRP1 | 0238-0000 | LAYING 6 DI PIPE & FITTINGS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 55250 | 0 | 0 | 55250 | 0 | 55250 | 17956.25 | 0 | N | 55250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0239-0000-L | IPCRP1 | IPCRP1 | 0239-0000 | LAYING 12 DI PIPE & FITTINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0239-0000-R | IPCRP1 | IPCRP1 | 0239-0000 | LAYING 12 DI PIPE & FITTINGS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 738000 | 0 | 0 | 738000 | 0 | 738000 | 562232 | 0 | N | 738000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0239-1000-E | IPCRP1 | IPCRP1 | 0239-1000 | Lay 6 & 12 DI Pipe & Fittings | N | E |  | NR | P | 44461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 44461 | 0 | 0 | 44461 | 0 | 0 | 0 | Y | 44461 | 0 | 0 | 44461 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1975 | 1467.33 | 507.67 | 1975 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0239-1000-L | IPCRP1 | IPCRP1 | 0239-1000 | Lay 6 & 12 DI Pipe & Fittings | N | L |  | NR | P | 262920 | 223677.1 | 223677.1 | 223677.1 | 223677.1 | 73.5776 | 0 | 0 | 0 | 80324.46 | Y | 304001.56 | Y | -41081.56 | 0 | 0 | 262920 | 0 | 0 | 304001.56 | Y | -41081.56 | 0 | 0 | 262920 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -304001.56 | 0 | 0 | 304001.56 | 0 | 0 | 0 | 0 | 0 | 0 | -304001.56 | 0 | 0 | 304001.56 | 304001.56 | 0 | 0 | 0 | 2140 | 0 | 2175 | 2175 | 2140 | 1638 | 537 | 2175 | HR | 1975 | 1467.33 | 507.67 | 1975 | LF | 0 | 0 | 0 | 80324.46 | As/ NM (6/13/25) City considers offset at 10th St temporary until we tie it in past the proposed 10th St bridge (19.5').
Y | IPCRP1-0239-1000-S | IPCRP1 | IPCRP1 | 0239-1000 | Lay 6 & 12 DI Pipe & Fittings | N | S |  | UNIT | A | 0 | 9410.06 | 9410.06 | 9410.06 | 9410.06 | 100 | 0 | 0 | 0 | 0 | Y | 9410.06 | Y | -9410.06 | 0 | 0 | 0 | 0 | 0 | 9410.06 | Y | -9410.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9410.06 | 0 | 0 | 9410.06 | 0 | 0 | 0 | 0 | 0 | 0 | -9410.06 | 0 | 0 | 9410.06 | 9410.06 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 77.5 | -69.5 | 8 | NA | 1975 | 1467.33 | 507.67 | 1975 | LF | 9410.06 | 0 | 9410.06 | 0
Y | IPCRP1-0240-0000-L | IPCRP1 | IPCRP1 | 0240-0000 | F&D DI MJ 24 DIA & SMALLER FITTINGS (INC WEDGE T | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0240-0000-R | IPCRP1 | IPCRP1 | 0240-0000 | F&D DI MJ 24 DIA & SMALLER FITTINGS (INC WEDGE T | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40500 | 0 | 0 | 40500 | 0 | 40500 | 77184.45 | 0 | N | 40500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0241-0000-L | IPCRP1 | IPCRP1 | 0241-0000 | F&D 12 MJ BENDS (CL 55) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0241-0000-R | IPCRP1 | IPCRP1 | 0241-0000 | F&D 12 MJ BENDS (CL 55) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4500 | 0 | 0 | 4500 | 0 | 4500 | 8487 | 0 | N | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0242-0000-L | IPCRP1 | IPCRP1 | 0242-0000 | F&D 12 MJ CAPS (CL 55) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0242-0000-R | IPCRP1 | IPCRP1 | 0242-0000 | F&D 12 MJ CAPS (CL 55) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 846 | 0 | N | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0243-0000-L | IPCRP1 | IPCRP1 | 0243-0000 | F&D 12 MJ TEES (CL 55) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0243-0000-R | IPCRP1 | IPCRP1 | 0243-0000 | F&D 12 MJ TEES (CL 55) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 6829.5 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0244-0000-L | IPCRP1 | IPCRP1 | 0244-0000 | F, D & LAY 48 STRAIGHT ST PIPE, 5/8 WT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0244-0000-R | IPCRP1 | IPCRP1 | 0244-0000 | F, D & LAY 48 STRAIGHT ST PIPE, 5/8 WT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750000 | 0 | 0 | 750000 | 0 | 750000 | 450000 | 0 | N | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0244-1000-C | IPCRP1 | IPCRP1 | 0244-1000 | Install 48 Straight Steel WM Pipe | N | C |  | NR | P | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 750 | 0 | 0 | 750 | 0 | 0 | 0 | N | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 12.56 | 30 | 0 | 30 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0244-1000-E | IPCRP1 | IPCRP1 | 0244-1000 | Install 48 Straight Steel WM Pipe | N | E |  | NR | P | 246.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 246.42 | 0 | 0 | 246.42 | 0 | 0 | 0 | N | 246.42 | 0 | 0 | 246.42 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 12.56 | 30 | 0 | 30 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0244-1000-L | IPCRP1 | IPCRP1 | 0244-1000 | Install 48 Straight Steel WM Pipe | N | L |  | NR | P | 2986.63 | 2777.66 | 2777.66 | 2777.66 | 2777.66 | 100 | 0 | 0 | 0 | 0 | Y | 2777.66 | Y | 208.97 | 0 | 0 | 2986.63 | 0 | 0 | 2777.66 | Y | 208.97 | 0 | 0 | 2986.63 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2777.66 | 0 | 0 | 2777.66 | 0 | 0 | 0 | 0 | 0 | 0 | -2777.66 | 0 | 0 | 2777.66 | 2777.66 | 0 | 0 | 0 | 24 | 0 | 24 | 24 | 24 | 24 | 0 | 24 | HR | 12.56 | 30 | 0 | 30 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0244-1010-L | IPCRP1 | IPCRP1 | 0244-1010 | PM - Steel Water Main Straight Pipe 48 in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 50 | 50 | 0 | 50 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0244-1010-M | IPCRP1 | IPCRP1 | 0244-1010 | PM - Steel Water Main Straight Pipe 48 in | N | M |  | NR | P | 20000 | 52513.11 | 52513.11 | 52513.11 | 52513.11 | 100 | 0 | 0 | 0 | 0 | Y | 52513.11 | Y | -32513.11 | 0 | 0 | 20000 | 0 | 0 | 52513.11 | Y | -32513.11 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -52513.11 | 0 | 0 | 52513.11 | 0 | 0 | 0 | 0 | 0 | 0 | -52513.11 | 0 | 0 | 52513.11 | 52513.11 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 12 | -5 | 7 | EA | 50 | 50 | 0 | 50 | LF | 52513.11 | -4503.35 | 57016.46 | 0 | APS @$1,771.11 for spacers and American Cast Iron @$55,245.35 for 48" steel pipe and joints
Y | IPCRP1-0245-0000-L | IPCRP1 | IPCRP1 | 0245-0000 | UNDERDRAIN FILLER, TYPE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0245-0000-R | IPCRP1 | IPCRP1 | 0245-0000 | UNDERDRAIN FILLER, TYPE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42000 | 0 | 0 | 42000 | 0 | 42000 | 1400 | 0 | N | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0245-1000-L | IPCRP1 | IPCRP1 | 0245-1000 | Underdrain Filter, Type 1 | N | L |  | NR | P | 6840.46 | 345.78 | 345.78 | 345.78 | 345.78 | 5.0549 | 0 | 0 | 0 | 6494.68 | N | 6840.46 | N | 0 | 0 | 0 | 6840.46 | 0 | 0 | 6840.46 | N | 0 | 0 | 0 | 6840.46 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6840.46 | 0 | 0 | 6840.46 | 0 | 0 | 0 | 0 | 0 | 0 | -6840.46 | 0 | 0 | 6840.46 | 6840.46 | 0 | 0 | 0 | 67.2 | 0 | 67.2 | 67.2 | 67.2 | 3 | 64.2 | 67.2 | HR | 210 | 7 | 203 | 210 | CY | 0 | 0 | 0 | 6494.68
Y | IPCRP1-0245-1000-M | IPCRP1 | IPCRP1 | 0245-1000 | Underdrain Filter, Type 1 | N | M |  | NR | P | 9355.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9355.5 | N | 9355.5 | N | 0 | 0 | 0 | 9355.5 | 0 | 0 | 9355.5 | N | 0 | 0 | 0 | 9355.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9355.5 | 0 | 0 | 9355.5 | 0 | 0 | 0 | 0 | 0 | 0 | -9355.5 | 0 | 0 | 9355.5 | 9355.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 210 | 7 | 203 | 210 | CY | 0 | 0 | 0 | 9355.5
Y | IPCRP1-0246-0000-L | IPCRP1 | IPCRP1 | 0246-0000 | 8 DIA PERF CORR POLY UNDERDRAIN TUBING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0246-0000-R | IPCRP1 | IPCRP1 | 0246-0000 | 8 DIA PERF CORR POLY UNDERDRAIN TUBING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 12400 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0247-0000-L | IPCRP1 | IPCRP1 | 0247-0000 | 10 DIA PERF CORR POLY UNDERDRAIN TUBING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0247-0000-R | IPCRP1 | IPCRP1 | 0247-0000 | 10 DIA PERF CORR POLY UNDERDRAIN TUBING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 284000 | 0 | 0 | 284000 | 0 | 284000 | 0 | 0 | N | 284000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0247-1000-E | IPCRP1 | IPCRP1 | 0247-1000 | 8 & 10 Dia Perf Corr Poly Underdrain Tubing | N | E |  | NR | P | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 9600 | 0 | 0 | 9600 | 0 | 0 | 0 | Y | 9600 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 1560 | 62 | 1498 | 1560 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0247-1000-L | IPCRP1 | IPCRP1 | 0247-1000 | 8 & 10 Dia Perf Corr Poly Underdrain Tubing | N | L |  | NR | P | 44455 | 1793.28 | 1793.28 | 1793.28 | 1793.28 | 4.0339 | 0 | 0 | 0 | 42661.72 | N | 44455 | N | 0 | 0 | 0 | 44455 | 0 | 0 | 44455 | N | 0 | 0 | 0 | 44455 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -44455 | 0 | 0 | 44455 | 0 | 0 | 0 | 0 | 0 | 0 | -44455 | 0 | 0 | 44455 | 44455 | 0 | 0 | 0 | 400 | 0 | 400 | 400 | 400 | 15 | 385 | 400 | HR | 1560 | 62 | 1498 | 1560 | LF | 0 | 0 | 0 | 42661.72
Y | IPCRP1-0247-1000-M | IPCRP1 | IPCRP1 | 0247-1000 | 8 & 10 Dia Perf Corr Poly Underdrain Tubing | N | M |  | NR | P | 16980 | 3050.05 | 3050.05 | 2577.38 | 3050.05 | 15.1789 | 0 | 0 | 0 | 13929.95 | N | 16980 | N | 0 | 0 | 0 | 16980 | 0 | 0 | 16980 | N | 0 | 0 | 0 | 16980 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16980 | 0 | 0 | 16980 | 0 | 0 | 0 | 0 | 0 | 0 | -16980 | 0 | 0 | 16980 | 16980 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 53 | -53 | 0 | LF | 1560 | 62 | 1498 | 1560 | LF | 3050.05 | 472.67 | 2577.38 | 13929.95
Y | IPCRP1-0248-0000-L | IPCRP1 | IPCRP1 | 0248-0000 | HPBO (MOD) CORR BEAM MEDIAN BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0248-0000-R | IPCRP1 | IPCRP1 | 0248-0000 | HPBO (MOD) CORR BEAM MEDIAN BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 21600 | 0 | 0 | 21600 | 0 | 21600 | 0 | 0 | N | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0249-0000-L | IPCRP1 | IPCRP1 | 0249-0000 | SINGLE SLOPE CONC MEDIAN BARRIER (OPTIONAL) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0249-0000-R | IPCRP1 | IPCRP1 | 0249-0000 | SINGLE SLOPE CONC MEDIAN BARRIER (OPTIONAL) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 44100 | 0 | 0 | 44100 | 0 | 44100 | 0 | 0 | N | 44100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0250-0000-L | IPCRP1 | IPCRP1 | 0250-0000 | SINGLE SLOPE TRAFFIC BARRIER WALL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0250-0000-R | IPCRP1 | IPCRP1 | 0250-0000 | SINGLE SLOPE TRAFFIC BARRIER WALL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5600 | 0 | 0 | 5600 | 0 | 5600 | 0 | 0 | N | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0251-0000-L | IPCRP1 | IPCRP1 | 0251-0000 | SINGLE SLOPE CONC MED BARRIER - WIDE (OPT) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0251-0000-R | IPCRP1 | IPCRP1 | 0251-0000 | SINGLE SLOPE CONC MED BARRIER - WIDE (OPT) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 200550 | 0 | 0 | 200550 | 0 | 200550 | 0 | 0 | N | 200550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0252-0000-L | IPCRP1 | IPCRP1 | 0252-0000 | SINGLE SLOPE CONC HALF SECT BARRIER (OPT) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0252-0000-R | IPCRP1 | IPCRP1 | 0252-0000 | SINGLE SLOPE CONC HALF SECT BARRIER (OPT) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 121275 | 0 | 0 | 121275 | 0 | 121275 | 0 | 0 | N | 121275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0252-1000-C | IPCRP1 | IPCRP1 | 0252-1000 | Prep & Set Pads for Conc Barrier | N | C |  | NR | P | 15373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15373 | Y | 15373 | Y | 0 | 0 | 0 | 15373 | 0 | 0 | 15373 | Y | 0 | 0 | 0 | 15373 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15373 | 0 | 0 | 15373 | 0 | 0 | 0 | 0 | 0 | 0 | -15373 | 0 | 0 | 15373 | 15373 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1846 | 0 | 1991 | 1991 | LF | 0 | 0 | 0 | 15373
Y | IPCRP1-0252-1000-L | IPCRP1 | IPCRP1 | 0252-1000 | Prep & Set Pads for Conc Barrier | N | L |  | NR | P | 9672 | 0.02 | 0.02 | 0.02 | 0.02 | 0.00020678 | 0 | 0 | 0 | 9671.98 | Y | 9672 | Y | 0 | 0 | 0 | 9672 | 0 | 0 | 9672 | Y | 0 | 0 | 0 | 9672 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9672 | 0 | 0 | 9672 | 0 | 0 | 0 | 0 | 0 | 0 | -9672 | 0 | 0 | 9672 | 9672 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 96 | -16 | 16 |  | HR | 1846 | 0 | 1991 | 1991 | LF | 0 | 0 | 0 | 9671.98
Y | IPCRP1-0252-1010-E | IPCRP1 | IPCRP1 | 0252-1010 | Set Conc Barrier - All Types | N | E |  | NR | P | 11707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 11707 | 0 | 0 | 11707 | 0 | 0 | 0 | Y | 11707 | 0 | 0 | 11707 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1846 | 20 | 1971 | 1991 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0252-1010-L | IPCRP1 | IPCRP1 | 0252-1010 | Set Conc Barrier - All Types | N | L |  | NR | P | 117063 | 2520.45 | 2520.45 | 2520.45 | 2520.45 | 2.1531 | 0 | 0 | 0 | 114542.55 | Y | 117063 | Y | 0 | 0 | 0 | 117063 | 0 | 0 | 117063 | Y | 0 | 0 | 0 | 117063 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -117063 | 0 | 0 | 117063 | 0 | 0 | 0 | 0 | 0 | 0 | -117063 | 0 | 0 | 117063 | 117063 | 0 | 0 | 0 | 1100.44 | 0 | 1100.43 | 1100.43 | 1100.44 | 7 | 1093.43 | 1100.43 | HR | 1846 | 20 | 1971 | 1991 | LF | 0 | 0 | 0 | 114542.55 | 2,078.00 - 87.00 (cc: 0216-1000) = 1,991.00 LF
Y | IPCRP1-0252-1020-L | IPCRP1 | IPCRP1 | 0252-1020 | PM - Precast Barrier, All Types | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1846 | 0 | 2078 | 2078 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0252-1020-M | IPCRP1 | IPCRP1 | 0252-1020 | PM - Precast Barrier, All Types | N | M |  | NR | P | 182269 | 492217.73 | 492217.73 | 31612.6 | 492217.73 | 7.0333 | 0 | 0 | 0 | -42746 | Y | 449471.73 | Y | -267202.73 | 0 | 0 | 182269 | 0 | 0 | 449471.73 | Y | -267202.73 | 0 | 0 | 182269 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -449471.73 | 0 | 0 | 449471.73 | 0 | 0 | 0 | 0 | 10800 | 0 | -449471.73 | 0 | 0 | 449471.73 | 449471.73 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | -1 | 0 | NA | 1846 | 0 | 2078 | 2078 | LF | 492217.73 | 460605.13 | 31612.6 | -42746
Y | IPCRP1-0253-0000-L | IPCRP1 | IPCRP1 | 0253-0000 | CONC BARRIER - SPECIAL SECTION TYPE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0253-0000-R | IPCRP1 | IPCRP1 | 0253-0000 | CONC BARRIER - SPECIAL SECTION TYPE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0254-0000-L | IPCRP1 | IPCRP1 | 0254-0000 | CONC BARRIER - SPECIAL SECTION TYPE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0254-0000-R | IPCRP1 | IPCRP1 | 0254-0000 | CONC BARRIER - SPECIAL SECTION TYPE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0255-0000-L | IPCRP1 | IPCRP1 | 0255-0000 | CONC BARRIER - SPECIAL SECTION TYPE 3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0255-0000-R | IPCRP1 | IPCRP1 | 0255-0000 | CONC BARRIER - SPECIAL SECTION TYPE 3 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 34000 | 0 | 0 | 34000 | 0 | 34000 | 0 | 0 | N | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0256-0000-L | IPCRP1 | IPCRP1 | 0256-0000 | CONC BARRIER - SPECIAL SECTION TYPE 4 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0256-0000-R | IPCRP1 | IPCRP1 | 0256-0000 | CONC BARRIER - SPECIAL SECTION TYPE 4 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 20000 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0257-0000-L | IPCRP1 | IPCRP1 | 0257-0000 | CONC BARRIER - SPECIAL SECTION TYPE 5 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0257-0000-R | IPCRP1 | IPCRP1 | 0257-0000 | CONC BARRIER - SPECIAL SECTION TYPE 5 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0257-1000-E | IPCRP1 | IPCRP1 | 0257-1000 | Install & Strip Formwork to Transition Barrier | N | E |  | NR | P | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 750 | 0 | 0 | 750 | 0 | 0 | 0 | N | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1040 | 165.5 | 0 | 165.5 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0257-1000-L | IPCRP1 | IPCRP1 | 0257-1000 | Install & Strip Formwork to Transition Barrier | N | L |  | NR | P | 24814 | 782.91 | 782.91 | 782.91 | 782.91 | 100 | 0 | 0 | 0 | 0 | Y | 782.91 | Y | 24031.09 | 0 | 0 | 24814 | 0 | 0 | 782.91 | Y | 24031.09 | 0 | 0 | 24814 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -782.91 | 0 | 0 | 782.91 | 0 | 0 | 0 | 0 | 0 | 0 | -782.91 | 0 | 0 | 782.91 | 782.91 | 0 | 0 | 0 | 210 | 0 | 6 | 6 | 210 | 34 | -28 | 6 | HR | 1040 | 165.5 | 0 | 165.5 | SF | 0 | 0 | 0 | 0 | All Transition Barriers (9ea) will be Precast, therefore no concrete to place. re-entered 1-12-2024
Y | IPCRP1-0257-1010-C | IPCRP1 | IPCRP1 | 0257-1010 | Place Concrete to Transition Barrier | N | C |  | NR | P | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 132 | 0 | 0 | 132 | 0 | 0 | 0 | N | 132 | 0 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 44 | 4.05 | 0 | 4.05 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0257-1010-E | IPCRP1 | IPCRP1 | 0257-1010 | Place Concrete to Transition Barrier | N | E |  | NR | P | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | N | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 44 | 4.05 | 0 | 4.05 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0257-1010-L | IPCRP1 | IPCRP1 | 0257-1010 | Place Concrete to Transition Barrier | N | L |  | NR | P | 46906 | 391.45 | 391.45 | 391.45 | 391.45 | 100 | 0 | 0 | 0 | 0 | Y | 391.45 | Y | 46514.55 | 0 | 0 | 46906 | 0 | 0 | 391.45 | Y | 46514.55 | 0 | 0 | 46906 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -391.45 | 0 | 0 | 391.45 | 0 | 0 | 0 | 0 | 0 | 0 | -391.45 | 0 | 0 | 391.45 | 391.45 | 0 | 0 | 0 | 438.28 | 0 | 3 | 3 | 438.28 | 3 | 0 | 3 | HR | 44 | 4.05 | 0 | 4.05 | CY | 0 | 0 | 0 | 0 | All Transition Barriers (9ea) will be Precast, therefore no concrete required.
Y | IPCRP1-0257-1020-C | IPCRP1 | IPCRP1 | 0257-1020 | Furn Formwork for Transition Barrier | N | C |  | NR | P | 3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3397 | 0 | 0 | 3397 | 0 | 0 | 0 | Y | 3397 | 0 | 0 | 3397 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1040 | 165.5 | 0 | 165.5 | SF | 0 | 0 | 0 | 0 | Change PMF (Consumable) from $3,397.00 to 0.00.
Y | IPCRP1-0257-1020-L | IPCRP1 | IPCRP1 | 0257-1020 | Furn Formwork for Transition Barrier | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1040 | 165.5 | 0 | 165.5 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0258-0000-L | IPCRP1 | IPCRP1 | 0258-0000 | R&D HPBO (MOD) CB MEDIAN BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0258-0000-R | IPCRP1 | IPCRP1 | 0258-0000 | R&D HPBO (MOD) CB MEDIAN BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 146375 | 0 | 0 | 146375 | 0 | 146375 | 27000 | 0 | N | 146375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | IPCRP1-0258-1010-L | IPCRP1 | IPCRP1 | 0258-1010 | Self-Perform Remove HPBO CBGR (Median Barrier) | N | L |  | UNIT | P | 0 | 22044.94 | 22044.94 | 22044.94 | 22044.94 | 100 | 0 | 0 | 0 | 0 | N | 22044.94 | N | -22044.94 | 0 | 0 | 0 | 0 | 0 | 22044.94 | N | -22044.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22044.94 | 14604.56 | 7440.38 | 7440.38 | -14604.56 | 0 | 0 | 0 | 0 | 0 | -22044.94 | 0 | 0 | 22044.94 | 22044.94 | 0 | 0 | 0 | 0 | 0 | 176 | 176 | 0 | 176 | 0 | 176 | HR | 0 | 953.75 | 0 | 953.75 | LF | 0 | 0 | 0 | 0
N | IPCRP1-0258-1010-S | IPCRP1 | IPCRP1 | 0258-1010 | Self-Perform Remove HPBO CBGR (Median Barrier) | N | S |  | UNIT | A | 0 | 1937.02 | 1937.02 | 1937.02 | 1937.02 | 100 | 0 | 0 | 0 | 0 | N | 1937.02 | N | -1937.02 | 0 | 0 | 0 | 0 | 0 | 1937.02 | N | -1937.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1937.02 | 1937.02 | 0 | 1937.02 | 0 | 0 | 0 | 0 | 1937.02 | 0 | -1937.02 | 0 | 0 | 1937.02 | 1937.02 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 15 | 15 | NA | 0 | 953.75 | 0 | 953.75 | LF | 1937.02 | 0 | 1937.02 | 0
Y | IPCRP1-0259-0000-L | IPCRP1 | IPCRP1 | 0259-0000 | R&D CONC MEDIAN BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0259-0000-R | IPCRP1 | IPCRP1 | 0259-0000 | R&D CONC MEDIAN BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 69125 | 0 | 0 | 69125 | 0 | 69125 | 14000 | 0 | N | 69125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0260-0000-L | IPCRP1 | IPCRP1 | 0260-0000 | R&D CONC BARRIER - HALF SECTION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0260-0000-R | IPCRP1 | IPCRP1 | 0260-0000 | R&D CONC BARRIER - HALF SECTION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 83700 | 0 | 0 | 83700 | 0 | 83700 | 27600 | 0 | N | 83700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0260-1000-E | IPCRP1 | IPCRP1 | 0260-1000 | R&D Conc Barrier - all types | N | E |  | NR | P | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 10400 | 0 | 0 | 10400 | 0 | 0 | 0 | Y | 10400 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1232 | 1481 | 0 | 1481 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0260-1000-L | IPCRP1 | IPCRP1 | 0260-1000 | R&D Conc Barrier - all types | N | L |  | NR | P | 61478 | 77205.42 | 77205.42 | 77205.42 | 77205.42 | 125.5822 | 0 | 0 | 0 | 0 | N | 61478 | N | 0 | 0 | 0 | 61478 | 0 | 0 | 61478 | N | 0 | 0 | 0 | 61478 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -61478 | 45967.78 | 5726.61 | 61478 | 0 | 0 | 0 | 0 | 0 | 0 | -61478 | 0 | 0 | 61478 | 61478 | 0 | 0 | 0 | 416 | 0 | 416 | 416 | 416 | 549 | -133 | 416 | HR | 1232 | 1481 | 0 | 1481 | LF | 0 | 0 | 0 | 0 | Confirmed QTD thru Sep 25. 80.0' (R&D Med Barrier) + 196' (R&D Half Barrier) = 276.0'
N | IPCRP1-0260-1000-S | IPCRP1 | IPCRP1 | 0260-1000 | R&D Conc Barrier - all types | N | S |  | UNIT | A | 0 | 5947.87 | 5947.87 | 5947.87 | 5947.87 | 100 | 0 | 0 | 0 | 0 | N | 5947.87 | N | -5947.87 | 0 | 0 | 0 | 0 | 0 | 5947.87 | N | -5947.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5947.87 | 5423.66 | 524.21 | 5947.87 | 0 | 0 | 0 | 0 | 5423.66 | 0 | -5947.87 | 0 | 0 | 5947.87 | 5947.87 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 0 | 0 | 46 | 46 | NA | 1232 | 1481 | 0 | 1481 | LF | 5947.87 | 0 | 5947.87 | 0
Y | IPCRP1-0260-1010-L | IPCRP1 | IPCRP1 | 0260-1010 | Sawcut for Conc Barrier Removal | N | L |  | UNIT | P | 0 | 6073.61 | 6073.61 | 6073.61 | 6073.61 | 36.31 | 0 | 0 | 0 | 10653.49 | Y | 16727.1 | Y | -16727.1 | 0 | 0 | 0 | 0 | 0 | 16727.1 | Y | -16727.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16727.1 | 0 | 5006.51 | 16727.1 | 0 | 0 | 0 | 0 | 0 | 0 | -16727.1 | 0 | 0 | 16727.1 | 16727.1 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 42 | 78 | 120 | HR | 1232 | 2625 | 0 | 2625 | LF | 0 | 0 | 0 | 10653.49 | Scope included in barrier removal item. QTD to match Barrier Removal QTD.
Y | IPCRP1-0260-1010-S | IPCRP1 | IPCRP1 | 0260-1010 | Sawcut for Conc Barrier Removal | N | S |  | NR | A | 16016 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | -10000 | Y | 0 | Y | 16016 | 0 | 0 | 16016 | 0 | 0 | 0 | Y | 16016 | 0 | 0 | 16016 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1232 | 2625 | 0 | 2625 | LF | 10000 | 0 | 10000 | -10000
Y | IPCRP1-0261-0000-L | IPCRP1 | IPCRP1 | 0261-0000 | TRANS (TYPE 2) HPBO CB TO SS CONC MED BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0261-0000-R | IPCRP1 | IPCRP1 | 0261-0000 | TRANS (TYPE 2) HPBO CB TO SS CONC MED BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13000 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | N | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0262-0000-L | IPCRP1 | IPCRP1 | 0262-0000 | TRANS (TYPE 5) 1/2 SECT TO FULL SECT SS CONC MED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0262-0000-R | IPCRP1 | IPCRP1 | 0262-0000 | TRANS (TYPE 5) 1/2 SECT TO FULL SECT SS CONC MED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8000 | 0 | 0 | 8000 | 0 | 8000 | 0 | 0 | N | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0262-1000-L | IPCRP1 | IPCRP1 | 0262-1000 | TRANS (TYPE 5) 1/2 SECT TO FULL SECT SS CONC MED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0262-1000-M | IPCRP1 | IPCRP1 | 0262-1000 | TRANS (TYPE 5) 1/2 SECT TO FULL SECT SS CONC MED | N | M |  | NR | P | 7000 | 3051.4 | 3051.4 | 0 | 3051.4 | 0 | 0 | 0 | 0 | 0 | Y | 3051.4 | Y | 3948.6 | 0 | 0 | 7000 | 0 | 0 | 3051.4 | Y | 3948.6 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3051.4 | 0 | 0 | 3051.4 | 0 | 0 | 0 | 0 | 0 | 0 | -3051.4 | 0 | 0 | 3051.4 | 3051.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2 | 0 | 2 | 2 | EA | 3051.4 | 3051.4 | 0 | 0
Y | IPCRP1-0263-0000-L | IPCRP1 | IPCRP1 | 0263-0000 | STEEL RAILING & HANDRAIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0263-0000-R | IPCRP1 | IPCRP1 | 0263-0000 | STEEL RAILING & HANDRAIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1094500 | 0 | 0 | 1094500 | 0 | 1094500 | 465212 | 0 | N | 1094500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0264-0000-L | IPCRP1 | IPCRP1 | 0264-0000 | CONC SIDEWALKS & DRIVEWAYS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0264-0000-R | IPCRP1 | IPCRP1 | 0264-0000 | CONC SIDEWALKS & DRIVEWAYS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25500 | 0 | 0 | 25500 | 0 | 25500 | 0 | 0 | N | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0264-1000-L | IPCRP1 | IPCRP1 | 0264-1000 | Conc SW & Driveways | N | L |  | UNIT | P | 0 | 131.63 | 131.63 | 131.63 | 131.63 | 100 | 0 | 0 | 0 | 0 | Y | 131.63 | Y | -131.63 | 0 | 0 | 0 | 0 | 0 | 131.63 | Y | -131.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -131.63 | 0 | 0 | 131.63 | 0 | 0 | 0 | 0 | 0 | 0 | -131.63 | 0 | 0 | 131.63 | 131.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 30 | 0 | 15 | 15 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0264-1000-S | IPCRP1 | IPCRP1 | 0264-1000 | Conc SW & Driveways | N | S |  | NR | P | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | N | 12500 | N | 13000 | 0 | 0 | 25500 | 0 | 0 | 12500 | N | 13000 | 0 | 0 | 25500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12500 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | -12500 | 0 | 0 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 30 | 0 | 15 | 15 | CY | 0 | 0 | 0 | 12500 | 50% of item is self-performed, and 50% of item included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0265-0000-L | IPCRP1 | IPCRP1 | 0265-0000 | F&D 6 MJ DI GATE VALVE COMPLETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0265-0000-R | IPCRP1 | IPCRP1 | 0265-0000 | F&D 6 MJ DI GATE VALVE COMPLETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4800 | 0 | 0 | 4800 | 0 | 4800 | 4800 | 0 | N | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0266-0000-L | IPCRP1 | IPCRP1 | 0266-0000 | F&D 12 MJ DI GATE VALVE COMPLETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0266-0000-R | IPCRP1 | IPCRP1 | 0266-0000 | F&D 12 MJ DI GATE VALVE COMPLETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 55000 | 0 | 0 | 55000 | 0 | 55000 | 30000 | 0 | N | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0267-0000-L | IPCRP1 | IPCRP1 | 0267-0000 | SET 6 MJ DI GATE VALVE COMPLETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0267-0000-R | IPCRP1 | IPCRP1 | 0267-0000 | SET 6 MJ DI GATE VALVE COMPLETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1125 | 0 | 0 | 1125 | 0 | 1125 | 1125 | 0 | N | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0268-0000-L | IPCRP1 | IPCRP1 | 0268-0000 | SET 12 MJ DI GATE VALVE COMPLETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0268-0000-R | IPCRP1 | IPCRP1 | 0268-0000 | SET 12 MJ DI GATE VALVE COMPLETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4500 | 0 | 0 | 4500 | 0 | 4500 | 2250 | 0 | N | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0269-0000-L | IPCRP1 | IPCRP1 | 0269-0000 | SECURITY BOLLARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0269-0000-R | IPCRP1 | IPCRP1 | 0269-0000 | SECURITY BOLLARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 66000 | 0 | 0 | 66000 | 0 | 66000 | 33000 | 0 | N | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0269-1000-C | IPCRP1 | IPCRP1 | 0269-1000 | Excav & Install Bollards Complete | N | C |  | NR | P | 20 | 79303 | 79303 | 76158 | 79303 | 96.0342 | 0 | 0 | 0 | 0 | Y | 79303 | Y | -79283 | 0 | 0 | 20 | 0 | 0 | 79303 | Y | -79283 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -79303 | 0 | 0 | 79303 | 0 | 0 | 0 | 0 | 0 | 0 | -79303 | 0 | 0 | 79303 | 79303 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6 | 6 | 12 | TN | 6 | 3 | 3 | 6 | EA | 79303 | 3145 | 76158 | 0
Y | IPCRP1-0269-1000-E | IPCRP1 | IPCRP1 | 0269-1000 | Excav & Install Bollards Complete | N | E |  | NR | P | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 6 | 3 | 3 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0269-1000-L | IPCRP1 | IPCRP1 | 0269-1000 | Excav & Install Bollards Complete | N | L |  | NR | P | 28061 | 18547.36 | 18547.36 | 18547.36 | 18547.36 | 66.0966 | 0 | 0 | 0 | 9513.64 | N | 28061 | N | 0 | 0 | 0 | 28061 | 0 | 0 | 28061 | N | 0 | 0 | 0 | 28061 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28061 | 0 | 0 | 28061 | 0 | 0 | 0 | 0 | 0 | 0 | -28061 | 0 | 0 | 28061 | 28061 | 0 | 0 | 0 | 264 | 0 | 264 | 264 | 264 | 154 | 110 | 264 | HR | 6 | 3 | 3 | 6 | EA | 0 | 0 | 0 | 9513.64 | 3ea at Delancey St Bridge & 3ea at 10th St Bridge
Y | IPCRP1-0269-1000-S | IPCRP1 | IPCRP1 | 0269-1000 | Excav & Install Bollards Complete | N | S |  | UNIT | A | 0 | 497.16 | 497.16 | 497.16 | 497.16 | 100 | 0 | 0 | 0 | 0 | N | 497.16 | N | -497.16 | 0 | 0 | 0 | 0 | 0 | 497.16 | N | -497.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -497.16 | 0 | 0 | 497.16 | 0 | 0 | 0 | 0 | 0 | 0 | -497.16 | 0 | 0 | 497.16 | 497.16 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 6 | 3 | 3 | 6 | EA | 497.16 | 0 | 497.16 | 0
Y | IPCRP1-0269-1010-L | IPCRP1 | IPCRP1 | 0269-1010 | Flatbed Trucking (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0269-1010-S | IPCRP1 | IPCRP1 | 0269-1010 | Flatbed Trucking (CLOSED) | N | S |  | NR | A | 2780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2780 | 0 | 0 | 2780 | 0 | 0 | 0 | Y | 2780 | 0 | 0 | 2780 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 2 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0270-0000-L | IPCRP1 | IPCRP1 | 0270-0000 | PROT SAFETY SHIELDING OVER HIGHWAY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0270-0000-R | IPCRP1 | IPCRP1 | 0270-0000 | PROT SAFETY SHIELDING OVER HIGHWAY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 24080 | 0 | 0 | 24080 | 0 | 24080 | 0 | 0 | N | 24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0270-1000-C | IPCRP1 | IPCRP1 | 0270-1000 | Install Vert Shielding at Houston Retaining Wall | N | C |  | NR | P | 20797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 20787 | 0 | 0 | 20797 | 0 | 0 | 10 | Y | 20787 | 0 | 0 | 20797 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 5640 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 10 | Change PMF (Consumable) from $20,797.00 to $10,398.50
Y | IPCRP1-0270-1000-E | IPCRP1 | IPCRP1 | 0270-1000 | Install Vert Shielding at Houston Retaining Wall | N | E |  | NR | P | 6714.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 6714.25 | 0 | 0 | 6714.25 | 0 | 0 | 0 | N | 6714.25 | 0 | 0 | 6714.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 5640 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0270-1000-L | IPCRP1 | IPCRP1 | 0270-1000 | Install Vert Shielding at Houston Retaining Wall | N | L |  | NR | P | 145670.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 145670.37 | 0 | 0 | 145670.37 | 0 | 0 | 0 | Y | 145670.37 | 0 | 0 | 145670.37 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940 | 0 | 0 | 0 | 940 | 0 | 0 | 0 | HR | 5640 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Change PMF (Quantity) from 5,640.00 to 2,820.00, Change PMF (MH) from 940.00 to 470.00, Change PMF (Labor) from $145,670.37 to $72,835.18
Y | IPCRP1-0271-0000-L | IPCRP1 | IPCRP1 | 0271-0000 | F&D HYDRANTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0271-0000-R | IPCRP1 | IPCRP1 | 0271-0000 | F&D HYDRANTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9400 | 0 | 0 | 9400 | 0 | 9400 | 14100 | 0 | N | 9400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0272-0000-L | IPCRP1 | IPCRP1 | 0272-0000 | SET HYDRANTS COMPLETE W/ WT RG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0272-0000-R | IPCRP1 | IPCRP1 | 0272-0000 | SET HYDRANTS COMPLETE W/ WT RG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16000 | 0 | 0 | 16000 | 0 | 16000 | 12000 | 0 | N | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0273-0000-L | IPCRP1 | IPCRP1 | 0273-0000 | REMOVE HYDRANTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0273-0000-R | IPCRP1 | IPCRP1 | 0273-0000 | REMOVE HYDRANTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2400 | 0 | 0 | 2400 | 0 | 2400 | 1200 | 0 | N | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0274-0000-L | IPCRP1 | IPCRP1 | 0274-0000 | F, D & I HYDRANT FENDERS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0274-0000-R | IPCRP1 | IPCRP1 | 0274-0000 | F, D & I HYDRANT FENDERS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4800 | 0 | 0 | 4800 | 0 | 4800 | 2400 | 0 | N | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0274-1000-E | IPCRP1 | IPCRP1 | 0274-1000 | Rem & Inst Hydrant & Hydrant Fender Set | N | E |  | NR | P | 1561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1561 | 0 | 0 | 1561 | 0 | 0 | 0 | Y | 1561 | 0 | 0 | 1561 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 4 | 2.75 | 1.25 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0274-1000-L | IPCRP1 | IPCRP1 | 0274-1000 | Rem & Inst Hydrant & Hydrant Fender Set | N | L |  | NR | P | 12587 | 2167.73 | 2167.73 | 2167.73 | 2167.73 | 17.2224 | 0 | 0 | 0 | 10418.96 | Y | 12586.69 | Y | 0.31 | 0 | 0 | 12587 | 0 | 0 | 12586.69 | Y | 0.31 | 0 | 0 | 12587 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12586.69 | 0 | 0 | 12586.69 | 0 | 0 | 0 | 0 | 0 | 0 | -12586.69 | 0 | 0 | 12586.69 | 12586.69 | 0 | 0 | 0 | 112 | 0 | 112 | 112 | 112 | 18 | 94 | 112 | HR | 4 | 2.75 | 1.25 | 4 | EA | 0 | 0 | 0 | 10418.96 | Claim 0.75 for hydrant + 0.25 for hydrant fender set. (3 x 0.75) + (2 x 0.25) = 2.75 ea
Y | IPCRP1-0274-1000-S | IPCRP1 | IPCRP1 | 0274-1000 | Rem & Inst Hydrant & Hydrant Fender Set | N | S |  | UNIT | A | 0 | 488.72 | 488.72 | 488.72 | 488.72 | 100 | 0 | 0 | 0 | 0 | N | 488.72 | N | -488.72 | 0 | 0 | 0 | 0 | 0 | 488.72 | N | -488.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -488.72 | 0 | 0 | 488.72 | 0 | 0 | 0 | 0 | 0 | 0 | -488.72 | 0 | 0 | 488.72 | 488.72 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 4 | 2.75 | 1.25 | 4 | EA | 488.72 | 0 | 488.72 | 0
Y | IPCRP1-0274-1010-L | IPCRP1 | IPCRP1 | 0274-1010 | PM - Hydrant & Hydrant Fender Set | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4 | 2.75 | 1.25 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0274-1010-M | IPCRP1 | IPCRP1 | 0274-1010 | PM - Hydrant & Hydrant Fender Set | N | M |  | NR | P | 8300 | 9619.16 | 9619.16 | 9161.66 | 9619.16 | 95.2439 | 0 | 0 | 0 | 0 | Y | 9619.16 | Y | -1319.16 | 0 | 0 | 8300 | 0 | 0 | 9619.16 | Y | -1319.16 | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9619.16 | 0 | 0 | 9619.16 | 0 | 0 | 0 | 0 | 0 | 0 | -9619.16 | 0 | 0 | 9619.16 | 9619.16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 23 | -15 | 8 | EA | 4 | 2.75 | 1.25 | 4 | EA | 9619.16 | 457.5 | 9161.66 | 0 | T MINA SUPPLY INC @$99,627.00
Y | IPCRP1-0275-0000-L | IPCRP1 | IPCRP1 | 0275-0000 | CRUSHED STONE (IN-PLACE MEASURE) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0275-0000-R | IPCRP1 | IPCRP1 | 0275-0000 | CRUSHED STONE (IN-PLACE MEASURE) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 178000 | 0 | 0 | 178000 | 0 | 178000 | 220920 | 0 | N | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0275-1000-E | IPCRP1 | IPCRP1 | 0275-1000 | Inst Crushed Stone (In-Place Measure) | N | E |  | NR | P | 16020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16020 | 0 | 0 | 16020 | 0 | 0 | 0 | Y | 16020 | 0 | 0 | 16020 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 445 | 594.88 | 0 | 594.88 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0275-1000-L | IPCRP1 | IPCRP1 | 0275-1000 | Inst Crushed Stone (In-Place Measure) | N | L |  | NR | P | 68858.24 | 76921.43 | 76921.43 | 76921.43 | 76921.43 | 120.6992 | 0 | 0 | 0 | -13191.56 | Y | 63729.87 | Y | 5128.37 | 0 | 0 | 68858.24 | 0 | 0 | 63729.87 | Y | 5128.37 | 0 | 0 | 68858.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63729.87 | 5981.78 | 7209.78 | 63729.87 | 0 | 0 | 0 | 0 | 0 | 0 | -63729.87 | 0 | 0 | 63729.87 | 63729.87 | 0 | 0 | 0 | 640.8 | 0 | 530.5 | 530.5 | 640.8 | 636 | -105.5 | 530.5 | HR | 445 | 594.88 | 0 | 594.88 | CY | 0 | 0 | 0 | -13191.56
Y | IPCRP1-0275-1000-S | IPCRP1 | IPCRP1 | 0275-1000 | Inst Crushed Stone (In-Place Measure) | N | S |  | UNIT | A | 0 | 4049.28 | 4049.28 | 4049.28 | 4049.28 | 110.5793 | 0 | 0 | 0 | -387.4 | Y | 3661.88 | Y | -3661.88 | 0 | 0 | 0 | 0 | 0 | 3661.88 | Y | -3661.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3661.88 | 387.4 | 0 | 3661.88 | 0 | 0 | 0 | 0 | 387.4 | 0 | -3661.88 | 0 | 0 | 3661.88 | 3661.88 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 29 | -28.5 | 0.5 | NA | 445 | 594.88 | 0 | 594.88 | CY | 4049.28 | 0 | 4049.28 | -387.4
Y | IPCRP1-0276-0000-L | IPCRP1 | IPCRP1 | 0276-0000 | F&D VARIOUS CASTINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0276-0000-R | IPCRP1 | IPCRP1 | 0276-0000 | F&D VARIOUS CASTINGS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6900 | 0 | 0 | 6900 | 0 | 6900 | 9729 | 0 | N | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0276-1000-L | IPCRP1 | IPCRP1 | 0276-1000 | F&D VARIOUS CASTINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3 | 4.23 | 3.14 | 7.37 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0276-1000-M | IPCRP1 | IPCRP1 | 0276-1000 | F&D VARIOUS CASTINGS | N | M |  | NR | P | 4725 | 18974.12 | 18974.12 | 17746.09 | 18974.12 | 54.2379 | 0 | 0 | 0 | 13744.88 | N | 32719 | N | -27994 | 0 | 0 | 4725 | 0 | 0 | 32719 | N | -27994 | 0 | 0 | 4725 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32719 | 0 | 0 | 32719 | 0 | 0 | 0 | 0 | 0 | 0 | -32719 | 0 | 0 | 32719 | 32719 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 27 | 43 | 70 | EA | 3 | 4.23 | 3.14 | 7.37 | TN | 25376.12 | 1228.03 | 24148.09 | 13744.88 | T MINA SUPPLY INC @ $27,994
Y | IPCRP1-0277-0000-L | IPCRP1 | IPCRP1 | 0277-0000 | ANCHOR BOLTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0277-0000-R | IPCRP1 | IPCRP1 | 0277-0000 | ANCHOR BOLTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 27350 | 0 | 0 | 27350 | 0 | 27350 | 23944 | 0 | N | 27350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0278-0000-L | IPCRP1 | IPCRP1 | 0278-0000 | DRILLED SHAFT FOR OH SIGN STRUCTURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0278-0000-R | IPCRP1 | IPCRP1 | 0278-0000 | DRILLED SHAFT FOR OH SIGN STRUCTURES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 976800 | 0 | 0 | 976800 | 0 | 976800 | 634698 | 0 | N | 976800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 976800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0278-1000-C | IPCRP1 | IPCRP1 | 0278-1000 | DRILLED SHAFT FOR OH SIGN STRUCTURES | N | C |  | UNIT | U | 0 | 19311.01 | 19311.01 | 9161 | 19311.01 | 30.5367 | 0 | 0 | 0 | 10688.99 | Y | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 76.12 | 76.12 | 0 | 51.5 | 24.62 | 76.12 | NA | 264 | 171.54 | 49.2 | 220.74 | CY | 19311.01 | 10150.01 | 9161 | 10688.99
Y | IPCRP1-0278-1000-L | IPCRP1 | IPCRP1 | 0278-1000 | DRILLED SHAFT FOR OH SIGN STRUCTURES | N | L |  | UNIT | P | 0 | 357801.81 | 357801.81 | 357801.81 | 357801.81 | 63.4865 | 0 | 0 | 0 | 205784.99 | Y | 563586.8 | Y | -563586.8 | 0 | 0 | 0 | 0 | 0 | 563586.8 | Y | -563586.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -563586.8 | 0 | 0 | 563586.8 | 0 | 0 | 0 | 0 | 0 | 0 | -563586.8 | 0 | 0 | 563586.8 | 563586.8 | 0 | 0 | 0 | 0 | 0 | 3440 | 3440 | 0 | 2229.5 | 1210.5 | 3440 | HR | 264 | 171.54 | 49.2 | 220.74 | CY | 0 | 0 | 0 | 205784.99 | Converted to self-perform, same budget amount. Placeholder labor forecast is 3000 MH. $103,450.30 in subcontract is placeholder for equipment budget.
Y | IPCRP1-0278-1000-S | IPCRP1 | IPCRP1 | 0278-1000 | DRILLED SHAFT FOR OH SIGN STRUCTURES | N | S |  | NR | A | 661209.12 | 15019.71 | 15019.71 | 15019.71 | 15019.71 | 50.0657 | 0 | 0 | 0 | 14980.29 | Y | 30000 | Y | 631209.12 | 0 | 0 | 661209.12 | 0 | 0 | 30000 | Y | 631209.12 | 0 | 0 | 661209.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 121.5 | -121.5 | 0 | EA | 264 | 171.54 | 49.2 | 220.74 | CY | 15019.71 | 0 | 15019.71 | 14980.29
Y | IPCRP1-0278-1010-L | IPCRP1 | IPCRP1 | 0278-1010 | Test Pit, Drilled Shafts for Sign Structures | N | L |  | UNIT | P | 0 | 22442.84 | 22442.84 | 22442.84 | 22442.84 | 64.044 | 0 | 0 | 0 | 12600 | Y | 35042.84 | Y | -35042.84 | 0 | 0 | 0 | 0 | 0 | 35042.84 | Y | -35042.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -35042.84 | 0 | 0 | 35042.84 | 0 | 0 | 0 | 0 | 0 | 0 | -35042.84 | 0 | 0 | 35042.84 | 35042.84 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 166 | 84 | 250 | HR | 0 | 10 | 4 | 14 | EA | 0 | 0 | 0 | 12600 | 4 in OSS #1, 4 in OSS #2, 4 in OSS #8S, 1 in OSS #3N, 1 in OSS #8N = 14 total, 50 mh per each.
Y | IPCRP1-0278-1010-S | IPCRP1 | IPCRP1 | 0278-1010 | Test Pit, Drilled Shafts for Sign Structures | N | S |  | UNIT | A | 0 | 3027.62 | 3027.62 | 3027.62 | 3027.62 | 100 | 0 | 0 | 0 | 0 | N | 3027.62 | N | -3027.62 | 0 | 0 | 0 | 0 | 0 | 3027.62 | N | -3027.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3027.62 | 0 | 0 | 3027.62 | 0 | 0 | 0 | 0 | 0 | 0 | -3027.62 | 0 | 0 | 3027.62 | 3027.62 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 24 | 0 | 24 | NA | 0 | 10 | 4 | 14 | EA | 3027.62 | 0 | 3027.62 | 0
Y | IPCRP1-0279-0000-L | IPCRP1 | IPCRP1 | 0279-0000 | TRUSS ARM CANT SIGN STRUCT (12 YD ARM, 20 SY AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0279-0000-R | IPCRP1 | IPCRP1 | 0279-0000 | TRUSS ARM CANT SIGN STRUCT (12 YD ARM, 20 SY AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0280-0000-L | IPCRP1 | IPCRP1 | 0280-0000 | TRUSS ARM CANT SIGN STRUCT (12 YD ARM, 20 SY AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0280-0000-R | IPCRP1 | IPCRP1 | 0280-0000 | TRUSS ARM CANT SIGN STRUCT (12 YD ARM, 20 SY AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0281-0000-L | IPCRP1 | IPCRP1 | 0281-0000 | SINGLE SPAN SIGN STRUCT (25 YD MAX SPAN, 60 SY MA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0281-0000-R | IPCRP1 | IPCRP1 | 0281-0000 | SINGLE SPAN SIGN STRUCT (25 YD MAX SPAN, 60 SY MA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 200000 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | N | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0282-0000-L | IPCRP1 | IPCRP1 | 0282-0000 | SINGLE SPAN SIGN STRUCT (40 YD MAX SPAN, 90 SY MA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0282-0000-R | IPCRP1 | IPCRP1 | 0282-0000 | SINGLE SPAN SIGN STRUCT (40 YD MAX SPAN, 90 SY MA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300000 | 0 | 0 | 300000 | 0 | 300000 | 0 | 0 | N | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0283-0000-L | IPCRP1 | IPCRP1 | 0283-0000 | SINGLE SPAN SIGN STRUCT (50 YD MAX SPAN, 90 SY MA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0283-0000-R | IPCRP1 | IPCRP1 | 0283-0000 | SINGLE SPAN SIGN STRUCT (50 YD MAX SPAN, 90 SY MA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 375000 | 0 | 0 | 375000 | 0 | 375000 | 0 | 0 | N | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0284-0000-L | IPCRP1 | IPCRP1 | 0284-0000 | OH SIGN PANELS W/ HIGH VIS SHEETING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0284-0000-R | IPCRP1 | IPCRP1 | 0284-0000 | OH SIGN PANELS W/ HIGH VIS SHEETING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 130600 | 0 | 0 | 130600 | 0 | 130600 | 0 | 0 | N | 130600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0285-0000-L | IPCRP1 | IPCRP1 | 0285-0000 | REFERENCE MARKER PANEL RELOCATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0285-0000-R | IPCRP1 | IPCRP1 | 0285-0000 | REFERENCE MARKER PANEL RELOCATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2400 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | N | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0286-0000-L | IPCRP1 | IPCRP1 | 0286-0000 | REM SINGLE SPAN OH SIGN PANEL, STRUCT & FOUND | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0286-0000-R | IPCRP1 | IPCRP1 | 0286-0000 | REM SINGLE SPAN OH SIGN PANEL, STRUCT & FOUND | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50000 | 0 | 0 | 50000 | 0 | 50000 | 50000 | 0 | N | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0287-0000-L | IPCRP1 | IPCRP1 | 0287-0000 | R&D BRIDGE MNTD SIGN PANEL & SP ASSEMBLY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0287-0000-R | IPCRP1 | IPCRP1 | 0287-0000 | R&D BRIDGE MNTD SIGN PANEL & SP ASSEMBLY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 60000 | 0 | 0 | 60000 | 0 | 60000 | 60000 | 0 | N | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0288-0000-L | IPCRP1 | IPCRP1 | 0288-0000 | RELOCATE SIGN PANEL W/ASSEMBLY SIZE I (< 30SF) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0288-0000-R | IPCRP1 | IPCRP1 | 0288-0000 | RELOCATE SIGN PANEL W/ASSEMBLY SIZE I (< 30SF) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4500 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | N | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0289-0000-L | IPCRP1 | IPCRP1 | 0289-0000 | F, D & I BANDS, RODS, ETC, COMP FOR REST JTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0289-0000-R | IPCRP1 | IPCRP1 | 0289-0000 | F, D & I BANDS, RODS, ETC, COMP FOR REST JTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11323.5 | 0 | 0 | 11323.5 | 0 | 11323.5 | 0 | 0 | N | 11323.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11323.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0289-1000-L | IPCRP1 | IPCRP1 | 0289-1000 | Furn Bands, Rods, Etc Comp for Restrained Joints | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 7549 | 0 | 7549 | 7549 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0289-1000-M | IPCRP1 | IPCRP1 | 0289-1000 | Furn Bands, Rods, Etc Comp for Restrained Joints | N | M |  | NR | P | 7549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7549 | N | 7549 | N | 0 | 0 | 0 | 7549 | 0 | 0 | 7549 | N | 0 | 0 | 0 | 7549 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7549 | 0 | 0 | 7549 | 0 | 0 | 0 | 0 | 0 | 0 | -7549 | 0 | 0 | 7549 | 7549 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 7549 | 0 | 7549 | 7549 | LB | 0 | 0 | 0 | 7549
Y | IPCRP1-0290-0000-L | IPCRP1 | IPCRP1 | 0290-0000 | F & PLACE POLYETHYLENE SLEEVE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0290-0000-R | IPCRP1 | IPCRP1 | 0290-0000 | F & PLACE POLYETHYLENE SLEEVE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 660 | 0 | 0 | 660 | 0 | 660 | 0 | 0 | N | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0290-1000-L | IPCRP1 | IPCRP1 | 0290-1000 | F&I Polytehylene Sleeve | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 440 | 0 | 440 | 440 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0290-1000-M | IPCRP1 | IPCRP1 | 0290-1000 | F&I Polytehylene Sleeve | N | M |  | NR | P | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | N | 440 | N | 0 | 0 | 0 | 440 | 0 | 0 | 440 | N | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -440 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | -440 | 0 | 0 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 440 | 0 | 440 | 440 | LF | 0 | 0 | 0 | 440
Y | IPCRP1-0291-0000-L | IPCRP1 | IPCRP1 | 0291-0000 | F, D & PLACE FILTER FABRIC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0291-0000-R | IPCRP1 | IPCRP1 | 0291-0000 | F, D & PLACE FILTER FABRIC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 39855 | 0 | 0 | 39855 | 0 | 39855 | 0 | 0 | N | 39855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0291-1000-L | IPCRP1 | IPCRP1 | 0291-1000 | Install Filter Fabric | N | L |  | NR | P | 19753.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19753.01 | N | 19753.01 | N | 0 | 0 | 0 | 19753.01 | 0 | 0 | 19753.01 | N | 0 | 0 | 0 | 19753.01 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19753.01 | 0 | 0 | 19753.01 | 0 | 0 | 0 | 0 | 0 | 0 | -19753.01 | 0 | 0 | 19753.01 | 19753.01 | 0 | 0 | 0 | 192 | 0 | 192 | 192 | 192 | 0 | 192 | 192 | HR | 26570 | 0 | 26570 | 26570 | SF | 0 | 0 | 0 | 19753.01
Y | IPCRP1-0291-1010-L | IPCRP1 | IPCRP1 | 0291-1010 | PM - Filter Fabric | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 26570 | 0 | 26570 | 26570 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0291-1010-M | IPCRP1 | IPCRP1 | 0291-1010 | PM - Filter Fabric | N | M |  | NR | P | 6642.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6642.5 | N | 6642.5 | N | 0 | 0 | 0 | 6642.5 | 0 | 0 | 6642.5 | N | 0 | 0 | 0 | 6642.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6642.5 | 0 | 0 | 6642.5 | 0 | 0 | 0 | 0 | 0 | 0 | -6642.5 | 0 | 0 | 6642.5 | 6642.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 26570 | 0 | 26570 | 26570 | SF | 0 | 0 | 0 | 6642.5
Y | IPCRP1-0292-0000-L | IPCRP1 | IPCRP1 | 0292-0000 | F, D & I - 6 PIPE TO WALL PENETRATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0292-0000-R | IPCRP1 | IPCRP1 | 0292-0000 | F, D & I - 6 PIPE TO WALL PENETRATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 900 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | N | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0293-0000-L | IPCRP1 | IPCRP1 | 0293-0000 | F, D & I - 8 PIPE TO WALL PENETRATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0293-0000-R | IPCRP1 | IPCRP1 | 0293-0000 | F, D & I - 8 PIPE TO WALL PENETRATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1800 | 0 | 0 | 1800 | 0 | 1800 | 1200 | 0 | N | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0294-0000-L | IPCRP1 | IPCRP1 | 0294-0000 | F, D & I - 12 PIPE TO WALL PENETRATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0294-0000-R | IPCRP1 | IPCRP1 | 0294-0000 | F, D & I - 12 PIPE TO WALL PENETRATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | N | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0295-0000-L | IPCRP1 | IPCRP1 | 0295-0000 | F, D & I - 20 PIPE TO WALL PENETRATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0295-0000-R | IPCRP1 | IPCRP1 | 0295-0000 | F, D & I - 20 PIPE TO WALL PENETRATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200 | 0 | 0 | 1200 | 0 | 1200 | 0 | 0 | N | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0296-0000-L | IPCRP1 | IPCRP1 | 0296-0000 | F, D & I - 24 PIPE TO WALL PENETRATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0296-0000-R | IPCRP1 | IPCRP1 | 0296-0000 | F, D & I - 24 PIPE TO WALL PENETRATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4500 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | N | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0297-0000-L | IPCRP1 | IPCRP1 | 0297-0000 | F, D & I - 36 PIPE TO WALL PENETRATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0297-0000-R | IPCRP1 | IPCRP1 | 0297-0000 | F, D & I - 36 PIPE TO WALL PENETRATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1800 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | N | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0297-1000-L | IPCRP1 | IPCRP1 | 0297-1000 | F, D & I - Pipe to Wall Penetration (8 - 36) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 11 | 2 | 9 | 11 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0297-1000-M | IPCRP1 | IPCRP1 | 0297-1000 | F, D & I - Pipe to Wall Penetration (8 - 36) | N | M |  | NR | P | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7350 | N | 7350 | N | 0 | 0 | 0 | 7350 | 0 | 0 | 7350 | N | 0 | 0 | 0 | 7350 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7350 | 0 | 0 | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | -7350 | 0 | 0 | 7350 | 7350 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 11 | 2 | 9 | 11 | EA | 0 | 0 | 0 | 7350
Y | IPCRP1-0298-0000-L | IPCRP1 | IPCRP1 | 0298-0000 | F & PLACE CIP CONC CL 40 & PC CONC CL 50 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0298-0000-R | IPCRP1 | IPCRP1 | 0298-0000 | F & PLACE CIP CONC CL 40 & PC CONC CL 50 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8510 | 0 | 0 | 8510 | 0 | 8510 | 0 | 0 | N | 8510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0298-1000-E | IPCRP1 | IPCRP1 | 0298-1000 | Placing Concrete | N | E |  | NR | P | 780.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 780.26 | 0 | 0 | 780.26 | 0 | 0 | 0 | Y | 780.26 | 0 | 0 | 780.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2.3 | 0 | 2.3 | 2.3 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0298-1000-L | IPCRP1 | IPCRP1 | 0298-1000 | Placing Concrete | N | L |  | NR | P | 4165.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4165.47 | N | 4165.47 | N | 0 | 0 | 0 | 4165.47 | 0 | 0 | 4165.47 | N | 0 | 0 | 0 | 4165.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4165.47 | 0 | 0 | 4165.47 | 0 | 0 | 0 | 0 | 0 | 0 | -4165.47 | 0 | 0 | 4165.47 | 4165.47 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 40 | 0 | 40 | 40 | HR | 2.3 | 0 | 2.3 | 2.3 | CY | 0 | 0 | 0 | 4165.47
Y | IPCRP1-0299-0000-L | IPCRP1 | IPCRP1 | 0299-0000 | F, D & PLACE STRUCT, REINF & MISC STEEL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0299-0000-R | IPCRP1 | IPCRP1 | 0299-0000 | F, D & PLACE STRUCT, REINF & MISC STEEL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8706 | 0 | 0 | 8706 | 0 | 8706 | 0 | 0 | N | 8706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0299-1000-E | IPCRP1 | IPCRP1 | 0299-1000 | F,D & I Struct, Reinf & Misc Steel | N | E |  | NR | P | 780.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 780.26 | 0 | 0 | 780.26 | 0 | 0 | 0 | Y | 780.26 | 0 | 0 | 780.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 435.3 | 0 | 435.3 | 435.3 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0299-1000-L | IPCRP1 | IPCRP1 | 0299-1000 | F,D & I Struct, Reinf & Misc Steel | N | L |  | NR | P | 4165.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4165.47 | N | 4165.47 | N | 0 | 0 | 0 | 4165.47 | 0 | 0 | 4165.47 | N | 0 | 0 | 0 | 4165.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4165.47 | 0 | 0 | 4165.47 | 0 | 0 | 0 | 0 | 0 | 0 | -4165.47 | 0 | 0 | 4165.47 | 4165.47 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 40 | 0 | 40 | 40 | HR | 435.3 | 0 | 435.3 | 435.3 | LB | 0 | 0 | 0 | 4165.47
Y | IPCRP1-0299-1000-M | IPCRP1 | IPCRP1 | 0299-1000 | F,D & I Struct, Reinf & Misc Steel | N | M |  | NR | P | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641 | N | 641 | N | 0 | 0 | 0 | 641 | 0 | 0 | 641 | N | 0 | 0 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -641 | 0 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | -641 | 0 | 0 | 641 | 641 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 435.3 | 0 | 435.3 | 435.3 | LB | 0 | 0 | 0 | 641
Y | IPCRP1-0300-0000-L | IPCRP1 | IPCRP1 | 0300-0000 | F, D & PLACE SCREENED GRAVEL OR BROKEN STONE BED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0300-0000-R | IPCRP1 | IPCRP1 | 0300-0000 | F, D & PLACE SCREENED GRAVEL OR BROKEN STONE BED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 75360 | 0 | 0 | 75360 | 0 | 75360 | 15124 | 0 | N | 75360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0301-0000-L | IPCRP1 | IPCRP1 | 0301-0000 | MISCELLANEOUS METALS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0301-0000-R | IPCRP1 | IPCRP1 | 0301-0000 | MISCELLANEOUS METALS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 72000 | 0 | 0 | 72000 | 0 | 72000 | 6081.6 | 0 | N | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0301-1000-L | IPCRP1 | IPCRP1 | 0301-1000 | Inst Stair Nosing w/ Studs | N | L |  | NR | P | 19850.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18174.2 | N | 18174.2 | N | 1676.74 | 0 | 0 | 19850.94 | 0 | 0 | 18174.2 | N | 1676.74 | 0 | 0 | 19850.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18174.2 | 0 | 0 | 18174.2 | 0 | 0 | 0 | 0 | 0 | 0 | -18174.2 | 0 | 0 | 18174.2 | 18174.2 | 0 | 0 | 0 | 168 | 0 | 153.81 | 153.81 | 168 | 0 | 153.81 | 153.81 | HR | 2400 | 202.72 | 2197.28 | 2400 | LB | 0 | 0 | 0 | 18174.2 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0301-1010-L | IPCRP1 | IPCRP1 | 0301-1010 | Furnish Mics Metals (includes Stair Nosings) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2400 | 202.72 | 2197.28 | 2400 | LB | 0 | 0 | 0 | 0 | JB (9/19) DSB, 28ea x 4' x 1.81lb/lf = 202.72lbs)
Y | IPCRP1-0301-1010-M | IPCRP1 | IPCRP1 | 0301-1010 | Furnish Mics Metals (includes Stair Nosings) | N | M |  | NR | P | 30680 | 16569.63 | 16569.63 | 15873.68 | 16569.63 | 51.7395 | 0 | 0 | 0 | 14110.37 | N | 30680 | N | 0 | 0 | 0 | 30680 | 0 | 0 | 30680 | N | 0 | 0 | 0 | 30680 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30680 | 0 | 0 | 30680 | 0 | 0 | 0 | 0 | 0 | 0 | -30680 | 0 | 0 | 30680 | 30680 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 287 | -287 | 0 | EA | 2400 | 202.72 | 2197.28 | 2400 | LB | 16569.63 | 695.95 | 15873.68 | 14110.37
Y | IPCRP1-0302-0000-L | IPCRP1 | IPCRP1 | 0302-0000 | FOUND FOR LIGHT STAND, 45ft LONG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0302-0000-R | IPCRP1 | IPCRP1 | 0302-0000 | FOUND FOR LIGHT STAND, 45ft LONG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 80000 | 0 | 0 | 80000 | 0 | 80000 | 50000 | 0 | N | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0303-0000-L | IPCRP1 | IPCRP1 | 0303-0000 | FUEL PRICE ADJUSTMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0303-0000-R | IPCRP1 | IPCRP1 | 0303-0000 | FUEL PRICE ADJUSTMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0303-1000-C | IPCRP1 | IPCRP1 | 0303-1000 | FUEL PRICE ADJUSTMENT | N | C |  | NR | P | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | N | 100000 | N | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | N | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 100000
Y | IPCRP1-0303-1000-L | IPCRP1 | IPCRP1 | 0303-1000 | FUEL PRICE ADJUSTMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0304-0000-L | IPCRP1 | IPCRP1 | 0304-0000 | STEEL/ IRON PRICE ADJUSTMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0304-0000-R | IPCRP1 | IPCRP1 | 0304-0000 | STEEL/ IRON PRICE ADJUSTMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 1000000 | 1000000 | 0 | N | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0304-1000-C | IPCRP1 | IPCRP1 | 0304-1000 | STEEL/ IRON PRICE ADJUSTMENT | N | C |  | NR | P | 1000000 | 990000 | 990000 | 916254.96 | 990000 | 91.6255 | 0 | 0 | 0 | 10000 | Y | 1000000 | Y | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000 | Y | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1000000 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1027445.88 | -327438.19 | 700007.69 | EA | 1 | 0 | 8 | 8 | FP | 990000 | 73745.04 | 916254.96 | 10000
Y | IPCRP1-0304-1000-L | IPCRP1 | IPCRP1 | 0304-1000 | STEEL/ IRON PRICE ADJUSTMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 8 | 8 | FP | 0 | 0 | 0 | 0 | Sub = ASW = 465K, Consum = CFS = 805K PMF (Quan) represents 85% of value submitted to date in Millions. seq #3040 (1M) + seq #54510 (3.058M) + seq #56010 (13.941M = 18.0M
Y | IPCRP1-0304-1000-S | IPCRP1 | IPCRP1 | 0304-1000 | STEEL/ IRON PRICE ADJUSTMENT | N | S |  | UNIT | A | 0 | 465005.06 | 465005.06 | 465005.06 | 465005.06 | 100 | 0 | 0 | 0 | 0 | Y | 465005.06 | Y | -465005.06 | 0 | 0 | 0 | 0 | 0 | 465005.06 | Y | -465005.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -465005.06 | 0 | 0 | 465005.06 | 0 | 0 | 0 | 0 | 0 | 0 | -465005.06 | 0 | 0 | 465005.06 | 465005.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | -4 | 0 | NA | 1 | 0 | 8 | 8 | FP | 465005.06 | 0 | 465005.06 | 0 | PMF (Quan) represents value submitted to date in Millions. Sub = ASW = 465K, Consum = CFS Steel = 666K.
Y | IPCRP1-0305-0000-L | IPCRP1 | IPCRP1 | 0305-0000 | REM EXIST ST BOLLARDS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0305-0000-R | IPCRP1 | IPCRP1 | 0305-0000 | REM EXIST ST BOLLARDS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19500 | 0 | 0 | 19500 | 0 | 19500 | 12000 | 0 | N | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0305-1000-L | IPCRP1 | IPCRP1 | 0305-1000 | Remove Exist St Bollards | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 13 | 8 | 5 | 13 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0305-1000-S | IPCRP1 | IPCRP1 | 0305-1000 | Remove Exist St Bollards | N | S |  | NR | A | 13656.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13656.91 | N | 13656.91 | N | 0 | 0 | 0 | 13656.91 | 0 | 0 | 13656.91 | N | 0 | 0 | 0 | 13656.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13656.91 | 0 | 0 | 13656.91 | 0 | 0 | 0 | 0 | 0 | 0 | -13656.91 | 0 | 0 | 13656.91 | 13656.91 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 13 | 8 | 5 | 13 | EA | 0 | 0 | 0 | 13656.91
Y | IPCRP1-0306-0000-L | IPCRP1 | IPCRP1 | 0306-0000 | F&I NEW ST BOLLARDS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0306-0000-R | IPCRP1 | IPCRP1 | 0306-0000 | F&I NEW ST BOLLARDS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10500 | 0 | 0 | 10500 | 0 | 10500 | 6000 | 0 | N | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0306-1000-E | IPCRP1 | IPCRP1 | 0306-1000 | Inst New St Bollards | N | E |  | NR | P | 195.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 195.07 | 0 | 0 | 195.07 | 0 | 0 | 0 | Y | 195.07 | 0 | 0 | 195.07 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 7 | 4 | 0 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0306-1000-L | IPCRP1 | IPCRP1 | 0306-1000 | Inst New St Bollards | N | L |  | NR | P | 2437.87 | 818.35 | 818.35 | 818.35 | 818.35 | 100 | 0 | 0 | 0 | 0 | Y | 818.35 | Y | 1619.52 | 0 | 0 | 2437.87 | 0 | 0 | 818.35 | Y | 1619.52 | 0 | 0 | 2437.87 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -818.35 | 0 | 0 | 818.35 | 0 | 0 | 0 | 0 | 0 | 0 | -818.35 | 0 | 0 | 818.35 | 818.35 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 7 | HR | 7 | 4 | 0 | 4 | EA | 0 | 0 | 0 | 0 | 5ea at ERH Lot were cancelled, 4ea needed for Gate Control protection at Montgomery St Parking Lot.
Y | IPCRP1-0306-1010-L | IPCRP1 | IPCRP1 | 0306-1010 | PM - New Steel Bollards | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 7 | 9 | 0 | 9 | EA | 0 | 0 | 0 | 0 | Was not aware of need for 4ea at Mont St Parking Lot. Ordered 5ea for ERH Lot, but lost them. Need to now order 4ea for Mont St Parking Lot. If we find "lost" bollards, DDC will pay for these under the item (see PCO #340).
Y | IPCRP1-0306-1010-M | IPCRP1 | IPCRP1 | 0306-1010 | PM - New Steel Bollards | N | M |  | NR | P | 5250 | 35127 | 35127 | 35127 | 35127 | 100 | 0 | 0 | 0 | 0 | Y | 35127 | Y | -29877 | 0 | 0 | 5250 | 0 | 0 | 35127 | Y | -29877 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -35127 | 0 | 0 | 35127 | 0 | 0 | 0 | 0 | 0 | 0 | -35127 | 0 | 0 | 35127 | 35127 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9 | -5.43 | 3.57 | LF | 7 | 9 | 0 | 9 | EA | 35127 | 0 | 35127 | 0
Y | IPCRP1-0307-0000-L | IPCRP1 | IPCRP1 | 0307-0000 | PROCTOR ANALYSIS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0307-0000-R | IPCRP1 | IPCRP1 | 0307-0000 | PROCTOR ANALYSIS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0307-1000-L | IPCRP1 | IPCRP1 | 0307-1000 | Proctor Anaylsis | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 120 | 0 | 120 | 120 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0307-1000-S | IPCRP1 | IPCRP1 | 0307-1000 | Proctor Anaylsis | N | S |  | NR | A | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | N | 9000 | N | 0 | 0 | 0 | 9000 | 0 | 0 | 9000 | N | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9000 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | -9000 | 0 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 120 | 0 | 120 | 120 | EA | 0 | 0 | 0 | 9000
Y | IPCRP1-0308-0000-L | IPCRP1 | IPCRP1 | 0308-0000 | IN-PLACE SOIL DENSITY TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0308-0000-R | IPCRP1 | IPCRP1 | 0308-0000 | IN-PLACE SOIL DENSITY TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 24000 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | N | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0308-1000-L | IPCRP1 | IPCRP1 | 0308-1000 | IN-PLACE SOIL DENSITY TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 120 | 0 | 120 | 120 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0308-1000-S | IPCRP1 | IPCRP1 | 0308-1000 | IN-PLACE SOIL DENSITY TEST | N | S |  | NR | A | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | N | 21000 | N | 0 | 0 | 0 | 21000 | 0 | 0 | 21000 | N | 0 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21000 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | -21000 | 0 | 0 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 120 | 0 | 120 | 120 | EA | 0 | 0 | 0 | 21000
Y | IPCRP1-0309-0000-L | IPCRP1 | IPCRP1 | 0309-0000 | MAINTENANCE OF SITE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0309-0000-R | IPCRP1 | IPCRP1 | 0309-0000 | MAINTENANCE OF SITE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1439640 | 0 | 0 | 1439640 | 0 | 1439640 | 1166220 | 0 | N | 1439640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439640 | 0 | 0.25 | -0.25 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0309-1000-C | IPCRP1 | IPCRP1 | 0309-1000 | Maintenance of Site | N | C |  | NR | P | 81095.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81085 | Y | 81085 | Y | 10.49 | 0 | 0 | 81095.49 | 0 | 0 | 81085 | Y | 10.49 | 0 | 0 | 81095.49 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -81085 | 0 | 0 | 81085 | 0 | 0 | 0 | 0 | 0 | 0 | -81085 | 0 | 0 | 81085 | 81085 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 52 | 224 | 88 | 312 | WK | 0 | 0 | 0 | 81085
Y | IPCRP1-0309-1000-L | IPCRP1 | IPCRP1 | 0309-1000 | Maintenance of Site | N | L |  | UNIT | P | 720000 | 1134093.83 | 1134093.83 | 1134093.83 | 1134093.83 | 72.6983 | 0 | 0 | 0 | 425906.17 | Y | 1560000 | Y | -840000 | 0 | 0 | 720000 | 0 | 0 | 1560000 | Y | -840000 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1560000 | 0 | 0 | 1560000 | 0 | 0 | 0 | 0 | 0 | 0 | -1560000 | 0 | 0 | 1560000 | 1560000 | 0 | 0 | 0 | 6000 | 0 | 12590.62 | 12590.62 | 6000 | 9215.5 | 3375.12 | 12590.62 | HR | 52 | 224 | 88 | 312 | WK | 0 | 0 | 0 | 425906.17
Y | IPCRP1-0309-1000-S | IPCRP1 | IPCRP1 | 0309-1000 | Maintenance of Site | N | S |  | UNIT | A | 0 | 252815.34 | 252815.34 | 252815.33 | 252815.34 | 100 | 0 | 0 | 0 | 0 | Y | 252815.34 | Y | -252815.34 | 0 | 0 | 0 | 0 | 0 | 252815.34 | Y | -252815.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -252815.34 | 0 | 0 | 252815.34 | 0 | 0 | 0 | 0 | 0 | 0 | -252815.34 | 0 | 0 | 252815.34 | 252815.34 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 2227 | -2203 | 24 | NA | 52 | 224 | 88 | 312 | WK | 252815.34 | 0.01 | 252815.33 | 0 | KMA charged here @$2,880
Y | IPCRP1-0310-0000-L | IPCRP1 | IPCRP1 | 0310-0000 | TEST PITS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0310-0000-R | IPCRP1 | IPCRP1 | 0310-0000 | TEST PITS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 480000 | 0 | 0 | 480000 | 0 | 480000 | 37518 | 0 | N | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0310-1000-E | IPCRP1 | IPCRP1 | 0310-1000 | TEST PITS | N | E |  | NR | P | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 48000 | 0 | 0 | 48000 | 0 | 0 | 0 | Y | 48000 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1600 | 166.9 | 1433.1 | 1600 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0310-1000-L | IPCRP1 | IPCRP1 | 0310-1000 | TEST PITS | N | L |  | NR | P | 406696 | 124504.4 | 124504.4 | 124504.4 | 124504.4 | 30.6136 | 0 | 0 | 0 | 282191.6 | N | 406696 | N | 0 | 0 | 0 | 406696 | 0 | 0 | 406696 | N | 0 | 0 | 0 | 406696 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -406696 | 0 | 0 | 406696 | 0 | 0 | 0 | 0 | 0 | 0 | -406696 | 0 | 0 | 406696 | 406696 | 0 | 0 | 0 | 3840 | 0 | 3840 | 3840 | 3840 | 1059 | 2781 | 3840 | HR | 1600 | 166.9 | 1433.1 | 1600 | CY | 0 | 0 | 0 | 282191.6
Y | IPCRP1-0310-1000-S | IPCRP1 | IPCRP1 | 0310-1000 | TEST PITS | N | S |  | UNIT | A | 0 | 17867.02 | 17867.02 | 17867.02 | 17867.02 | 100 | 0 | 0 | 0 | 0 | Y | 17867.02 | Y | -17867.02 | 0 | 0 | 0 | 0 | 0 | 17867.02 | Y | -17867.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17867.02 | 0 | 0 | 17867.02 | 0 | 0 | 0 | 0 | 0 | 0 | -17867.02 | 0 | 0 | 17867.02 | 17867.02 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 154 | -152 | 2 | NA | 1600 | 166.9 | 1433.1 | 1600 | CY | 17867.02 | 0 | 17867.02 | 0
Y | IPCRP1-0311-0000-L | IPCRP1 | IPCRP1 | 0311-0000 | REM OF TRACK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0311-0000-R | IPCRP1 | IPCRP1 | 0311-0000 | REM OF TRACK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18000 | 0 | 0 | 18000 | 0 | 18000 | 0 | 0 | N | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0312-0000-L | IPCRP1 | IPCRP1 | 0312-0000 | DEMO OF ROADWAY VAULTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0312-0000-R | IPCRP1 | IPCRP1 | 0312-0000 | DEMO OF ROADWAY VAULTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 39000 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | N | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0313-0000-L | IPCRP1 | IPCRP1 | 0313-0000 | DEMO OF TROLLEY TRACK TRUSS BLOCKS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0313-0000-R | IPCRP1 | IPCRP1 | 0313-0000 | DEMO OF TROLLEY TRACK TRUSS BLOCKS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0313-1000-C | IPCRP1 | IPCRP1 | 0313-1000 | Demo Road Vaults, Trolley Trck Truss Blck, & Rem | N | C |  | NR | P | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | N | 800 | N | 0 | 0 | 0 | 800 | 0 | 0 | 800 | N | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -800 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | -800 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | ST | 160 | 0 | 160 | 160 | CY | 0 | 0 | 0 | 800
Y | IPCRP1-0313-1000-E | IPCRP1 | IPCRP1 | 0313-1000 | Demo Road Vaults, Trolley Trck Truss Blck, & Rem | N | E |  | NR | P | 6310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6310 | 0 | 0 | 6310 | 0 | 0 | 0 | Y | 6310 | 0 | 0 | 6310 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 160 | 0 | 160 | 160 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0313-1000-L | IPCRP1 | IPCRP1 | 0313-1000 | Demo Road Vaults, Trolley Trck Truss Blck, & Rem | N | L |  | NR | P | 23394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23394 | N | 23394 | N | 0 | 0 | 0 | 23394 | 0 | 0 | 23394 | N | 0 | 0 | 0 | 23394 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23394 | 0 | 0 | 23394 | 0 | 0 | 0 | 0 | 0 | 0 | -23394 | 0 | 0 | 23394 | 23394 | 0 | 0 | 0 | 194 | 0 | 194 | 194 | 194 | 0 | 194 | 194 | HR | 160 | 0 | 160 | 160 | CY | 0 | 0 | 0 | 23394
Y | IPCRP1-0314-0000-L | IPCRP1 | IPCRP1 | 0314-0000 | PEDESTRIAN ST BARRICADES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0314-0000-R | IPCRP1 | IPCRP1 | 0314-0000 | PEDESTRIAN ST BARRICADES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0314-1000-C | IPCRP1 | IPCRP1 | 0314-1000 | PEDESTRIAN ST BARRICADES | N | C |  | NR | P | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | N | 2000 | N | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | N | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | ST | 1000 | 0 | 1000 | 1000 | LF | 0 | 0 | 0 | 2000
Y | IPCRP1-0314-1000-E | IPCRP1 | IPCRP1 | 0314-1000 | PEDESTRIAN ST BARRICADES | N | E |  | NR | P | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 192 | 0 | 0 | 192 | 0 | 0 | 0 | Y | 192 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | ST | 1000 | 0 | 1000 | 1000 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0314-1000-L | IPCRP1 | IPCRP1 | 0314-1000 | PEDESTRIAN ST BARRICADES | N | L |  | NR | P | 3292.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3292.17 | N | 3292.17 | N | 0 | 0 | 0 | 3292.17 | 0 | 0 | 3292.17 | N | 0 | 0 | 0 | 3292.17 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3292.17 | 0 | 0 | 3292.17 | 0 | 0 | 0 | 0 | 0 | 0 | -3292.17 | 0 | 0 | 3292.17 | 3292.17 | 0 | 0 | 0 | 32 | 0 | 32 | 32 | 32 | 0 | 32 | 32 | HR | 1000 | 0 | 1000 | 1000 | LF | 0 | 0 | 0 | 3292.17
Y | IPCRP1-0315-0000-L | IPCRP1 | IPCRP1 | 0315-0000 | RODENT CONTROL SURVEY & MONITOR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0315-0000-R | IPCRP1 | IPCRP1 | 0315-0000 | RODENT CONTROL SURVEY & MONITOR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 167405 | 0 | 0 | 167405 | 0 | 167405 | 137275.74 | 0 | N | 167405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0316-0000-L | IPCRP1 | IPCRP1 | 0316-0000 | RODENT BAIT STATIONS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0316-0000-R | IPCRP1 | IPCRP1 | 0316-0000 | RODENT BAIT STATIONS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 33600 | 0 | 0 | 33600 | 0 | 33600 | 9996 | 0 | N | 33600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0317-0000-L | IPCRP1 | IPCRP1 | 0317-0000 | BAITING OF RODENT BAIT STATIONS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0317-0000-R | IPCRP1 | IPCRP1 | 0317-0000 | BAITING OF RODENT BAIT STATIONS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 396000 | 0 | 0 | 396000 | 0 | 396000 | 8591 | 0 | N | 396000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0318-0000-L | IPCRP1 | IPCRP1 | 0318-0000 | WATERBUG BAIT APPLICATIONS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | BL | 0 | 0 | 0 | 0
Y | IPCRP1-0318-0000-R | IPCRP1 | IPCRP1 | 0318-0000 | WATERBUG BAIT APPLICATIONS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3360 | 0 | 0 | 3360 | 0 | 3360 | 2940 | 0 | N | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | BL | 0 | 0 | 0 | 0
Y | IPCRP1-0318-1000-L | IPCRP1 | IPCRP1 | 0318-1000 | Rodent Control Survey & Monitor (Dynamic PC) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.43 | 0.57 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0318-1000-S | IPCRP1 | IPCRP1 | 0318-1000 | Rodent Control Survey & Monitor (Dynamic PC) | N | S |  | NR | A | 20800 | 43984.59 | 43984.59 | 18376.9 | 43984.59 | 42.4635 | 0 | 0 | 0 | 0 | N | 43276.9 | N | -22476.9 | 0 | 0 | 20800 | 0 | 0 | 43276.9 | N | -22476.9 | 0 | 0 | 20800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -43276.9 | 0 | 0 | 43276.9 | 0 | 0 | 0 | 0 | 0 | 0 | -43276.9 | 0 | 0 | 43276.9 | 43276.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 48.86 | 69.14 | 118 | LF | 1 | 0.43 | 0.57 | 1 | LS | 43984.59 | 25607.69 | 18376.9 | 0
Y | IPCRP1-0318-1010-L | IPCRP1 | IPCRP1 | 0318-1010 | Rodent Control Sub (Joes Pest Conrol) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.09 | 0.91 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0318-1010-S | IPCRP1 | IPCRP1 | 0318-1010 | Rodent Control Sub (Joes Pest Conrol) | N | S |  | NR | A | 402100 | 378966.88 | 378966.88 | 33095.47 | 378966.88 | 8.733 | 0 | 0 | 0 | 2 | Y | 378968.88 | Y | 23131.12 | 0 | 0 | 402100 | 0 | 0 | 378968.88 | Y | 23131.12 | 0 | 0 | 402100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -378968.88 | 0 | 326.63 | 378968.88 | 0 | 0 | 0 | 0 | 0 | 0 | -378968.88 | 0 | 0 | 378968.88 | 378968.88 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1570.53 | 36940.81 | 38511.34 | EA | 1 | 0.09 | 0.91 | 1 | LS | 378966.88 | 345871.41 | 33095.47 | 2 | Change PMF (Subcontractor) from $380,493.88 to $378,968.88 (to match Commitment) JOES'S PEST base @378,993.88 + CO@1,500
Y | IPCRP1-0319-0000-L | IPCRP1 | IPCRP1 | 0319-0000 | STRUCT STEEL H PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0319-0000-R | IPCRP1 | IPCRP1 | 0319-0000 | STRUCT STEEL H PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42761250 | 0 | 0 | 42761250 | 0 | 42761250 | 27648946.51 | 0 | N | 42761250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42761250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0320-0000-L | IPCRP1 | IPCRP1 | 0320-0000 | MINI PILES (GROUTED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0320-0000-R | IPCRP1 | IPCRP1 | 0320-0000 | MINI PILES (GROUTED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11972200 | 0 | 0 | 11972200 | 0 | 11972200 | 0 | 0 | N | 11972200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11972200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0321-0000-L | IPCRP1 | IPCRP1 | 0321-0000 | MINI PILES, LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0321-0000-R | IPCRP1 | IPCRP1 | 0321-0000 | MINI PILES, LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 350000 | 0 | 0 | 350000 | 0 | 350000 | 75000 | 0 | N | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0322-0000-L | IPCRP1 | IPCRP1 | 0322-0000 | CLEAN BACKFILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0322-0000-R | IPCRP1 | IPCRP1 | 0322-0000 | CLEAN BACKFILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 295394.63 | 0 | 0 | 295394.63 | 0 | 295394.63 | 332450.81 | 0 | N | 295394.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295394.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0323-0000-L | IPCRP1 | IPCRP1 | 0323-0000 | F & PLACE SHEET & BRACE IN TRENCH FOR WM 12 & LE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0323-0000-R | IPCRP1 | IPCRP1 | 0323-0000 | F & PLACE SHEET & BRACE IN TRENCH FOR WM 12 & LE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 32750 | 0 | 0 | 32750 | 0 | 32750 | 19869.8 | 0 | N | 32750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0323-1000-C | IPCRP1 | IPCRP1 | 0323-1000 | Timber Lagging 3 in | N | C |  | NR | P | 19650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19650 | N | 19650 | N | 0 | 0 | 0 | 19650 | 0 | 0 | 19650 | N | 0 | 0 | 0 | 19650 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19650 | 0 | 0 | 19650 | 0 | 0 | 0 | 0 | 0 | 0 | -19650 | 0 | 0 | 19650 | 19650 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 0 | 1 | 1 | LF | 6550 | 3973.96 | 2576.04 | 6550 | SF | 0 | 0 | 0 | 19650
Y | IPCRP1-0323-1000-L | IPCRP1 | IPCRP1 | 0323-1000 | Timber Lagging 3 in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6550 | 3973.96 | 2576.04 | 6550 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0324-0000-L | IPCRP1 | IPCRP1 | 0324-0000 | HYDRAULIC FILL FOR ABANDON SEWERS & WMS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0324-0000-R | IPCRP1 | IPCRP1 | 0324-0000 | HYDRAULIC FILL FOR ABANDON SEWERS & WMS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 418600 | 0 | 0 | 418600 | 0 | 418600 | 225662 | 0 | N | 418600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0324-1000-E | IPCRP1 | IPCRP1 | 0324-1000 | Install Hydraulic Fill | N | E |  | NR | P | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2100 | 0 | 0 | 2100 | 0 | 0 | 0 | Y | 2100 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2093 | 1128.41 | 964.59 | 2093 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0324-1000-L | IPCRP1 | IPCRP1 | 0324-1000 | Install Hydraulic Fill | N | L |  | NR | P | 55014.47 | 35167.7 | 35167.7 | 35167.7 | 35167.7 | 63.9245 | 0 | 0 | 0 | 19846.77 | Y | 55014.47 | Y | 0 | 0 | 0 | 55014.47 | 0 | 0 | 55014.47 | Y | 0 | 0 | 0 | 55014.47 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -55014.47 | 0 | 0 | 55014.47 | 0 | 0 | 0 | 0 | 0 | 0 | -55014.47 | 0 | 0 | 55014.47 | 55014.47 | 0 | 0 | 0 | 504 | 0 | 484.86 | 484.86 | 504 | 293.5 | 191.36 | 484.86 | HR | 2093 | 1128.41 | 964.59 | 2093 | CY | 0 | 0 | 0 | 19846.77
Y | IPCRP1-0324-1000-S | IPCRP1 | IPCRP1 | 0324-1000 | Install Hydraulic Fill | N | S |  | UNIT | A | 0 | 563.69 | 563.69 | 563.69 | 563.69 | 100 | 0 | 0 | 0 | 0 | N | 563.69 | N | -563.69 | 0 | 0 | 0 | 0 | 0 | 563.69 | N | -563.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -563.69 | 0 | 0 | 563.69 | 0 | 0 | 0 | 0 | 0 | 0 | -563.69 | 0 | 0 | 563.69 | 563.69 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 0 | 4.5 | 0 | 4.5 | NA | 2093 | 1128.41 | 964.59 | 2093 | CY | 563.69 | 0 | 563.69 | 0
Y | IPCRP1-0325-0000-L | IPCRP1 | IPCRP1 | 0325-0000 | ADDITIONAL CONCRETE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0325-0000-R | IPCRP1 | IPCRP1 | 0325-0000 | ADDITIONAL CONCRETE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 167500 | 0 | 0 | 167500 | 0 | 167500 | 322920 | 0 | N | 167500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0326-0000-L | IPCRP1 | IPCRP1 | 0326-0000 | ADD SELECT GRANULAR BACKFILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0326-0000-R | IPCRP1 | IPCRP1 | 0326-0000 | ADD SELECT GRANULAR BACKFILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 427000 | 0 | 0 | 427000 | 0 | 427000 | 0 | 0 | N | 427000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0327-0000-L | IPCRP1 | IPCRP1 | 0327-0000 | ADD STEEL REBAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0327-0000-R | IPCRP1 | IPCRP1 | 0327-0000 | ADD STEEL REBAR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 396545 | 0 | 0 | 396545 | 0 | 396545 | 549738.99 | 0 | N | 396545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0327-1000-L | IPCRP1 | IPCRP1 | 0327-1000 | Rebar Black | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 396545 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0327-1000-S | IPCRP1 | IPCRP1 | 0327-1000 | Rebar Black | N | S |  | NR | P | 3965.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 3965.45 | 0 | 0 | 3965.45 | 0 | 0 | 0 | N | 3965.45 | 0 | 0 | 3965.45 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 396545 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | Scope included in cc: 2000-1000, Rebar Summary
Y | IPCRP1-0328-0000-L | IPCRP1 | IPCRP1 | 0328-0000 | SPECIAL CARE EXCAV & RESTORE FOR SW WORK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0328-0000-R | IPCRP1 | IPCRP1 | 0328-0000 | SPECIAL CARE EXCAV & RESTORE FOR SW WORK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5375 | 0 | 0 | 5375 | 0 | 5375 | 0 | 0 | N | 5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0328-1000-E | IPCRP1 | IPCRP1 | 0328-1000 | Special Care Excav & Restorre for SW Work | N | E |  | NR | P | 195.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 195.07 | 0 | 0 | 195.07 | 0 | 0 | 0 | Y | 195.07 | 0 | 0 | 195.07 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1075 | 0 | 1075 | 1075 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0328-1000-L | IPCRP1 | IPCRP1 | 0328-1000 | Special Care Excav & Restorre for SW Work | N | L |  | NR | P | 2437.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437.87 | N | 2437.87 | N | 0 | 0 | 0 | 2437.87 | 0 | 0 | 2437.87 | N | 0 | 0 | 0 | 2437.87 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2437.87 | 0 | 0 | 2437.87 | 0 | 0 | 0 | 0 | 0 | 0 | -2437.87 | 0 | 0 | 2437.87 | 2437.87 | 0 | 0 | 0 | 22 | 0 | 22 | 22 | 22 | 0 | 22 | 22 | HR | 1075 | 0 | 1075 | 1075 | SF | 0 | 0 | 0 | 2437.87
Y | IPCRP1-0329-0000-L | IPCRP1 | IPCRP1 | 0329-0000 | SPECIAL CARE EXCAV & RESTORE FOR CURB WORK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0329-0000-R | IPCRP1 | IPCRP1 | 0329-0000 | SPECIAL CARE EXCAV & RESTORE FOR CURB WORK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42600 | 0 | 0 | 42600 | 0 | 42600 | 0 | 0 | N | 42600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0329-1000-E | IPCRP1 | IPCRP1 | 0329-1000 | SPECIAL CARE EXCAV & RESTORE FOR CURB WORK | N | E |  | NR | P | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 2130 | 0 | 2130 | 2130 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0329-1000-L | IPCRP1 | IPCRP1 | 0329-1000 | SPECIAL CARE EXCAV & RESTORE FOR CURB WORK | N | L |  | NR | P | 2128.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2128.43 | N | 2128.43 | N | 0 | 0 | 0 | 2128.43 | 0 | 0 | 2128.43 | N | 0 | 0 | 0 | 2128.43 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2128.43 | 0 | 0 | 2128.43 | 0 | 0 | 0 | 0 | 0 | 0 | -2128.43 | 0 | 0 | 2128.43 | 2128.43 | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 20 | 0 | 20 | 20 | HR | 2130 | 0 | 2130 | 2130 | SF | 0 | 0 | 0 | 2128.43
Y | IPCRP1-0329-1000-S | IPCRP1 | IPCRP1 | 0329-1000 | SPECIAL CARE EXCAV & RESTORE FOR CURB WORK | N | S |  | UNIT | A | 0 | 1648.44 | 1648.44 | 1648.44 | 1648.44 | 100 | 0 | 0 | 0 | 0 | N | 1648.44 | N | -1648.44 | 0 | 0 | 0 | 0 | 0 | 1648.44 | N | -1648.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1648.44 | 0 | 0 | 1648.44 | 0 | 0 | 0 | 0 | 0 | 0 | -1648.44 | 0 | 0 | 1648.44 | 1648.44 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 13 | 0 | 13 | NA | 2130 | 0 | 2130 | 2130 | SF | 1648.44 | 0 | 1648.44 | 0
Y | IPCRP1-0329-1010-L | IPCRP1 | IPCRP1 | 0329-1010 | Vac Truck Excavation | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2130 | 0 | 2130 | 2130 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0329-1010-S | IPCRP1 | IPCRP1 | 0329-1010 | Vac Truck Excavation | N | S |  | NR | A | 39333 | 2015500 | 2015500 | 1762134.05 | 2015500 | 87.4291 | 0 | 0 | 0 | 0 | Y | 2015500 | Y | -1976167 | 0 | 0 | 39333 | 0 | 0 | 2015500 | Y | -1976167 | 0 | 0 | 39333 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2015500 | 0 | 27353 | 2015500 | 0 | 0 | 0 | 0 | 0 | 0 | -2015500 | 0 | 0 | 2015500 | 2015500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 50008.36 | -50007.36 | 1 | LS | 2130 | 0 | 2130 | 2130 | SF | 2015500 | 253365.95 | 1762134.05 | 0 | McVac @$100K
Y | IPCRP1-0330-0000-L | IPCRP1 | IPCRP1 | 0330-0000 | STEEL FOUNDATION PLATE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0330-0000-R | IPCRP1 | IPCRP1 | 0330-0000 | STEEL FOUNDATION PLATE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0330-1000-E | IPCRP1 | IPCRP1 | 0330-1000 | STEEL FOUNDATION PLATE | N | E |  | NR | P | 1252.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1252.17 | 0 | 0 | 1252.17 | 0 | 0 | 0 | Y | 1252.17 | 0 | 0 | 1252.17 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 250 | 0 | 250 | 250 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0330-1000-L | IPCRP1 | IPCRP1 | 0330-1000 | STEEL FOUNDATION PLATE | N | L |  | NR | P | 1850.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850.16 | N | 1850.16 | N | 0 | 0 | 0 | 1850.16 | 0 | 0 | 1850.16 | N | 0 | 0 | 0 | 1850.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1850.16 | 0 | 0 | 1850.16 | 0 | 0 | 0 | 0 | 0 | 0 | -1850.16 | 0 | 0 | 1850.16 | 1850.16 | 0 | 0 | 0 | 16 | 0 | 16 | 16 | 16 | 0 | 16 | 16 | HR | 250 | 0 | 250 | 250 | LB | 0 | 0 | 0 | 1850.16
Y | IPCRP1-0330-1000-M | IPCRP1 | IPCRP1 | 0330-1000 | STEEL FOUNDATION PLATE | N | M |  | NR | P | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | N | 1250 | N | 0 | 0 | 0 | 1250 | 0 | 0 | 1250 | N | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1250 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | -1250 | 0 | 0 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 250 | 0 | 250 | 250 | LB | 0 | 0 | 0 | 1250
Y | IPCRP1-0331-0000-L | IPCRP1 | IPCRP1 | 0331-0000 | PAVING TRAY (NEIGHBOURHOOD TOTEM) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0331-0000-R | IPCRP1 | IPCRP1 | 0331-0000 | PAVING TRAY (NEIGHBOURHOOD TOTEM) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 17500 | 0 | 0 | 17500 | 0 | 17500 | 0 | 0 | N | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0331-1000-E | IPCRP1 | IPCRP1 | 0331-1000 | Paving Tray (Neighbourhood Totem) | N | E |  | NR | P | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 645 | 0 | 0 | 645 | 0 | 0 | 0 | Y | 645 | 0 | 0 | 645 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 5 | 0 | 5 | 5 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0331-1000-L | IPCRP1 | IPCRP1 | 0331-1000 | Paving Tray (Neighbourhood Totem) | N | L |  | NR | P | 4625.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4625.4 | N | 4625.4 | N | 0 | 0 | 0 | 4625.4 | 0 | 0 | 4625.4 | N | 0 | 0 | 0 | 4625.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4625.4 | 0 | 0 | 4625.4 | 0 | 0 | 0 | 0 | 0 | 0 | -4625.4 | 0 | 0 | 4625.4 | 4625.4 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 40 | 0 | 40 | 40 | HR | 5 | 0 | 5 | 5 | EA | 0 | 0 | 0 | 4625.4
Y | IPCRP1-0331-1000-S | IPCRP1 | IPCRP1 | 0331-1000 | Paving Tray (Neighbourhood Totem) | N | S |  | NR | A | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | N | 12500 | N | 0 | 0 | 0 | 12500 | 0 | 0 | 12500 | N | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12500 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | -12500 | 0 | 0 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 5 | 0 | 5 | 5 | EA | 0 | 0 | 0 | 12500
Y | IPCRP1-0332-0000-L | IPCRP1 | IPCRP1 | 0332-0000 | WAYFINDING SIGN FOOTING TYPE C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0332-0000-R | IPCRP1 | IPCRP1 | 0332-0000 | WAYFINDING SIGN FOOTING TYPE C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0332-1000-C | IPCRP1 | IPCRP1 | 0332-1000 | Exc & Install Wayfinding Sign Footing - Complete | N | C |  | NR | P | 783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783 | N | 783 | N | 0 | 0 | 0 | 783 | 0 | 0 | 783 | N | 0 | 0 | 0 | 783 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -783 | 0 | 0 | 783 | 0 | 0 | 0 | 0 | 0 | 0 | -783 | 0 | 0 | 783 | 783 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 783
Y | IPCRP1-0332-1000-E | IPCRP1 | IPCRP1 | 0332-1000 | Exc & Install Wayfinding Sign Footing - Complete | N | E |  | NR | P | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0332-1000-L | IPCRP1 | IPCRP1 | 0332-1000 | Exc & Install Wayfinding Sign Footing - Complete | N | L |  | NR | P | 23221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23221 | N | 23221 | N | 0 | 0 | 0 | 23221 | 0 | 0 | 23221 | N | 0 | 0 | 0 | 23221 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23221 | 0 | 0 | 23221 | 0 | 0 | 0 | 0 | 0 | 0 | -23221 | 0 | 0 | 23221 | 23221 | 0 | 0 | 0 | 208 | 0 | 208 | 208 | 208 | 0 | 208 | 208 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 23221
Y | IPCRP1-0332-1000-M | IPCRP1 | IPCRP1 | 0332-1000 | Exc & Install Wayfinding Sign Footing - Complete | N | M |  | NR | P | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | N | 500 | N | 0 | 0 | 0 | 500 | 0 | 0 | 500 | N | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | -500 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 500
Y | IPCRP1-0332-1000-S | IPCRP1 | IPCRP1 | 0332-1000 | Exc & Install Wayfinding Sign Footing - Complete | N | S |  | NR | A | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | N | 84 | N | 0 | 0 | 0 | 84 | 0 | 0 | 84 | N | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -84 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | -84 | 0 | 0 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 84
Y | IPCRP1-0333-0000-L | IPCRP1 | IPCRP1 | 0333-0000 | ALLOWANCE FOR DECORATIVE MESH FABRIC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0333-0000-R | IPCRP1 | IPCRP1 | 0333-0000 | ALLOWANCE FOR DECORATIVE MESH FABRIC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 500000 | 0 | 0 | 500000 | 0 | 500000 | 123417.28 | 0 | N | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0333-1000-C | IPCRP1 | IPCRP1 | 0333-1000 | ALLOWANCE FOR DECORATIVE MESH FABRIC | N | C |  | NR | P | 500000 | 43700.26 | 43700.26 | 41313.78 | 43700.26 | 41.3138 | 0 | 0 | 0 | 56299.74 | N | 100000 | N | 400000 | 0 | 0 | 500000 | 0 | 0 | 100000 | N | 400000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 401 | 739.2 | 1140.2 | EA | 3125 | 156.5 | 1923.5 | 2080 | HR | 43700.26 | 2386.48 | 41313.78 | 56299.74
Y | IPCRP1-0333-1000-E | IPCRP1 | IPCRP1 | 0333-1000 | ALLOWANCE FOR DECORATIVE MESH FABRIC | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 3125 | 156.5 | 1923.5 | 2080 | HR | 0 | 0 | 0 | 25000
Y | IPCRP1-0333-1000-L | IPCRP1 | IPCRP1 | 0333-1000 | ALLOWANCE FOR DECORATIVE MESH FABRIC | N | L |  | UNIT | P | 0 | 19079.68 | 19079.68 | 19079.68 | 19079.68 | 7.6317 | 0 | 0 | 0 | 230924.64 | Y | 250004.32 | Y | -250004.32 | 0 | 0 | 0 | 0 | 0 | 250004.32 | Y | -250004.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250004.32 | 0 | 0 | 250004.32 | 0 | 0 | 0 | 0 | 0 | 0 | -250004.32 | 0 | 0 | 250004.32 | 250004.32 | 0 | 0 | 0 | 0 | 0 | 2080 | 2080 | 0 | 156.5 | 1923.5 | 2080 | HR | 3125 | 156.5 | 1923.5 | 2080 | HR | 0 | 0 | 0 | 230924.64 | Install Green Fabric on Fencing (Nov 22), DDC Art Work in Park (Dec 23) & Houston St Art (Nov 24). Cost included for Install of Green Fabric on Fencing (Nov 2022) & DDC T&M Art Work (Dec 2023) & Houston St Art (Nov 24) under this code.
Y | IPCRP1-0334-0000-L | IPCRP1 | IPCRP1 | 0334-0000 | FLASHING ARROW BOARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0334-0000-R | IPCRP1 | IPCRP1 | 0334-0000 | FLASHING ARROW BOARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0334-1000-E | IPCRP1 | IPCRP1 | 0334-1000 | Furn Flashing Arrow Boards (FAB) | N | E |  | NR | P | 43447.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 43447.04 | 0 | 0 | 43447.04 | 0 | 0 | 0 | Y | 43447.04 | 0 | 0 | 43447.04 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 4 | 0 | 4 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0334-1000-L | IPCRP1 | IPCRP1 | 0334-1000 | Furn Flashing Arrow Boards (FAB) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4 | 0 | 4 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0335-0000-L | IPCRP1 | IPCRP1 | 0335-0000 | CLEARING & GRUBBING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0
Y | IPCRP1-0335-0000-R | IPCRP1 | IPCRP1 | 0335-0000 | CLEARING & GRUBBING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18920000 | 0 | 0 | 18920000 | 0 | 18920000 | 16568000 | 0 | N | 18920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18920000 | 0 | 1.1 | -1.1 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0
Y | IPCRP1-0335-1000-C | IPCRP1 | IPCRP1 | 0335-1000 | Clear & Grub | N | C |  | UNIT | U | 0 | 13359.35 | 13359.35 | 13359.35 | 13359.35 | 100 | 0 | 0 | 0 | 0 | Y | 13359.35 | Y | -13359.35 | 0 | 0 | 0 | 0 | 0 | 13359.35 | Y | -13359.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13359.35 | 0 | 0 | 13359.35 | 0 | 0 | 0 | 0 | 0 | 0 | -13359.35 | 0 | 0 | 13359.35 | 13359.35 | 0 | 0 | 0 | 0 | 0 | 43.2 | 43.2 | 0 | 40 | 3.2 | 43.2 | NA | 47.3 | 41.3 | 0 | 41.3 | AC | 10210.3 | -3149.05 | 13359.35 | 0 | Carter, Milchman & Frank @$3,919.50, Infinity Lumber @$5,330.52, J.H. Fisher @$789.02, Triboro @$3,222.70
Y | IPCRP1-0335-1000-E | IPCRP1 | IPCRP1 | 0335-1000 | Clear & Grub | N | E |  | NR | P | 410000 | -8.33 | -7076.88 | -7076.88 | -8.33 | 0 | 0 | 0 | 0 | 8.33 | Y | 0 | Y | 410000 | 0 | 0 | 410000 | 0 | 0 | 0 | Y | 410000 | 0 | 0 | 410000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 161 | 0.88 | 161.88 | LF | 47.3 | 41.3 | 0 | 41.3 | AC | -8.33 | 7068.55 | -7076.88 | 8.33
Y | IPCRP1-0335-1000-L | IPCRP1 | IPCRP1 | 0335-1000 | Clear & Grub | N | L |  | NR | P | 955970 | 752841.49 | 752841.49 | 752841.49 | 752841.49 | 100 | 0 | 0 | 0 | 0.01 | Y | 752841.5 | Y | 203128.5 | 0 | 0 | 955970 | 0 | 0 | 752841.5 | Y | 203128.5 | 0 | 0 | 955970 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -752841.5 | 0 | 0 | 752841.5 | 0 | 0 | 0 | 0 | 0 | 0 | -752841.5 | 0 | 0 | 752841.5 | 752841.5 | 0 | 0 | 0 | 8000 | 0 | 5891 | 5891 | 8000 | 5891 | 0 | 5891 | HR | 47.3 | 41.3 | 0 | 41.3 | AC | 0 | 0 | 0 | 0.01 | As / JP (9/9) PMF = 42.29 AC, this includes 7.65 AC left in Phase 2 (Reach H, T&F area) and compost area 2x (1.16 AC) Change CTD (Quantity) from 22.47 to 24.41 (March 2024). Equipment cost and commitments will be moved to the new equipment code (2000-1230) for February '22 report (3.14.2022)
Y | IPCRP1-0335-1000-S | IPCRP1 | IPCRP1 | 0335-1000 | Clear & Grub | N | S |  | UNIT | A | 0 | 39263.66 | 39263.66 | 39263.66 | 39263.66 | 100 | 0 | 0 | 0 | 0 | Y | 39263.66 | Y | -39263.66 | 0 | 0 | 0 | 0 | 0 | 39263.66 | Y | -39263.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39263.66 | 0 | 0 | 39263.66 | 0 | 0 | 0 | 0 | 0 | 0 | -39263.66 | 0 | 0 | 39263.66 | 39263.66 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 314.5 | -298.5 | 16 | NA | 47.3 | 41.3 | 0 | 41.3 | AC | 39263.66 | 0 | 39263.66 | 0
Y | IPCRP1-0336-0000-L | IPCRP1 | IPCRP1 | 0336-0000 | STORM WATER POLLUTION PREVENTION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0336-0000-R | IPCRP1 | IPCRP1 | 0336-0000 | STORM WATER POLLUTION PREVENTION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25000 | 0 | 0 | 25000 | 0 | 25000 | 12105.6 | 0 | N | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0336-1000-C | IPCRP1 | IPCRP1 | 0336-1000 | STORM WATER POLLUTION PREVENTION | N | C |  | UNIT | U | 0 | 580931.67 | 580931.67 | 580931.67 | 580931.67 | 96.8219 | 0 | 0 | 0 | 19068.33 | Y | 600000 | Y | -600000 | 0 | 0 | 0 | 0 | 0 | 600000 | Y | -600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -600000 | 0 | 13337.19 | 600000 | 0 | 0 | 0 | 0 | 13337.19 | 0 | -600000 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 1074 | 1074 | 0 | 17457 | -16383 | 1074 | EA | 260 | 220 | 40 | 260 | WK | 563424.72 | -17506.95 | 580931.67 | 19068.33
Y | IPCRP1-0336-1000-L | IPCRP1 | IPCRP1 | 0336-1000 | STORM WATER POLLUTION PREVENTION | N | L |  | UNIT | P | 0 | 733578.52 | 733578.52 | 733578.52 | 733578.52 | 88.9442 | 0 | 0 | 0 | 91184.2 | Y | 824762.72 | Y | -824762.72 | 0 | 0 | 0 | 0 | 0 | 824762.72 | Y | -824762.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -824762.72 | 1904.72 | 112.58 | 824762.72 | 0 | 0 | 0 | 0 | 0 | 0 | -824762.72 | 0 | 0 | 824762.72 | 824762.72 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 0 | 5376.5 | 1123.5 | 6500 | HR | 260 | 220 | 40 | 260 | WK | 0 | 0 | 0 | 91184.2
Y | IPCRP1-0336-1000-M | IPCRP1 | IPCRP1 | 0336-1000 | STORM WATER POLLUTION PREVENTION | N | M |  | UNIT | U | 0 | 23340.22 | -37634.33 | -37634.33 | 23340.22 | 100 | 0 | 0 | 0 | -60974.55 | Y | -37634.33 | Y | 37634.33 | 0 | 0 | 0 | 0 | 0 | -37634.33 | Y | 37634.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 37634.33 | 0 | 0 | -37634.33 | 0 | 0 | 0 | 0 | 0 | 0 | 37634.33 | 0 | 0 | -37634.33 | -37634.33 | 0 | 0 | 0 | 0 | 0 | -627.8 | -627.8 | 0 | 1181 | -1808.8 | -627.8 | NA | 260 | 220 | 40 | 260 | WK | 23340.22 | 60974.55 | -37634.33 | -60974.55 | Requested to remove $39,206.17 commitments from Material code a few times.
Y | IPCRP1-0336-1000-S | IPCRP1 | IPCRP1 | 0336-1000 | STORM WATER POLLUTION PREVENTION | N | S |  | NR | A | 10000 | 1096149.87 | 1096149.87 | 851949.57 | 1096149.87 | 77.722 | 0 | 0 | 0 | 0 | Y | 1096149.87 | Y | -1086149.87 | 0 | 0 | 10000 | 0 | 0 | 1096149.87 | Y | -1086149.87 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1096149.87 | 3938.61 | 0 | 1096149.87 | 0 | 0 | 0 | 0 | 0 | 0 | -1096149.87 | 0 | 0 | 1096149.87 | 1096149.87 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 487657.61 | -487656.61 | 1 | EA | 260 | 220 | 40 | 260 | WK | 1096149.87 | 244200.3 | 851949.57 | 0 | KMA CO added. MIRMAX CIVIL ENGINEERING @$205,450.00
Y | IPCRP1-0337-0000-L | IPCRP1 | IPCRP1 | 0337-0000 | AIR QUALITY MONITORING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0337-0000-R | IPCRP1 | IPCRP1 | 0337-0000 | AIR QUALITY MONITORING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300000 | 0 | 0 | 300000 | 0 | 300000 | 240000 | 0 | N | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0338-0000-L | IPCRP1 | IPCRP1 | 0338-0000 | NOISE MONITORING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0338-0000-R | IPCRP1 | IPCRP1 | 0338-0000 | NOISE MONITORING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 24000 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0339-0000-L | IPCRP1 | IPCRP1 | 0339-0000 | ARCH CONC TEXT FINISHES (PED BRIDGES) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0339-0000-R | IPCRP1 | IPCRP1 | 0339-0000 | ARCH CONC TEXT FINISHES (PED BRIDGES) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 535750 | 0 | 0 | 535750 | 0 | 535750 | 136833.5 | 0 | N | 535750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0339-1000-E | IPCRP1 | IPCRP1 | 0339-1000 | Inst & Rem Formliner, Rub & Seal (Ped Bridges) | N | E |  | NR | P | 31300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 31300 | 0 | 0 | 31300 | 0 | 0 | 0 | N | 31300 | 0 | 0 | 31300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 23000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0339-1000-L | IPCRP1 | IPCRP1 | 0339-1000 | Inst & Rem Formliner, Rub & Seal (Ped Bridges) | N | L |  | NR | P | 287014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 287014 | 0 | 0 | 287014 | 0 | 0 | 0 | Y | 287014 | 0 | 0 | 287014 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420 | 0 | 0 | 0 | 2420 | 0 | 0 | 0 | HR | 23000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070
Y | IPCRP1-0339-1000-M | IPCRP1 | IPCRP1 | 0339-1000 | Inst & Rem Formliner, Rub & Seal (Ped Bridges) | N | M |  | NR | P | 23750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 23750 | 0 | 0 | 23750 | 0 | 0 | 0 | N | 23750 | 0 | 0 | 23750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 23000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0339-1010-C | IPCRP1 | IPCRP1 | 0339-1010 | Furn Arch Form Liner (Ped Bridges) | N | C |  | NR | P | 260002.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 260002.72 | 0 | 0 | 260002.72 | 0 | 0 | 0 | N | 260002.72 | 0 | 0 | 260002.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 23000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0339-1010-L | IPCRP1 | IPCRP1 | 0339-1010 | Furn Arch Form Liner (Ped Bridges) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 23000 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | work included in Structural Concrete Sub (D'Annunzio) cc: 0147-1070, Change PMF (Quantity) from 23,000.00 to 0.00
Y | IPCRP1-0340-0000-L | IPCRP1 | IPCRP1 | 0340-0000 | ARCH CONC TEXT FINISHES (FLOOD WALLS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0340-0000-R | IPCRP1 | IPCRP1 | 0340-0000 | ARCH CONC TEXT FINISHES (FLOOD WALLS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 957750 | 0 | 0 | 957750 | 0 | 957750 | 324825.25 | 0 | N | 957750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0340-1000-E | IPCRP1 | IPCRP1 | 0340-1000 | Flood Wall Mock-Up | N | E |  | NR | P | 52135 | 63.15 | 63.15 | 63.15 | 63.15 | 100 | 0 | 0 | 0 | 0 | Y | 63.15 | Y | 52071.85 | 0 | 0 | 52135 | 0 | 0 | 63.15 | Y | 52071.85 | 0 | 0 | 52135 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63.15 | 0 | 0 | 63.15 | 0 | 0 | 0 | 0 | 0 | 0 | -63.15 | 0 | 0 | 63.15 | 63.15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | -2 | 0 | LS | 1 | 1 | 0 | 1 | LS | 63.15 | 0 | 63.15 | 0
Y | IPCRP1-0340-1000-L | IPCRP1 | IPCRP1 | 0340-1000 | Flood Wall Mock-Up | N | L |  | NR | P | 478066 | 156005.23 | 156005.23 | 156005.23 | 156005.23 | 100 | 0 | 0 | 0 | 0 | Y | 156005.23 | Y | 322060.77 | 0 | 0 | 478066 | 0 | 0 | 156005.23 | Y | 322060.77 | 0 | 0 | 478066 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -156005.23 | 0 | 0 | 156005.23 | 0 | 0 | 0 | 0 | 0 | 0 | -156005.23 | 0 | 0 | 156005.23 | 156005.23 | 0 | 0 | 0 | 4030.88 | 0 | 1184.5 | 1184.5 | 4030.88 | 1184.5 | 0 | 1184.5 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Change PMF (MH) from 1,187.00 to 1,179.50 (to match CTD).
Y | IPCRP1-0340-1000-M | IPCRP1 | IPCRP1 | 0340-1000 | Flood Wall Mock-Up | N | M |  | NR | P | 39559 | 1283.08 | 1283.08 | 1283.08 | 1283.08 | 100 | 0 | 0 | 0 | 0 | Y | 1283.08 | Y | 38275.92 | 0 | 0 | 39559 | 0 | 0 | 1283.08 | Y | 38275.92 | 0 | 0 | 39559 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1283.08 | 0 | 0 | 1283.08 | 0 | 0 | 0 | 0 | 0 | 0 | -1283.08 | 0 | 0 | 1283.08 | 1283.08 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73.66 | 0 | 73.66 | EA | 1 | 1 | 0 | 1 | LS | 1283.08 | 0 | 1283.08 | 0 | Change PMF (MH) from 1,187.00 to 1,179.50 (to match CTD).
Y | IPCRP1-0340-1010-C | IPCRP1 | IPCRP1 | 0340-1010 | Furn Arch Form Liner (Flood Walls) | N | C |  | NR | P | 433074.09 | 381765.49 | 381765.49 | 369218.51 | 381765.49 | 85.2553 | 0 | 0 | 0 | 51308.6 | N | 433074.09 | N | 0 | 0 | 0 | 433074.09 | 0 | 0 | 433074.09 | N | 0 | 0 | 0 | 433074.09 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -433074.09 | 0 | 0 | 433074.09 | 0 | 0 | 0 | 0 | 0 | 0 | -433074.09 | 0 | 0 | 433074.09 | 433074.09 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5592.37 | -5592.37 | 0 | ST | 38310 | 0 | 38310 | 38310 | SF | 381568.52 | 12546.98 | 369021.54 | 51308.6
Y | IPCRP1-0340-1010-L | IPCRP1 | IPCRP1 | 0340-1010 | Furn Arch Form Liner (Flood Walls) | N | L |  | UNIT | P | 0 | 21696.54 | 21696.54 | 21696.54 | 21696.54 | 100 | 0 | 0 | 0 | 0 | Y | 21696.54 | Y | -21696.54 | 0 | 0 | 0 | 0 | 0 | 21696.54 | Y | -21696.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21696.54 | 0 | 0 | 21696.54 | 0 | 0 | 0 | 0 | 0 | 0 | -21696.54 | 0 | 0 | 21696.54 | 21696.54 | 0 | 0 | 0 | 0 | 0 | 163.5 | 163.5 | 0 | 163.5 | 0 | 163.5 | HR | 38310 | 0 | 38310 | 38310 | SF | 0 | 0 | 0 | 0 | Labor cost to install Storage Area under FDR at Montgomery St. Refer to Shawn C email dated 10/24/24 for projection.
Y | IPCRP1-0340-1010-S | IPCRP1 | IPCRP1 | 0340-1010 | Furn Arch Form Liner (Flood Walls) | N | S |  | UNIT | A | 0 | 1013.29 | 1013.29 | 1013.29 | 1013.29 | 100 | 0 | 0 | 0 | 0 | N | 1013.29 | N | -1013.29 | 0 | 0 | 0 | 0 | 0 | 1013.29 | N | -1013.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1013.29 | 0 | 0 | 1013.29 | 0 | 0 | 0 | 0 | 0 | 0 | -1013.29 | 0 | 0 | 1013.29 | 1013.29 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 38310 | 0 | 38310 | 38310 | SF | 1013.29 | 0 | 1013.29 | 0
Y | IPCRP1-0340-1020-L | IPCRP1 | IPCRP1 | 0340-1020 | Install Arch Formliner to Floodwall | N | L |  | UNIT | P | 0 | 476273.83 | 476273.83 | 476273.83 | 476273.83 | 47.4255 | 0 | 0 | 0 | 527982.57 | Y | 1004256.4 | Y | -1004256.4 | 0 | 0 | 0 | 0 | 0 | 1004256.4 | Y | -1004256.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1004256.4 | 30206.67 | 28580.19 | 1004256.4 | 0 | 0 | 0 | 0 | 0 | 0 | -1004256.4 | 0 | 0 | 1004256.4 | 1004256.4 | 0 | 0 | 0 | 0 | 0 | 7662 | 7662 | 0 | 3590 | 4072 | 7662 | HR | 38310 | 15526.4 | 22783.6 | 38310 | SF | 0 | 0 | 0 | 527982.57
Y | IPCRP1-0340-1020-S | IPCRP1 | IPCRP1 | 0340-1020 | Install Arch Formliner to Floodwall | N | S |  | UNIT | A | 0 | 6915.82 | 6915.82 | 6915.82 | 6915.82 | 103.8794 | 0 | 0 | 0 | -258.27 | Y | 6657.55 | Y | -6657.55 | 0 | 0 | 0 | 0 | 0 | 6657.55 | Y | -6657.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6657.55 | 258.27 | 1245.01 | 6657.55 | 0 | 0 | 0 | 0 | 258.27 | 0 | -6657.55 | 0 | 0 | 6657.55 | 6657.55 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 42 | -36 | 6 | NA | 38310 | 15526.4 | 22783.6 | 38310 | SF | 6915.82 | 0 | 6915.82 | -258.27
Y | IPCRP1-0341-0000-L | IPCRP1 | IPCRP1 | 0341-0000 | CON ED FLOODWALL UTILITY CROSSING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0341-0000-R | IPCRP1 | IPCRP1 | 0341-0000 | CON ED FLOODWALL UTILITY CROSSING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 644840 | 0 | 0 | 644840 | 0 | 644840 | 0 | 0 | N | 644840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0341-1000-C | IPCRP1 | IPCRP1 | 0341-1000 | CON ED FLOODWALL UTILITY CROSSING | N | C |  | NR | P | 644840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644840 | N | 644840 | N | 0 | 0 | 0 | 644840 | 0 | 0 | 644840 | N | 0 | 0 | 0 | 644840 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -644840 | 0 | 0 | 644840 | 0 | 0 | 0 | 0 | 0 | 0 | -644840 | 0 | 0 | 644840 | 644840 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 644840
Y | IPCRP1-0341-1000-L | IPCRP1 | IPCRP1 | 0341-1000 | CON ED FLOODWALL UTILITY CROSSING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0342-0000-L | IPCRP1 | IPCRP1 | 0342-0000 | JET GROUT TEST PROGRAM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0342-0000-R | IPCRP1 | IPCRP1 | 0342-0000 | JET GROUT TEST PROGRAM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 1500000 | 1500000 | 0 | N | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0343-0000-L | IPCRP1 | IPCRP1 | 0343-0000 | JET GROUT UTIL CROSS SEEPAGE BARR - ANGLED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0343-0000-R | IPCRP1 | IPCRP1 | 0343-0000 | JET GROUT UTIL CROSS SEEPAGE BARR - ANGLED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1113000 | 0 | 0 | 1113000 | 0 | 1113000 | 738000 | 0 | N | 1113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0344-0000-L | IPCRP1 | IPCRP1 | 0344-0000 | ANGLED JET GROUT UTIL X-ING, FLOODWALLS W OBSTRUC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0344-0000-R | IPCRP1 | IPCRP1 | 0344-0000 | ANGLED JET GROUT UTIL X-ING, FLOODWALLS W OBSTRUC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 76000 | 0 | 0 | 76000 | 0 | 76000 | 28000 | 0 | N | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0345-0000-L | IPCRP1 | IPCRP1 | 0345-0000 | JET GROUT, GATE & FLOODWALL FOUNDATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0345-0000-R | IPCRP1 | IPCRP1 | 0345-0000 | JET GROUT, GATE & FLOODWALL FOUNDATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18754000 | 0 | 0 | 18754000 | 0 | 18754000 | 6284000 | 0 | N | 18754000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18754000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0346-0000-L | IPCRP1 | IPCRP1 | 0346-0000 | VERT JET GROUT, UTIL X-ING, FLOODWALLS W OBSTRUCT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0346-0000-R | IPCRP1 | IPCRP1 | 0346-0000 | VERT JET GROUT, UTIL X-ING, FLOODWALLS W OBSTRUCT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1577400 | 0 | 0 | 1577400 | 0 | 1577400 | 2187800 | 0 | N | 1577400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1577400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0347-0000-L | IPCRP1 | IPCRP1 | 0347-0000 | JET GROUT, GATE X-ING SEEPAGE BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0347-0000-R | IPCRP1 | IPCRP1 | 0347-0000 | JET GROUT, GATE X-ING SEEPAGE BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2463000 | 0 | 0 | 2463000 | 0 | 2463000 | 1215000 | 0 | N | 2463000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2463000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0348-0000-L | IPCRP1 | IPCRP1 | 0348-0000 | JET GROUT, FLOOD GATE FOUND & SEEP BARR W OBSTRUC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0348-0000-R | IPCRP1 | IPCRP1 | 0348-0000 | JET GROUT, FLOOD GATE FOUND & SEEP BARR W OBSTRUC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 168000 | 0 | 0 | 168000 | 0 | 168000 | 169200 | 0 | N | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0348-1000-L | IPCRP1 | IPCRP1 | 0348-1000 | Jet Grout/ Mini-Pile Sub (Atlantic P&F) | N | L |  | UNIT | P | 0 | 263463.56 | 263463.56 | 263463.56 | 263463.56 | 100 | 0 | 0 | 0 | 0 | Y | 263463.56 | Y | -263463.56 | 0 | 0 | 0 | 0 | 0 | 263463.56 | Y | -263463.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -263463.56 | 0 | 0 | 263463.56 | 0 | 0 | 0 | 0 | 0 | 0 | -263463.56 | 0 | 0 | 263463.56 | 263463.56 | 0 | 0 | 0 | 0 | 0 | 1639.5 | 1639.5 | 0 | 1639.5 | 0 | 1639.5 | HR | 1 | 0.97 | 0.03 | 1 | LS | 0 | 0 | 0 | 0 | Atlantic Pile Base (+$37,099,798) , less SCO#1, Utility MP (-$3,547,216) plus SCO#2 Downtime (+$600,000) less SCO#3 (E10th MP (-$4,297,464), less SCO#4 Scope Reduction MP (-$7,244,680) less SCO#5 Jet Grout Spoils Reduction (-$4,300,000) = $14,852,378.00
Y | IPCRP1-0348-1000-M | IPCRP1 | IPCRP1 | 0348-1000 | Jet Grout/ Mini-Pile Sub (Atlantic P&F) | N | M |  | UNIT | U | 0 | 2071312.47 | 2071312.47 | 1869224.94 | 2071312.47 | 107.201 | 0 | 0 | 0 | 0 | N | 1743664 | N | -1743664 | 0 | 0 | 0 | 0 | 0 | 1743664 | N | -1743664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1743664 | 181440 | 0 | 1743664 | 0 | 0 | 0 | 0 | 25470 | 0 | -1743664 | 0 | 0 | 1743664 | 1743664 | 0 | 0 | 0 | 0 | 0 | 74036 | 74036 | 0 | 68423 | 5613 | 74036 | NA | 1 | 0.97 | 0.03 | 1 | LS | 2071445.6 | 202087.53 | 1869358.07 | 0
Y | IPCRP1-0348-1000-S | IPCRP1 | IPCRP1 | 0348-1000 | Jet Grout/ Mini-Pile Sub (Atlantic P&F) | N | S |  | NR | A | 36786895 | 15089516.2 | 15089516.2 | 8696438.56 | 15089516.2 | 96.8392 | 0 | 0 | 0 | -6109226.58 | Y | 8980289.62 | Y | 27806605.38 | 0 | 0 | 36786895 | 0 | 0 | 8980289.62 | Y | 27806605.38 | 0 | 0 | 36786895 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8980289.62 | 0 | 0 | 8980289.62 | 0 | 0 | 0 | 0 | 0 | 0 | -8980289.62 | 0 | 0 | 8980289.62 | 8980289.62 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6607.78 | -6607.78 | 0 | LF | 1 | 0.97 | 0.03 | 1 | LS | 15089516.2 | 6393077.64 | 8696438.56 | -6109226.58 | APF SCO #2 (Down Time) +$600,000 - processed. SCO #3 (-$4,297,464) & SCO#4 (-$9744,675) - not processed/ executed. Atlantic Pile Base @$37,099,798, -3,547,216 from CO1 underrun from VE3, current contract is $33,552,582
Y | IPCRP1-0349-0000-L | IPCRP1 | IPCRP1 | 0349-0000 | OBSTRUCT CLEAR, PREFAB VERT DRAIN INSTALL (PRE-DR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0349-0000-R | IPCRP1 | IPCRP1 | 0349-0000 | OBSTRUCT CLEAR, PREFAB VERT DRAIN INSTALL (PRE-DR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200000 | 0 | 0 | 1200000 | 0 | 1200000 | 4115070 | 0 | N | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0350-0000-L | IPCRP1 | IPCRP1 | 0350-0000 | OBSTRUCT CLEAR, DEEP SOIL MIX COL INSTALL (PRE-DR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0350-0000-R | IPCRP1 | IPCRP1 | 0350-0000 | OBSTRUCT CLEAR, DEEP SOIL MIX COL INSTALL (PRE-DR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4000000 | 0 | 0 | 4000000 | 0 | 4000000 | 0 | 0 | N | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0350-1000-L | IPCRP1 | IPCRP1 | 0350-1000 | OBSTRUCT CLEAR, DEEP SOIL MIX COL INSTALL (PRE-DR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 10000 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0350-1000-S | IPCRP1 | IPCRP1 | 0350-1000 | OBSTRUCT CLEAR, DEEP SOIL MIX COL INSTALL (PRE-DR | N | S |  | NR | P | 4018054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 4018054 | 0 | 0 | 4018054 | 0 | 0 | 0 | N | 4018054 | 0 | 0 | 4018054 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 10000 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Work included in Seq #15 Deep Soil Mixing Sub (Geo-Solutions)
Y | IPCRP1-0351-0000-L | IPCRP1 | IPCRP1 | 0351-0000 | DECK DRAIN FOR ESPLANADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0351-0000-R | IPCRP1 | IPCRP1 | 0351-0000 | DECK DRAIN FOR ESPLANADE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 441000 | 0 | 0 | 441000 | 0 | 441000 | 145500 | 0 | N | 441000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0351-1000-L | IPCRP1 | IPCRP1 | 0351-1000 | DECK DRAIN FOR ESPLANADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560 | Y | 1560 | Y | -1560 | 0 | 0 | 0 | 0 | 0 | 1560 | Y | -1560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1560 | 0 | 0 | 1560 | 0 | 0 | 0 | 0 | 0 | 0 | -1560 | 0 | 0 | 1560 | 1560 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 12 | 12 | HR | 294 | 155 | 12 | 167 | EA | 0 | 0 | 0 | 1560
Y | IPCRP1-0351-1000-M | IPCRP1 | IPCRP1 | 0351-1000 | DECK DRAIN FOR ESPLANADE | N | M |  | UNIT | U | 0 | 45145.57 | 45145.57 | 45144.46 | 45145.57 | 90.2889 | 0 | 0 | 0 | 4854.43 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | -335 | 0 | EA | 294 | 155 | 12 | 167 | EA | 45145.57 | 1.11 | 45144.46 | 4854.43 | IPC takeoff is 167ea. Only 12ea are in the CIP esplanade deck [11ea (Phase 1)/ 1ea (Phase 2)]. 155ea are being cast into the Esplanade Bulb Tees.
Y | IPCRP1-0351-1000-S | IPCRP1 | IPCRP1 | 0351-1000 | DECK DRAIN FOR ESPLANADE | N | S |  | NR | A | 395253.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 395253.72 | 0 | 0 | 395253.72 | 0 | 0 | 0 | Y | 395253.72 | 0 | 0 | 395253.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 294 | 155 | 12 | 167 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0352-0000-L | IPCRP1 | IPCRP1 | 0352-0000 | CON ED VAULT MODIFY ALLOWANCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0352-0000-R | IPCRP1 | IPCRP1 | 0352-0000 | CON ED VAULT MODIFY ALLOWANCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16795 | 0 | 0 | 16795 | 0 | 16795 | 0 | 0 | N | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0352-1000-C | IPCRP1 | IPCRP1 | 0352-1000 | CON ED VAULT MODIFY ALLOWANCE | N | C |  | NR | P | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16795 | N | 16795 | N | 0 | 0 | 0 | 16795 | 0 | 0 | 16795 | N | 0 | 0 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16795 | 0 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | -16795 | 0 | 0 | 16795 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 16795
Y | IPCRP1-0352-1000-L | IPCRP1 | IPCRP1 | 0352-1000 | CON ED VAULT MODIFY ALLOWANCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0353-0000-L | IPCRP1 | IPCRP1 | 0353-0000 | MOVABLE TL4 SS JERSEY BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0353-0000-R | IPCRP1 | IPCRP1 | 0353-0000 | MOVABLE TL4 SS JERSEY BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300000 | 0 | 0 | 300000 | 0 | 300000 | 0 | 0 | N | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0353-1000-E | IPCRP1 | IPCRP1 | 0353-1000 | Inst Movable TL4 SS Jersey Barrier | N | E |  | NR | P | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | Y | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 158.5 | 0 | 158.5 | 158.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0353-1000-L | IPCRP1 | IPCRP1 | 0353-1000 | Inst Movable TL4 SS Jersey Barrier | N | L |  | NR | P | 16449.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16449.36 | N | 16449.36 | N | 0 | 0 | 0 | 16449.36 | 0 | 0 | 16449.36 | N | 0 | 0 | 0 | 16449.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16449.36 | 0 | 0 | 16449.36 | 0 | 0 | 0 | 0 | 0 | 0 | -16449.36 | 0 | 0 | 16449.36 | 16449.36 | 0 | 0 | 0 | 160 | 0 | 160 | 160 | 160 | 0 | 160 | 160 | HR | 158.5 | 0 | 158.5 | 158.5 | LF | 0 | 0 | 0 | 16449.36
Y | IPCRP1-0353-1010-L | IPCRP1 | IPCRP1 | 0353-1010 | Furn Movable TL4 SS Jersey Barrier | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 158.5 | 0 | 158.5 | 158.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0353-1010-M | IPCRP1 | IPCRP1 | 0353-1010 | Furn Movable TL4 SS Jersey Barrier | N | M |  | NR | P | 282922.5 | 979080.38 | 979080.38 | 195816.08 | 979080.38 | 19.9812 | 0 | 0 | 0 | 919.62 | Y | 980000 | Y | -697077.5 | 0 | 0 | 282922.5 | 0 | 0 | 980000 | Y | -697077.5 | 0 | 0 | 282922.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -980000 | 0 | 0 | 980000 | 0 | 0 | 0 | 0 | 0 | 0 | -980000 | 0 | 0 | 980000 | 980000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5.6 | -5.6 | 0 | EA | 158.5 | 0 | 158.5 | 158.5 | LF | 979080.38 | 783264.3 | 195816.08 | 919.62
Y | IPCRP1-0354-0000-L | IPCRP1 | IPCRP1 | 0354-0000 | CONC FOR ESPLANADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0354-0000-R | IPCRP1 | IPCRP1 | 0354-0000 | CONC FOR ESPLANADE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 38412500 | 0 | 0 | 38412500 | 0 | 38412500 | 21291600 | 0 | N | 38412500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38412500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0354-1000-L | IPCRP1 | IPCRP1 | 0354-1000 | Install & strip formwork for Esplanade | N | L |  | NR | P | 4314259.19 | 4697932.34 | 4697932.34 | 4697932.34 | 4697932.34 | 62.0906 | 0 | 0 | 0 | 2868323.72 | Y | 7566256.06 | Y | -3251996.87 | 0 | 0 | 4314259.19 | 0 | 0 | 7566256.06 | Y | -3251996.87 | 0 | 0 | 4314259.19 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7566256.06 | 145790.3 | 73176.18 | 7566256.06 | 0 | 0 | 0 | 0 | 0 | 0 | -7566256.06 | 0 | 0 | 7566256.06 | 7566256.06 | 0 | 0 | 0 | 36511.9 | 0 | 58200 | 58200 | 36511.9 | 36503 | 21697 | 58200 | HR | 164304 | 97560.46 | 47939.54 | 145500 | SF | 0 | 0 | 0 | 2868323.72
Y | IPCRP1-0354-1000-S | IPCRP1 | IPCRP1 | 0354-1000 | Install & strip formwork for Esplanade | N | S |  | UNIT | A | 0 | 31161.52 | 31161.52 | 31161.52 | 31161.52 | 129.5839 | 0 | 0 | 0 | -7114.15 | Y | 24047.37 | Y | -24047.37 | 0 | 0 | 0 | 0 | 0 | 24047.37 | Y | -24047.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24047.37 | 1872.45 | 2293.44 | 24047.37 | 0 | 0 | 0 | 0 | 1872.45 | 0 | -24047.37 | 0 | 0 | 24047.37 | 24047.37 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 227.5 | -225.5 | 2 | NA | 164304 | 97560.46 | 47939.54 | 145500 | SF | 31161.52 | 0 | 31161.52 | -7114.15
Y | IPCRP1-0354-1010-E | IPCRP1 | IPCRP1 | 0354-1010 | Place concrete for Esplanade | N | E |  | NR | P | 413020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 413020 | 0 | 0 | 413020 | 0 | 0 | 0 | N | 413020 | 0 | 0 | 413020 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 11901 | 8681.32 | 5339.68 | 14021 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0354-1010-L | IPCRP1 | IPCRP1 | 0354-1010 | Place concrete for Esplanade | N | L |  | NR | P | 1337408 | 827426.5 | 827426.5 | 827426.5 | 827426.5 | 59.7075 | 0 | 0 | 0 | 558372.95 | Y | 1385799.45 | Y | -48391.45 | 0 | 0 | 1337408 | 0 | 0 | 1385799.45 | Y | -48391.45 | 0 | 0 | 1337408 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1385799.45 | 29517.92 | 30365.21 | 1385799.45 | 0 | 0 | 0 | 0 | 0 | 0 | -1385799.45 | 0 | 0 | 1385799.45 | 1385799.45 | 0 | 0 | 0 | 11600.17 | 0 | 10500 | 10500 | 11600.17 | 6251.5 | 4248.5 | 10500 | HR | 11901 | 8681.32 | 5339.68 | 14021 | CY | 0 | 0 | 0 | 558372.95 | Total QTY for item ESCR-4.06 HP ES is this code +0354-1031
Y | IPCRP1-0354-1010-S | IPCRP1 | IPCRP1 | 0354-1010 | Place concrete for Esplanade | N | S |  | UNIT | A | 0 | 4590.11 | 4590.11 | 4590.11 | 4590.11 | 133.6985 | 0 | 0 | 0 | -1156.93 | Y | 3433.18 | Y | -3433.18 | 0 | 0 | 0 | 0 | 0 | 3433.18 | Y | -3433.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3433.18 | 387.4 | 393.16 | 3433.18 | 0 | 0 | 0 | 0 | 387.4 | 0 | -3433.18 | 0 | 0 | 3433.18 | 3433.18 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 34.5 | -22.5 | 12 | NA | 11901 | 8681.32 | 5339.68 | 14021 | CY | 4590.11 | 0 | 4590.11 | -1156.93
Y | IPCRP1-0354-1020-C | IPCRP1 | IPCRP1 | 0354-1020 | Furn formwork for Esplanade | N | C |  | NR | P | 1140239 | 599040.57 | 599040.57 | 599040.57 | 599040.57 | 54.9458 | 0 | 0 | 0 | 491198.43 | Y | 1090239 | Y | 50000 | 0 | 0 | 1140239 | 0 | 0 | 1090239 | Y | 50000 | 0 | 0 | 1140239 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1090239 | 0 | 0 | 1090239 | 0 | 0 | 0 | 0 | 2068.63 | 0 | -1090239 | 0 | 0 | 1090239 | 1090239 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 374322.53 | 274525.4 | 648847.93 | LS | 246353 | 94354.46 | 51145.54 | 145500 | SF | 592925.29 | -742.3 | 593667.59 | 491198.43
Y | IPCRP1-0354-1020-L | IPCRP1 | IPCRP1 | 0354-1020 | Furn formwork for Esplanade | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 246353 | 94354.46 | 51145.54 | 145500 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0354-1020-M | IPCRP1 | IPCRP1 | 0354-1020 | Furn formwork for Esplanade | N | M |  | UNIT | U | 50000 | 92640.67 | 92640.67 | 92640.67 | 92640.67 | 98.1053 | 0 | 0 | 0 | 1789.12 | Y | 94429.79 | Y | -44429.79 | 0 | 0 | 50000 | 0 | 0 | 94429.79 | Y | -44429.79 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -94429.79 | 0 | 0 | 94429.79 | 0 | 0 | 0 | 0 | 0 | 0 | -94429.79 | 0 | 0 | 94429.79 | 94429.79 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 1190 | -890 | 300 | LS | 246353 | 94354.46 | 51145.54 | 145500 | SF | 83542.74 | -9097.93 | 92640.67 | 1789.12 | needs to be removed - TRIBORO CONTRACTORS SUPPLY CO - IPCRP1-1607-1
Y | IPCRP1-0354-1022-C | IPCRP1 | IPCRP1 | 0354-1022 | Furnish Steel Deck Work Platforms for Combi-Wall S | N | C |  | UNIT | U | 0 | 605793.95 | 605793.95 | 605793.95 | 605793.95 | 100 | 0 | 0 | 0 | 0 | Y | 605793.95 | Y | -605793.95 | 0 | 0 | 0 | 0 | 0 | 605793.95 | Y | -605793.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -605793.95 | 0 | 0 | 605793.95 | 0 | 0 | 0 | 0 | 0 | 0 | -605793.95 | 0 | 0 | 605793.95 | 605793.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8888 | -8888 | 0 | NA | 0 | 0.9 | 0.1 | 1 | LS | 602338.15 | -3455.8 | 605793.95 | 0
Y | IPCRP1-0354-1022-L | IPCRP1 | IPCRP1 | 0354-1022 | Furnish Steel Deck Work Platforms for Combi-Wall S | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0.9 | 0.1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0354-1022-S | IPCRP1 | IPCRP1 | 0354-1022 | Furnish Steel Deck Work Platforms for Combi-Wall S | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | Y | 8000 | Y | -8000 | 0 | 0 | 0 | 0 | 0 | 8000 | Y | -8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | -8000 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0.9 | 0.1 | 1 | LS | 0 | 0 | 0 | 8000
Y | IPCRP1-0354-1024-L | IPCRP1 | IPCRP1 | 0354-1024 | Install & Remove Steel Deck Work Platforms for Com | N | L |  | UNIT | P | 0 | 159785.14 | 159785.14 | 159785.14 | 159785.14 | 79.7185 | 0 | 0 | 0 | 40651.58 | Y | 200436.72 | Y | -200436.72 | 0 | 0 | 0 | 0 | 0 | 200436.72 | Y | -200436.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200436.72 | 587.58 | 0 | 200436.72 | 0 | 0 | 0 | 0 | 0 | 0 | -200436.72 | 0 | 0 | 200436.72 | 200436.72 | 0 | 0 | 0 | 0 | 0 | 1432.51 | 1432.51 | 0 | 1150.5 | 282.01 | 1432.51 | HR | 0 | 70.5 | 9.5 | 80 | EA | 0 | 0 | 0 | 40651.58 | 2 per day set, 2 per day remove
Y | IPCRP1-0354-1024-S | IPCRP1 | IPCRP1 | 0354-1024 | Install & Remove Steel Deck Work Platforms for Com | N | S |  | UNIT | A | 0 | 2027.39 | 2027.39 | 2027.39 | 2027.39 | 100 | 0 | 0 | 0 | 0 | Y | 2027.39 | Y | -2027.39 | 0 | 0 | 0 | 0 | 0 | 2027.39 | Y | -2027.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2027.39 | 0 | 0 | 2027.39 | 0 | 0 | 0 | 0 | 0 | 0 | -2027.39 | 0 | 0 | 2027.39 | 2027.39 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 16.5 | -12.5 | 4 | NA | 0 | 70.5 | 9.5 | 80 | EA | 2027.39 | 0 | 2027.39 | 0
Y | IPCRP1-0354-1030-C | IPCRP1 | IPCRP1 | 0354-1030 | Esplanade via Marine Sub, Formwork (Non-VECP) | N | C |  | UNIT | U | 0 | 5552.54 | 5552.54 | 5328.98 | 5552.54 | 26.6449 | 0 | 0 | 0 | 14447.46 | Y | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | -447 | 0 | NA | 8659 | 6691.22 | 2227.07 | 8918.29 | SF | 5552.54 | 223.56 | 5328.98 | 14447.46
Y | IPCRP1-0354-1030-E | IPCRP1 | IPCRP1 | 0354-1030 | Esplanade via Marine Sub, Formwork (Non-VECP) | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 8659 | 6691.22 | 2227.07 | 8918.29 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0354-1030-L | IPCRP1 | IPCRP1 | 0354-1030 | Esplanade via Marine Sub, Formwork (Non-VECP) | N | L |  | UNIT | P | 0 | 435909.82 | 435909.82 | 435909.82 | 435909.82 | 86.129 | 0 | 0 | 0 | 70203.16 | Y | 506112.98 | Y | -506112.98 | 0 | 0 | 0 | 0 | 0 | 506112.98 | Y | -506112.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -506112.98 | 0 | 0 | 506112.98 | 0 | 0 | 0 | 0 | 0 | 0 | -506112.98 | 0 | 0 | 506112.98 | 506112.98 | 0 | 0 | 0 | 0 | 0 | 3968.82 | 3968.82 | 0 | 3450.5 | 518.32 | 3968.82 | HR | 8659 | 6691.22 | 2227.07 | 8918.29 | SF | 0 | 0 | 0 | 70203.16
Y | IPCRP1-0354-1030-M | IPCRP1 | IPCRP1 | 0354-1030 | Esplanade via Marine Sub, Formwork (Non-VECP) | N | M |  | UNIT | U | 0 | 397.5 | 397.5 | 397.5 | 397.5 | 100 | 0 | 0 | 0 | 0 | Y | 397.5 | Y | -397.5 | 0 | 0 | 0 | 0 | 0 | 397.5 | Y | -397.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -397.5 | 0 | 0 | 397.5 | 0 | 0 | 0 | 0 | 0 | 0 | -397.5 | 0 | 0 | 397.5 | 397.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -30 | 0 | NA | 8659 | 6691.22 | 2227.07 | 8918.29 | SF | 397.5 | 0 | 397.5 | 0
Y | IPCRP1-0354-1030-S | IPCRP1 | IPCRP1 | 0354-1030 | Esplanade via Marine Sub, Formwork (Non-VECP) | N | S |  | NR | A | 8453700.31 | 86724.53 | 86724.53 | 81349.53 | 86724.53 | 81.3495 | 0 | 0 | 0 | 13275.47 | Y | 100000 | Y | 8353700.31 | 0 | 0 | 8453700.31 | 0 | 0 | 100000 | Y | 8353700.31 | 0 | 0 | 8453700.31 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 37 | -37 | 0 | LS | 8659 | 6691.22 | 2227.07 | 8918.29 | SF | 86724.53 | 5375 | 81349.53 | 13275.47 | J. ANTHONY EQUIPMENT CO., INC. 1. See John Bo email 8/26 with updated quantities. 2. Sub is J Anthony Equipment.
Y | IPCRP1-0354-1031-C | IPCRP1 | IPCRP1 | 0354-1031 | Esplanade via Marine Sub, Conc Placement (Non-VEC | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 406.69 | 73.64 | 480.33 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0354-1031-L | IPCRP1 | IPCRP1 | 0354-1031 | Esplanade via Marine Sub, Conc Placement (Non-VEC | N | L |  | UNIT | P | 0 | 98529.84 | 98529.84 | 98529.84 | 98529.84 | 86.3531 | 0 | 0 | 0 | 15571.24 | Y | 114101.08 | Y | -114101.08 | 0 | 0 | 0 | 0 | 0 | 114101.08 | Y | -114101.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -114101.08 | -56.29 | 56.29 | 114101.08 | 0 | 0 | 0 | 0 | 0 | 0 | -114101.08 | 0 | 0 | 114101.08 | 114101.08 | 0 | 0 | 0 | 0 | 0 | 928.5 | 928.5 | 0 | 822 | 106.5 | 928.5 | HR | 0 | 406.69 | 73.64 | 480.33 | CY | 0 | 0 | 0 | 15571.24 | 1. See John Bo email 8/26 with updated quantities.
Y | IPCRP1-0354-1031-S | IPCRP1 | IPCRP1 | 0354-1031 | Esplanade via Marine Sub, Conc Placement (Non-VEC | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 406.69 | 73.64 | 480.33 | CY | 0 | 0 | 0 | 0 | 1. See John Bo email 8/26 with updated quantities.
Y | IPCRP1-0355-0000-L | IPCRP1 | IPCRP1 | 0355-0000 | CONC FOR FLOODWALL & GATES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0355-0000-R | IPCRP1 | IPCRP1 | 0355-0000 | CONC FOR FLOODWALL & GATES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5187000 | 0 | 0 | 5187000 | 0 | 5187000 | 2159001 | 0 | N | 5187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0355-1000-E | IPCRP1 | IPCRP1 | 0355-1000 | Install & strip formwork for FW & Gates | N | E |  | NR | P | 226815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 226815 | 0 | 0 | 226815 | 0 | 0 | 0 | Y | 226815 | 0 | 0 | 226815 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 45000 | 28913.68 | 23086.32 | 52000 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0355-1000-L | IPCRP1 | IPCRP1 | 0355-1000 | Install & strip formwork for FW & Gates | N | L |  | NR | P | 2303421.97 | 1276409.74 | 1276409.74 | 1276409.74 | 1276409.74 | 45.2216 | 0 | 0 | 0 | 1546157.53 | Y | 2822567.27 | Y | -519145.3 | 0 | 0 | 2303421.97 | 0 | 0 | 2822567.27 | Y | -519145.3 | 0 | 0 | 2303421.97 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2822567.27 | 99232.13 | 88475.73 | 2822567.27 | 0 | 0 | 0 | 0 | 0 | 0 | -2822567.27 | 0 | 0 | 2822567.27 | 2822567.27 | 0 | 0 | 0 | 14516.13 | 0 | 20800 | 20800 | 14516.13 | 9465.5 | 11334.5 | 20800 | HR | 45000 | 28913.68 | 23086.32 | 52000 | SF | 0 | 0 | 0 | 1546157.53 | see VS response 3/24/25 to Devin T takeoffs
Y | IPCRP1-0355-1000-S | IPCRP1 | IPCRP1 | 0355-1000 | Install & strip formwork for FW & Gates | N | S |  | UNIT | A | 0 | 15156.84 | 15156.84 | 15156.84 | 15156.84 | 122.3223 | 0 | 0 | 0 | 0 | N | 12390.91 | N | -12390.91 | 0 | 0 | 0 | 0 | 0 | 12390.91 | N | -12390.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12390.91 | 1033.08 | 917.37 | 12390.91 | 0 | 0 | 0 | 0 | 1033.08 | 0 | -12390.91 | 0 | 0 | 12390.91 | 12390.91 | 0 | 0 | 0 | 0 | 0 | 97.5 | 97.5 | 0 | 104 | -6.5 | 97.5 | NA | 45000 | 28913.68 | 23086.32 | 52000 | SF | 15156.84 | 0 | 15156.84 | 0
Y | IPCRP1-0355-1010-C | IPCRP1 | IPCRP1 | 0355-1010 | Place concrete for Floodwall & Gates | N | C |  | NR | P | 9553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9553 | N | 9553 | N | 0 | 0 | 0 | 9553 | 0 | 0 | 9553 | N | 0 | 0 | 0 | 9553 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9553 | 0 | 0 | 9553 | 0 | 0 | 0 | 0 | 0 | 0 | -9553 | 0 | 0 | 9553 | 9553 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 3463 | 1899.6 | 1512.4 | 3412 | CY | 0 | 0 | 0 | 9553
Y | IPCRP1-0355-1010-E | IPCRP1 | IPCRP1 | 0355-1010 | Place concrete for Floodwall & Gates | N | E |  | NR | P | 95412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 95412 | 0 | 0 | 95412 | 0 | 0 | 0 | Y | 95412 | 0 | 0 | 95412 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 3463 | 1899.6 | 1512.4 | 3412 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0355-1010-L | IPCRP1 | IPCRP1 | 0355-1010 | Place concrete for Floodwall & Gates | N | L |  | NR | P | 515032 | 323102.11 | 323102.11 | 323102.11 | 323102.11 | 47.4708 | 0 | 0 | 0 | 357531.41 | Y | 680633.52 | Y | -165601.52 | 0 | 0 | 515032 | 0 | 0 | 680633.52 | Y | -165601.52 | 0 | 0 | 515032 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -680633.52 | 31545.58 | 18513.77 | 680633.52 | 0 | 0 | 0 | 0 | 0 | 0 | -680633.52 | 0 | 0 | 680633.52 | 680633.52 | 0 | 0 | 0 | 3809.67 | 0 | 5118 | 5118 | 3809.67 | 2553 | 2565 | 5118 | HR | 3463 | 1899.6 | 1512.4 | 3412 | CY | 0 | 0 | 0 | 357531.41
Y | IPCRP1-0355-1010-S | IPCRP1 | IPCRP1 | 0355-1010 | Place concrete for Floodwall & Gates | N | S |  | UNIT | A | 0 | 2637.81 | 2637.81 | 2637.81 | 2637.81 | 136.3378 | 0 | 0 | 0 | 0 | N | 1934.76 | N | -1934.76 | 0 | 0 | 0 | 0 | 0 | 1934.76 | N | -1934.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1934.76 | 64.57 | 262.11 | 1934.76 | 0 | 0 | 0 | 0 | 64.57 | 0 | -1934.76 | 0 | 0 | 1934.76 | 1934.76 | 0 | 0 | 0 | 0 | 0 | 15.5 | 15.5 | 0 | 18.5 | -3 | 15.5 | NA | 3463 | 1899.6 | 1512.4 | 3412 | CY | 2637.81 | 0 | 2637.81 | 0
Y | IPCRP1-0355-1020-C | IPCRP1 | IPCRP1 | 0355-1020 | Furn formwork for Floodwall & Gates | N | C |  | NR | P | 146988 | 124219.11 | 124219.11 | 119556.44 | 124219.11 | 81.3376 | 0 | 0 | 0 | 22768.89 | N | 146988 | N | 0 | 0 | 0 | 146988 | 0 | 0 | 146988 | N | 0 | 0 | 0 | 146988 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -146988 | 0 | 12422.55 | 146988 | 0 | 0 | 0 | 20272.35 | 0 | 0 | -146988 | 0 | 0 | 146988 | 146988 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9703 | -9703 | 0 | LF | 45000 | 27717.08 | 24282.92 | 52000 | SF | 124173.38 | 4662.67 | 119510.71 | 22768.89
Y | IPCRP1-0355-1020-L | IPCRP1 | IPCRP1 | 0355-1020 | Furn formwork for Floodwall & Gates | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 45000 | 27717.08 | 24282.92 | 52000 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0355-1030-L | IPCRP1 | IPCRP1 | 0355-1030 | Set Embeds at Flood Wall Gates | N | L |  | UNIT | P | 0 | 59543.63 | 59543.63 | 59543.63 | 59543.63 | 44.8244 | 0 | 0 | 0 | 73293.77 | Y | 132837.4 | Y | -132837.4 | 0 | 0 | 0 | 0 | 0 | 132837.4 | Y | -132837.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -132837.4 | 0 | 0 | 132837.4 | 0 | 0 | 0 | 0 | 0 | 0 | -132837.4 | 0 | 0 | 132837.4 | 132837.4 | 0 | 0 | 0 | 0 | 0 | 984 | 984 | 0 | 443 | 541 | 984 | HR | 0 | 43 | 39 | 82 | EA | 0 | 0 | 0 | 73293.77 | PMF (Quan): 36ea (Montg St FG), 28ea (E14t FG) = 64ea. See Gent email dated 9/13/24.
Y | IPCRP1-0355-1040-C | IPCRP1 | IPCRP1 | 0355-1040 | Embed Material for Conc Floodwall & Gates | N | C |  | UNIT | U | 0 | 1837.27 | 1837.27 | 1687.5 | 1837.27 | 33.75 | 0 | 0 | 0 | 3162.73 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 1687.5 | 5000 | 0 | 0 | 0 | 0 | 1837.27 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | -5 | 0 | NA | 0 | 0.9 | 0.1 | 1 | LS | 1837.27 | 149.77 | 1687.5 | 3162.73
Y | IPCRP1-0355-1040-L | IPCRP1 | IPCRP1 | 0355-1040 | Embed Material for Conc Floodwall & Gates | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0.9 | 0.1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0355-1040-M | IPCRP1 | IPCRP1 | 0355-1040 | Embed Material for Conc Floodwall & Gates | N | M |  | UNIT | U | 0 | 28246.2 | 28246.2 | 28246.2 | 28246.2 | 94.154 | 0 | 0 | 0 | 1753.8 | Y | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -3 | 0 | NA | 0 | 0.9 | 0.1 | 1 | LS | 28246.2 | 0 | 28246.2 | 1753.8
Y | IPCRP1-0355-1050-L | IPCRP1 | IPCRP1 | 0355-1050 | Torch Cut Exp Jt in FW Sheet (App 20ft/Loc) | N | L |  | UNIT | P | 0 | 5815.31 | 5815.31 | 5815.31 | 5815.31 | 31.5789 | 0 | 0 | 0 | 12599.84 | N | 18415.15 | N | -18415.15 | 0 | 0 | 0 | 0 | 0 | 18415.15 | N | -18415.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18415.15 | 0 | 0 | 18415.15 | 0 | 0 | 0 | 0 | 0 | 0 | -18415.15 | 0 | 0 | 18415.15 | 18415.15 | 0 | 0 | 0 | 0 | 0 | 136.17 | 136.17 | 0 | 43 | 93.17 | 136.17 | HR | 0 | 12 | 26 | 38 | EA | 0 | 0 | 0 | 12599.84 | 2. As / DT (9/26) QTD = 12.0ea takeoff is 38 EA, 2.5 MH per (2 dockies for an hour, 1 OE for half hour), 95 hours total, inclusive of burning, firewatch, and disposal. Devin Taylor Friday, February 28, 2025 2.59 PM
Y | IPCRP1-0356-0000-L | IPCRP1 | IPCRP1 | 0356-0000 | CONC PARK FEATURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0356-0000-R | IPCRP1 | IPCRP1 | 0356-0000 | CONC PARK FEATURES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 14026000 | 0 | 0 | 14026000 | 0 | 14026000 | 7296040 | 0 | N | 14026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0356-1000-E | IPCRP1 | IPCRP1 | 0356-1000 | Install & strip formwork for Conc Park Features | N | E |  | NR | P | 391573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 391573 | 0 | 0 | 391573 | 0 | 0 | 0 | N | 391573 | 0 | 0 | 391573 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 105067 | 114972.23 | 118410.77 | 233383 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0356-1000-L | IPCRP1 | IPCRP1 | 0356-1000 | Install & strip formwork for Conc Park Features | N | L |  | NR | P | 4188854 | 3632099.52 | 3632099.52 | 3632099.52 | 3632099.52 | 48.63 | 0 | 0 | 0 | 3836746.54 | Y | 7468846.06 | Y | -3279992.06 | 0 | 0 | 4188854 | 0 | 0 | 7468846.06 | Y | -3279992.06 | 0 | 0 | 4188854 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7468846.06 | 52342.06 | 17473.56 | 7468846.06 | 0 | 0 | 0 | 0 | 0 | 0 | -7468846.06 | 0 | 0 | 7468846.06 | 7468846.06 | 0 | 0 | 0 | 35653.16 | 0 | 58350 | 58350 | 35653.16 | 28651.5 | 29698.5 | 58350 | HR | 105067 | 114972.23 | 118410.77 | 233383 | SF | 0 | 0 | 0 | 3836746.54 | Refer to Winston takeoff provided on 11/11/25 Refer to Gent email (9/18/24) with revised takeoff quantities. JPaget and FR are working on a new take-off as per conversation in September 2024. Devin and Franklin are working on a new take-off (January 2025).
Y | IPCRP1-0356-1000-S | IPCRP1 | IPCRP1 | 0356-1000 | Install & strip formwork for Conc Park Features | N | S |  | UNIT | A | 0 | 46608.44 | 46608.44 | 46608.44 | 46608.44 | 103.1351 | 0 | 0 | 0 | -1416.81 | Y | 45191.63 | Y | -45191.63 | 0 | 0 | 0 | 0 | 0 | 45191.63 | Y | -45191.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45191.63 | 1291.35 | 0 | 45191.63 | 0 | 0 | 0 | 0 | 1291.35 | 0 | -45191.63 | 0 | 0 | 45191.63 | 45191.63 | 0 | 0 | 0 | 0 | 0 | 326.5 | 326.5 | 0 | 360.5 | -34 | 326.5 | NA | 105067 | 114972.23 | 118410.77 | 233383 | SF | 46608.44 | 0 | 46608.44 | -1416.81
Y | IPCRP1-0356-1010-E | IPCRP1 | IPCRP1 | 0356-1010 | Place concrete for Conc Park Features | N | E |  | NR | P | 191188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 191188 | 0 | 0 | 191188 | 0 | 0 | 0 | N | 191188 | 0 | 0 | 191188 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 7013 | 3720.17 | 3109.83 | 6830 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0356-1010-L | IPCRP1 | IPCRP1 | 0356-1010 | Place concrete for Conc Park Features | N | L |  | NR | P | 822611 | 960552.45 | 960552.45 | 960552.45 | 960552.45 | 58.598 | 0 | 0 | 0 | 678672.23 | Y | 1639224.68 | Y | -816613.68 | 0 | 0 | 822611 | 0 | 0 | 1639224.68 | Y | -816613.68 | 0 | 0 | 822611 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1639224.68 | 16121.54 | 10043.57 | 1639224.68 | 0 | 0 | 0 | 0 | 0 | 0 | -1639224.68 | 0 | 0 | 1639224.68 | 1639224.68 | 0 | 0 | 0 | 7633.15 | 0 | 13660 | 13660 | 7633.15 | 8174.5 | 5485.5 | 13660 | HR | 7013 | 3720.17 | 3109.83 | 6830 | CY | 0 | 0 | 0 | 678672.23 | Refer to Winston takeoff provided on 11/11/25 Refer to Gent email (9/18/24) with revised takeoff quantities. John P requested Franklin R to initiate a fresh take-off for this specific scope of work. (October 2024).
Y | IPCRP1-0356-1010-S | IPCRP1 | IPCRP1 | 0356-1010 | Place concrete for Conc Park Features | N | S |  | UNIT | A | 0 | 62734.63 | 62734.63 | 58645.63 | 62734.63 | 93.8683 | 0 | 0 | 0 | 0 | N | 62476.51 | N | -62476.51 | 0 | 0 | 0 | 0 | 0 | 62476.51 | N | -62476.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -62476.51 | 0 | 131.05 | 62476.51 | 0 | 0 | 0 | 0 | 0 | 0 | -62476.51 | 0 | 0 | 62476.51 | 62476.51 | 0 | 0 | 0 | 0 | 0 | 76.5 | 76.5 | 0 | 74.68 | 1.82 | 76.5 | NA | 7013 | 3720.17 | 3109.83 | 6830 | CY | 62734.63 | 4089 | 58645.63 | 0
Y | IPCRP1-0356-1020-C | IPCRP1 | IPCRP1 | 0356-1020 | CM - formwork for Conc Park Features | N | C |  | NR | P | 343191 | 615085.04 | 615085.04 | 500140 | 615085.04 | 44.7997 | 0 | 0 | 0 | 501305.96 | Y | 1116391 | Y | -773200 | 0 | 0 | 343191 | 0 | 0 | 1116391 | Y | -773200 | 0 | 0 | 343191 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1116391 | 0 | 9903.25 | 1116391 | 0 | 0 | 0 | 7050.72 | 37529.85 | 0 | -1116391 | 0 | 0 | 1116391 | 1116391 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 91843.07 | 158036.39 | 249879.46 | LF | 105067 | 113349.03 | 120033.97 | 233383 | SF | 615085.04 | 114945.04 | 500140 | 501305.96
Y | IPCRP1-0356-1020-L | IPCRP1 | IPCRP1 | 0356-1020 | CM - formwork for Conc Park Features | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 105067 | 113349.03 | 120033.97 | 233383 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0357-0000-L | IPCRP1 | IPCRP1 | 0357-0000 | CONC UTIL X-ING & GATE SEEPAGE WALL CLOSURE POURS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0357-0000-R | IPCRP1 | IPCRP1 | 0357-0000 | CONC UTIL X-ING & GATE SEEPAGE WALL CLOSURE POURS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 357000 | 0 | 0 | 357000 | 0 | 357000 | 282210 | 0 | N | 357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0357-1000-E | IPCRP1 | IPCRP1 | 0357-1000 | Install & strip formwork Util X-ings & GS Wall Cl | N | E |  | NR | P | 17447.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 17447.5 | 0 | 0 | 17447.5 | 0 | 0 | 0 | Y | 17447.5 | 0 | 0 | 17447.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 3350 | 2937.71 | 412.29 | 3350 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0357-1000-L | IPCRP1 | IPCRP1 | 0357-1000 | Install & strip formwork Util X-ings & GS Wall Cl | N | L |  | NR | P | 134145.26 | 94058.52 | 94058.52 | 94058.52 | 94058.52 | 70.1169 | 0 | 0 | 0 | 40086.74 | N | 134145.26 | N | 0 | 0 | 0 | 134145.26 | 0 | 0 | 134145.26 | N | 0 | 0 | 0 | 134145.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -134145.26 | 0 | 0 | 134145.26 | 0 | 0 | 0 | 0 | 0 | 0 | -134145.26 | 0 | 0 | 134145.26 | 134145.26 | 0 | 0 | 0 | 1116.66 | 0 | 1116.66 | 1116.66 | 1116.66 | 721.5 | 395.16 | 1116.66 | HR | 3350 | 2937.71 | 412.29 | 3350 | SF | 0 | 0 | 0 | 40086.74
Y | IPCRP1-0357-1000-S | IPCRP1 | IPCRP1 | 0357-1000 | Install & strip formwork Util X-ings & GS Wall Cl | N | S |  | UNIT | A | 0 | 6362.36 | 6362.36 | 6362.36 | 6362.36 | 100 | 0 | 0 | 0 | 0 | N | 6362.36 | N | -6362.36 | 0 | 0 | 0 | 0 | 0 | 6362.36 | N | -6362.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6362.36 | 0 | 0 | 6362.36 | 0 | 0 | 0 | 0 | 0 | 0 | -6362.36 | 0 | 0 | 6362.36 | 6362.36 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 0 | 54 | 0 | 54 | NA | 3350 | 2937.71 | 412.29 | 3350 | SF | 6362.36 | 0 | 6362.36 | 0
Y | IPCRP1-0357-1010-E | IPCRP1 | IPCRP1 | 0357-1010 | Place conc for Util X-ings & GS Wall Closures | N | E |  | NR | P | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | Y | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 238 | 431.49 | 0 | 431.49 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0357-1010-L | IPCRP1 | IPCRP1 | 0357-1010 | Place conc for Util X-ings & GS Wall Closures | N | L |  | NR | P | 46285.68 | 39960.51 | 39960.51 | 39960.51 | 39960.51 | 86.3345 | 0 | 0 | 0 | 6325.17 | N | 46285.68 | N | 0 | 0 | 0 | 46285.68 | 0 | 0 | 46285.68 | N | 0 | 0 | 0 | 46285.68 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -46285.68 | 0 | 0 | 46285.68 | 0 | 0 | 0 | 0 | 0 | 0 | -46285.68 | 0 | 0 | 46285.68 | 46285.68 | 0 | 0 | 0 | 432 | 0 | 432 | 432 | 432 | 298.5 | 133.5 | 432 | HR | 238 | 431.49 | 0 | 431.49 | CY | 0 | 0 | 0 | 6325.17
Y | IPCRP1-0357-1020-C | IPCRP1 | IPCRP1 | 0357-1020 | Furn formwork for Util X-ings & GS Wall Closures | N | C |  | NR | P | 10942.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10942.44 | N | 10942.44 | N | 0 | 0 | 0 | 10942.44 | 0 | 0 | 10942.44 | N | 0 | 0 | 0 | 10942.44 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10942.44 | 0 | 0 | 10942.44 | 0 | 0 | 0 | 0 | 0 | 0 | -10942.44 | 0 | 0 | 10942.44 | 10942.44 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 3350 | 2937.71 | 412.29 | 3350 | SF | 0 | 0 | 0 | 10942.44
Y | IPCRP1-0357-1020-L | IPCRP1 | IPCRP1 | 0357-1020 | Furn formwork for Util X-ings & GS Wall Closures | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3350 | 2937.71 | 412.29 | 3350 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0358-0000-L | IPCRP1 | IPCRP1 | 0358-0000 | EARTH EXCAV FOR STRUCTURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0358-0000-R | IPCRP1 | IPCRP1 | 0358-0000 | EARTH EXCAV FOR STRUCTURES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 555250 | 0 | 0 | 555250 | 0 | 555250 | 371751.25 | 0 | N | 555250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0358-1000-E | IPCRP1 | IPCRP1 | 0358-1000 | EARTH EXCAV FOR STRUCTURES | N | E |  | NR | P | 10153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 10153 | 0 | 0 | 10153 | 0 | 0 | 0 | Y | 10153 | 0 | 0 | 10153 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 4442 | 3588.93 | 853.07 | 4442 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0358-1000-L | IPCRP1 | IPCRP1 | 0358-1000 | EARTH EXCAV FOR STRUCTURES | N | L |  | NR | P | 55564.06 | 749502.88 | 749502.88 | 749502.88 | 749502.88 | 82.0025 | 0 | 0 | 0 | 164497.12 | Y | 914000 | Y | -858435.94 | 0 | 0 | 55564.06 | 0 | 0 | 914000 | Y | -858435.94 | 0 | 0 | 55564.06 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -914000 | 18999.81 | 13647.66 | 914000 | 0 | 0 | 0 | 0 | 0 | 0 | -914000 | 0 | 0 | 914000 | 914000 | 0 | 0 | 0 | 507.66 | 0 | 7150.97 | 7150.97 | 507.66 | 5898.5 | 1252.47 | 7150.97 | HR | 4442 | 3588.93 | 853.07 | 4442 | CY | 0 | 0 | 0 | 164497.12 | Change PMF (MH) from 507.66 to 1,330, Change PMF (Labor) from $55,564.06 to $150,000.00
Y | IPCRP1-0358-1000-S | IPCRP1 | IPCRP1 | 0358-1000 | EARTH EXCAV FOR STRUCTURES | N | S |  | UNIT | A | 0 | 111158.49 | 111158.49 | 111158.49 | 111158.49 | 100 | 0 | 0 | 0 | 0 | Y | 111158.49 | Y | -111158.49 | 0 | 0 | 0 | 0 | 0 | 111158.49 | Y | -111158.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -111158.49 | 8910.29 | 6159.51 | 111158.49 | 0 | 0 | 0 | 0 | 8910.29 | 0 | -111158.49 | 0 | 0 | 111158.49 | 111158.49 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 770.5 | -756.5 | 14 | NA | 4442 | 3588.93 | 853.07 | 4442 | CY | 111158.49 | 0 | 111158.49 | 0
Y | IPCRP1-0359-0000-L | IPCRP1 | IPCRP1 | 0359-0000 | FILL, PLACE MEASUREMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0359-0000-R | IPCRP1 | IPCRP1 | 0359-0000 | FILL, PLACE MEASUREMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6868130 | 0 | 0 | 6868130 | 0 | 6868130 | 1927123 | 0 | N | 6868130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6868130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0359-1000-E | IPCRP1 | IPCRP1 | 0359-1000 | Handle & Install CA Fill | N | E |  | NR | P | 4208000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 4208000 | 0 | 0 | 4208000 | 0 | 0 | 0 | N | 4208000 | 0 | 0 | 4208000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 400000 | 192712.13 | 377287.87 | 570000 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0359-1000-L | IPCRP1 | IPCRP1 | 0359-1000 | Handle & Install CA Fill | N | L |  | NR | P | 5586652 | 2780995.42 | 2780995.42 | 2780995.42 | 2780995.42 | 33.4776 | 0 | 0 | 0 | 5526048.38 | Y | 8307043.8 | Y | -2720391.8 | 0 | 0 | 5586652 | 0 | 0 | 8307043.8 | Y | -2720391.8 | 0 | 0 | 5586652 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8307043.8 | 5214.64 | 0 | 8307043.8 | 0 | 0 | 0 | 0 | 0 | 0 | -8307043.8 | 0 | 0 | 8307043.8 | 8307043.8 | 0 | 0 | 0 | 49600 | 0 | 62900 | 62900 | 49600 | 21088.5 | 41811.5 | 62900 | HR | 400000 | 192712.13 | 377287.87 | 570000 | CY | 0 | 0 | 0 | 5526048.38 | 1. Increased PMF from bid takoff quantity underrun to field producted takeoff quantity (which matches bid estimated quantity). 3. DDC QTD thru Aug 2025 = 184,957.03cy. Chagne PMF (Quantity) from 400,000.00 to 570,000.00, Change PMF (MH) from 49,600.00 to $51,300.00
Y | IPCRP1-0359-1000-S | IPCRP1 | IPCRP1 | 0359-1000 | Handle & Install CA Fill | N | S |  | UNIT | A | 0 | 523090.95 | 523090.95 | 441209.12 | 523090.95 | 29.7712 | 0 | 0 | 0 | 958909.05 | Y | 1482000 | Y | -1482000 | 0 | 0 | 0 | 0 | 0 | 1482000 | Y | -1482000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1482000 | 387.4 | 262.11 | 1482000 | 0 | 0 | 0 | 0 | 0 | 0 | -1482000 | 0 | 0 | 1482000 | 1482000 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 219418.66 | -219393.66 | 25 | NA | 400000 | 192712.13 | 377287.87 | 570000 | CY | 523090.95 | 81881.83 | 441209.12 | 958909.05 | 1. Increased PMF from bid takoff quantity underrun to field producted takeoff quantity (which matches bid estimated quantity). 2. Assumed overall production of 0.11 MH/CY, with 0.09MH to Labor, and 0.02MH to Sub via KMA Teamsters (1/19/2024). 3. DDC QTD thru Aug = 171,795.28 x 85% = 146,025.99cy 4. Refer to VS response 8/19 to GB analysis
Y | IPCRP1-0359-1010-E | IPCRP1 | IPCRP1 | 0359-1010 | Relocate CA Fill from Surcharge to Final Location | N | E |  | NR | P | 688600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 688600 | 0 | 0 | 688600 | 0 | 0 | 0 | Y | 688600 | 0 | 0 | 688600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 110000 | 435 | 0 | 435 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0359-1010-L | IPCRP1 | IPCRP1 | 0359-1010 | Relocate CA Fill from Surcharge to Final Location | N | L |  | NR | P | 1186753.7 | 21803.65 | 21803.65 | 21803.65 | 21803.65 | 100 | 0 | 0 | 0 | 0 | Y | 21803.65 | Y | 1164950.05 | 0 | 0 | 1186753.7 | 0 | 0 | 21803.65 | Y | 1164950.05 | 0 | 0 | 1186753.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21803.65 | 0 | 0 | 21803.65 | 0 | 0 | 0 | 0 | 0 | 0 | -21803.65 | 0 | 0 | 21803.65 | 21803.65 | 0 | 0 | 0 | 10120 | 0 | 166.5 | 166.5 | 10120 | 166.5 | 0 | 166.5 | HR | 110000 | 435 | 0 | 435 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0359-1010-S | IPCRP1 | IPCRP1 | 0359-1010 | Relocate CA Fill from Surcharge to Final Location | N | S |  | UNIT | A | 0 | 2001.57 | 2001.57 | 2001.57 | 2001.57 | 100 | 0 | 0 | 0 | 0 | N | 2001.57 | N | -2001.57 | 0 | 0 | 0 | 0 | 0 | 2001.57 | N | -2001.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2001.57 | 0 | 0 | 2001.57 | 0 | 0 | 0 | 0 | 0 | 0 | -2001.57 | 0 | 0 | 2001.57 | 2001.57 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 16 | 0 | 16 | NA | 110000 | 435 | 0 | 435 | CY | 2001.57 | 0 | 2001.57 | 0
Y | IPCRP1-0359-1020-E | IPCRP1 | IPCRP1 | 0359-1020 | Load Out Excess CA Fill for Disposal | N | E |  | NR | P | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 80000 | 0 | 0 | 80000 | 0 | 0 | 0 | Y | 80000 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 50000 | 0 | 50000 | 50000 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0359-1020-L | IPCRP1 | IPCRP1 | 0359-1020 | Load Out Excess CA Fill for Disposal | N | L |  | NR | P | 147417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147417 | N | 147417 | N | 0 | 0 | 0 | 147417 | 0 | 0 | 147417 | N | 0 | 0 | 0 | 147417 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -147417 | 0 | 0 | 147417 | 0 | 0 | 0 | 0 | 0 | 0 | -147417 | 0 | 0 | 147417 | 147417 | 0 | 0 | 0 | 1200 | 0 | 1200 | 1200 | 1200 | 0 | 1200 | 1200 | HR | 50000 | 0 | 50000 | 50000 | CY | 0 | 0 | 0 | 147417
Y | IPCRP1-0360-0000-L | IPCRP1 | IPCRP1 | 0360-0000 | SELECT GRAN FILL, PLACE MEASURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0360-0000-R | IPCRP1 | IPCRP1 | 0360-0000 | SELECT GRAN FILL, PLACE MEASURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8000 | 0 | 0 | 8000 | 0 | 8000 | 0 | 0 | N | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0360-1000-E | IPCRP1 | IPCRP1 | 0360-1000 | Place Select Granular Fill | N | E |  | NR | P | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | Y | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 40 | 0 | 40 | 40 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0360-1000-L | IPCRP1 | IPCRP1 | 0360-1000 | Place Select Granular Fill | N | L |  | NR | P | 5083.7 | -7.26 | -7.26 | -7.26 | -7.26 | -0.10828 | 0 | 0 | 0 | 6711.9 | N | 6704.64 | N | -1620.94 | 0 | 0 | 5083.7 | 0 | 0 | 6704.64 | N | -1620.94 | 0 | 0 | 5083.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6704.64 | 0 | 0 | 6704.64 | 0 | 0 | 0 | 0 | 0 | 0 | -6704.64 | 0 | 0 | 6704.64 | 6704.64 | 0 | 0 | 0 | 48 | 0 | 64 | 64 | 48 | 0 | 64 | 64 | HR | 40 | 0 | 40 | 40 | CY | 0 | 0 | 0 | 6711.9 | 34 MH do not belong here, should have been removed. (As per Vinny''s email on 3/11/22)
Y | IPCRP1-0361-0000-L | IPCRP1 | IPCRP1 | 0361-0000 | CRUSHED STONE FILL, L-WALL DRAINAGE, PLACE MEASUR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0361-0000-R | IPCRP1 | IPCRP1 | 0361-0000 | CRUSHED STONE FILL, L-WALL DRAINAGE, PLACE MEASUR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 45000 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | N | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0361-1000-E | IPCRP1 | IPCRP1 | 0361-1000 | Place Crushed Stone Fill for L Wall Drainage | N | E |  | NR | P | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3600 | 0 | 0 | 3600 | 0 | 0 | 0 | Y | 3600 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 225 | 0 | 225 | 225 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0361-1000-L | IPCRP1 | IPCRP1 | 0361-1000 | Place Crushed Stone Fill for L Wall Drainage | N | L |  | NR | P | 12266.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12266.4 | N | 12266.4 | N | 0 | 0 | 0 | 12266.4 | 0 | 0 | 12266.4 | N | 0 | 0 | 0 | 12266.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12266.4 | 0 | 0 | 12266.4 | 0 | 0 | 0 | 0 | 0 | 0 | -12266.4 | 0 | 0 | 12266.4 | 12266.4 | 0 | 0 | 0 | 112 | 0 | 112 | 112 | 112 | 0 | 112 | 112 | HR | 225 | 0 | 225 | 225 | CY | 0 | 0 | 0 | 12266.4
Y | IPCRP1-0362-0000-L | IPCRP1 | IPCRP1 | 0362-0000 | LIGHTWEIGHT FILL, PLACE MEASUREMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0362-0000-R | IPCRP1 | IPCRP1 | 0362-0000 | LIGHTWEIGHT FILL, PLACE MEASUREMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13347000 | 0 | 0 | 13347000 | 0 | 13347000 | 9049662 | 0 | N | 13347000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13347000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0362-1000-E | IPCRP1 | IPCRP1 | 0362-1000 | Place Lightweight Fill | N | E |  | NR | P | 989457.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 989457.6 | 0 | 0 | 989457.6 | 0 | 0 | 0 | Y | 989457.6 | 0 | 0 | 989457.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 88980 | 60331.08 | 43668.92 | 104000 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0362-1000-L | IPCRP1 | IPCRP1 | 0362-1000 | Place Lightweight Fill | N | L |  | NR | P | 1242750.73 | 799396.11 | 799396.11 | 799396.11 | 799396.11 | 53.8358 | 0 | 0 | 0 | 685480.96 | Y | 1484877.07 | Y | -242126.34 | 0 | 0 | 1242750.73 | 0 | 0 | 1484877.07 | Y | -242126.34 | 0 | 0 | 1242750.73 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1484877.07 | 23933.82 | 1105.27 | 1484877.07 | 0 | 0 | 0 | 0 | 0 | 0 | -1484877.07 | 0 | 0 | 1484877.07 | 1484877.07 | 0 | 0 | 0 | 11033.52 | 0 | 11440 | 11440 | 11033.52 | 6236.5 | 5203.5 | 11440 | HR | 88980 | 60331.08 | 43668.92 | 104000 | CY | 0 | 0 | 0 | 685480.96 | 1. CTD Quantity matches PTD Quantity from DDC. We believe this to be extremely low. Our drone survey yields a significantly higher value, but VS does not have confidence in this quantity either. Suggest for GB to sit with Team, & then PMCM to resolve. Suggest pay 85% of ticket value until resolved.
Y | IPCRP1-0362-1000-S | IPCRP1 | IPCRP1 | 0362-1000 | Place Lightweight Fill | N | S |  | UNIT | A | 0 | 78861.93 | 78861.93 | 78861.93 | 78861.93 | 105.0757 | 0 | 0 | 0 | -3809.47 | Y | 75052.46 | Y | -75052.46 | 0 | 0 | 0 | 0 | 0 | 75052.46 | Y | -75052.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -75052.46 | 3809.47 | 0 | 75052.46 | 0 | 0 | 0 | 0 | 3809.47 | 0 | -75052.46 | 0 | 0 | 75052.46 | 75052.46 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 639 | -631 | 8 | NA | 88980 | 60331.08 | 43668.92 | 104000 | CY | 78861.93 | 0 | 78861.93 | -3809.47 | 3. thru Oct 24, DDC has paid 85% x barge ticket quantity = 85% (45,089.36) = 38,325.96cy. Need to speak w DDC to rectify 15% release. 2. Refer to VS response 8/19 to GB analysis.
Y | IPCRP1-0362-1010-L | IPCRP1 | IPCRP1 | 0362-1010 | PM - Lightweight Fill | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 88980 | 60331.08 | 43668.92 | 104000 | CY | 0 | 0 | 0 | 0 | CTD Quantity = 1.15% x Install CTD Quantity, until all is resolved. Stored LW Material at Green Asphalt & trucked over ($117,040.63). (re-entered on 1/12/2024) CARVER SAND & GRAVEL, LLC@$995,661.88, GREEN ASPHALT CO LLC@$117,040.63, NORLITE, LLC@$5,175,000.00, COEYMANS MARINE TOWING LLC@$488,750.00, PORT OF COEYMANS@$787,982.81
Y | IPCRP1-0362-1010-M | IPCRP1 | IPCRP1 | 0362-1010 | PM - Lightweight Fill | N | M |  | NR | P | 4671450 | 10067389.35 | 10067389.35 | 6231766.74 | 10067389.35 | 61.8933 | 0 | 0 | 0 | 1169.49 | Y | 10068558.84 | Y | -5397108.84 | 0 | 0 | 4671450 | 0 | 0 | 10068558.84 | Y | -5397108.84 | 0 | 0 | 4671450 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10068558.84 | 0 | 0 | 10068558.84 | 0 | 0 | 0 | 0 | 0 | 0 | -10068558.84 | 0 | 0 | 10068558.84 | 10068558.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 283366.65 | -2 | 283364.65 | CY | 88980 | 60331.08 | 43668.92 | 104000 | CY | 10069695.85 | 3835622.61 | 6234073.24 | 1169.49 | Stored LW Material at Green Asphalt & trucked over ($117,040.63). 3. Make PMF, 900K less than Commitment to account for duplicate commitment on Mat until we exhaust remaining Norlite material on ground Stored LW Material at Green Asphalt & trucked over ($117,040.63). (re-entered on 1/12/2024). deleted note - Soil Solutions
Y | IPCRP1-0363-0000-L | IPCRP1 | IPCRP1 | 0363-0000 | MONITOR SETTLEMENT, 3 MO, EAST RIVER PARK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0363-0000-R | IPCRP1 | IPCRP1 | 0363-0000 | MONITOR SETTLEMENT, 3 MO, EAST RIVER PARK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 500000 | 0 | 0 | 500000 | 0 | 500000 | 378750 | 0 | N | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0364-0000-L | IPCRP1 | IPCRP1 | 0364-0000 | EXCAV FILL ON & BEHIND ESPLANADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0364-0000-R | IPCRP1 | IPCRP1 | 0364-0000 | EXCAV FILL ON & BEHIND ESPLANADE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6279000 | 0 | 0 | 6279000 | 0 | 6279000 | 5629082.5 | 0 | N | 6279000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6279000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0364-1000-E | IPCRP1 | IPCRP1 | 0364-1000 | Excavate Fill On & Behind Esplanade | N | E |  | NR | P | 120556.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 120556.5 | 0 | 0 | 120556.5 | 0 | 0 | 0 | Y | 120556.5 | 0 | 0 | 120556.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 50232 | 46686.74 | 5738.92 | 52425.66 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0364-1000-L | IPCRP1 | IPCRP1 | 0364-1000 | Excavate Fill On & Behind Esplanade | N | L |  | NR | P | 699232.73 | 1115868.78 | 1115868.78 | 1115868.78 | 1115868.78 | 95.356 | 0 | 0 | 0 | 54344.69 | Y | 1170213.47 | Y | -470980.74 | 0 | 0 | 699232.73 | 0 | 0 | 1170213.47 | Y | -470980.74 | 0 | 0 | 699232.73 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1170213.47 | 8898.81 | 26349.1 | 1170213.47 | 0 | 0 | 0 | 0 | 0 | 0 | -1170213.47 | 0 | 0 | 1170213.47 | 1170213.47 | 0 | 0 | 0 | 6429.69 | 0 | 9247.56 | 9247.56 | 6429.69 | 8851.5 | 396.06 | 9247.56 | HR | 50232 | 46686.74 | 5738.92 | 52425.66 | CY | 0 | 0 | 0 | 54344.69 | Thru 9/30 DDC & IPC quantities match = 41,556.30 as per Andrew note last month.
Y | IPCRP1-0364-1000-S | IPCRP1 | IPCRP1 | 0364-1000 | Excavate Fill On & Behind Esplanade | N | S |  | UNIT | A | 0 | 173590.74 | 173590.74 | 173590.74 | 173590.74 | 102.6367 | 0 | 0 | 0 | -4459.53 | Y | 169131.21 | Y | -169131.21 | 0 | 0 | 0 | 0 | 0 | 169131.21 | Y | -169131.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -169131.21 | 1226.78 | 786.32 | 169131.21 | 0 | 0 | 0 | 0 | 1226.78 | 0 | -169131.21 | 0 | 0 | 169131.21 | 169131.21 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | 0 | 1421.5 | -1333.5 | 88 | NA | 50232 | 46686.74 | 5738.92 | 52425.66 | CY | 173590.74 | 0 | 173590.74 | -4459.53
Y | IPCRP1-0365-0000-L | IPCRP1 | IPCRP1 | 0365-0000 | EXCAV RIP RAP & MISC FILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0365-0000-R | IPCRP1 | IPCRP1 | 0365-0000 | EXCAV RIP RAP & MISC FILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 943950 | 0 | 0 | 943950 | 0 | 943950 | 247590 | 0 | N | 943950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 943950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0365-1000-L | IPCRP1 | IPCRP1 | 0365-1000 | Excavate Rip Rap & Misc Fill | N | L |  | UNIT | P | 0 | 21277.11 | 21277.11 | 21277.11 | 21277.11 | 34.8396 | 0 | 0 | 0 | 39794.51 | Y | 61071.62 | Y | -61071.62 | 0 | 0 | 0 | 0 | 0 | 61071.62 | Y | -61071.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -61071.62 | 3241.46 | 0 | 61071.62 | 0 | 0 | 0 | 0 | 0 | 0 | -61071.62 | 0 | 0 | 61071.62 | 61071.62 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | 160.5 | 319.5 | 480 | HR | 2697 | 707.4 | 1989.6 | 2697 | CY | 0 | 0 | 0 | 39794.51
Y | IPCRP1-0365-1000-S | IPCRP1 | IPCRP1 | 0365-1000 | Excavate Rip Rap & Misc Fill | N | S |  | NR | A | 943950 | 4579.22 | 4579.22 | 4579.22 | 4579.22 | 0 | 0 | 0 | 0 | -4579.22 | Y | 0 | Y | 943950 | 0 | 0 | 943950 | 0 | 0 | 0 | Y | 943950 | 0 | 0 | 943950 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 36.5 | -36.5 | 0 | CY | 2697 | 707.4 | 1989.6 | 2697 | CY | 4579.22 | 0 | 4579.22 | -4579.22
Y | IPCRP1-0366-0000-L | IPCRP1 | IPCRP1 | 0366-0000 | EXPOXY COATED REBAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0366-0000-R | IPCRP1 | IPCRP1 | 0366-0000 | EXPOXY COATED REBAR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11808796 | 0 | 0 | 11808796 | 0 | 11808796 | 4820800.38 | 0 | N | 11808796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11808796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0367-0000-L | IPCRP1 | IPCRP1 | 0367-0000 | HAZ INVESTIGATION DERIVED WASTE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0367-0000-R | IPCRP1 | IPCRP1 | 0367-0000 | HAZ INVESTIGATION DERIVED WASTE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57750 | 0 | 0 | 57750 | 0 | 57750 | 350 | 0 | N | 57750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0367-1000-L | IPCRP1 | IPCRP1 | 0367-1000 | HAZ INVESTIGATION DERIVED WASTE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 165 | 1 | 164 | 165 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0367-1000-S | IPCRP1 | IPCRP1 | 0367-1000 | HAZ INVESTIGATION DERIVED WASTE | N | S |  | NR | A | 57420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57420 | N | 57420 | N | 0 | 0 | 0 | 57420 | 0 | 0 | 57420 | N | 0 | 0 | 0 | 57420 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -57420 | 0 | 0 | 57420 | 0 | 0 | 0 | 0 | 0 | 0 | -57420 | 0 | 0 | 57420 | 57420 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 165 | 1 | 164 | 165 | EA | 0 | 0 | 0 | 57420
Y | IPCRP1-0368-0000-L | IPCRP1 | IPCRP1 | 0368-0000 | INVESTIGATION DERIVED WASTE (NON-HAZ) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0368-0000-R | IPCRP1 | IPCRP1 | 0368-0000 | INVESTIGATION DERIVED WASTE (NON-HAZ) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 21450 | 0 | 0 | 21450 | 0 | 21450 | 0 | 0 | N | 21450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0368-1000-L | IPCRP1 | IPCRP1 | 0368-1000 | Investigation Derived Waste (Non-Hazard) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 165 | 0 | 165 | 165 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0368-1000-S | IPCRP1 | IPCRP1 | 0368-1000 | Investigation Derived Waste (Non-Hazard) | N | S |  | NR | A | 21656.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21656.25 | N | 21656.25 | N | 0 | 0 | 0 | 21656.25 | 0 | 0 | 21656.25 | N | 0 | 0 | 0 | 21656.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21656.25 | 0 | 0 | 21656.25 | 0 | 0 | 0 | 0 | 0 | 0 | -21656.25 | 0 | 0 | 21656.25 | 21656.25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 165 | 0 | 165 | 165 | EA | 0 | 0 | 0 | 21656.25
Y | IPCRP1-0369-0000-L | IPCRP1 | IPCRP1 | 0369-0000 | MGP CONTAMIN INVEST DERIVED WASTE (NON-HAZ) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0369-0000-R | IPCRP1 | IPCRP1 | 0369-0000 | MGP CONTAMIN INVEST DERIVED WASTE (NON-HAZ) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 43990 | 0 | 0 | 43990 | 0 | 43990 | 0 | 0 | N | 43990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0369-1000-C | IPCRP1 | IPCRP1 | 0369-1000 | MGP CONTAMIN INVEST DERIVED WASTE (NON-HAZ) | N | C |  | UNIT | U | 0 | 2258.07 | 2258.07 | 2258.07 | 2258.07 | 100 | 0 | 0 | 0 | 0 | N | 2258.07 | N | -2258.07 | 0 | 0 | 0 | 0 | 0 | 2258.07 | N | -2258.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2258.07 | 0 | 0 | 2258.07 | 0 | 0 | 0 | 0 | 0 | 0 | -2258.07 | 0 | 0 | 2258.07 | 2258.07 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 0 | 3 | NA | 83 | 0 | 83 | 83 | EA | 2258.07 | 0 | 2258.07 | 0
Y | IPCRP1-0369-1000-L | IPCRP1 | IPCRP1 | 0369-1000 | MGP CONTAMIN INVEST DERIVED WASTE (NON-HAZ) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 83 | 0 | 83 | 83 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0369-1000-S | IPCRP1 | IPCRP1 | 0369-1000 | MGP CONTAMIN INVEST DERIVED WASTE (NON-HAZ) | N | S |  | NR | A | 43990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43990 | N | 43990 | N | 0 | 0 | 0 | 43990 | 0 | 0 | 43990 | N | 0 | 0 | 0 | 43990 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -43990 | 0 | 0 | 43990 | 0 | 0 | 0 | 0 | 0 | 0 | -43990 | 0 | 0 | 43990 | 43990 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SY | 83 | 0 | 83 | 83 | EA | 0 | 0 | 0 | 43990
Y | IPCRP1-0370-0000-L | IPCRP1 | IPCRP1 | 0370-0000 | ADD/DED PRICE ADD/REDC RECOVERY WELL FT (4.25 RW6 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0370-0000-R | IPCRP1 | IPCRP1 | 0370-0000 | ADD/DED PRICE ADD/REDC RECOVERY WELL FT (4.25 RW6 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 126000 | 0 | 0 | 126000 | 0 | 126000 | 0 | 0 | N | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0370-1000-L | IPCRP1 | IPCRP1 | 0370-1000 | ADD/DED PRICE ADD/REDC RECOVERY WELL FT (4.25 RW6 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 420 | 0 | 420 | 420 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0370-1000-S | IPCRP1 | IPCRP1 | 0370-1000 | ADD/DED PRICE ADD/REDC RECOVERY WELL FT (4.25 RW6 | N | S |  | NR | A | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | N | 126000 | N | 0 | 0 | 0 | 126000 | 0 | 0 | 126000 | N | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -126000 | 0 | 0 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | -126000 | 0 | 0 | 126000 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 420 | 0 | 420 | 420 | LF | 0 | 0 | 0 | 126000
Y | IPCRP1-0371-0000-L | IPCRP1 | IPCRP1 | 0371-0000 | RECOVERY WELL INST TO 60ft BELOW GRADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0371-0000-R | IPCRP1 | IPCRP1 | 0371-0000 | RECOVERY WELL INST TO 60ft BELOW GRADE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 168000 | 0 | 0 | 168000 | 0 | 168000 | 0 | 0 | N | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0371-1000-L | IPCRP1 | IPCRP1 | 0371-1000 | RECOVERY WELL INST TO 60ft BELOW GRADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 14 | 0 | 14 | 14 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0371-1000-S | IPCRP1 | IPCRP1 | 0371-1000 | RECOVERY WELL INST TO 60ft BELOW GRADE | N | S |  | NR | A | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168000 | N | 168000 | N | 0 | 0 | 0 | 168000 | 0 | 0 | 168000 | N | 0 | 0 | 0 | 168000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -168000 | 0 | 0 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | -168000 | 0 | 0 | 168000 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 14 | 0 | 14 | 14 | EA | 0 | 0 | 0 | 168000
Y | IPCRP1-0372-0000-L | IPCRP1 | IPCRP1 | 0372-0000 | STONE COLUMNS FOR GROUND IMPROVEMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0372-0000-R | IPCRP1 | IPCRP1 | 0372-0000 | STONE COLUMNS FOR GROUND IMPROVEMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 21045000 | 0 | 0 | 21045000 | 0 | 21045000 | 20415600 | 0 | N | 21045000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21045000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0372-1000-C | IPCRP1 | IPCRP1 | 0372-1000 | Stone Columns for Ground Improve - Support | N | C |  | UNIT | U | 0 | 20167.92 | 20167.92 | 20167.92 | 20167.92 | 100 | 0 | 0 | 0 | 0 | N | 20167.92 | N | -20167.92 | 0 | 0 | 0 | 0 | 0 | 20167.92 | N | -20167.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20167.92 | 0 | 0 | 20167.92 | 0 | 0 | 0 | 0 | 0 | 0 | -20167.92 | 0 | 0 | 20167.92 | 20167.92 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 35075 | 34026 | 0 | 34026 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0372-1000-E | IPCRP1 | IPCRP1 | 0372-1000 | Stone Columns for Ground Improve - Support | N | E |  | NR | P | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 102000 | 0 | 0 | 102000 | 0 | 0 | 0 | N | 102000 | 0 | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 35075 | 34026 | 0 | 34026 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0372-1000-L | IPCRP1 | IPCRP1 | 0372-1000 | Stone Columns for Ground Improve - Support | N | L |  | NR | P | 314727.8 | 61955.71 | 61955.71 | 61955.71 | 61955.71 | 100 | 0 | 0 | 0 | 0 | Y | 61955.71 | Y | 252772.09 | 0 | 0 | 314727.8 | 0 | 0 | 61955.71 | Y | 252772.09 | 0 | 0 | 314727.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -61955.71 | 0 | 0 | 61955.71 | 0 | 0 | 0 | 0 | 0 | 0 | -61955.71 | 0 | 0 | 61955.71 | 61955.71 | 0 | 0 | 0 | 2720 | 0 | 516.5 | 516.5 | 2720 | 516.5 | 0 | 516.5 | HR | 35075 | 34026 | 0 | 34026 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0372-1000-S | IPCRP1 | IPCRP1 | 0372-1000 | Stone Columns for Ground Improve - Support | N | S |  | UNIT | A | 0 | 17700 | 17700 | 17700 | 17700 | 100 | 0 | 0 | 0 | 0 | Y | 17700 | Y | -17700 | 0 | 0 | 0 | 0 | 0 | 17700 | Y | -17700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17700 | 0 | 0 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | -17700 | 0 | 0 | 17700 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5 | -147.5 | 0 | NA | 35075 | 34026 | 0 | 34026 | CY | 17700 | 0 | 17700 | 0
Y | IPCRP1-0372-1010-L | IPCRP1 | IPCRP1 | 0372-1010 | Stone Columns for Ground Improve - Mat | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 35075 | 34026 | 0 | 34026 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0372-1010-M | IPCRP1 | IPCRP1 | 0372-1010 | Stone Columns for Ground Improve - Mat | N | M |  | NR | P | 577280 | 1282913.2 | 1282913.2 | 1282913.2 | 1282913.2 | 100 | 0 | 0 | 0 | 0 | Y | 1282913.2 | Y | -705633.2 | 0 | 0 | 577280 | 0 | 0 | 1282913.2 | Y | -705633.2 | 0 | 0 | 577280 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1282913.2 | 0 | 0 | 1282913.2 | 0 | 0 | 0 | 0 | 0 | 0 | -1282913.2 | 0 | 0 | 1282913.2 | 1282913.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 61103.17 | 0 | 61103.17 | LF | 35075 | 34026 | 0 | 34026 | CY | 1227303.92 | -55609.28 | 1282913.2 | 0 | Based on conversion of 1.5T/CY, and needing EE quantity (35,075) x 1.10% loss factor @ $22/CY = $1,273,223.00 Angie reports stone column material invoices were paid in September 2023. 34,026 CY x 1.5 T/CY = 51,039 T @ $22/T = $1,122,858. Loss Factor = $1,282,913/ $1,122,858 = 14.25% (say 15%).
Y | IPCRP1-0373-0000-L | IPCRP1 | IPCRP1 | 0373-0000 | RIGID INCLUSIONS FOR GROUND IMPROVEMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0373-0000-R | IPCRP1 | IPCRP1 | 0373-0000 | RIGID INCLUSIONS FOR GROUND IMPROVEMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 26050000 | 0 | 0 | 26050000 | 0 | 26050000 | 13072670 | 0 | N | 26050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0374-0000-L | IPCRP1 | IPCRP1 | 0374-0000 | RIGID INCLUSIONS TEST PROGRAM (LOAD & PIT TESTS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0374-0000-R | IPCRP1 | IPCRP1 | 0374-0000 | RIGID INCLUSIONS TEST PROGRAM (LOAD & PIT TESTS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 1500000 | 1500000 | 0 | N | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0374-1000-L | IPCRP1 | IPCRP1 | 0374-1000 | RIGID INCLUSIONS FOR GROUND IMPROVEMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HR | 26050 | 13072.67 | 6927.33 | 20000 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0374-1000-S | IPCRP1 | IPCRP1 | 0374-1000 | RIGID INCLUSIONS FOR GROUND IMPROVEMENT | N | S |  | NR | A | 20547583.54 | 20508437.5 | 20508437.5 | 12310025.33 | 20508437.5 | 73.2221 | 0 | 0 | 0 | -3696550 | Y | 16811887.5 | Y | 3735696.04 | 0 | 0 | 20547583.54 | 0 | 0 | 16811887.5 | Y | 3735696.04 | 0 | 0 | 20547583.54 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16811887.5 | 0 | 1510562.4 | 16811887.5 | 0 | 0 | 0 | 0 | 0 | 0 | -16811887.5 | 0 | 0 | 16811887.5 | 16811887.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 15271.54 | 17425.25 | 32696.79 | LF | 26050 | 13072.67 | 6927.33 | 20000 | CY | 20508437.5 | 8198412.17 | 12310025.33 | -3696550 | American Pile subcontract, $17,300,000
Y | IPCRP1-0374-1010-L | IPCRP1 | IPCRP1 | 0374-1010 | Rigid Inclusions Test Program (Load & Test Pits) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0374-1010-S | IPCRP1 | IPCRP1 | 0374-1010 | Rigid Inclusions Test Program (Load & Test Pits) | N | S |  | NR | A | 772702.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 772702.63 | 0 | 0 | 772702.63 | 0 | 0 | 0 | Y | 772702.63 | 0 | 0 | 772702.63 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | Scope included in 0374-1000, Rigid Inclusion for Ground Improvement.
Y | IPCRP1-0374-1020-C | IPCRP1 | IPCRP1 | 0374-1020 | Obstruction Clearance (Pre-Drill)/ American Pile S | N | C |  | UNIT | U | 0 | 3602.34 | 3602.34 | 3602.33 | 3602.34 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 3602.33 | 0 | 0 | 0 | 0 | 0 | 3602.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -21 | 0 | NA | 1475 | 1378.5 | 0 | 1378.5 | LF | 3602.34 | 0.01 | 3602.33 | 0
Y | IPCRP1-0374-1020-E | IPCRP1 | IPCRP1 | 0374-1020 | Obstruction Clearance (Pre-Drill)/ American Pile S | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1475 | 1378.5 | 0 | 1378.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0374-1020-L | IPCRP1 | IPCRP1 | 0374-1020 | Obstruction Clearance (Pre-Drill)/ American Pile S | N | L |  | UNIT | P | 0 | 255115.86 | 255115.86 | 255115.86 | 255115.86 | 213.2822 | 0 | 0 | 0 | -135501.62 | Y | 119614.24 | Y | -119614.24 | 0 | 0 | 0 | 0 | 0 | 119614.24 | Y | -119614.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -119614.24 | 135501.62 | 93072.06 | 119614.24 | 0 | 0 | 0 | 0 | 0 | 0 | -119614.24 | 0 | 0 | 119614.24 | 119614.24 | 0 | 0 | 0 | 0 | 0 | 773.5 | 773.5 | 0 | 1716.5 | -943 | 773.5 | HR | 1475 | 1378.5 | 0 | 1378.5 | LF | 0 | 0 | 0 | -135501.62
Y | IPCRP1-0374-1020-M | IPCRP1 | IPCRP1 | 0374-1020 | Obstruction Clearance (Pre-Drill)/ American Pile S | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1475 | 1378.5 | 0 | 1378.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0374-1020-S | IPCRP1 | IPCRP1 | 0374-1020 | Obstruction Clearance (Pre-Drill)/ American Pile S | N | S |  | NR | A | 1236386.01 | 1228.69 | 1228.69 | 1228.69 | 1228.69 | 937.5734 | 0 | 0 | 0 | -1097.64 | Y | 131.05 | Y | 1236254.96 | 0 | 0 | 1236386.01 | 0 | 0 | 131.05 | Y | 1236254.96 | 0 | 0 | 1236386.01 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -131.05 | 1097.64 | 131.05 | 131.05 | 0 | 0 | 0 | 0 | 1097.64 | 0 | -131.05 | 0 | 0 | 131.05 | 131.05 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1475 | 1378.5 | 0 | 1378.5 | LF | 1228.69 | 0 | 1228.69 | -1097.64 | included in 2000-1160 Support for Rigid Inclusion Sub (American Pile).
Y | IPCRP1-0375-0000-L | IPCRP1 | IPCRP1 | 0375-0000 | LOAD TRANSFER PLATFORM (WORK PAD), REACH G-J | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0375-0000-R | IPCRP1 | IPCRP1 | 0375-0000 | LOAD TRANSFER PLATFORM (WORK PAD), REACH G-J | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 588750 | 0 | 0 | 588750 | 0 | 588750 | 544002 | 0 | N | 588750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0375-1000-E | IPCRP1 | IPCRP1 | 0375-1000 | Install Load Transfer (Stone) Platform (Work Pad) | N | E |  | NR | P | 25120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 25120 | 0 | 0 | 25120 | 0 | 0 | 0 | Y | 25120 | 0 | 0 | 25120 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 7850 | 8353.36 | 0 | 8353.36 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0375-1000-L | IPCRP1 | IPCRP1 | 0375-1000 | Install Load Transfer (Stone) Platform (Work Pad) | N | L |  | NR | P | 163433.86 | 100072.98 | 100072.98 | 100072.98 | 100072.98 | 61.2315 | 0 | 0 | 0 | 63360.88 | N | 163433.86 | N | 0 | 0 | 0 | 163433.86 | 0 | 0 | 163433.86 | N | 0 | 0 | 0 | 163433.86 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -163433.86 | 13472.54 | 3300.83 | 163433.86 | 0 | 0 | 0 | 0 | 0 | 0 | -163433.86 | 0 | 0 | 163433.86 | 163433.86 | 0 | 0 | 0 | 1507.2 | 0 | 1507.2 | 1507.2 | 1507.2 | 764 | 743.2 | 1507.2 | HR | 7850 | 8353.36 | 0 | 8353.36 | CY | 0 | 0 | 0 | 63360.88
Y | IPCRP1-0375-1000-S | IPCRP1 | IPCRP1 | 0375-1000 | Install Load Transfer (Stone) Platform (Work Pad) | N | S |  | UNIT | A | 0 | 17882.18 | 17882.18 | 17882.18 | 17882.18 | 114.4656 | 0 | 0 | 0 | -2259.86 | Y | 15622.32 | Y | -15622.32 | 0 | 0 | 0 | 0 | 0 | 15622.32 | Y | -15622.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15622.32 | 2259.86 | 1179.48 | 15622.32 | 0 | 0 | 0 | 0 | 2259.86 | 0 | -15622.32 | 0 | 0 | 15622.32 | 15622.32 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 0 | 114 | -62 | 52 | NA | 7850 | 8353.36 | 0 | 8353.36 | CY | 17882.18 | 0 | 17882.18 | -2259.86
Y | IPCRP1-0376-0000-L | IPCRP1 | IPCRP1 | 0376-0000 | Obstruction Clearance (Pre-Drill) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0376-0000-R | IPCRP1 | IPCRP1 | 0376-0000 | Obstruction Clearance (Pre-Drill) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1475000 | 0 | 0 | 1475000 | 0 | 1475000 | 4093518 | 0 | N | 1475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0377-0000-L | IPCRP1 | IPCRP1 | 0377-0000 | STONE COLUMNS TEST PROGRAM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0377-0000-R | IPCRP1 | IPCRP1 | 0377-0000 | STONE COLUMNS TEST PROGRAM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 1000000 | 1000000 | 0 | N | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0378-0000-L | IPCRP1 | IPCRP1 | 0378-0000 | 42 in DIP CL 56 COM SEWR IN JACKD 66 in ST SLEEVE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0378-0000-R | IPCRP1 | IPCRP1 | 0378-0000 | 42 in DIP CL 56 COM SEWR IN JACKD 66 in ST SLEEVE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 23800000 | 0 | 0 | 23800000 | 0 | 23800000 | 23800000 | 0 | N | 23800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0378-1000-C | IPCRP1 | IPCRP1 | 0378-1000 | Microtunnel Sub (JR Cruz) | N | C |  | UNIT | U | 0 | 56396 | 56396 | 56396 | 56396 | 100 | 0 | 0 | 0 | 0 | Y | 56396 | Y | -56396 | 0 | 0 | 0 | 0 | 0 | 56396 | Y | -56396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -56396 | 0 | 0 | 56396 | 0 | 0 | 0 | 0 | 0 | 0 | -56396 | 0 | 0 | 56396 | 56396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Bond
Y | IPCRP1-0378-1000-L | IPCRP1 | IPCRP1 | 0378-1000 | Microtunnel Sub (JR Cruz) | N | L |  | UNIT | P | 0 | 11218.76 | 11218.76 | 11218.76 | 11218.76 | 100 | 0 | 0 | 0 | 0 | Y | 11218.76 | Y | -11218.76 | 0 | 0 | 0 | 0 | 0 | 11218.76 | Y | -11218.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11218.76 | 0 | 0 | 11218.76 | 0 | 0 | 0 | 0 | 0 | 0 | -11218.76 | 0 | 0 | 11218.76 | 11218.76 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 0 | 70 | 0 | 70 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0378-1000-S | IPCRP1 | IPCRP1 | 0378-1000 | Microtunnel Sub (JR Cruz) | N | S |  | NR | A | 13086346 | 7960772.41 | 7960772.41 | 7960772.41 | 7960772.41 | 100 | 0 | 0 | 0 | 0 | Y | 7960772.41 | Y | 5125573.59 | 0 | 0 | 13086346 | 0 | 0 | 7960772.41 | Y | 5125573.59 | 0 | 0 | 13086346 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7960772.41 | 39432.87 | 0 | 7960772.41 | 0 | 0 | 0 | 0 | 0 | 0 | -7960772.41 | 0 | 0 | 7960772.41 | 7960772.41 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 103744.54 | -103742.86 | 1.68 | SH | 1 | 1 | 0 | 1 | LS | 7960772.41 | 0 | 7960772.41 | 0 | EE Cruz subcontract, $7,800,000
Y | IPCRP1-0379-0000-L | IPCRP1 | IPCRP1 | 0379-0000 | F&I FLOODGATE (A.1) - MNTGMERY RLLER GATE 44ft 8in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0379-0000-R | IPCRP1 | IPCRP1 | 0379-0000 | F&I FLOODGATE (A.1) - MNTGMERY RLLER GATE 44ft 8in | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1750000 | 0 | 0 | 1750000 | 0 | 1750000 | 1636249.98 | 0 | N | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0380-0000-L | IPCRP1 | IPCRP1 | 0380-0000 | F&I FLOODGATE (A.2) PIER 42 SWING GATE 23ft-3in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0380-0000-R | IPCRP1 | IPCRP1 | 0380-0000 | F&I FLOODGATE (A.2) PIER 42 SWING GATE 23ft-3in | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1250000 | 0 | 0 | 1250000 | 0 | 1250000 | 1168749.99 | 0 | N | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0381-0000-L | IPCRP1 | IPCRP1 | 0381-0000 | F&I FLOODGATE (K.1) - FDR N/B SWING GATE 35ft-1in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0381-0000-R | IPCRP1 | IPCRP1 | 0381-0000 | F&I FLOODGATE (K.1) - FDR N/B SWING GATE 35ft-1in | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1250000 | 0 | 0 | 1250000 | 0 | 1250000 | 562499.99 | 0 | N | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0382-0000-L | IPCRP1 | IPCRP1 | 0382-0000 | F&I FLOODGATE (K.2)- FDR S/B SWING GATE, 36 ft-0in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0382-0000-R | IPCRP1 | IPCRP1 | 0382-0000 | F&I FLOODGATE (K.2)- FDR S/B SWING GATE, 36 ft-0in | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1250000 | 0 | 0 | 1250000 | 0 | 1250000 | 562500.01 | 0 | N | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0383-0000-L | IPCRP1 | IPCRP1 | 0383-0000 | F&I FLOODGATE (K.5)-E14TH ROLLER GATE, 34ft-2in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0383-0000-R | IPCRP1 | IPCRP1 | 0383-0000 | F&I FLOODGATE (K.5)-E14TH ROLLER GATE, 34ft-2in | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1750000 | 0 | 0 | 1750000 | 0 | 1750000 | 787499.99 | 0 | N | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0384-0000-L | IPCRP1 | IPCRP1 | 0384-0000 | F&I FLOODGATE (K.6) - E14TH ST PEDESTRIAN GATE, 5 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0384-0000-R | IPCRP1 | IPCRP1 | 0384-0000 | F&I FLOODGATE (K.6) - E14TH ST PEDESTRIAN GATE, 5 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 1000000 | 450000.02 | 0 | N | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0385-0000-L | IPCRP1 | IPCRP1 | 0385-0000 | 24 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0385-0000-R | IPCRP1 | IPCRP1 | 0385-0000 | 24 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 10000 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
N | IPCRP1-0385-1000-C | IPCRP1 | IPCRP1 | 0385-1000 | 24 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | C |  | UNIT | U | 0 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | N | 50000 | N | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | N | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 50000 | 50000 | NA | 2 | 1 | 1 | 2 | TE | 50000 | 50000 | 0 | 0
Y | IPCRP1-0385-1000-L | IPCRP1 | IPCRP1 | 0385-1000 | 24 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2 | 1 | 1 | 2 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0385-1000-S | IPCRP1 | IPCRP1 | 0385-1000 | 24 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | S |  | NR | A | 16026.26 | 5950 | 5950 | 5950 | 5950 | 37.1266 | 0 | 0 | 0 | 10076.26 | N | 16026.26 | N | 0 | 0 | 0 | 16026.26 | 0 | 0 | 16026.26 | N | 0 | 0 | 0 | 16026.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16026.26 | 0 | 0 | 16026.26 | 0 | 0 | 0 | 0 | 0 | 0 | -16026.26 | 0 | 0 | 16026.26 | 16026.26 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | -1 | 0 | LF | 2 | 1 | 1 | 2 | TE | 5950 | 0 | 5950 | 10076.26 | Soil Solutions - $5,950 at Pier 42 Gate (1ea)
Y | IPCRP1-0386-0000-L | IPCRP1 | IPCRP1 | 0386-0000 | 24 X 0.5 ST PIPE PILE, LATERAL PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0386-0000-R | IPCRP1 | IPCRP1 | 0386-0000 | 24 X 0.5 ST PIPE PILE, LATERAL PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 240000 | 0 | 0 | 240000 | 0 | 240000 | 80000 | 0 | N | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
N | IPCRP1-0386-1000-C | IPCRP1 | IPCRP1 | 0386-1000 | 24X 0.5 St Pipe Pile, Lateral Pile Load Test | N | C |  | UNIT | U | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | N | 20000 | N | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | N | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 20000 | 20000 | NA | 3 | 1 | 2 | 3 | TE | 20000 | 20000 | 0 | 0
Y | IPCRP1-0386-1000-L | IPCRP1 | IPCRP1 | 0386-1000 | 24X 0.5 St Pipe Pile, Lateral Pile Load Test | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3 | 1 | 2 | 3 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0386-1000-S | IPCRP1 | IPCRP1 | 0386-1000 | 24X 0.5 St Pipe Pile, Lateral Pile Load Test | N | S |  | NR | A | 120276.35 | 10000 | 10000 | 10000 | 10000 | 11.1111 | 0 | 0 | 0 | 80000 | Y | 90000 | Y | 30276.35 | 0 | 0 | 120276.35 | 0 | 0 | 90000 | Y | 30276.35 | 0 | 0 | 120276.35 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -90000 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | -90000 | 0 | 0 | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | -1 | 0 | LF | 3 | 1 | 2 | 3 | TE | 10000 | 0 | 10000 | 80000 | Soil Solutions - 10K at Pier 42 Gate (1ea)
Y | IPCRP1-0387-0000-L | IPCRP1 | IPCRP1 | 0387-0000 | 24 X 0.5 ST PIPE PILE, STATIC COMP TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0387-0000-R | IPCRP1 | IPCRP1 | 0387-0000 | 24 X 0.5 ST PIPE PILE, STATIC COMP TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 60000 | 0 | 0 | 60000 | 0 | 60000 | 20000 | 0 | N | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
N | IPCRP1-0387-1000-C | IPCRP1 | IPCRP1 | 0387-1000 | 24 X 0.5 ST PIPE PILE, STATIC COMP TEST | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 3 | 1 | 2 | 3 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0387-1000-L | IPCRP1 | IPCRP1 | 0387-1000 | 24 X 0.5 ST PIPE PILE, STATIC COMP TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3 | 1 | 2 | 3 | TE | 0 | 0 | 0 | 0 | Soil Solutions - 40K at Pier 42 Gate (1ea) & ADT - 19K FDR Gates for testing
Y | IPCRP1-0387-1000-S | IPCRP1 | IPCRP1 | 0387-1000 | 24 X 0.5 ST PIPE PILE, STATIC COMP TEST | N | S |  | NR | A | 471977.09 | 94225.36 | 94225.36 | 79280 | 94225.36 | 22.3324 | 0 | 0 | 0 | 260774.64 | Y | 355000 | Y | 116977.09 | 0 | 0 | 471977.09 | 0 | 0 | 355000 | Y | 116977.09 | 0 | 0 | 471977.09 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -355000 | 0 | 0 | 355000 | 0 | 0 | 0 | 0 | 0 | 0 | -355000 | 0 | 0 | 355000 | 355000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 228.5 | -228.5 | 0 | LF | 3 | 1 | 2 | 3 | TE | 94225.36 | 14945.36 | 79280 | 260774.64
Y | IPCRP1-0388-0000-L | IPCRP1 | IPCRP1 | 0388-0000 | COATED 24 X 0.5 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0388-0000-R | IPCRP1 | IPCRP1 | 0388-0000 | COATED 24 X 0.5 ST PIPE PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1164100 | 0 | 0 | 1164100 | 0 | 1164100 | 139450.5 | 0 | N | 1164100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0388-1000-L | IPCRP1 | IPCRP1 | 0388-1000 | COATED 24 X 0.5 ST PIPE PILE | N | L |  | UNIT | P | 628672.46 | 67675.08 | 67675.08 | 67675.08 | 67675.08 | 17.8959 | 0 | 0 | 0 | 310484.92 | Y | 378160 | Y | 250512.46 | 0 | 0 | 628672.46 | 0 | 0 | 378160 | Y | 250512.46 | 0 | 0 | 628672.46 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -378160 | 0 | 0 | 378160 | 0 | 0 | 0 | 0 | 0 | 0 | -378160 | 0 | 0 | 378160 | 378160 | 0 | 0 | 0 | 0 | 0 | 2852.51 | 2852.51 | 0 | 471.5 | 2381.01 | 2852.51 | HR | 3326 | 398.43 | 2001 | 2399.43 | LF | 0 | 0 | 0 | 310484.92 | Soil Solutions installed 8ea, theoretical (725') actual 398.43' at P42 Swing Gate. Deduct 600 LF as a result of VECP#11 (Reach B FW near CE Vault
Y | IPCRP1-0388-1000-M | IPCRP1 | IPCRP1 | 0388-1000 | COATED 24 X 0.5 ST PIPE PILE | N | M |  | UNIT | U | 265372.96 | 746948.08 | 746948.08 | 481865.96 | 746948.08 | 74.7448 | 0 | 0 | 0 | -102266.48 | Y | 644681.6 | Y | -379308.64 | 0 | 0 | 265372.96 | 0 | 0 | 644681.6 | Y | -379308.64 | 0 | 0 | 265372.96 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -644681.6 | 0 | 0 | 644681.6 | 0 | 0 | 0 | 0 | 0 | 0 | -644681.6 | 0 | 0 | 644681.6 | 644681.6 | 0 | 0 | 0 | 0 | 0 | 5177 | 5177 | 0 | 5177 | 0 | 5177 | NA | 3326 | 398.43 | 2001 | 2399.43 | LF | 746948.08 | 265082.12 | 481865.96 | -102266.48
Y | IPCRP1-0388-1000-S | IPCRP1 | IPCRP1 | 0388-1000 | COATED 24 X 0.5 ST PIPE PILE | N | S |  | NR | A | 0 | 214007.86 | 214007.86 | 151218.56 | 214007.86 | 70.6603 | 0 | 0 | 0 | 0 | Y | 214007.86 | Y | -214007.86 | 0 | 0 | 0 | 0 | 0 | 214007.86 | Y | -214007.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -214007.86 | 0 | 0 | 214007.86 | 0 | 0 | 0 | 0 | 0 | 0 | -214007.86 | 0 | 0 | 214007.86 | 214007.86 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 495.21 | -495.21 | 0 | LS | 3326 | 398.43 | 2001 | 2399.43 | LF | 214007.86 | 62789.3 | 151218.56 | 0
Y | IPCRP1-0389-0000-L | IPCRP1 | IPCRP1 | 0389-0000 | COATED 24 X 0.5 ST PIPE PILE, IN JET GROUT COUM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0389-0000-R | IPCRP1 | IPCRP1 | 0389-0000 | COATED 24 X 0.5 ST PIPE PILE, IN JET GROUT COUM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 462000 | 0 | 0 | 462000 | 0 | 462000 | 0 | 0 | N | 462000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0389-1000-L | IPCRP1 | IPCRP1 | 0389-1000 | Coated 24in X 0.5in St Pipe Pile In Jet Grout Colu | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1155 | 0 | 1155 | 1155 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0389-1000-S | IPCRP1 | IPCRP1 | 0389-1000 | Coated 24in X 0.5in St Pipe Pile In Jet Grout Colu | N | S |  | NR | A | 356538.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356538.45 | N | 356538.45 | N | 0 | 0 | 0 | 356538.45 | 0 | 0 | 356538.45 | N | 0 | 0 | 0 | 356538.45 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -356538.45 | 0 | 0 | 356538.45 | 0 | 0 | 0 | 0 | 0 | 0 | -356538.45 | 0 | 0 | 356538.45 | 356538.45 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1155 | 0 | 1155 | 1155 | LF | 0 | 0 | 0 | 356538.45
Y | IPCRP1-0390-0000-L | IPCRP1 | IPCRP1 | 0390-0000 | COATED 24 X 0.5 ST PIPE PILE, IN TIMBER CRIBBIN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0390-0000-R | IPCRP1 | IPCRP1 | 0390-0000 | COATED 24 X 0.5 ST PIPE PILE, IN TIMBER CRIBBIN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 499800 | 0 | 0 | 499800 | 0 | 499800 | 0 | 0 | N | 499800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0390-1000-L | IPCRP1 | IPCRP1 | 0390-1000 | Coated 24in X 0.5in St Pipe Pile In Timber Crbbin | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1470 | 0 | 1470 | 1470 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0390-1000-S | IPCRP1 | IPCRP1 | 0390-1000 | Coated 24in X 0.5in St Pipe Pile In Timber Crbbin | N | S |  | NR | A | 375985.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375985.58 | N | 375985.58 | N | 0 | 0 | 0 | 375985.58 | 0 | 0 | 375985.58 | N | 0 | 0 | 0 | 375985.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -375985.58 | 0 | 0 | 375985.58 | 0 | 0 | 0 | 0 | 0 | 0 | -375985.58 | 0 | 0 | 375985.58 | 375985.58 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1470 | 0 | 1470 | 1470 | LF | 0 | 0 | 0 | 375985.58
Y | IPCRP1-0391-0000-L | IPCRP1 | IPCRP1 | 0391-0000 | 24 X 0.75 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0391-0000-R | IPCRP1 | IPCRP1 | 0391-0000 | 24 X 0.75 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 60000 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0391-1000-L | IPCRP1 | IPCRP1 | 0391-1000 | 24 X 0.75 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5 | 0 | 5 | 5 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0391-1000-S | IPCRP1 | IPCRP1 | 0391-1000 | 24 X 0.75 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | S |  | NR | A | 56067.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 56067.95 | 0 | 0 | 56067.95 | 0 | 0 | 0 | Y | 56067.95 | 0 | 0 | 56067.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 5 | 0 | 5 | 5 | TE | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0392-0000-L | IPCRP1 | IPCRP1 | 0392-0000 | COATED 24 X 0.75 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0392-0000-R | IPCRP1 | IPCRP1 | 0392-0000 | COATED 24 X 0.75 ST PIPE PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3009600 | 0 | 0 | 3009600 | 0 | 3009600 | 1473505 | 0 | N | 3009600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0392-1000-L | IPCRP1 | IPCRP1 | 0392-1000 | COATED 24 X 0.75 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5472 | 2429.5 | 3042.5 | 5472 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0392-1000-M | IPCRP1 | IPCRP1 | 0392-1000 | COATED 24 X 0.75 ST PIPE PILE | N | M |  | UNIT | U | 0 | 1615081.02 | 1615081.02 | 1615081.02 | 1615081.02 | 110.5867 | 0 | 0 | 0 | -154614.72 | Y | 1460466.3 | Y | -1460466.3 | 0 | 0 | 0 | 0 | 0 | 1460466.3 | Y | -1460466.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1460466.3 | 0 | 0 | 1460466.3 | 0 | 0 | 0 | 0 | 85341.34 | 0 | -1460466.3 | 0 | 0 | 1460466.3 | 1460466.3 | 0 | 0 | 0 | 0 | 0 | 62767.56 | 62767.56 | 0 | 69412.55 | -6644.99 | 62767.56 | EA | 5472 | 2429.5 | 3042.5 | 5472 | LF | 1460466.3 | -154614.72 | 1615081.02 | -154614.72
Y | IPCRP1-0392-1000-S | IPCRP1 | IPCRP1 | 0392-1000 | COATED 24 X 0.75 ST PIPE PILE | N | S |  | NR | A | 2429932.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2429932.98 | 0 | 0 | 2429932.98 | 0 | 0 | 0 | Y | 2429932.98 | 0 | 0 | 2429932.98 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 5472 | 2429.5 | 3042.5 | 5472 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0393-0000-L | IPCRP1 | IPCRP1 | 0393-0000 | 30 X 1 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0393-0000-R | IPCRP1 | IPCRP1 | 0393-0000 | 30 X 1 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 45000 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | N | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0393-1000-L | IPCRP1 | IPCRP1 | 0393-1000 | 30 X 1 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3 | 0 | 3 | 3 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0393-1000-S | IPCRP1 | IPCRP1 | 0393-1000 | 30 X 1 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | S |  | NR | A | 33640.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33640.74 | N | 33640.74 | N | 0 | 0 | 0 | 33640.74 | 0 | 0 | 33640.74 | N | 0 | 0 | 0 | 33640.74 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -33640.74 | 0 | 0 | 33640.74 | 0 | 0 | 0 | 0 | 0 | 0 | -33640.74 | 0 | 0 | 33640.74 | 33640.74 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 3 | 0 | 3 | 3 | TE | 0 | 0 | 0 | 33640.74
Y | IPCRP1-0394-0000-L | IPCRP1 | IPCRP1 | 0394-0000 | ROCK SOCKET FOR 30 X 1 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0394-0000-R | IPCRP1 | IPCRP1 | 0394-0000 | ROCK SOCKET FOR 30 X 1 ST PIPE PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2025000 | 0 | 0 | 2025000 | 0 | 2025000 | 0 | 0 | N | 2025000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0394-1000-L | IPCRP1 | IPCRP1 | 0394-1000 | ROCK SOCKET FOR 30 X 1 ST PIPE PILE | N | L |  | UNIT | P | 0 | 10803 | 10803 | 10803 | 10803 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 1881.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.5 | -80.5 | 0 | HR | 27 | 0 | 27 | 27 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0394-1000-S | IPCRP1 | IPCRP1 | 0394-1000 | ROCK SOCKET FOR 30 X 1 ST PIPE PILE | N | S |  | NR | A | 1653605.91 | 196.58 | 196.58 | 196.58 | 196.58 | 0.011888 | 0 | 0 | 0 | 1653409.33 | N | 1653605.91 | N | 0 | 0 | 0 | 1653605.91 | 0 | 0 | 1653605.91 | N | 0 | 0 | 0 | 1653605.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1653605.91 | 0 | 196.58 | 1653605.91 | 0 | 0 | 0 | 0 | 0 | 0 | -1653605.91 | 0 | 0 | 1653605.91 | 1653605.91 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 27 | 0 | 27 | 27 | EA | 196.58 | 0 | 196.58 | 1653409.33
Y | IPCRP1-0395-0000-L | IPCRP1 | IPCRP1 | 0395-0000 | COATED 30 X 1 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0395-0000-R | IPCRP1 | IPCRP1 | 0395-0000 | COATED 30 X 1 ST PIPE PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3648750 | 0 | 0 | 3648750 | 0 | 3648750 | 0 | 0 | N | 3648750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3648750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0395-1000-L | IPCRP1 | IPCRP1 | 0395-1000 | COATED 30 X 1 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4865 | 0 | 4865 | 4865 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0395-1000-S | IPCRP1 | IPCRP1 | 0395-1000 | COATED 30 X 1 ST PIPE PILE | N | S |  | NR | A | 2916441.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916441.98 | N | 2916441.98 | N | 0 | 0 | 0 | 2916441.98 | 0 | 0 | 2916441.98 | N | 0 | 0 | 0 | 2916441.98 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2916441.98 | 0 | 0 | 2916441.98 | 0 | 0 | 0 | 0 | 0 | 0 | -2916441.98 | 0 | 0 | 2916441.98 | 2916441.98 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 4865 | 0 | 4865 | 4865 | LF | 0 | 0 | 0 | 2916441.98
Y | IPCRP1-0396-0000-L | IPCRP1 | IPCRP1 | 0396-0000 | COATED 30 X 1 ST PIPE PILE, IN JET GROUT COLUMN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0396-0000-R | IPCRP1 | IPCRP1 | 0396-0000 | COATED 30 X 1 ST PIPE PILE, IN JET GROUT COLUMN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 330000 | 0 | 0 | 330000 | 0 | 330000 | 0 | 0 | N | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0396-1000-L | IPCRP1 | IPCRP1 | 0396-1000 | COATED 30 X 1 ST PIPE PILE, IN JET GROUT COLUMN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 440 | 0 | 440 | 440 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0396-1000-S | IPCRP1 | IPCRP1 | 0396-1000 | COATED 30 X 1 ST PIPE PILE, IN JET GROUT COLUMN | N | S |  | NR | A | 270961.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270961.06 | N | 270961.06 | N | 0 | 0 | 0 | 270961.06 | 0 | 0 | 270961.06 | N | 0 | 0 | 0 | 270961.06 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -270961.06 | 0 | 0 | 270961.06 | 0 | 0 | 0 | 0 | 0 | 0 | -270961.06 | 0 | 0 | 270961.06 | 270961.06 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 440 | 0 | 440 | 440 | LF | 0 | 0 | 0 | 270961.06
Y | IPCRP1-0397-0000-L | IPCRP1 | IPCRP1 | 0397-0000 | 30 X 1 ST PIPE PILE, LATERAL PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0397-0000-R | IPCRP1 | IPCRP1 | 0397-0000 | 30 X 1 ST PIPE PILE, LATERAL PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 80000 | 0 | 0 | 80000 | 0 | 80000 | 0 | 0 | N | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0397-1000-L | IPCRP1 | IPCRP1 | 0397-1000 | 30 X 1 ST PIPE PILE, LATERAL PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0397-1000-S | IPCRP1 | IPCRP1 | 0397-1000 | 30 X 1 ST PIPE PILE, LATERAL PILE LOAD TEST | N | S |  | NR | A | 40092.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40092.1 | N | 40092.1 | N | 0 | 0 | 0 | 40092.1 | 0 | 0 | 40092.1 | N | 0 | 0 | 0 | 40092.1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -40092.1 | 0 | 0 | 40092.1 | 0 | 0 | 0 | 0 | 0 | 0 | -40092.1 | 0 | 0 | 40092.1 | 40092.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 0 | 1 | 1 | TE | 0 | 0 | 0 | 40092.1
Y | IPCRP1-0398-0000-L | IPCRP1 | IPCRP1 | 0398-0000 | STATIC COMPRESSION TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0398-0000-R | IPCRP1 | IPCRP1 | 0398-0000 | STATIC COMPRESSION TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 525000 | 0 | 0 | 525000 | 0 | 525000 | 0 | 0 | N | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0398-1000-L | IPCRP1 | IPCRP1 | 0398-1000 | STATIC COMPRESSION TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3 | 0 | 3 | 3 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0398-1000-S | IPCRP1 | IPCRP1 | 0398-1000 | STATIC COMPRESSION TEST | N | S |  | NR | A | 471977.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471977.09 | N | 471977.09 | N | 0 | 0 | 0 | 471977.09 | 0 | 0 | 471977.09 | N | 0 | 0 | 0 | 471977.09 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -471977.09 | 0 | 0 | 471977.09 | 0 | 0 | 0 | 0 | 0 | 0 | -471977.09 | 0 | 0 | 471977.09 | 471977.09 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 3 | 0 | 3 | 3 | TE | 0 | 0 | 0 | 471977.09
Y | IPCRP1-0399-0000-L | IPCRP1 | IPCRP1 | 0399-0000 | 36 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0399-0000-R | IPCRP1 | IPCRP1 | 0399-0000 | 36 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50000 | 0 | 0 | 50000 | 0 | 50000 | 40000 | 0 | N | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0400-0000-L | IPCRP1 | IPCRP1 | 0400-0000 | ROCK SOCKET FOR 36 X 0.5 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0400-0000-R | IPCRP1 | IPCRP1 | 0400-0000 | ROCK SOCKET FOR 36 X 0.5 ST PIPE PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2150000 | 0 | 0 | 2150000 | 0 | 2150000 | 1150000 | 0 | N | 2150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0401-0000-L | IPCRP1 | IPCRP1 | 0401-0000 | COATED 36 X 0.5 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0401-0000-R | IPCRP1 | IPCRP1 | 0401-0000 | COATED 36 X 0.5 ST PIPE PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16915800 | 0 | 0 | 16915800 | 0 | 16915800 | 18585599.99 | 0 | N | 16915800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16915800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0402-0000-L | IPCRP1 | IPCRP1 | 0402-0000 | COATED 36 X 0.5 ST PIPE PILE, IN PREDRILLED LOC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0402-0000-R | IPCRP1 | IPCRP1 | 0402-0000 | COATED 36 X 0.5 ST PIPE PILE, IN PREDRILLED LOC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11950400 | 0 | 0 | 11950400 | 0 | 11950400 | 2877600 | 0 | N | 11950400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11950400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0403-0000-L | IPCRP1 | IPCRP1 | 0403-0000 | COATED 36 X 0.5 ST PIPE PILE, W INTERLOCK SEAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0403-0000-R | IPCRP1 | IPCRP1 | 0403-0000 | COATED 36 X 0.5 ST PIPE PILE, W INTERLOCK SEAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1533600 | 0 | 0 | 1533600 | 0 | 1533600 | 0 | 0 | N | 1533600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0404-0000-L | IPCRP1 | IPCRP1 | 0404-0000 | COATED 36 X 0.5 ST PIPE PILE, W IL SEAL, PREDRI | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0404-0000-R | IPCRP1 | IPCRP1 | 0404-0000 | COATED 36 X 0.5 ST PIPE PILE, W IL SEAL, PREDRI | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1533600 | 0 | 0 | 1533600 | 0 | 1533600 | 0 | 0 | N | 1533600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0405-0000-L | IPCRP1 | IPCRP1 | 0405-0000 | 42 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0405-0000-R | IPCRP1 | IPCRP1 | 0405-0000 | 42 X 0.5 ST PIPE PILE, DYNAMIC PILE LOAD TEST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 260000 | 0 | 0 | 260000 | 0 | 260000 | 190000 | 0 | N | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0405-1000-C | IPCRP1 | IPCRP1 | 0405-1000 | Combi Wall Sub (Skanska) | N | C |  | UNIT | U | 0 | 74853 | 74853 | 74853 | 74853 | 100 | 0 | 0 | 0 | 0 | Y | 74853 | Y | -74853 | 0 | 0 | 0 | 0 | 0 | 74853 | Y | -74853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -74853 | 0 | 0 | 74853 | 0 | 0 | 0 | 0 | 0 | 0 | -74853 | 0 | 0 | 74853 | 74853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.63 | 0.37 | 1 | LS | 0 | 0 | 0 | 0 | Bond. (Increased by $20k from $54,853)
Y | IPCRP1-0405-1000-L | IPCRP1 | IPCRP1 | 0405-1000 | Combi Wall Sub (Skanska) | N | L |  | UNIT | P | 0 | 42481.38 | 42481.38 | 42481.38 | 42481.38 | 36.9799 | 0 | 0 | 0 | 72395.69 | Y | 114877.07 | Y | -114877.07 | 0 | 0 | 0 | 0 | 0 | 114877.07 | Y | -114877.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -114877.07 | 11921.81 | 0 | 114877.07 | 0 | 0 | 0 | 0 | 0 | 0 | -114877.07 | 0 | 0 | 114877.07 | 114877.07 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 296 | 504 | 800 | HR | 1 | 0.63 | 0.37 | 1 | LS | 0 | 0 | 0 | 72395.69
Y | IPCRP1-0405-1000-S | IPCRP1 | IPCRP1 | 0405-1000 | Combi Wall Sub (Skanska) | N | S |  | NR | A | 25402655 | 19601502.92 | 19601502.92 | 12726266.04 | 19601502.92 | 65.9856 | 0 | 0 | 0 | -315083.92 | Y | 19286419 | Y | 6116236 | 0 | 0 | 25402655 | 0 | 0 | 19286419 | Y | 6116236 | 0 | 0 | 25402655 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19286419 | 0 | 713828 | 19286419 | 0 | 0 | 0 | 30235.3 | 559319.87 | 0 | -19286419 | 0 | 0 | 19286419 | 19286419 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 146430.44 | 226466.08 | 372896.52 | LS | 1 | 0.63 | 0.37 | 1 | LS | 19601502.92 | 6875236.88 | 12726266.04 | -315083.92 | Skanksa Base Contract @$18,840,240.00 Add 200K to PMF for Obstruction Clearing for LP Foundations.
Y | IPCRP1-0405-1010-C | IPCRP1 | IPCRP1 | 0405-1010 | F&D Pile Material for Combi Wall | N | C |  | UNIT | U | 0 | 378128.4 | 378128.4 | 160201.33 | 378128.4 | 29.8491 | 0 | 0 | 0 | 158575.89 | Y | 536704.29 | Y | -536704.29 | 0 | 0 | 0 | 0 | 0 | 536704.29 | Y | -536704.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -536704.29 | 8834.32 | 0 | 536704.29 | 0 | 0 | 0 | 8834.31 | 0 | 0 | -536704.29 | 0 | 0 | 536704.29 | 536704.29 | 0 | 0 | 0 | 0 | 0 | 306.59 | 306.59 | 0 | 327 | -20.41 | 306.59 | NA | 1 | 0.91 | 0.09 | 1 | LS | 378128.4 | 217927.07 | 160201.33 | 158575.89
Y | IPCRP1-0405-1010-L | IPCRP1 | IPCRP1 | 0405-1010 | F&D Pile Material for Combi Wall | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.91 | 0.09 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0405-1010-M | IPCRP1 | IPCRP1 | 0405-1010 | F&D Pile Material for Combi Wall | N | M |  | NR | P | 25307612 | 25663724.99 | 25663724.99 | 17622601.23 | 25663724.99 | 97.0824 | 0 | 0 | 0 | -7511521.23 | Y | 18152203.76 | Y | 7155408.24 | 0 | 0 | 25307612 | 0 | 0 | 18152203.76 | Y | 7155408.24 | 0 | 0 | 25307612 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18152203.76 | 335789.58 | 0 | 18152203.76 | 0 | 0 | 0 | 53804.78 | 0 | 0 | -18152203.76 | 0 | 0 | 18152203.76 | 18152203.76 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 279880.29 | -135 | 279745.29 | AC | 1 | 0.91 | 0.09 | 1 | LS | 18139756.24 | 8041123.76 | 10098632.48 | -7511521.23 | Change PMF (Mat) from $16,525,509.41 to $16,536,577.31, matching CTD Note for CTC (GO): Stored Material is backed up but commitment is $16,431,724.63 J.D. FIELDS @$3,458,403.84; TRINITY @$12,065,447.08; holding $1,000,000 for misc. steel TBD
Y | IPCRP1-0405-1020-L | IPCRP1 | IPCRP1 | 0405-1020 | Shear Studs for Combi-Wall & Flood Wall | N | L |  | UNIT | P | 0 | 194389.08 | 194389.08 | 194389.08 | 194389.08 | 59.6824 | 0 | 0 | 0 | 131316.95 | Y | 325706.03 | Y | -325706.03 | 0 | 0 | 0 | 0 | 0 | 325706.03 | Y | -325706.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -325706.03 | 3144.4 | 1734.35 | 325706.03 | 0 | 0 | 0 | 0 | 0 | 0 | -325706.03 | 0 | 0 | 325706.03 | 325706.03 | 0 | 0 | 0 | 0 | 0 | 2515.76 | 2515.76 | 0 | 1520 | 995.76 | 2515.76 | HR | 0 | 13229.5 | 7770.5 | 21000 | EA | 0 | 0 | 0 | 131316.95
Y | IPCRP1-0405-1020-S | IPCRP1 | IPCRP1 | 0405-1020 | Shear Studs for Combi-Wall & Flood Wall | N | S |  | UNIT | P | 0 | 262822.57 | 262822.57 | 173286.44 | 262822.57 | 65.9329 | 0 | 0 | 0 | 0 | Y | 262822.57 | Y | -262822.57 | 0 | 0 | 0 | 0 | 0 | 262822.57 | Y | -262822.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -262822.57 | 0 | 5139.56 | 262822.57 | 0 | 0 | 0 | 0 | 0 | 0 | -262822.57 | 0 | 0 | 262822.57 | 262822.57 | 0 | 0 | 0 | 0 | 0 | 24288.54 | 24288.54 | 0 | 18130.94 | 6157.6 | 24288.54 | EA | 0 | 13229.5 | 7770.5 | 21000 | EA | 262822.57 | 89536.13 | 173286.44 | 0
Y | IPCRP1-0406-0000-L | IPCRP1 | IPCRP1 | 0406-0000 | 42 X 0.625 ST PIPE PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0406-0000-R | IPCRP1 | IPCRP1 | 0406-0000 | 42 X 0.625 ST PIPE PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1226400 | 0 | 0 | 1226400 | 0 | 1226400 | 1428000 | 0 | N | 1226400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0406-1000-L | IPCRP1 | IPCRP1 | 0406-1000 | 42 X 0.625 ST PIPE PILE | N | L |  | UNIT | P | 0 | 191996.34 | 191996.34 | 191996.34 | 191996.34 | 100 | 0 | 0 | 0 | 0 | Y | 191996.34 | Y | -191996.34 | 0 | 0 | 0 | 0 | 0 | 191996.34 | Y | -191996.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -191996.34 | 0 | 0 | 191996.34 | 0 | 0 | 0 | 0 | 0 | 0 | -191996.34 | 0 | 0 | 191996.34 | 191996.34 | 0 | 0 | 0 | 0 | 0 | 1326 | 1326 | 0 | 1326 | 0 | 1326 | HR | 1533 | 1155 | 0 | 1155 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0406-1000-M | IPCRP1 | IPCRP1 | 0406-1000 | 42 X 0.625 ST PIPE PILE | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | 2625 | 0 | 0 | 2625 | 2625 | NA | 1533 | 1155 | 0 | 1155 | LF | 0 | 0 | 0 | 0 | Refer to RD comments dated 10/25/24 for reduced Phase 1 quantity. deleted note - TRINITY PRODUCTS INC base PO @$358,968.75 Work included in 0405-1000 (Skanska subcontract).
Y | IPCRP1-0406-1000-S | IPCRP1 | IPCRP1 | 0406-1000 | 42 X 0.625 ST PIPE PILE | N | S |  | NR | A | 902778.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 902778.49 | 0 | 0 | 902778.49 | 0 | 0 | 0 | Y | 902778.49 | 0 | 0 | 902778.49 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1533 | 1155 | 0 | 1155 | LF | 0 | 0 | 0 | 0 | Work included in 0405-1000 (Skanska subcontract). These are LP foundations, all given to Skanska. We have self perform 27ea in Phase 1, each 35' long (945') less 5' short on LPC502 (see RFI#872). See ZH email dated 3/12/24. 75ea total, 43 Phase 1, 32 Phase 2. Skanska installed 16ea (560') in Phase 1. It is to our benefit to allow Skanska to install.
Y | IPCRP1-0407-0000-L | IPCRP1 | IPCRP1 | 0407-0000 | 42 X 0.625 ST PIPE PILE, IN PREDRILL LOC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0407-0000-R | IPCRP1 | IPCRP1 | 0407-0000 | 42 X 0.625 ST PIPE PILE, IN PREDRILL LOC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 817600 | 0 | 0 | 817600 | 0 | 817600 | -0.01 | 0 | N | 817600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0407-1000-L | IPCRP1 | IPCRP1 | 0407-1000 | 42 X 0.625 St Pipe Pile, in Predrilled Loc | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1022 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0407-1000-S | IPCRP1 | IPCRP1 | 0407-1000 | 42 X 0.625 St Pipe Pile, in Predrilled Loc | N | S |  | NR | A | 588339.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 588339.34 | 0 | 0 | 588339.34 | 0 | 0 | 0 | Y | 588339.34 | 0 | 0 | 588339.34 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1022 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Work included in 0405-1000 (Skanska subcontract).
Y | IPCRP1-0408-0000-L | IPCRP1 | IPCRP1 | 0408-0000 | 9.625 OD X 0.54 MICROPILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0408-0000-R | IPCRP1 | IPCRP1 | 0408-0000 | 9.625 OD X 0.54 MICROPILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4179200 | 0 | 0 | 4179200 | 0 | 4179200 | 1594112 | 0 | N | 4179200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4179200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0408-1000-C | IPCRP1 | IPCRP1 | 0408-1000 | Micropile Support | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0408-1000-L | IPCRP1 | IPCRP1 | 0408-1000 | Micropile Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0408-1000-S | IPCRP1 | IPCRP1 | 0408-1000 | Micropile Support | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0409-0000-L | IPCRP1 | IPCRP1 | 0409-0000 | PILE LOAD TEST, 9.625 X 0.54 MP, STATIC COMP TE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0409-0000-R | IPCRP1 | IPCRP1 | 0409-0000 | PILE LOAD TEST, 9.625 X 0.54 MP, STATIC COMP TE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 150000 | 0 | 0 | 150000 | 0 | 150000 | 50000 | 0 | N | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0410-0000-L | IPCRP1 | IPCRP1 | 0410-0000 | PILE LOAD TEST, 9.625 X 0.54 MP, STATIC TENS TE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0410-0000-R | IPCRP1 | IPCRP1 | 0410-0000 | PILE LOAD TEST, 9.625 X 0.54 MP, STATIC TENS TE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50000 | 0 | 0 | 50000 | 0 | 50000 | 50000 | 0 | N | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-0411-0000-L | IPCRP1 | IPCRP1 | 0411-0000 | COATED NZ19 OR = ST SHT PILE WALL NON-P-I-M | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0411-0000-R | IPCRP1 | IPCRP1 | 0411-0000 | COATED NZ19 OR = ST SHT PILE WALL NON-P-I-M | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 103105 | 0 | 0 | 103105 | 0 | 103105 | 0 | 0 | N | 103105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0412-0000-L | IPCRP1 | IPCRP1 | 0412-0000 | BARE AZ-20-700N OR = ST SHT PILE NON-P-I-M | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0412-0000-R | IPCRP1 | IPCRP1 | 0412-0000 | BARE AZ-20-700N OR = ST SHT PILE NON-P-I-M | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3827670 | 0 | 0 | 3827670 | 0 | 3827670 | 1771764.4 | 0 | N | 3827670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3827670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0413-0000-L | IPCRP1 | IPCRP1 | 0413-0000 | COATED AZ-20-700N OR = ST SHT PILE NON-P-I-M | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0413-0000-R | IPCRP1 | IPCRP1 | 0413-0000 | COATED AZ-20-700N OR = ST SHT PILE NON-P-I-M | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19486200 | 0 | 0 | 19486200 | 0 | 19486200 | 10699297 | 0 | N | 19486200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19486200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0414-0000-L | IPCRP1 | IPCRP1 | 0414-0000 | COATED AZ-20-700N OR = ST SHT PILE, IN CONC BULKH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0414-0000-R | IPCRP1 | IPCRP1 | 0414-0000 | COATED AZ-20-700N OR = ST SHT PILE, IN CONC BULKH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 122250 | 0 | 0 | 122250 | 0 | 122250 | 0 | 0 | N | 122250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0415-0000-L | IPCRP1 | IPCRP1 | 0415-0000 | COATED AZ-20-700N OR = ST SHT PILE, IN TIMBER CRI | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0415-0000-R | IPCRP1 | IPCRP1 | 0415-0000 | COATED AZ-20-700N OR = ST SHT PILE, IN TIMBER CRI | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2735100 | 0 | 0 | 2735100 | 0 | 2735100 | 8424975 | 0 | N | 2735100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2735100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0415-1000-L | IPCRP1 | IPCRP1 | 0415-1000 | PM - Furnish Piles Sheets & Materials | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 270620 | 188470.39 | 82149.61 | 270620 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0415-1000-M | IPCRP1 | IPCRP1 | 0415-1000 | PM - Furnish Piles Sheets & Materials | N | M |  | NR | P | 7232321 | 8254312.77 | 8254312.77 | 8020311.08 | 8254312.77 | 95.321 | 0 | 0 | 0 | 159687.86 | Y | 8414000.63 | Y | -1181679.63 | 0 | 0 | 7232321 | 0 | 0 | 8414000.63 | Y | -1181679.63 | 0 | 0 | 7232321 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8414000.63 | 0 | 0 | 8414000.63 | 0 | 0 | 0 | 0 | 0 | 0 | -8414000.63 | 0 | 0 | 8414000.63 | 8414000.63 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6881468.12 | -345425.02 | 6536043.1 | EA | 270620 | 188470.39 | 82149.61 | 270620 | SF | 8266352.52 | 234001.69 | 8032350.83 | 159687.86 | SKYLINE STEEL, LLC @$ 7,668,342.13
Y | IPCRP1-0415-1010-C | IPCRP1 | IPCRP1 | 0415-1010 | Offload & Stage sheeting on/off site | N | C |  | UNIT | U | 0 | 565209.91 | 565209.91 | 390438.68 | 565209.91 | 69.8544 | 0 | 0 | 0 | -6277.45 | Y | 558932.46 | Y | -558932.46 | 0 | 0 | 0 | 0 | 0 | 558932.46 | Y | -558932.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -558932.46 | 1886.83 | 1992.08 | 558932.46 | 0 | 0 | 0 | 4108.57 | 2168.88 | 0 | -558932.46 | 0 | 0 | 558932.46 | 558932.46 | 0 | 0 | 0 | 0 | 0 | 1047.49 | 1047.49 | 0 | 1728.4 | -680.91 | 1047.49 | NA | 270620 | 233367 | 37253 | 270620 | SF | 565209.91 | 174771.23 | 390438.68 | -6277.45 | consumable cost is storage of sheeting at Port of Coymans (298K)
Y | IPCRP1-0415-1010-E | IPCRP1 | IPCRP1 | 0415-1010 | Offload & Stage sheeting on/off site | N | E |  | NR | P | 76318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 76318 | 0 | 0 | 76318 | 0 | 0 | 0 | N | 76318 | 0 | 0 | 76318 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 270620 | 233367 | 37253 | 270620 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0415-1010-L | IPCRP1 | IPCRP1 | 0415-1010 | Offload & Stage sheeting on/off site | N | L |  | NR | P | 193785 | 209466.92 | 209466.92 | 209466.92 | 209466.92 | 76.4172 | 0 | 0 | 0 | 64642.6 | Y | 274109.52 | Y | -80324.52 | 0 | 0 | 193785 | 0 | 0 | 274109.52 | Y | -80324.52 | 0 | 0 | 193785 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -274109.52 | 0.01 | 1742.83 | 274109.52 | 0 | 0 | 0 | 0 | 0 | 0 | -274109.52 | 0 | 0 | 274109.52 | 274109.52 | 0 | 0 | 0 | 1402.9 | 0 | 1941.26 | 1941.26 | 1402.9 | 1475 | 466.26 | 1941.26 | HR | 270620 | 233367 | 37253 | 270620 | SF | 0 | 0 | 0 | 64642.6
Y | IPCRP1-0415-1010-S | IPCRP1 | IPCRP1 | 0415-1010 | Offload & Stage sheeting on/off site | N | S |  | UNIT | A | 0 | 7149.19 | 7149.19 | 7149.19 | 7149.19 | 100 | 0 | 0 | 0 | 0 | Y | 7149.19 | Y | -7149.19 | 0 | 0 | 0 | 0 | 0 | 7149.19 | Y | -7149.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7149.19 | 0 | 0 | 7149.19 | 0 | 0 | 0 | 0 | 0 | 0 | -7149.19 | 0 | 0 | 7149.19 | 7149.19 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 58 | -54 | 4 | NA | 270620 | 233367 | 37253 | 270620 | SF | 7149.19 | 0 | 7149.19 | 0
Y | IPCRP1-0415-1020-E | IPCRP1 | IPCRP1 | 0415-1020 | Drive Sheets | N | E |  | NR | P | 1821220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1821220 | 0 | 0 | 1821220 | 0 | 0 | 0 | Y | 1821220 | 0 | 0 | 1821220 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 270620 | 196166.5 | 74453.5 | 270620 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0415-1020-L | IPCRP1 | IPCRP1 | 0415-1020 | Drive Sheets | N | L |  | NR | P | 3246477 | 1085731.31 | 1085731.31 | 1085731.31 | 1085731.31 | 57.2989 | 0 | 0 | 0 | 809124.21 | Y | 1894855.52 | Y | 1351621.48 | 0 | 0 | 3246477 | 0 | 0 | 1894855.52 | Y | 1351621.48 | 0 | 0 | 3246477 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1894855.52 | 25253.9 | 5261.13 | 1894855.52 | 0 | 0 | 0 | 0 | 0 | 0 | -1894855.52 | 0 | 0 | 1894855.52 | 1894855.52 | 0 | 0 | 0 | 21833.61 | 0 | 13535 | 13535 | 21833.61 | 7672.5 | 5862.5 | 13535 | HR | 270620 | 196166.5 | 74453.5 | 270620 | SF | 0 | 0 | 0 | 809124.21
Y | IPCRP1-0415-1020-S | IPCRP1 | IPCRP1 | 0415-1020 | Drive Sheets | N | S |  | UNIT | A | 0 | 6384.75 | 6384.75 | 6384.75 | 6384.75 | 100 | 0 | 0 | 0 | 0 | Y | 6384.75 | Y | -6384.75 | 0 | 0 | 0 | 0 | 0 | 6384.75 | Y | -6384.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6384.75 | 0 | 0 | 6384.75 | 0 | 0 | 0 | 0 | 0 | 0 | -6384.75 | 0 | 0 | 6384.75 | 6384.75 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 0 | 51.5 | -47 | 4.5 | NA | 270620 | 196166.5 | 74453.5 | 270620 | SF | 6384.75 | 0 | 6384.75 | 0
Y | IPCRP1-0415-1030-C | IPCRP1 | IPCRP1 | 0415-1030 | Predrill and Probe For Obstructions | N | C |  | NR | P | 129000 | 128424.67 | 128424.67 | 127623.09 | 128424.67 | 90.0934 | 0 | 0 | 0 | 13231.77 | Y | 141656.44 | Y | -12656.44 | 0 | 0 | 129000 | 0 | 0 | 141656.44 | Y | -12656.44 | 0 | 0 | 129000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -141656.44 | 0 | 0 | 141656.44 | 0 | 0 | 0 | 0 | 0 | 0 | -141656.44 | 0 | 0 | 141656.44 | 141656.44 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3038 | -51.06 | 2986.94 | EA | 215 | 3074 | 2460 | 5534 | LF | 128424.67 | 801.58 | 127623.09 | 13231.77
Y | IPCRP1-0415-1030-E | IPCRP1 | IPCRP1 | 0415-1030 | Predrill and Probe For Obstructions | N | E |  | NR | P | 284796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 284796 | 0 | 0 | 284796 | 0 | 0 | 0 | Y | 284796 | 0 | 0 | 284796 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2556.04 | 0 | 2556.04 | EA | 215 | 3074 | 2460 | 5534 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0415-1030-L | IPCRP1 | IPCRP1 | 0415-1030 | Predrill and Probe For Obstructions | N | L |  | NR | P | 572314.11 | 1112721.62 | 1112721.62 | 1112721.62 | 1112721.62 | 58.7231 | 0 | 0 | 0 | 782141.08 | Y | 1894862.7 | Y | -1322548.59 | 0 | 0 | 572314.11 | 0 | 0 | 1894862.7 | Y | -1322548.59 | 0 | 0 | 572314.11 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1894862.7 | 0 | 0 | 1894862.7 | 0 | 0 | 0 | 0 | 0 | 0 | -1894862.7 | 0 | 0 | 1894862.7 | 1894862.7 | 0 | 0 | 0 | 3888 | 0 | 13599.95 | 13599.95 | 3888 | 8033.5 | 5566.45 | 13599.95 | HR | 215 | 3074 | 2460 | 5534 | LF | 0 | 0 | 0 | 782141.08
Y | IPCRP1-0415-1030-S | IPCRP1 | IPCRP1 | 0415-1030 | Predrill and Probe For Obstructions | N | S |  | UNIT | A | 0 | 58005.74 | 58005.74 | 58005.73 | 58005.74 | 100 | 0 | 0 | 0 | 0 | Y | 58005.74 | Y | -58005.74 | 0 | 0 | 0 | 0 | 0 | 58005.74 | Y | -58005.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -58005.74 | 0 | 0 | 58005.74 | 0 | 0 | 0 | 0 | 0 | 0 | -58005.74 | 0 | 0 | 58005.74 | 58005.74 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 505.5 | -489.5 | 16 | NA | 215 | 3074 | 2460 | 5534 | LF | 58005.74 | 0.01 | 58005.73 | 0
Y | IPCRP1-0416-0000-L | IPCRP1 | IPCRP1 | 0416-0000 | 3 HDG TIE ROD & ALL APPURTENANCES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0416-0000-R | IPCRP1 | IPCRP1 | 0416-0000 | 3 HDG TIE ROD & ALL APPURTENANCES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3804000 | 0 | 0 | 3804000 | 0 | 3804000 | 2145624 | 0 | N | 3804000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3804000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0416-1000-C | IPCRP1 | IPCRP1 | 0416-1000 | PM - Furnish Tierod Materials | N | C |  | UNIT | U | 0 | 210947.39 | 210947.39 | 196534.91 | 210947.39 | 102.0915 | 0 | 0 | 0 | -18438.74 | Y | 192508.65 | Y | -192508.65 | 0 | 0 | 0 | 0 | 0 | 192508.65 | Y | -192508.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -192508.65 | 4026.26 | 7146.22 | 192508.65 | 0 | 0 | 0 | 6880.5 | 19425.13 | 0 | -192508.65 | 0 | 0 | 192508.65 | 192508.65 | 0 | 0 | 0 | 0 | 0 | 5601.03 | 5601.03 | 0 | 5913.97 | -312.94 | 5601.03 | NA | 47550 | 41242 | 6308 | 47550 | LF | 210947.39 | 14412.48 | 196534.91 | -18438.74 | Raia International @209,351.87
Y | IPCRP1-0416-1000-L | IPCRP1 | IPCRP1 | 0416-1000 | PM - Furnish Tierod Materials | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 47550 | 41242 | 6308 | 47550 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0416-1000-M | IPCRP1 | IPCRP1 | 0416-1000 | PM - Furnish Tierod Materials | N | M |  | NR | P | 2577500 | 3763004.76 | 3763004.76 | 3270446.49 | 3763004.76 | 98.2494 | 0 | 0 | 0 | -434286.78 | Y | 3328717.98 | Y | -751217.98 | 0 | 0 | 2577500 | 0 | 0 | 3328717.98 | Y | -751217.98 | 0 | 0 | 2577500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3328717.98 | 7415 | 0 | 3328717.98 | 0 | 0 | 0 | 8928.36 | 0 | 0 | -3328717.98 | 0 | 0 | 3328717.98 | 3328717.98 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 122772.03 | -10 | 122762.03 | EA | 47550 | 41242 | 6308 | 47550 | LF | 3337646.34 | 492558.27 | 2845088.07 | -434286.78 | Change OMF (Mat) from $3,418,563.93 to $3,328,717.98 Anker Schroeder @$3,275,688 and East Coast Steel @$548,358. The bid plug number is smaller than the actual buy-out number.
Y | IPCRP1-0416-1010-E | IPCRP1 | IPCRP1 | 0416-1010 | Backfill Blkhead/Anchor/TieRod (CLOSED) | N | E |  | NR | P | 35532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 35532 | 0 | 0 | 35532 | 0 | 0 | 0 | N | 35532 | 0 | 0 | 35532 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 7050 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0416-1010-L | IPCRP1 | IPCRP1 | 0416-1010 | Backfill Blkhead/Anchor/TieRod (CLOSED) | N | L |  | NR | P | 137392.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 137392.89 | 0 | 0 | 137392.89 | 0 | 0 | 0 | Y | 137392.89 | 0 | 0 | 137392.89 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1128 | 0 | 0 | 0 | 1128 | 0 | 0 | 0 | HR | 7050 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | Lock this code after adjustment so that nothing can be charged here
Y | IPCRP1-0416-1012-L | IPCRP1 | IPCRP1 | 0416-1012 | Unload, Shakeout, Deliver Tie Rod Material | N | L |  | UNIT | P | 0 | 85796.67 | 85796.67 | 85796.67 | 85796.67 | 25.8424 | 0 | 0 | 0 | 246203.33 | Y | 332000 | Y | -332000 | 0 | 0 | 0 | 0 | 0 | 332000 | Y | -332000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -332000 | 0 | 4156.09 | 332000 | 0 | 0 | 0 | 0 | 0 | 0 | -332000 | 0 | 0 | 332000 | 332000 | 0 | 0 | 0 | 0 | 0 | 2342.65 | 2342.65 | 0 | 640.5 | 1702.15 | 2342.65 | HR | 850 | 450.2 | 399.8 | 850 | TN | 0 | 0 | 0 | 246203.33
Y | IPCRP1-0416-1012-S | IPCRP1 | IPCRP1 | 0416-1012 | Unload, Shakeout, Deliver Tie Rod Material | N | S |  | UNIT | A | 0 | 5117.15 | 5117.15 | 5117.15 | 5117.15 | 100 | 0 | 0 | 0 | 0 | Y | 5117.15 | Y | -5117.15 | 0 | 0 | 0 | 0 | 0 | 5117.15 | Y | -5117.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5117.15 | 0 | 0 | 5117.15 | 0 | 0 | 0 | 0 | 0 | 0 | -5117.15 | 0 | 0 | 5117.15 | 5117.15 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 43 | -30 | 13 | NA | 850 | 450.2 | 399.8 | 850 | TN | 5117.15 | 0 | 5117.15 | 0
Y | IPCRP1-0416-1014-L | IPCRP1 | IPCRP1 | 0416-1014 | Install Tie Rod Pieces @ Deadmen & Pipe Pile | N | L |  | UNIT | P | 0 | 386491.01 | 386491.01 | 386491.01 | 386491.01 | 50.7846 | 0 | 0 | 0 | 374548.99 | Y | 761040 | Y | -761040 | 0 | 0 | 0 | 0 | 0 | 761040 | Y | -761040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -761040 | 4736.81 | 11985.23 | 761040 | 0 | 0 | 0 | 0 | 0 | 0 | -761040 | 0 | 0 | 761040 | 761040 | 0 | 0 | 0 | 0 | 0 | 5428.96 | 5428.96 | 0 | 2775 | 2653.96 | 5428.96 | HR | 1208 | 729 | 581 | 1310 | EA | 0 | 0 | 0 | 374548.99
N | IPCRP1-0416-1014-S | IPCRP1 | IPCRP1 | 0416-1014 | Install Tie Rod Pieces @ Deadmen & Pipe Pile | N | S |  | UNIT | A | 0 | 129.13 | 129.13 | 129.13 | 129.13 | 100 | 0 | 0 | 0 | 0 | N | 129.13 | N | -129.13 | 0 | 0 | 0 | 0 | 0 | 129.13 | N | -129.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -129.13 | 129.13 | 0 | 129.13 | 0 | 0 | 0 | 0 | 129.13 | 0 | -129.13 | 0 | 0 | 129.13 | 129.13 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | NA | 1208 | 729 | 581 | 1310 | EA | 129.13 | 0 | 129.13 | 0
Y | IPCRP1-0416-1016-L | IPCRP1 | IPCRP1 | 0416-1016 | Install Tie Rod, Center Pieces | N | L |  | UNIT | P | 0 | 167036.6 | 167036.6 | 167036.6 | 167036.6 | 39.5072 | 0 | 0 | 0 | 255763.4 | Y | 422800 | Y | -422800 | 0 | 0 | 0 | 0 | 0 | 422800 | Y | -422800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -422800 | 0 | 0 | 422800 | 0 | 0 | 0 | 0 | 0 | 0 | -422800 | 0 | 0 | 422800 | 422800 | 0 | 0 | 0 | 0 | 0 | 3032.19 | 3032.19 | 0 | 1204 | 1828.19 | 3032.19 | HR | 1208 | 650 | 660 | 1310 | EA | 0 | 0 | 0 | 255763.4
Y | IPCRP1-0416-1018-L | IPCRP1 | IPCRP1 | 0416-1018 | Pre-Tension Tie Rod Load to 50K | N | L |  | UNIT | P | 0 | 96654.34 | 96654.34 | 96654.34 | 96654.34 | 52.9021 | 0 | 0 | 0 | 86049.84 | Y | 182704.18 | Y | -182704.18 | 0 | 0 | 0 | 0 | 0 | 182704.18 | Y | -182704.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -182704.18 | 0 | 0 | 182704.18 | 0 | 0 | 0 | 0 | 0 | 0 | -182704.18 | 0 | 0 | 182704.18 | 182704.18 | 0 | 0 | 0 | 0 | 0 | 1242.78 | 1242.78 | 0 | 669.5 | 573.28 | 1242.78 | HR | 609 | 325 | 330 | 655 | EA | 0 | 0 | 0 | 86049.84
Y | IPCRP1-0416-1020-C | IPCRP1 | IPCRP1 | 0416-1020 | Compaction Testing (CLOSED) | N | C |  | NR | P | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 27500 | 0 | 0 | 27500 | 0 | 0 | 0 | N | 27500 | 0 | 0 | 27500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 11000 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0416-1020-L | IPCRP1 | IPCRP1 | 0416-1020 | Compaction Testing (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 11000 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0416-1020-S | IPCRP1 | IPCRP1 | 0416-1020 | Compaction Testing (CLOSED) | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 11000 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0417-0000-L | IPCRP1 | IPCRP1 | 0417-0000 | COATED PAZ42/NZ19 OR = COMBI-WALL INSTALLED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0417-0000-R | IPCRP1 | IPCRP1 | 0417-0000 | COATED PAZ42/NZ19 OR = COMBI-WALL INSTALLED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 26610600 | 0 | 0 | 26610600 | 0 | 26610600 | 18244143.83 | 0 | N | 26610600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26610600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0418-0000-L | IPCRP1 | IPCRP1 | 0418-0000 | COATED PAZ43/NZ19 OR = COMBI-WALL, IN PREDRILL LO | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0418-0000-R | IPCRP1 | IPCRP1 | 0418-0000 | COATED PAZ43/NZ19 OR = COMBI-WALL, IN PREDRILL LO | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7798770 | 0 | 0 | 7798770 | 0 | 7798770 | 4149888.15 | 0 | N | 7798770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7798770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0419-0000-L | IPCRP1 | IPCRP1 | 0419-0000 | COATED PAZ43/NZ19 OR = COMBI-WALL, INTERLOCK SEAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0419-0000-R | IPCRP1 | IPCRP1 | 0419-0000 | COATED PAZ43/NZ19 OR = COMBI-WALL, INTERLOCK SEAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15305010 | 0 | 0 | 15305010 | 0 | 15305010 | 9899820 | 0 | N | 15305010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15305010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0420-0000-L | IPCRP1 | IPCRP1 | 0420-0000 | COATED AZ-46-700N OR = ST SHT PILE, INTERLOCK SEA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0420-0000-R | IPCRP1 | IPCRP1 | 0420-0000 | COATED AZ-46-700N OR = ST SHT PILE, INTERLOCK SEA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2091800 | 0 | 0 | 2091800 | 0 | 2091800 | 0 | 0 | N | 2091800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2091800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0421-0000-L | IPCRP1 | IPCRP1 | 0421-0000 | COATED AZ-46-700N OR = ST SHT PILE, P-I-M | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0421-0000-R | IPCRP1 | IPCRP1 | 0421-0000 | COATED AZ-46-700N OR = ST SHT PILE, P-I-M | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15234600 | 0 | 0 | 15234600 | 0 | 15234600 | 10310186 | 0 | N | 15234600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15234600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0422-0000-L | IPCRP1 | IPCRP1 | 0422-0000 | COATED AZ-46-700N OR = ST SHT PILE, P-I-M, LOW HR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0422-0000-R | IPCRP1 | IPCRP1 | 0422-0000 | COATED AZ-46-700N OR = ST SHT PILE, P-I-M, LOW HR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7114500 | 0 | 0 | 7114500 | 0 | 7114500 | 0 | 0 | N | 7114500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7114500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0423-0000-L | IPCRP1 | IPCRP1 | 0423-0000 | COATED AZ-46-700N OR = ST SHT PILE, TIMB CRIB, NO | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0423-0000-R | IPCRP1 | IPCRP1 | 0423-0000 | COATED AZ-46-700N OR = ST SHT PILE, TIMB CRIB, NO | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1953000 | 0 | 0 | 1953000 | 0 | 1953000 | 0 | 0 | N | 1953000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1953000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0423-1000-L | IPCRP1 | IPCRP1 | 0423-1000 | Furnish Steel Sheet Pile Materials | N | L |  | UNIT | P | 0 | -141.74 | -141.74 | -141.74 | -141.74 | 0 | 0 | 0 | 0 | 141.74 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275.47 | 275.47 | 0 | 0 | 275.47 | 275.47 | HR | 112207 | 104800 | 7407 | 112207 | SF | 0 | 0 | 0 | 141.74
Y | IPCRP1-0423-1000-M | IPCRP1 | IPCRP1 | 0423-1000 | Furnish Steel Sheet Pile Materials | N | M |  | NR | P | 5426023 | 5710883.81 | 5710883.81 | 5631931.32 | 5710883.81 | 98.6175 | 0 | 0 | 0 | 0 | Y | 5710883.81 | Y | -284860.81 | 0 | 0 | 5426023 | 0 | 0 | 5710883.81 | Y | -284860.81 | 0 | 0 | 5426023 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5710883.81 | 0 | 0 | 5710883.81 | 0 | 0 | 0 | 0 | 0 | 0 | -5710883.81 | 0 | 0 | 5710883.81 | 5710883.81 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4620990.76 | -9365.86 | 4611624.9 | EA | 112207 | 104800 | 7407 | 112207 | SF | 5710883.81 | 78952.49 | 5631931.32 | 0 | SKYLINE STEEL, LLC $ 5,359,480.47
Y | IPCRP1-0423-1010-C | IPCRP1 | IPCRP1 | 0423-1010 | drilling templates | N | C |  | NR | P | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | 100000 | Y | 100000 | 0 | 0 | 200000 | 0 | 0 | 100000 | Y | 100000 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 10 | 0 | 5 | 5 | EA | 0 | 0 | 0 | 100000
Y | IPCRP1-0423-1010-L | IPCRP1 | IPCRP1 | 0423-1010 | drilling templates | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 10 | 0 | 5 | 5 | EA | 0 | 0 | 0 | 0 | VS (12/15/24) halfway done, picking up half the budget.
Y | IPCRP1-0423-1020-E | IPCRP1 | IPCRP1 | 0423-1020 | Drive Piles (land based 458 DBL) - PIM | N | E |  | NR | P | 1530293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1530293 | 0 | 0 | 1530293 | 0 | 0 | 0 | Y | 1530293 | 0 | 0 | 1530293 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 86632 | 51550.93 | 23268.07 | 74819 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0423-1020-L | IPCRP1 | IPCRP1 | 0423-1020 | Drive Piles (land based 458 DBL) - PIM | N | L |  | NR | P | 3449996 | 690272.56 | 690272.56 | 690272.56 | 690272.56 | 65.0978 | 0 | 0 | 0 | 370090.44 | Y | 1060363 | Y | 2389633 | 0 | 0 | 3449996 | 0 | 0 | 1060363 | Y | 2389633 | 0 | 0 | 3449996 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1060363 | 0 | 0 | 1060363 | 0 | 0 | 0 | 0 | 0 | 0 | -1060363 | 0 | 0 | 1060363 | 1060363 | 0 | 0 | 0 | 22900 | 0 | 7587.48 | 7587.48 | 22900 | 4956.5 | 2630.98 | 7587.48 | HR | 86632 | 51550.93 | 23268.07 | 74819 | SF | 0 | 0 | 0 | 370090.44
Y | IPCRP1-0423-1020-S | IPCRP1 | IPCRP1 | 0423-1020 | Drive Piles (land based 458 DBL) - PIM | N | S |  | UNIT | A | 0 | 144040 | 144040 | 144040 | 144040 | 100 | 0 | 0 | 0 | 0 | Y | 144040 | Y | -144040 | 0 | 0 | 0 | 0 | 0 | 144040 | Y | -144040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -144040 | 0 | 0 | 144040 | 0 | 0 | 0 | 0 | 0 | 0 | -144040 | 0 | 0 | 144040 | 144040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | -127 | 0 | NA | 86632 | 51550.93 | 23268.07 | 74819 | SF | 144040 | 0 | 144040 | 0 | Change PMF (Sub) from $244,540.00 to $144,040.00. KMA CO
Y | IPCRP1-0423-1030-E | IPCRP1 | IPCRP1 | 0423-1030 | Drive Piles (land based 58 DBL) - PIM in Low Head | N | E |  | NR | P | 1550340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1550340 | 0 | 0 | 1550340 | 0 | 0 | 0 | N | 1550340 | 0 | 0 | 1550340 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 15810 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work deleted as per VECP #6,
Y | IPCRP1-0423-1030-L | IPCRP1 | IPCRP1 | 0423-1030 | Drive Piles (land based 58 DBL) - PIM in Low Head | N | L |  | NR | P | 3123112.9 | 18.92 | 18.92 | 18.92 | 18.92 | 100 | 0 | 0 | 0 | 0 | Y | 18.92 | Y | 3123093.98 | 0 | 0 | 3123112.9 | 0 | 0 | 18.92 | Y | 3123093.98 | 0 | 0 | 3123112.9 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18.92 | 0 | 0 | 18.92 | 0 | 0 | 0 | 0 | 0 | 0 | -18.92 | 0 | 0 | 18.92 | 18.92 | 0 | 0 | 0 | 20880 | 0 | 0 | 0 | 20880 | 0 | 0 | 0 | HR | 15810 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work deleted as per VECP #6,
Y | IPCRP1-0423-1040-E | IPCRP1 | IPCRP1 | 0423-1040 | Drive Piles (land based 31 DBL) - Non PIM in Timb | N | E |  | NR | P | 23163.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 23163.75 | 0 | 0 | 23163.75 | 0 | 0 | 0 | Y | 23163.75 | 0 | 0 | 23163.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 9765 | 0 | 9765 | 9765 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0423-1040-L | IPCRP1 | IPCRP1 | 0423-1040 | Drive Piles (land based 31 DBL) - Non PIM in Timb | N | L |  | NR | P | 40827.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40827.97 | N | 40827.97 | N | 0 | 0 | 0 | 40827.97 | 0 | 0 | 40827.97 | N | 0 | 0 | 0 | 40827.97 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -40827.97 | 0 | 0 | 40827.97 | 0 | 0 | 0 | 0 | 0 | 0 | -40827.97 | 0 | 0 | 40827.97 | 40827.97 | 0 | 0 | 0 | 275 | 0 | 275 | 275 | 275 | 0 | 275 | 275 | HR | 9765 | 0 | 9765 | 9765 | SF | 0 | 0 | 0 | 40827.97
Y | IPCRP1-0423-1050-L | IPCRP1 | IPCRP1 | 0423-1050 | Furnish Backfill Material (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1000 | 0 | 1 | 1 | TN | 0 | 0 | 0 | 0 | VS (12/15/24) halfway done, picking up half the budget
Y | IPCRP1-0423-1050-M | IPCRP1 | IPCRP1 | 0423-1050 | Furnish Backfill Material (CLOSED) | N | M |  | NR | P | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | Y | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1000 | 0 | 1 | 1 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0423-1060-C | IPCRP1 | IPCRP1 | 0423-1060 | Predrill & Backfill Bulkhead Line (Med) | N | C |  | NR | P | 273.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 273.46 | 0 | 0 | 273.46 | 0 | 0 | 0 | Y | 273.46 | 0 | 0 | 273.46 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 24 | -24 | 0 | LF | 2150 | 0 | 2150 | 2150 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-0423-1060-E | IPCRP1 | IPCRP1 | 0423-1060 | Predrill & Backfill Bulkhead Line (Med) | N | E |  | NR | P | 78240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 78240 | 0 | 0 | 78240 | 0 | 0 | 0 | Y | 78240 | 0 | 0 | 78240 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2150 | 0 | 2150 | 2150 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-0423-1060-L | IPCRP1 | IPCRP1 | 0423-1060 | Predrill & Backfill Bulkhead Line (Med) | N | L |  | NR | P | 104728.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104728.77 | N | 104728.77 | N | 0 | 0 | 0 | 104728.77 | 0 | 0 | 104728.77 | N | 0 | 0 | 0 | 104728.77 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -104728.77 | 0 | 0 | 104728.77 | 0 | 0 | 0 | 0 | 0 | 0 | -104728.77 | 0 | 0 | 104728.77 | 104728.77 | 0 | 0 | 0 | 768 | 0 | 768 | 768 | 768 | 0 | 768 | 768 | HR | 2150 | 0 | 2150 | 2150 | VF | 0 | 0 | 0 | 104728.77
Y | IPCRP1-0424-0000-L | IPCRP1 | IPCRP1 | 0424-0000 | PRECAST CONC SLAB UNIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0424-0000-R | IPCRP1 | IPCRP1 | 0424-0000 | PRECAST CONC SLAB UNIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 195200 | 0 | 0 | 195200 | 0 | 195200 | 0 | 0 | N | 195200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0425-0000-L | IPCRP1 | IPCRP1 | 0425-0000 | STRUCT ST (UNCOATED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0425-0000-R | IPCRP1 | IPCRP1 | 0425-0000 | STRUCT ST (UNCOATED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1459065 | 0 | 0 | 1459065 | 0 | 1459065 | 1807889.05 | 0 | N | 1459065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1459065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0425-1000-C | IPCRP1 | IPCRP1 | 0425-1000 | Structural Steel (Uncoated), PM | N | C |  | UNIT | U | 0 | 24574 | 24574 | 24574 | 24574 | 100 | 0 | 0 | 0 | 0 | Y | 24574 | Y | -24574 | 0 | 0 | 0 | 0 | 0 | 24574 | Y | -24574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24574 | 0 | 0 | 24574 | 0 | 0 | 0 | 0 | 0 | 0 | -24574 | 0 | 0 | 24574 | 24574 | 0 | 0 | 0 | 0 | 0 | 2355.75 | 2355.75 | 0 | 2407 | -51.25 | 2355.75 | NA | 291813 | 361577.81 | 294205 | 655782.81 | LB | 24574 | 0 | 24574 | 0
Y | IPCRP1-0425-1000-L | IPCRP1 | IPCRP1 | 0425-1000 | Structural Steel (Uncoated), PM | N | L |  | UNIT | P | 0 | -0.28 | -0.28 | -0.28 | -0.28 | 100 | 0 | 0 | 0 | 0 | Y | -0.28 | Y | 0.28 | 0 | 0 | 0 | 0 | 0 | -0.28 | Y | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0.28 | 0 | 0 | -0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28 | 0 | 0 | -0.28 | -0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 291813 | 361577.81 | 294205 | 655782.81 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0425-1000-M | IPCRP1 | IPCRP1 | 0425-1000 | Structural Steel (Uncoated), PM | N | M |  | UNIT | U | 0 | 1124763.67 | 1124763.67 | 1098894.94 | 1124763.67 | 98.0045 | 0 | 0 | 0 | -3494.35 | Y | 1121269.32 | Y | -1121269.32 | 0 | 0 | 0 | 0 | 0 | 1121269.32 | Y | -1121269.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1121269.32 | 0 | 0 | 1121269.32 | 0 | 0 | 0 | 0 | 0 | 0 | -1121269.32 | 0 | 0 | 1121269.32 | 1121269.32 | 0 | 0 | 0 | 0 | 0 | 29247.7 | 29247.7 | 0 | 29466.1 | -218.4 | 29247.7 | NA | 291813 | 361577.81 | 294205 | 655782.81 | LB | 1124763.67 | 25868.73 | 1098894.94 | -3494.35 | RD (4/29/25) est final qty = 655,782.81 lbs East Coast Steel Fabrication, $1,067,033.00
Y | IPCRP1-0425-1000-S | IPCRP1 | IPCRP1 | 0425-1000 | Structural Steel (Uncoated), PM | N | S |  | NR | A | 919210.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 919210.95 | 0 | 0 | 919210.95 | 0 | 0 | 0 | N | 919210.95 | 0 | 0 | 919210.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 291813 | 361577.81 | 294205 | 655782.81 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0425-1010-L | IPCRP1 | IPCRP1 | 0425-1010 | Structural Steel (Uncoated), Install | N | L |  | UNIT | P | 0 | 668572.8 | 668572.8 | 668572.8 | 668572.8 | 56.4117 | 0 | 0 | 0 | 516593.15 | Y | 1185165.95 | Y | -1185165.95 | 0 | 0 | 0 | 0 | 0 | 1185165.95 | Y | -1185165.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1185165.95 | 30777.29 | 513.19 | 1185165.95 | 0 | 0 | 0 | 0 | 0 | 0 | -1185165.95 | 0 | 0 | 1185165.95 | 1185165.95 | 0 | 0 | 0 | 0 | 0 | 8465 | 8465 | 0 | 4862 | 3603 | 8465 | HR | 291813 | 361577.81 | 294205 | 655782.81 | LB | 0 | 0 | 0 | 516593.15 | New code for labor activity of 0425-1000 Structural Steel (Uncoated)
Y | IPCRP1-0425-1010-S | IPCRP1 | IPCRP1 | 0425-1010 | Structural Steel (Uncoated), Install | N | S |  | UNIT | A | 0 | 498.35 | 498.35 | 498.35 | 498.35 | 100 | 0 | 0 | 0 | 0 | N | 498.35 | N | -498.35 | 0 | 0 | 0 | 0 | 0 | 498.35 | N | -498.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -498.35 | 0 | 0 | 498.35 | 0 | 0 | 0 | 0 | 0 | 0 | -498.35 | 0 | 0 | 498.35 | 498.35 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 291813 | 361577.81 | 294205 | 655782.81 | LB | 498.35 | 0 | 498.35 | 0
Y | IPCRP1-0426-0000-L | IPCRP1 | IPCRP1 | 0426-0000 | STRUCT ST (COATED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0426-0000-R | IPCRP1 | IPCRP1 | 0426-0000 | STRUCT ST (COATED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1417545 | 0 | 0 | 1417545 | 0 | 1417545 | 0 | 0 | N | 1417545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0426-1000-L | IPCRP1 | IPCRP1 | 0426-1000 | STRUCT ST (COATED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000.5 | Y | 22000.5 | Y | -22000.5 | 0 | 0 | 0 | 0 | 0 | 22000.5 | Y | -22000.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22000.5 | 0 | 0 | 22000.5 | 0 | 0 | 0 | 0 | 0 | 0 | -22000.5 | 0 | 0 | 22000.5 | 22000.5 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 150 | 150 | HR | 283509 | 0 | 11000 | 11000 | LB | 0 | 0 | 0 | 22000.5
Y | IPCRP1-0426-1000-M | IPCRP1 | IPCRP1 | 0426-1000 | STRUCT ST (COATED) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 283509 | 0 | 11000 | 11000 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0426-1000-S | IPCRP1 | IPCRP1 | 0426-1000 | STRUCT ST (COATED) | N | S |  | NR | A | 961095.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | Y | 22000 | Y | 939095.51 | 0 | 0 | 961095.51 | 0 | 0 | 22000 | Y | 939095.51 | 0 | 0 | 961095.51 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22000 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | -22000 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 283509 | 0 | 11000 | 11000 | LB | 0 | 0 | 0 | 22000
Y | IPCRP1-0427-0000-L | IPCRP1 | IPCRP1 | 0427-0000 | STRUCT ST (GALV) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0427-0000-R | IPCRP1 | IPCRP1 | 0427-0000 | STRUCT ST (GALV) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57640 | 0 | 0 | 57640 | 0 | 57640 | 43791.05 | 0 | N | 57640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0427-1000-L | IPCRP1 | IPCRP1 | 0427-1000 | STRUCT ST (GALV) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 11528 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0427-1000-S | IPCRP1 | IPCRP1 | 0427-1000 | STRUCT ST (GALV) | N | S |  | NR | A | 39079.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 39079.92 | 0 | 0 | 39079.92 | 0 | 0 | 0 | N | 39079.92 | 0 | 0 | 39079.92 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 11528 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | Moved to cc: 0446-1010 Marine Demo sub (Trevcon)
Y | IPCRP1-0428-0000-L | IPCRP1 | IPCRP1 | 0428-0000 | LONG EXP JT BTWN ESPLANADE & CUT OFF WALL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0428-0000-R | IPCRP1 | IPCRP1 | 0428-0000 | LONG EXP JT BTWN ESPLANADE & CUT OFF WALL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1596160 | 0 | 0 | 1596160 | 0 | 1596160 | 267990.4 | 0 | N | 1596160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0428-1000-L | IPCRP1 | IPCRP1 | 0428-1000 | Inst Long Exp Jt Btwn Esplanade & Cut Off Wall | N | L |  | NR | P | 110017.81 | 69734.07 | 69734.07 | 69734.07 | 69734.07 | 46.4894 | 0 | 0 | 0 | 80265.93 | Y | 150000 | Y | -39982.19 | 0 | 0 | 110017.81 | 0 | 0 | 150000 | Y | -39982.19 | 0 | 0 | 110017.81 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | -150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 931.09 | 0 | 1172.17 | 1172.17 | 931.09 | 553.5 | 618.67 | 1172.17 | HR | 4988 | 837.47 | 735.53 | 1573 | LF | 0 | 0 | 0 | 80265.93 | Adjust PMF down to 1,573.00 (Jacobs quantity) as a result of Comm Det to IPC dispute #22/ claim #14
Y | IPCRP1-0428-1000-S | IPCRP1 | IPCRP1 | 0428-1000 | Inst Long Exp Jt Btwn Esplanade & Cut Off Wall | N | S |  | UNIT | A | 0 | 1365.86 | 1365.86 | 1365.86 | 1365.86 | 100 | 0 | 0 | 0 | 0 | N | 1365.86 | N | -1365.86 | 0 | 0 | 0 | 0 | 0 | 1365.86 | N | -1365.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1365.86 | 0 | 0 | 1365.86 | 0 | 0 | 0 | 0 | 0 | 0 | -1365.86 | 0 | 0 | 1365.86 | 1365.86 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 12 | NA | 4988 | 837.47 | 735.53 | 1573 | LF | 1365.86 | 0 | 1365.86 | 0
Y | IPCRP1-0428-1010-L | IPCRP1 | IPCRP1 | 0428-1010 | PM - Long Exp Jt Btwn Esplanade & Cut Off Wall | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4988 | 837.47 | 735.53 | 1573 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0428-1010-M | IPCRP1 | IPCRP1 | 0428-1010 | PM - Long Exp Jt Btwn Esplanade & Cut Off Wall | N | M |  | NR | P | 1247000 | 497880 | 497880 | 267733.34 | 497880 | 53.7747 | 0 | 0 | 0 | 0 | Y | 497880 | Y | 749120 | 0 | 0 | 1247000 | 0 | 0 | 497880 | Y | 749120 | 0 | 0 | 1247000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -497880 | 0 | 0 | 497880 | 0 | 0 | 0 | 0 | 0 | 0 | -497880 | 0 | 0 | 497880 | 497880 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 266536.54 | 224790.26 | 491326.8 | EA | 4988 | 837.47 | 735.53 | 1573 | LF | 497880 | 230146.66 | 267733.34 | 0 | Portion of Susan Bauer PO #1320 ($487,080.00). Adjust PMF down to 1,573.00 (Jacobs quantity) as a result of Comm Det to IPC dispute #22/ claim #14
Y | IPCRP1-0429-0000-L | IPCRP1 | IPCRP1 | 0429-0000 | TRANS EXP JT AT PILE CAPS BTWN ESPLANADE SPANS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0429-0000-R | IPCRP1 | IPCRP1 | 0429-0000 | TRANS EXP JT AT PILE CAPS BTWN ESPLANADE SPANS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 390490 | 0 | 0 | 390490 | 0 | 390490 | 312607.9 | 0 | N | 390490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0429-1000-L | IPCRP1 | IPCRP1 | 0429-1000 | Inst Trans Exp Jt at Pile Caps Btwn Esplanade Spa | N | L |  | NR | P | 30398.01 | 76523.64 | 76523.64 | 76523.64 | 76523.64 | 54.6597 | 0 | 0 | 0 | 63476.36 | Y | 140000 | Y | -109601.99 | 0 | 0 | 30398.01 | 0 | 0 | 140000 | Y | -109601.99 | 0 | 0 | 30398.01 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -140000 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | -140000 | 0 | 0 | 140000 | 140000 | 0 | 0 | 0 | 257.26 | 0 | 1062.74 | 1062.74 | 257.26 | 577.5 | 485.24 | 1062.74 | HR | 2297 | 1838.85 | 1161.15 | 3000 | LF | 0 | 0 | 0 | 63476.36
Y | IPCRP1-0429-1000-S | IPCRP1 | IPCRP1 | 0429-1000 | Inst Trans Exp Jt at Pile Caps Btwn Esplanade Spa | N | S |  | UNIT | A | 0 | 3771.67 | 3771.67 | 3771.67 | 3771.67 | 100 | 0 | 0 | 0 | 0 | N | 3771.67 | N | -3771.67 | 0 | 0 | 0 | 0 | 0 | 3771.67 | N | -3771.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3771.67 | 0 | 0 | 3771.67 | 0 | 0 | 0 | 0 | 0 | 0 | -3771.67 | 0 | 0 | 3771.67 | 3771.67 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 0 | 33 | 0 | 33 | NA | 2297 | 1838.85 | 1161.15 | 3000 | LF | 3771.67 | 0 | 3771.67 | 0
Y | IPCRP1-0429-1010-L | IPCRP1 | IPCRP1 | 0429-1010 | PM - Trans Exp Jt at Pile Caps Btwn Esplanade Spa | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2297 | 1834.35 | 1165.65 | 3000 | LF | 0 | 0 | 0 | 0 | Adjust PMF up to 3,000.00 (Sumit's quantity) refer to his email dated 1/20/25
Y | IPCRP1-0429-1010-M | IPCRP1 | IPCRP1 | 0429-1010 | PM - Trans Exp Jt at Pile Caps Btwn Esplanade Spa | N | M |  | NR | P | 298610 | 408683 | 408683 | 271096.91 | 408683 | 66.3343 | 0 | 0 | 0 | 0 | Y | 408683 | Y | -110073 | 0 | 0 | 298610 | 0 | 0 | 408683 | Y | -110073 | 0 | 0 | 298610 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -408683 | 0 | 0 | 408683 | 0 | 0 | 0 | 0 | 0 | 0 | -408683 | 0 | 0 | 408683 | 408683 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 255604.06 | -255604.06 | 0 | EA | 2297 | 1834.35 | 1165.65 | 3000 | LF | 408683 | 137586.09 | 271096.91 | 0 | Adjust PMF up to 3,000.00 (Sumit's quantity) refer to his email dated 1/20/25
Y | IPCRP1-0430-0000-L | IPCRP1 | IPCRP1 | 0430-0000 | CONC DETERRENT FURNITURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0430-0000-R | IPCRP1 | IPCRP1 | 0430-0000 | CONC DETERRENT FURNITURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 180000 | 0 | 0 | 180000 | 0 | 180000 | 180000 | 0 | N | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0430-1000-E | IPCRP1 | IPCRP1 | 0430-1000 | Inst Conc Deterrent Furniture | N | E |  | NR | P | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | Y | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 15 | 15 | 0 | 15 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0430-1000-L | IPCRP1 | IPCRP1 | 0430-1000 | Inst Conc Deterrent Furniture | N | L |  | NR | P | 18020.22 | 1159.73 | 1159.73 | 1159.73 | 1159.73 | 100 | 0 | 0 | 0 | 0 | Y | 1159.73 | Y | 16860.49 | 0 | 0 | 18020.22 | 0 | 0 | 1159.73 | Y | 16860.49 | 0 | 0 | 18020.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1159.73 | 0 | 0 | 1159.73 | 0 | 0 | 0 | 0 | 0 | 0 | -1159.73 | 0 | 0 | 1159.73 | 1159.73 | 0 | 0 | 0 | 168 | 0 | 11 | 11 | 168 | 11 | 0 | 11 | HR | 15 | 15 | 0 | 15 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0430-1010-L | IPCRP1 | IPCRP1 | 0430-1010 | PM - Conc Deterrent Furniture | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 15 | 15 | 0 | 15 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0430-1010-M | IPCRP1 | IPCRP1 | 0430-1010 | PM - Conc Deterrent Furniture | N | M |  | NR | P | 154950 | 34000 | 34000 | 34000 | 34000 | 100 | 0 | 0 | 0 | 0 | Y | 34000 | Y | 120950 | 0 | 0 | 154950 | 0 | 0 | 34000 | Y | 120950 | 0 | 0 | 154950 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -34000 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | -34000 | 0 | 0 | 34000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5115 | 0 | 5115 | EA | 15 | 15 | 0 | 15 | EA | 34000 | 0 | 34000 | 0
Y | IPCRP1-0431-0000-L | IPCRP1 | IPCRP1 | 0431-0000 | RIP RAP ROCK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0431-0000-R | IPCRP1 | IPCRP1 | 0431-0000 | RIP RAP ROCK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 465600 | 0 | 0 | 465600 | 0 | 465600 | 495144 | 0 | N | 465600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0431-1000-E | IPCRP1 | IPCRP1 | 0431-1000 | Install Rip Rap | N | E |  | NR | P | 8507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 8507 | 0 | 0 | 8507 | 0 | 0 | 0 | Y | 8507 | 0 | 0 | 8507 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 12760 | 1237.86 | 593.14 | 1831 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0431-1000-L | IPCRP1 | IPCRP1 | 0431-1000 | Install Rip Rap | N | L |  | NR | P | 63872.16 | 51006.61 | 51006.61 | 51006.61 | 51006.61 | 65.3121 | 0 | 0 | 0 | 27090.16 | Y | 78096.77 | Y | -14224.61 | 0 | 0 | 63872.16 | 0 | 0 | 78096.77 | Y | -14224.61 | 0 | 0 | 63872.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -78096.77 | 0 | 0 | 78096.77 | 0 | 0 | 0 | 0 | 0 | 0 | -78096.77 | 0 | 0 | 78096.77 | 78096.77 | 0 | 0 | 0 | 595.47 | 0 | 604 | 604 | 595.47 | 396 | 208 | 604 | HR | 12760 | 1237.86 | 593.14 | 1831 | CY | 0 | 0 | 0 | 27090.16
Y | IPCRP1-0431-1000-M | IPCRP1 | IPCRP1 | 0431-1000 | Install Rip Rap | N | M |  | NR | P | 10527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 10527 | 0 | 0 | 10527 | 0 | 0 | 0 | N | 10527 | 0 | 0 | 10527 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 12760 | 1237.86 | 593.14 | 1831 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0431-1000-S | IPCRP1 | IPCRP1 | 0431-1000 | Install Rip Rap | N | S |  | UNIT | A | 0 | 4555.08 | 4555.08 | 4555.08 | 4555.08 | 100 | 0 | 0 | 0 | 0 | Y | 4555.08 | Y | -4555.08 | 0 | 0 | 0 | 0 | 0 | 4555.08 | Y | -4555.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4555.08 | 0 | 0 | 4555.08 | 0 | 0 | 0 | 0 | 0 | 0 | -4555.08 | 0 | 0 | 4555.08 | 4555.08 | 0 | 0 | 0 | 0 | 0 | 5.5 | 5.5 | 0 | 39.5 | -34 | 5.5 | NA | 12760 | 1237.86 | 593.14 | 1831 | CY | 4555.08 | 0 | 4555.08 | 0
Y | IPCRP1-0431-1010-L | IPCRP1 | IPCRP1 | 0431-1010 | PM - Rip Rap Rock | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 140 | 1237.86 | 593.14 | 1831 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0431-1010-M | IPCRP1 | IPCRP1 | 0431-1010 | PM - Rip Rap Rock | N | M |  | UNIT | U | 0 | 257211.88 | 257211.88 | 58459.45 | 257211.88 | 22.7281 | 0 | 0 | 0 | 0 | Y | 257211.88 | Y | -257211.88 | 0 | 0 | 0 | 0 | 0 | 257211.88 | Y | -257211.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -257211.88 | 0 | 0 | 257211.88 | 0 | 0 | 0 | 0 | 0 | 0 | -257211.88 | 0 | 0 | 257211.88 | 257211.88 | 0 | 0 | 0 | 0 | 0 | 73.96 | 73.96 | 0 | 1985.04 | -1911.08 | 73.96 | NA | 140 | 1237.86 | 593.14 | 1831 | CY | 257211.88 | 198752.43 | 58459.45 | 0 | Revised EST Final Quantity (ZH, 11.20.24) 1,217.15 (Phase 1) + 489 (new N embay) + 5 x 25 = 125 (last 5 outfalls) = 1,831.00 CY. Change PMF (Mat) from $2,178.12 to $250,912.82
Y | IPCRP1-0431-1010-S | IPCRP1 | IPCRP1 | 0431-1010 | PM - Rip Rap Rock | N | S |  | NR | A | 317574.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 317574.04 | 0 | 0 | 317574.04 | 0 | 0 | 0 | Y | 317574.04 | 0 | 0 | 317574.04 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 140 | 1237.86 | 593.14 | 1831 | CY | 0 | 0 | 0 | 0 | Change PMF (Sub) from $317,574.04 to $0.00
Y | IPCRP1-0432-0000-L | IPCRP1 | IPCRP1 | 0432-0000 | DEMO EXIST ESPLANADE TYPE A | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0432-0000-R | IPCRP1 | IPCRP1 | 0432-0000 | DEMO EXIST ESPLANADE TYPE A | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2697750 | 0 | 0 | 2640000 | 0 | 2697750 | 2749615 | 0 | N | 2697750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2697750 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0432-1000-E | IPCRP1 | IPCRP1 | 0432-1000 | Type A Esplanade Demo (Civil) | N | E |  | NR | P | 67989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 67989 | 0 | 0 | 67989 | 0 | 0 | 0 | N | 67989 | 0 | 0 | 67989 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 960 | 999.86 | 1.65 | 1001.51 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0432-1000-L | IPCRP1 | IPCRP1 | 0432-1000 | Type A Esplanade Demo (Civil) | N | L |  | NR | P | 367453 | 343379.87 | 343379.87 | 343379.87 | 343379.87 | 100 | 0 | 0 | 0 | 0.01 | Y | 343379.88 | Y | 24073.12 | 0 | 0 | 367453 | 0 | 0 | 343379.88 | Y | 24073.12 | 0 | 0 | 367453 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -343379.88 | 0 | 0 | 343379.88 | 0 | 0 | 0 | 0 | 0 | 0 | -343379.88 | 0 | 0 | 343379.88 | 343379.88 | 0 | 0 | 0 | 3059.06 | 0 | 2766 | 2766 | 3059.06 | 2766 | 0 | 2766 | HR | 960 | 999.86 | 1.65 | 1001.51 | LF | 0 | 0 | 0 | 0.01 | PCO #055 - Add 21.00 LF to account for oversized wall thickness. EE (960.00) + Overrun (20.51) + PCO#55 (21.00) for oversized wall thickness = 1,001.51. PTD = 960 + 20.51 + 16.85 = 997.36 LF.
Y | IPCRP1-0432-1000-S | IPCRP1 | IPCRP1 | 0432-1000 | Type A Esplanade Demo (Civil) | N | S |  | UNIT | A | 0 | 11140.48 | 11140.48 | 11140.48 | 11140.48 | 100 | 0 | 0 | 0 | 0 | Y | 11140.48 | Y | -11140.48 | 0 | 0 | 0 | 0 | 0 | 11140.48 | Y | -11140.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11140.48 | 0 | 0 | 11140.48 | 0 | 0 | 0 | 0 | 0 | 0 | -11140.48 | 0 | 0 | 11140.48 | 11140.48 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 20090 | -20085 | 5 | NA | 960 | 999.86 | 1.65 | 1001.51 | LF | 11140.48 | 0 | 11140.48 | 0
Y | IPCRP1-0432-1010-L | IPCRP1 | IPCRP1 | 0432-1010 | Demo Exist Esplanade Type A (Marine Portion) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 960 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0432-1010-S | IPCRP1 | IPCRP1 | 0432-1010 | Demo Exist Esplanade Type A (Marine Portion) | N | S |  | NR | A | 1971286.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1971286.75 | 0 | 0 | 1971286.75 | 0 | 0 | 0 | Y | 1971286.75 | 0 | 0 | 1971286.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 960 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0433-0000-L | IPCRP1 | IPCRP1 | 0433-0000 | DEMO STRUCT - AMPHITHEATRER ELECT SHED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0433-0000-R | IPCRP1 | IPCRP1 | 0433-0000 | DEMO STRUCT - AMPHITHEATRER ELECT SHED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0434-0000-L | IPCRP1 | IPCRP1 | 0434-0000 | DEMO EXIST ESPLANADE TYPE C-1 & C-2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0434-0000-R | IPCRP1 | IPCRP1 | 0434-0000 | DEMO EXIST ESPLANADE TYPE C-1 & C-2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4620000 | 0 | 0 | 4620000 | 0 | 4620000 | 4572000 | 0 | N | 4620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0434-1000-E | IPCRP1 | IPCRP1 | 0434-1000 | Demo Exist Esplanade Type C1 & C2 (Railing) | N | E |  | NR | P | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3850 | 0 | 0 | 3850 | 0 | 0 | 0 | Y | 3850 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2310 | 2311 | -25 | 2286 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0434-1000-L | IPCRP1 | IPCRP1 | 0434-1000 | Demo Exist Esplanade Type C1 & C2 (Railing) | N | L |  | NR | P | 21069.42 | 128655.06 | 128655.06 | 128655.06 | 128655.06 | 106.5615 | 0 | 0 | 0 | -7921.93 | Y | 120733.13 | Y | -99663.71 | 0 | 0 | 21069.42 | 0 | 0 | 120733.13 | Y | -99663.71 | 0 | 0 | 21069.42 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -120733.13 | 7921.93 | 18153.37 | 120733.13 | 0 | 0 | 0 | 0 | 0 | 0 | -120733.13 | 0 | 0 | 120733.13 | 120733.13 | 0 | 0 | 0 | 192.5 | 0 | 928.5 | 928.5 | 192.5 | 984.5 | -56 | 928.5 | HR | 2310 | 2311 | -25 | 2286 | LF | 0 | 0 | 0 | -7921.93 | As / Juan B. email 1/21/26, est final quantity = 2,285.97 LF
Y | IPCRP1-0434-1000-S | IPCRP1 | IPCRP1 | 0434-1000 | Demo Exist Esplanade Type C1 & C2 (Railing) | N | S |  | UNIT | A | 0 | 6770.02 | 6770.02 | 6770.02 | 6770.02 | 122.1311 | 0 | 0 | 0 | -1226.78 | Y | 5543.24 | Y | -5543.24 | 0 | 0 | 0 | 0 | 0 | 5543.24 | Y | -5543.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5543.24 | 1226.78 | 720.79 | 5543.24 | 0 | 0 | 0 | 0 | 1226.78 | 0 | -5543.24 | 0 | 0 | 5543.24 | 5543.24 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 38 | -35 | 3 | NA | 2310 | 2311 | -25 | 2286 | LF | 6770.02 | 0 | 6770.02 | -1226.78
Y | IPCRP1-0434-1010-L | IPCRP1 | IPCRP1 | 0434-1010 | Demo Exist Esplanade Type C-1 & C-2 (Marine Porti | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2310 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0434-1010-S | IPCRP1 | IPCRP1 | 0434-1010 | Demo Exist Esplanade Type C-1 & C-2 (Marine Porti | N | S |  | NR | A | 4600749.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4600749.85 | 0 | 0 | 4600749.85 | 0 | 0 | 0 | Y | 4600749.85 | 0 | 0 | 4600749.85 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2310 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0435-0000-L | IPCRP1 | IPCRP1 | 0435-0000 | DEMO EXIST CONC BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0435-0000-R | IPCRP1 | IPCRP1 | 0435-0000 | DEMO EXIST CONC BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7440 | 0 | 0 | 7440 | 0 | 7440 | 12060 | 0 | N | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0435-1000-E | IPCRP1 | IPCRP1 | 0435-1000 | Demo of Exist Conc Barrier | N | E |  | NR | P | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 248 | 402 | 0 | 402 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0435-1000-L | IPCRP1 | IPCRP1 | 0435-1000 | Demo of Exist Conc Barrier | N | L |  | NR | P | 3576.22 | 4885.83 | 4885.83 | 4885.83 | 4885.83 | 100 | 0 | 0 | 0 | 0 | Y | 4885.83 | Y | -1309.61 | 0 | 0 | 3576.22 | 0 | 0 | 4885.83 | Y | -1309.61 | 0 | 0 | 3576.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4885.83 | 0 | 0 | 4885.83 | 0 | 0 | 0 | 0 | 0 | 0 | -4885.83 | 0 | 0 | 4885.83 | 4885.83 | 0 | 0 | 0 | 32 | 0 | 48 | 48 | 32 | 48 | 0 | 48 | HR | 248 | 402 | 0 | 402 | LF | 0 | 0 | 0 | 0 | Change PMF (MH) from 100,00 to 32.00
Y | IPCRP1-0435-1010-L | IPCRP1 | IPCRP1 | 0435-1010 | Flatbed Trucking (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1.5 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0435-1010-S | IPCRP1 | IPCRP1 | 0435-1010 | Flatbed Trucking (CLOSED) | N | S |  | NR | A | 2085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2085 | 0 | 0 | 2085 | 0 | 0 | 0 | Y | 2085 | 0 | 0 | 2085 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1.5 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0436-0000-L | IPCRP1 | IPCRP1 | 0436-0000 | DEMO EXIST EMBEDDED CONC BARRIER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0436-0000-R | IPCRP1 | IPCRP1 | 0436-0000 | DEMO EXIST EMBEDDED CONC BARRIER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57200 | 0 | 0 | 57200 | 0 | 57200 | 56000 | 0 | N | 57200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0436-1000-E | IPCRP1 | IPCRP1 | 0436-1000 | Demo of Embedded Conc Barrier | N | E |  | NR | P | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4800 | 0 | 0 | 4800 | 0 | 0 | 0 | Y | 4800 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1430 | 1400 | 30 | 1430 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0436-1000-L | IPCRP1 | IPCRP1 | 0436-1000 | Demo of Embedded Conc Barrier | N | L |  | NR | P | 14304.88 | 21257.26 | 21257.26 | 21257.26 | 21257.26 | 88.5719 | 0 | 0 | 0 | 2742.74 | Y | 24000 | Y | -9695.12 | 0 | 0 | 14304.88 | 0 | 0 | 24000 | Y | -9695.12 | 0 | 0 | 14304.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24000 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | -24000 | 0 | 0 | 24000 | 24000 | 0 | 0 | 0 | 128 | 0 | 168.86 | 168.86 | 128 | 150 | 18.86 | 168.86 | HR | 1430 | 1400 | 30 | 1430 | LF | 0 | 0 | 0 | 2742.74
Y | IPCRP1-0436-1010-E | IPCRP1 | IPCRP1 | 0436-1010 | Flatbed Trucking (CLOSED) | N | E |  | NR | P | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 12510 | 0 | 0 | 12510 | 0 | 0 | 0 | N | 12510 | 0 | 0 | 12510 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 9 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0436-1010-L | IPCRP1 | IPCRP1 | 0436-1010 | Flatbed Trucking (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 9 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0437-0000-L | IPCRP1 | IPCRP1 | 0437-0000 | DEMO EXIST CONC CURB | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0437-0000-R | IPCRP1 | IPCRP1 | 0437-0000 | DEMO EXIST CONC CURB | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 58200 | 0 | 0 | 58200 | 0 | 58200 | 2000 | 0 | N | 58200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0437-1000-E | IPCRP1 | IPCRP1 | 0437-1000 | DEMO EXIST CONC CURB | N | E |  | NR | P | 4365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4365 | 0 | 0 | 4365 | 0 | 0 | 0 | Y | 4365 | 0 | 0 | 4365 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2910 | 100 | 2810 | 2910 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0437-1000-L | IPCRP1 | IPCRP1 | 0437-1000 | DEMO EXIST CONC CURB | N | L |  | NR | P | 13008.51 | -0.41 | -0.41 | -0.41 | -0.41 | -0.0031518 | 0 | 0 | 0 | 13008.92 | N | 13008.51 | N | 0 | 0 | 0 | 13008.51 | 0 | 0 | 13008.51 | N | 0 | 0 | 0 | 13008.51 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13008.51 | 0 | 0 | 13008.51 | 0 | 0 | 0 | 0 | 0 | 0 | -13008.51 | 0 | 0 | 13008.51 | 13008.51 | 0 | 0 | 0 | 116.4 | 0 | 116.4 | 116.4 | 116.4 | 0 | 116.4 | 116.4 | HR | 2910 | 100 | 2810 | 2910 | LF | 0 | 0 | 0 | 13008.92
Y | IPCRP1-0437-1010-L | IPCRP1 | IPCRP1 | 0437-1010 | Sawcutting Sub fro Demo of Exist Curb | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2910 | 0 | 2910 | 2910 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0437-1010-S | IPCRP1 | IPCRP1 | 0437-1010 | Sawcutting Sub fro Demo of Exist Curb | N | S |  | NR | A | 23280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23280 | N | 23280 | N | 0 | 0 | 0 | 23280 | 0 | 0 | 23280 | N | 0 | 0 | 0 | 23280 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23280 | 0 | 0 | 23280 | 0 | 0 | 0 | 0 | 0 | 0 | -23280 | 0 | 0 | 23280 | 23280 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 2910 | 0 | 2910 | 2910 | LF | 0 | 0 | 0 | 23280
Y | IPCRP1-0438-0000-L | IPCRP1 | IPCRP1 | 0438-0000 | DEMO EXIST ESPLANADE TYPE D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0438-0000-R | IPCRP1 | IPCRP1 | 0438-0000 | DEMO EXIST ESPLANADE TYPE D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4240472.5 | 0 | 0 | 4152500 | 0 | 4240472.5 | 4389742.5 | 0 | N | 4240472.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4240472.5 | 0 | 0 | 31.99 | 31.99 | 0 | 0 | 31.99 | 31.99 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0438-1000-E | IPCRP1 | IPCRP1 | 0438-1000 | Type D Esplanade Demo (Civil) | N | E |  | NR | P | 133274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 133274 | 0 | 0 | 133274 | 0 | 0 | 0 | N | 133274 | 0 | 0 | 133274 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1510 | 1769.03 | -144 | 1625.03 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0438-1000-L | IPCRP1 | IPCRP1 | 0438-1000 | Type D Esplanade Demo (Civil) | N | L |  | NR | P | 732285 | 657940.78 | 657940.78 | 657940.78 | 657940.78 | 101.2509 | 0 | 0 | 0 | -8128.4 | Y | 649812.38 | Y | 82472.62 | 0 | 0 | 732285 | 0 | 0 | 649812.38 | Y | 82472.62 | 0 | 0 | 732285 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -649812.38 | 10821.51 | 14221.96 | 649812.38 | 0 | 0 | 0 | 0 | 0 | 0 | -649812.38 | 0 | 0 | 649812.38 | 649812.38 | 0 | 0 | 0 | 5833.04 | 0 | 4783.95 | 4783.95 | 5833.04 | 4857.5 | -73.55 | 4783.95 | HR | 1510 | 1769.03 | -144 | 1625.03 | LF | 0 | 0 | 0 | -8128.4 | Change PMF (MH) from 6,003.42 to 5983.00
Y | IPCRP1-0438-1000-S | IPCRP1 | IPCRP1 | 0438-1000 | Type D Esplanade Demo (Civil) | N | S |  | UNIT | A | 0 | 1267210.42 | 1267210.42 | 1080793.32 | 1267210.42 | 85.2892 | 0 | 0 | 0 | 0 | Y | 1267210.42 | Y | -1267210.42 | 0 | 0 | 0 | 0 | 0 | 1267210.42 | Y | -1267210.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1267210.42 | 37770 | 7076.89 | 1267210.42 | 0 | 0 | 0 | 0 | 22950 | 0 | -1267210.42 | 0 | 0 | 1267210.42 | 1267210.42 | 0 | 0 | 0 | 0 | 0 | 491 | 491 | 0 | 9244 | -8753 | 491 | NA | 1510 | 1769.03 | -144 | 1625.03 | LF | 1267210.42 | 186417.1 | 1080793.32 | 0 | PCO #055 - Add 31.99 LF to account for oversized wall thickness. CONCRETE CUTTING CO INC@$1,189,807 and KMA INDUSTRIES INC@$2,160.00
Y | IPCRP1-0438-1010-L | IPCRP1 | IPCRP1 | 0438-1010 | Demo Exist Esplanade Type D (Marine Portion) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1570 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0438-1010-S | IPCRP1 | IPCRP1 | 0438-1010 | Demo Exist Esplanade Type D (Marine Portion) | N | S |  | NR | A | 2849092.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2849092.66 | 0 | 0 | 2849092.66 | 0 | 0 | 0 | Y | 2849092.66 | 0 | 0 | 2849092.66 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1570 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0439-0000-L | IPCRP1 | IPCRP1 | 0439-0000 | DEMO EXIST N EMBAYMENT (AS/ CONT DWG) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0439-0000-R | IPCRP1 | IPCRP1 | 0439-0000 | DEMO EXIST N EMBAYMENT (AS/ CONT DWG) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 1500000 | 1500000 | 0 | N | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0439-1000-E | IPCRP1 | IPCRP1 | 0439-1000 | Demo Exist N Embayment (Railing) | N | E |  | NR | P | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1430 | 0 | 0 | 1430 | 0 | 0 | 0 | Y | 1430 | 0 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 900 | 300 | 50 | 350 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0439-1000-L | IPCRP1 | IPCRP1 | 0439-1000 | Demo Exist N Embayment (Railing) | N | L |  | NR | P | 7827.8 | 6425.39 | 6425.39 | 6425.39 | 6425.39 | 100 | 0 | 0 | 0 | 0 | N | 6425.39 | N | 1402.41 | 0 | 0 | 7827.8 | 0 | 0 | 6425.39 | N | 1402.41 | 0 | 0 | 7827.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6425.39 | 0 | 0 | 6425.39 | 0 | 0 | 0 | 0 | 0 | 0 | -6425.39 | 0 | 0 | 6425.39 | 6425.39 | 0 | 0 | 0 | 71.52 | 0 | 46 | 46 | 71.52 | 46 | 0 | 46 | HR | 900 | 300 | 50 | 350 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0439-1000-S | IPCRP1 | IPCRP1 | 0439-1000 | Demo Exist N Embayment (Railing) | N | S |  | UNIT | A | 0 | 125.46 | 125.46 | 125.46 | 125.46 | 100 | 0 | 0 | 0 | 0 | N | 125.46 | N | -125.46 | 0 | 0 | 0 | 0 | 0 | 125.46 | N | -125.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -125.46 | 0 | 0 | 125.46 | 0 | 0 | 0 | 0 | 0 | 0 | -125.46 | 0 | 0 | 125.46 | 125.46 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | NA | 900 | 300 | 50 | 350 | LF | 125.46 | 0 | 125.46 | 0
Y | IPCRP1-0439-1010-L | IPCRP1 | IPCRP1 | 0439-1010 | Demo Exist N Embayment (Marine Portion) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 300 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0439-1010-S | IPCRP1 | IPCRP1 | 0439-1010 | Demo Exist N Embayment (Marine Portion) | N | S |  | NR | A | 1023267.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1023267.69 | 0 | 0 | 1023267.69 | 0 | 0 | 0 | Y | 1023267.69 | 0 | 0 | 1023267.69 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 300 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0440-0000-L | IPCRP1 | IPCRP1 | 0440-0000 | DEMO EXIST S EMBAYMENT (AS/ CONT DWG) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0440-0000-R | IPCRP1 | IPCRP1 | 0440-0000 | DEMO EXIST S EMBAYMENT (AS/ CONT DWG) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 855000 | 0 | 0 | 855000 | 0 | 855000 | 735000 | 0 | N | 855000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0440-1000-E | IPCRP1 | IPCRP1 | 0440-1000 | Demo Exist S Embayment (Civil Portion) | N | E |  | NR | P | 4008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4008 | 0 | 0 | 4008 | 0 | 0 | 0 | Y | 4008 | 0 | 0 | 4008 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 228 | 196 | 0 | 196 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0440-1000-L | IPCRP1 | IPCRP1 | 0440-1000 | Demo Exist S Embayment (Civil Portion) | N | L |  | NR | P | 20782 | 17743.02 | 17743.02 | 17743.02 | 17743.02 | 100 | 0 | 0 | 0 | 0 | Y | 17743.02 | Y | 3038.98 | 0 | 0 | 20782 | 0 | 0 | 17743.02 | Y | 3038.98 | 0 | 0 | 20782 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17743.02 | 0 | 0 | 17743.02 | 0 | 0 | 0 | 0 | 0 | 0 | -17743.02 | 0 | 0 | 17743.02 | 17743.02 | 0 | 0 | 0 | 189.31 | 0 | 117.5 | 117.5 | 189.31 | 117.5 | 0 | 117.5 | HR | 228 | 196 | 0 | 196 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0440-1000-S | IPCRP1 | IPCRP1 | 0440-1000 | Demo Exist S Embayment (Civil Portion) | N | S |  | UNIT | A | 0 | 229.27 | 229.27 | 229.27 | 229.27 | 100 | 0 | 0 | 0 | 0 | N | 229.27 | N | -229.27 | 0 | 0 | 0 | 0 | 0 | 229.27 | N | -229.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -229.27 | 0 | 0 | 229.27 | 0 | 0 | 0 | 0 | 0 | 0 | -229.27 | 0 | 0 | 229.27 | 229.27 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 228 | 196 | 0 | 196 | LF | 229.27 | 0 | 229.27 | 0
Y | IPCRP1-0440-1010-L | IPCRP1 | IPCRP1 | 0440-1010 | Demo Exist S Embayment (Marine Portion) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 193 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0440-1010-S | IPCRP1 | IPCRP1 | 0440-1010 | Demo Exist S Embayment (Marine Portion) | N | S |  | NR | A | 827003.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 827003.61 | 0 | 0 | 827003.61 | 0 | 0 | 0 | Y | 827003.61 | 0 | 0 | 827003.61 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 193 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0441-0000-L | IPCRP1 | IPCRP1 | 0441-0000 | DEMO EXIST ESPLANADE TYPE F | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0441-0000-R | IPCRP1 | IPCRP1 | 0441-0000 | DEMO EXIST ESPLANADE TYPE F | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 286000 | 0 | 0 | 286000 | 0 | 286000 | 260000 | 0 | N | 286000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0441-1000-E | IPCRP1 | IPCRP1 | 0441-1000 | Demo Exist Esplanade Type F (Railing) | N | E |  | NR | P | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 92 | 0 | 0 | 92 | 0 | 0 | 0 | Y | 92 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | SH | 44 | 20 | 0 | 20 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0441-1000-L | IPCRP1 | IPCRP1 | 0441-1000 | Demo Exist Esplanade Type F (Railing) | N | L |  | NR | P | 547.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 547.26 | 0 | 0 | 547.26 | 0 | 0 | 0 | Y | 547.26 | 0 | 0 | 547.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | HR | 44 | 20 | 0 | 20 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0441-1010-L | IPCRP1 | IPCRP1 | 0441-1010 | Demo Exist Esplanade Type F (Marine Portion) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 22 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0441-1010-S | IPCRP1 | IPCRP1 | 0441-1010 | Demo Exist Esplanade Type F (Marine Portion) | N | S |  | NR | A | 265930.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 265930.83 | 0 | 0 | 265930.83 | 0 | 0 | 0 | Y | 265930.83 | 0 | 0 | 265930.83 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 22 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0442-0000-L | IPCRP1 | IPCRP1 | 0442-0000 | DEMO STRUCT - FIRE BOATHOUSE IRR PUMP SHED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0442-0000-R | IPCRP1 | IPCRP1 | 0442-0000 | DEMO STRUCT - FIRE BOATHOUSE IRR PUMP SHED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 500000 | 0 | 0 | 500000 | 0 | 500000 | 500000 | 0 | N | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0443-0000-L | IPCRP1 | IPCRP1 | 0443-0000 | DEMO EXIST ESPLANADE TYPE G | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0443-0000-R | IPCRP1 | IPCRP1 | 0443-0000 | DEMO EXIST ESPLANADE TYPE G | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 200000 | 0 | 0 | 200000 | 0 | 200000 | 200000 | 0 | N | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0443-1000-E | IPCRP1 | IPCRP1 | 0443-1000 | Demo Exist Esplanade, Type G (Civil Portion) | N | E |  | NR | P | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 275 | 0 | 0 | 275 | 0 | 0 | 0 | Y | 275 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5 | 5 | 0 | 5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0443-1000-L | IPCRP1 | IPCRP1 | 0443-1000 | Demo Exist Esplanade, Type G (Civil Portion) | N | L |  | NR | P | 1426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1426 | 0 | 0 | 1426 | 0 | 0 | 0 | Y | 1426 | 0 | 0 | 1426 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | HR | 5 | 5 | 0 | 5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0443-1000-S | IPCRP1 | IPCRP1 | 0443-1000 | Demo Exist Esplanade, Type G (Civil Portion) | N | S |  | UNIT | A | 0 | 613.85 | 613.85 | 613.85 | 613.85 | 100 | 0 | 0 | 0 | 0 | N | 613.85 | N | -613.85 | 0 | 0 | 0 | 0 | 0 | 613.85 | N | -613.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -613.85 | 0 | 0 | 613.85 | 0 | 0 | 0 | 0 | 0 | 0 | -613.85 | 0 | 0 | 613.85 | 613.85 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | NA | 5 | 5 | 0 | 5 | LF | 613.85 | 0 | 613.85 | 0
Y | IPCRP1-0443-1010-L | IPCRP1 | IPCRP1 | 0443-1010 | Demo Exist Esplanade Type G (Marine Portion) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0443-1010-S | IPCRP1 | IPCRP1 | 0443-1010 | Demo Exist Esplanade Type G (Marine Portion) | N | S |  | NR | A | 185384.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 185384.13 | 0 | 0 | 185384.13 | 0 | 0 | 0 | Y | 185384.13 | 0 | 0 | 185384.13 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0444-0000-L | IPCRP1 | IPCRP1 | 0444-0000 | DEMO EXIST ESPLANADE STRUCT FOR PROP N EMBAYMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-0444-0000-R | IPCRP1 | IPCRP1 | 0444-0000 | DEMO EXIST ESPLANADE STRUCT FOR PROP N EMBAYMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2796600 | 0 | 0 | 2775000 | 0 | 2796600 | 2092350 | 0 | N | 2796600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796600 | 2.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-0444-1000-E | IPCRP1 | IPCRP1 | 0444-1000 | Demo of Exist Esplanade for Prop N Embayment (Civ | N | E |  | NR | P | 14257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 14257 | 0 | 0 | 14257 | 0 | 0 | 0 | Y | 14257 | 0 | 0 | 14257 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 370 | 310.1 | -28.25 | 281.85 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0444-1000-L | IPCRP1 | IPCRP1 | 0444-1000 | Demo of Exist Esplanade for Prop N Embayment (Civ | N | L |  | NR | P | 72607 | 124596.47 | 124596.47 | 124596.47 | 124596.47 | 97.3567 | 0 | 0 | 0 | 3382.87 | Y | 127979.34 | Y | -55372.34 | 0 | 0 | 72607 | 0 | 0 | 127979.34 | Y | -55372.34 | 0 | 0 | 72607 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -127979.34 | 0 | 837.11 | 127979.34 | 0 | 0 | 0 | 0 | 0 | 0 | -127979.34 | 0 | 0 | 127979.34 | 127979.34 | 0 | 0 | 0 | 638.84 | 0 | 823.55 | 823.55 | 638.84 | 801 | 22.55 | 823.55 | HR | 370 | 310.1 | -28.25 | 281.85 | LF | 0 | 0 | 0 | 3382.87 | PCO #055 - Add 2.88 LF to account for oversized wall thickness 2. As / Juan B. email 1/21/26, est final quantity = 278.97 + 2.88 = 281.85 LF.
Y | IPCRP1-0444-1000-S | IPCRP1 | IPCRP1 | 0444-1000 | Demo of Exist Esplanade for Prop N Embayment (Civ | N | S |  | UNIT | A | 0 | 2121.43 | 2121.43 | 2121.43 | 2121.43 | 100 | 0 | 0 | 0 | 0 | Y | 2121.43 | Y | -2121.43 | 0 | 0 | 0 | 0 | 0 | 2121.43 | Y | -2121.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2121.43 | 0 | 0 | 2121.43 | 0 | 0 | 0 | 0 | 0 | 0 | -2121.43 | 0 | 0 | 2121.43 | 2121.43 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 18 | -2 | 16 | NA | 370 | 310.1 | -28.25 | 281.85 | LF | 2121.43 | 0 | 2121.43 | 0
Y | IPCRP1-0444-1010-L | IPCRP1 | IPCRP1 | 0444-1010 | Demo of Exist Esplanade for Prop N Embayment (Mar | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 275 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0444-1010-S | IPCRP1 | IPCRP1 | 0444-1010 | Demo of Exist Esplanade for Prop N Embayment (Mar | N | S |  | NR | A | 2293059.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2293059.04 | 0 | 0 | 2293059.04 | 0 | 0 | 0 | Y | 2293059.04 | 0 | 0 | 2293059.04 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 275 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0445-0000-L | IPCRP1 | IPCRP1 | 0445-0000 | DEMO EXIST ESPLANADE STRUCT FOR PROP S EMBAYMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0445-0000-R | IPCRP1 | IPCRP1 | 0445-0000 | DEMO EXIST ESPLANADE STRUCT FOR PROP S EMBAYMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2606400 | 0 | 0 | 2587500 | 0 | 2606400 | 2083200 | 0 | N | 2606400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2606400 | 2.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0445-1000-E | IPCRP1 | IPCRP1 | 0445-1000 | Demo of Exist Esplanade for Prop S Embayment (Civ | N | E |  | NR | P | 32006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 32006 | 0 | 0 | 32006 | 0 | 0 | 0 | N | 32006 | 0 | 0 | 32006 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 345 | 277.76 | 0.58 | 278.34 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0445-1000-L | IPCRP1 | IPCRP1 | 0445-1000 | Demo of Exist Esplanade for Prop S Embayment (Civ | N | L |  | NR | P | 165700 | 212148.41 | 212148.41 | 212148.41 | 212148.41 | 100 | 0 | 0 | 0 | 0 | Y | 212148.41 | Y | -46448.41 | 0 | 0 | 165700 | 0 | 0 | 212148.41 | Y | -46448.41 | 0 | 0 | 165700 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -212148.41 | 0 | 0 | 212148.41 | 0 | 0 | 0 | 0 | 0 | 0 | -212148.41 | 0 | 0 | 212148.41 | 212148.41 | 0 | 0 | 0 | 1365.15 | 0 | 1465 | 1465 | 1365.15 | 1465 | 0 | 1465 | HR | 345 | 277.76 | 0.58 | 278.34 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0445-1000-S | IPCRP1 | IPCRP1 | 0445-1000 | Demo of Exist Esplanade for Prop S Embayment (Civ | N | S |  | UNIT | A | 0 | 244023.96 | 244023.96 | 244023.96 | 244023.96 | 100 | 0 | 0 | 0 | 0 | Y | 244023.96 | Y | -244023.96 | 0 | 0 | 0 | 0 | 0 | 244023.96 | Y | -244023.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -244023.96 | 0 | 0 | 244023.96 | 0 | 0 | 0 | 0 | 0 | 0 | -244023.96 | 0 | 0 | 244023.96 | 244023.96 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 50267.5 | -50265.5 | 2 | NA | 345 | 277.76 | 0.58 | 278.34 | LF | 244023.96 | 0 | 244023.96 | 0
Y | IPCRP1-0445-1010-L | IPCRP1 | IPCRP1 | 0445-1010 | Demo of Exist Esplanade for Prop S Embayment (Mar | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 280 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0445-1010-S | IPCRP1 | IPCRP1 | 0445-1010 | Demo of Exist Esplanade for Prop S Embayment (Mar | N | S |  | NR | A | 2408907.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2408907.06 | 0 | 0 | 2408907.06 | 0 | 0 | 0 | Y | 2408907.06 | 0 | 0 | 2408907.06 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 280 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon)
Y | IPCRP1-0446-0000-L | IPCRP1 | IPCRP1 | 0446-0000 | DEMO OF STRUCTURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0446-0000-R | IPCRP1 | IPCRP1 | 0446-0000 | DEMO OF STRUCTURES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 76000 | 0 | 0 | 76000 | 0 | 76000 | 319660 | 0 | N | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0446-1000-L | IPCRP1 | IPCRP1 | 0446-1000 | DEMO OF STRUCTURES | N | L |  | UNIT | P | 0 | 64377.69 | 64377.69 | 64377.69 | 64377.69 | 87.0911 | 0 | 0 | 0 | 9542.27 | Y | 73919.96 | Y | -73919.96 | 0 | 0 | 0 | 0 | 0 | 73919.96 | Y | -73919.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -73919.96 | 0 | -9542.27 | 73919.96 | 0 | 0 | 0 | 0 | 0 | 0 | -73919.96 | 0 | 0 | 73919.96 | 73919.96 | 0 | 0 | 0 | 0 | 0 | 603.5 | 603.5 | 0 | 533.5 | 70 | 603.5 | HR | 206 | 799.15 | 0 | 799.15 | CY | 0 | 0 | 0 | 9542.27 | 400 hrs
Y | IPCRP1-0446-1000-S | IPCRP1 | IPCRP1 | 0446-1000 | DEMO OF STRUCTURES | N | S |  | NR | A | 51380 | 2160.67 | 2160.67 | 2160.67 | 2160.67 | 100 | 0 | 0 | 0 | 0 | Y | 2160.67 | Y | 49219.33 | 0 | 0 | 51380 | 0 | 0 | 2160.67 | Y | 49219.33 | 0 | 0 | 51380 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2160.67 | 0 | 0 | 2160.67 | 0 | 0 | 0 | 0 | 0 | 0 | -2160.67 | 0 | 0 | 2160.67 | 2160.67 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17 | -17 | 0 | NA | 206 | 799.15 | 0 | 799.15 | CY | 2160.67 | 0 | 2160.67 | 0 | Moved to cc 0446-1010 Marine Demo Sub (Trevcon), Contract bid quantity = 190.00 CY
Y | IPCRP1-0446-1010-L | IPCRP1 | IPCRP1 | 0446-1010 | Marine Demo Sub (Trevcon) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.73 | 0.27 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0446-1010-S | IPCRP1 | IPCRP1 | 0446-1010 | Marine Demo Sub (Trevcon) | N | S |  | UNIT | A | 0 | 28638586.89 | 28638586.89 | 22060632.08 | 28638586.89 | 77.0311 | 0 | 0 | 0 | 0 | Y | 28638586.89 | Y | -28638586.89 | 0 | 0 | 0 | 0 | 0 | 28638586.89 | Y | -28638586.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28638586.89 | 442226.21 | 782186.08 | 28638586.89 | 0 | 0 | 0 | 0 | 55000 | 0 | -28638586.89 | 0 | 0 | 28638586.89 | 28638586.89 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 19034.34 | -19033.34 | 1 | NA | 1 | 0.73 | 0.27 | 1 | LS | 28638586.89 | 6577954.81 | 22060632.08 | 0 | Change PMF (Sub) from $25,351,856.33 to $26,108,059.13, matching Commitment Trevcon Base SV = $17,096,970.00. Plus SCO#01 - SCO #10, Recent CO-10.1 Additional Work/Removals at CSO #1, #2, #4 (between Bents 2-3, Bents 35-36, and Bents 62-63)
Y | IPCRP1-0447-0000-L | IPCRP1 | IPCRP1 | 0447-0000 | DEMO STRUCT - AMPHITHEATRE B-SHELL & SEAT AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0447-0000-R | IPCRP1 | IPCRP1 | 0447-0000 | DEMO STRUCT - AMPHITHEATRE B-SHELL & SEAT AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 1000000 | 1000000 | 0 | N | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0448-0000-L | IPCRP1 | IPCRP1 | 0448-0000 | REM OF WILLIAMSBURG BRIDGE SECURITY BOLLARDS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0448-0000-R | IPCRP1 | IPCRP1 | 0448-0000 | REM OF WILLIAMSBURG BRIDGE SECURITY BOLLARDS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 77625 | 0 | 0 | 77625 | 0 | 77625 | 64875 | 0 | N | 77625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0448-1000-L | IPCRP1 | IPCRP1 | 0448-1000 | Rem of Williamsburg Br Security Bollards | N | L |  | UNIT | P | 0 | 45340.28 | 45340.28 | 45340.28 | 45340.28 | 100 | 0 | 0 | 0 | 0 | Y | 45340.28 | Y | -45340.28 | 0 | 0 | 0 | 0 | 0 | 45340.28 | Y | -45340.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45340.28 | 0 | 0 | 45340.28 | 0 | 0 | 0 | 0 | 0 | 0 | -45340.28 | 0 | 0 | 45340.28 | 45340.28 | 0 | 0 | 0 | 0 | 0 | 359 | 359 | 0 | 359 | 0 | 359 | HR | 207 | 173 | 0 | 173 | EA | 0 | 0 | 0 | 0 | As per Nick D (10/13/23) still have 15ea remaining to remove, est PMF Quantity will be 173ea. Note 25ea bollards remain.
Y | IPCRP1-0448-1000-S | IPCRP1 | IPCRP1 | 0448-1000 | Rem of Williamsburg Br Security Bollards | N | S |  | NR | A | 72450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 72450 | 0 | 0 | 72450 | 0 | 0 | 0 | Y | 72450 | 0 | 0 | 72450 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 207 | 173 | 0 | 173 | EA | 0 | 0 | 0 | 0 | As per Nick D (10/13/23) still have 15ea remaining to remove, est PMF Quantity will be 173ea. Note 25ea bollards remain. No sub, self perform. As per Nick D (4/22/24) final confirmed quantity is 173.00 which we finished on 4/19.
Y | IPCRP1-0449-0000-L | IPCRP1 | IPCRP1 | 0449-0000 | DEMO STRUCT - COMFORT STATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0449-0000-R | IPCRP1 | IPCRP1 | 0449-0000 | DEMO STRUCT - COMFORT STATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 1000000 | 40000 | 0 | N | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0450-0000-L | IPCRP1 | IPCRP1 | 0450-0000 | DEMO STRUCT - SPORTS FIELD ELECT SHED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0450-0000-R | IPCRP1 | IPCRP1 | 0450-0000 | DEMO STRUCT - SPORTS FIELD ELECT SHED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 98000 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0451-0000-L | IPCRP1 | IPCRP1 | 0451-0000 | DEMO STRUCT - E RIVER HOUSING GUARD HOUSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0451-0000-R | IPCRP1 | IPCRP1 | 0451-0000 | DEMO STRUCT - E RIVER HOUSING GUARD HOUSE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 250000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0452-0000-L | IPCRP1 | IPCRP1 | 0452-0000 | DEMO STRUCT - TENNIS BUILDING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0452-0000-R | IPCRP1 | IPCRP1 | 0452-0000 | DEMO STRUCT - TENNIS BUILDING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 500000 | 0 | 0 | 500000 | 0 | 500000 | 500000 | 0 | N | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0453-0000-L | IPCRP1 | IPCRP1 | 0453-0000 | DEMO STRUCT - TRACK BUILDING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0453-0000-R | IPCRP1 | IPCRP1 | 0453-0000 | DEMO STRUCT - TRACK BUILDING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 500000 | 0 | 0 | 500000 | 0 | 500000 | 50000 | 0 | N | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0453-1010-L | IPCRP1 | IPCRP1 | 0453-1010 | Asbestos Rem at Tennis Building | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0453-1010-S | IPCRP1 | IPCRP1 | 0453-1010 | Asbestos Rem at Tennis Building | N | S |  | NR | A | 14850 | 9850 | 9850 | 9850 | 9850 | 100 | 0 | 0 | 0 | 0 | Y | 9850 | Y | 5000 | 0 | 0 | 14850 | 0 | 0 | 9850 | Y | 5000 | 0 | 0 | 14850 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9850 | 0 | 0 | 9850 | 0 | 0 | 0 | 0 | 0 | 0 | -9850 | 0 | 0 | 9850 | 9850 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3 | 0.34 | 3.34 | NA | 1 | 1 | 0 | 1 | LS | 9850 | 0 | 9850 | 0 | PAL ENVIRONMENTAL @$8,900.00
Y | IPCRP1-0454-0000-L | IPCRP1 | IPCRP1 | 0454-0000 | DEMO EXIST ROCK FILLED TIMB CRIB ON GRAVITY WALL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0454-0000-R | IPCRP1 | IPCRP1 | 0454-0000 | DEMO EXIST ROCK FILLED TIMB CRIB ON GRAVITY WALL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3889000 | 0 | 0 | 3889000 | 0 | 3889000 | 0 | 0 | N | 3889000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3889000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0454-1000-L | IPCRP1 | IPCRP1 | 0454-1000 | Demo Ex Rock Filled Timb Crib On Gravity Wall | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3889 | 0 | 3889 | 3889 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0454-1000-S | IPCRP1 | IPCRP1 | 0454-1000 | Demo Ex Rock Filled Timb Crib On Gravity Wall | N | S |  | NR | A | 3695495.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3695495.8 | N | 3695495.8 | N | 0 | 0 | 0 | 3695495.8 | 0 | 0 | 3695495.8 | N | 0 | 0 | 0 | 3695495.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3695495.8 | 0 | 0 | 3695495.8 | 0 | 0 | 0 | 0 | 0 | 0 | -3695495.8 | 0 | 0 | 3695495.8 | 3695495.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3889 | 0 | 3889 | 3889 | CY | 0 | 0 | 0 | 3695495.8
Y | IPCRP1-0454-1010-L | IPCRP1 | IPCRP1 | 0454-1010 | Utility Support for Relocations | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0454-1010-S | IPCRP1 | IPCRP1 | 0454-1010 | Utility Support for Relocations | N | S |  | NR | A | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | N | 30000 | N | 0 | 0 | 0 | 30000 | 0 | 0 | 30000 | N | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 30000
Y | IPCRP1-0455-0000-L | IPCRP1 | IPCRP1 | 0455-0000 | REM EXIST TIMBER PILE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0455-0000-R | IPCRP1 | IPCRP1 | 0455-0000 | REM EXIST TIMBER PILE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1510500 | 0 | 0 | 1510500 | 0 | 1510500 | 337000 | 0 | N | 1510500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0455-1000-E | IPCRP1 | IPCRP1 | 0455-1000 | Rem Exist Timber Pile (Civil) | N | E |  | NR | P | 166100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 166100 | 0 | 0 | 166100 | 0 | 0 | 0 | Y | 166100 | 0 | 0 | 166100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1510 | 674 | 836 | 1510 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0455-1000-L | IPCRP1 | IPCRP1 | 0455-1000 | Rem Exist Timber Pile (Civil) | N | L |  | NR | P | 610095.87 | 167911.33 | 167911.33 | 167911.33 | 167911.33 | 38.3875 | 0 | 0 | 0 | 269500 | Y | 437411.33 | Y | 172684.54 | 0 | 0 | 610095.87 | 0 | 0 | 437411.33 | Y | 172684.54 | 0 | 0 | 610095.87 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -437411.33 | 0 | 0 | 437411.33 | 0 | 0 | 0 | 0 | 0 | 0 | -437411.33 | 0 | 0 | 437411.33 | 437411.33 | 0 | 0 | 0 | 5436 | 0 | 3502 | 3502 | 5436 | 1346 | 2156 | 3502 | HR | 1510 | 674 | 836 | 1510 | EA | 0 | 0 | 0 | 269500 | As of 11/30/2025, DDC has paid 630ea. Trevcon has completed 49ea, leaving balance self performed by IPC = 581ea.
Y | IPCRP1-0455-1000-S | IPCRP1 | IPCRP1 | 0455-1000 | Rem Exist Timber Pile (Civil) | N | S |  | UNIT | A | 0 | 5150.63 | 5150.63 | 5150.63 | 5150.63 | 100 | 0 | 0 | 0 | 0 | N | 5150.63 | N | -5150.63 | 0 | 0 | 0 | 0 | 0 | 5150.63 | N | -5150.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5150.63 | 0 | 0 | 5150.63 | 0 | 0 | 0 | 0 | 0 | 0 | -5150.63 | 0 | 0 | 5150.63 | 5150.63 | 0 | 0 | 0 | 0 | 0 | 41.5 | 41.5 | 0 | 41.5 | 0 | 41.5 | NA | 1510 | 674 | 836 | 1510 | EA | 5150.63 | 0 | 5150.63 | 0
Y | IPCRP1-0455-1010-L | IPCRP1 | IPCRP1 | 0455-1010 | Rem Exist Timber Pile (Marine) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1511 | 0 | 1446 | 1446 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0455-1010-S | IPCRP1 | IPCRP1 | 0455-1010 | Rem Exist Timber Pile (Marine) | N | S |  | NR | P | 679950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650700 | Y | 650700 | Y | 29250 | 0 | 0 | 679950 | 0 | 0 | 650700 | Y | 29250 | 0 | 0 | 679950 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -650700 | 0 | 0 | 650700 | 0 | 0 | 0 | 0 | 0 | 0 | -650700 | 0 | 0 | 650700 | 650700 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1511 | 0 | 1446 | 1446 | EA | 0 | 0 | 0 | 650700 | IPC Budget $450/ea. Trevcon = $3,920/ea. Try to minimize what Trevcon has to remove. Moved 65ea ($29,250) to cc 0446-1010 Marine Demo sub (Trevcon).
Y | IPCRP1-0456-0000-L | IPCRP1 | IPCRP1 | 0456-0000 | REM MISCELLANEOUS UTILITY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0456-0000-R | IPCRP1 | IPCRP1 | 0456-0000 | REM MISCELLANEOUS UTILITY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50000 | 0 | 0 | 50000 | 0 | 50000 | 50000 | 0 | N | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0456-1000-L | IPCRP1 | IPCRP1 | 0456-1000 | Rem Miscelleneous Uility | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 | work performed & paid for in Nov 2022 (PP#10)
Y | IPCRP1-0456-1000-S | IPCRP1 | IPCRP1 | 0456-1000 | Rem Miscelleneous Uility | N | S |  | NR | A | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | Y | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0457-0000-L | IPCRP1 | IPCRP1 | 0457-0000 | PLASTIC FILTER FABRIC FOR REVETMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0457-0000-R | IPCRP1 | IPCRP1 | 0457-0000 | PLASTIC FILTER FABRIC FOR REVETMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 45330 | 0 | 0 | 45330 | 0 | 45330 | 11758.2 | 0 | N | 45330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0457-1000-L | IPCRP1 | IPCRP1 | 0457-1000 | Plastic Filter Fabric For Revetment (Marine) | N | L |  | UNIT | P | 0 | 1857.13 | 1857.13 | 1857.13 | 1857.13 | 70.3664 | 0 | 0 | 0 | 782.1 | N | 2639.23 | N | -2639.23 | 0 | 0 | 0 | 0 | 0 | 2639.23 | N | -2639.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2639.23 | 0 | 0 | 2639.23 | 0 | 0 | 0 | 0 | 0 | 0 | -2639.23 | 0 | 0 | 2639.23 | 2639.23 | 0 | 0 | 0 | 0 | 0 | 24.16 | 24.16 | 0 | 17 | 7.16 | 24.16 | HR | 3022 | 783.88 | 330.12 | 1114 | SY | 0 | 0 | 0 | 782.1
Y | IPCRP1-0457-1000-S | IPCRP1 | IPCRP1 | 0457-1000 | Plastic Filter Fabric For Revetment (Marine) | N | S |  | NR | A | 43068.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | Y | 1000 | Y | 42068.34 | 0 | 0 | 43068.34 | 0 | 0 | 1000 | Y | 42068.34 | 0 | 0 | 43068.34 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3022 | 783.88 | 330.12 | 1114 | SY | 0 | 0 | 0 | 1000 | Estimated Final Quantity (ZH, 2.14.24) 552sy (SE) + 272sy (NE) + 10x29 = 290sy (Outfalls) = 1,114sy.
Y | IPCRP1-0458-0000-L | IPCRP1 | IPCRP1 | 0458-0000 | INSTALL OF ANODE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0458-0000-R | IPCRP1 | IPCRP1 | 0458-0000 | INSTALL OF ANODE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6021400 | 0 | 0 | 6021400 | 0 | 6021400 | 3723000 | 0 | N | 6021400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6021400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0458-1000-L | IPCRP1 | IPCRP1 | 0458-1000 | Install of Anode - Cathodic Prot | N | L |  | UNIT | P | 0 | 4963.78 | 4963.78 | 4963.78 | 4963.78 | 12.3298 | 0 | 0 | 0 | 35294.74 | Y | 40258.52 | Y | -40258.52 | 0 | 0 | 0 | 0 | 0 | 40258.52 | Y | -40258.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -40258.52 | 0 | 0 | 40258.52 | 0 | 0 | 0 | 0 | 0 | 0 | -40258.52 | 0 | 0 | 40258.52 | 40258.52 | 0 | 0 | 0 | 0 | 0 | 310 | 310 | 0 | 38.5 | 271.5 | 310 | HR | 1 | 0.52 | 0.48 | 1 | LS | 0 | 0 | 0 | 35294.74
Y | IPCRP1-0458-1000-M | IPCRP1 | IPCRP1 | 0458-1000 | Install of Anode - Cathodic Prot | N | M |  | UNIT | U | 0 | 24047.1 | 24047.1 | 24047.1 | 24047.1 | 48.0942 | 0 | 0 | 0 | 25952.9 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101 | -2101 | 0 | NA | 1 | 0.52 | 0.48 | 1 | LS | 20845.64 | -839.3 | 21684.94 | 25952.9 | Material category is open for Cathodic Protection clips and accessories, replace this note with Bob Schmidt's PO.
Y | IPCRP1-0458-1000-S | IPCRP1 | IPCRP1 | 0458-1000 | Install of Anode - Cathodic Prot | N | S |  | NR | A | 1085800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | 10000 | Y | 1075800 | 0 | 0 | 1085800 | 0 | 0 | 10000 | Y | 1075800 | 0 | 0 | 1085800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0.52 | 0.48 | 1 | LS | 0 | 0 | 0 | 10000 | Moved to cc: 0446-1010 Marine Demo sub (Trevcon)
Y | IPCRP1-0458-1010-L | IPCRP1 | IPCRP1 | 0458-1010 | Install of Anode - Cathodic Prot (Marine) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1771 | 997 | 774 | 1771 | EA | 0 | 0 | 0 | 0 | Moved to cc: 0446-1010 Marine Demo Sub (Trevcon). Leaving 100K for sub work to tie in work at the deck level (a Trevcon exclusion). re-entered on 1-13-2024
Y | IPCRP1-0458-1010-S | IPCRP1 | IPCRP1 | 0458-1010 | Install of Anode - Cathodic Prot (Marine) | N | S |  | NR | A | 4907009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 4907009 | 0 | 0 | 4907009 | 0 | 0 | 0 | N | 4907009 | 0 | 0 | 4907009 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1771 | 997 | 774 | 1771 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0458-1020-L | IPCRP1 | IPCRP1 | 0458-1020 | Bonding Rod & Seam Weld in Bulkhead | N | L |  | UNIT | P | 0 | 100815.83 | 100815.83 | 100815.83 | 100815.83 | 74.6784 | 0 | 0 | 0 | 34184.17 | Y | 135000 | Y | -135000 | 0 | 0 | 0 | 0 | 0 | 135000 | Y | -135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -135000 | 1168.91 | 0 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | -135000 | 0 | 0 | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | 1006.59 | 1006.59 | 0 | 775.5 | 231.09 | 1006.59 | HR | 0 | 997 | 158 | 1155 | EA | 0 | 0 | 0 | 34184.17
Y | IPCRP1-0459-0000-L | IPCRP1 | IPCRP1 | 0459-0000 | CONC SECURITY WALL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0459-0000-R | IPCRP1 | IPCRP1 | 0459-0000 | CONC SECURITY WALL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250500 | 0 | 0 | 250500 | 0 | 250500 | 226785 | 0 | N | 250500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0459-1000-L | IPCRP1 | IPCRP1 | 0459-1000 | Install & Strip Forms for Conc Security Wall | N | L |  | NR | P | 23083.79 | 103590.2 | 103590.2 | 103590.2 | 103590.2 | 100 | 0 | 0 | 0 | 0 | Y | 103590.2 | Y | -80506.41 | 0 | 0 | 23083.79 | 0 | 0 | 103590.2 | Y | -80506.41 | 0 | 0 | 23083.79 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -103590.2 | 0 | 0 | 103590.2 | 0 | 0 | 0 | 0 | 0 | 0 | -103590.2 | 0 | 0 | 103590.2 | 103590.2 | 0 | 0 | 0 | 193.28 | 0 | 806 | 806 | 193.28 | 806 | 0 | 806 | HR | 3020 | 2462 | 0 | 2462 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0459-1000-S | IPCRP1 | IPCRP1 | 0459-1000 | Install & Strip Forms for Conc Security Wall | N | S |  | UNIT | A | 0 | 511.33 | 511.33 | 511.33 | 511.33 | 100 | 0 | 0 | 0 | 0 | N | 511.33 | N | -511.33 | 0 | 0 | 0 | 0 | 0 | 511.33 | N | -511.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -511.33 | 0 | 0 | 511.33 | 0 | 0 | 0 | 0 | 0 | 0 | -511.33 | 0 | 0 | 511.33 | 511.33 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 0 | 4.5 | 0 | 4.5 | NA | 3020 | 2462 | 0 | 2462 | SF | 511.33 | 0 | 511.33 | 0
Y | IPCRP1-0459-1010-L | IPCRP1 | IPCRP1 | 0459-1010 | Place Conc for Security Wall | N | L |  | NR | P | 36710.59 | 15309.45 | 15309.45 | 15309.45 | 15309.45 | 100 | 0 | 0 | 0 | 0 | Y | 15309.45 | Y | 21401.14 | 0 | 0 | 36710.59 | 0 | 0 | 15309.45 | Y | 21401.14 | 0 | 0 | 36710.59 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15309.45 | 0 | 0 | 15309.45 | 0 | 0 | 0 | 0 | 0 | 0 | -15309.45 | 0 | 0 | 15309.45 | 15309.45 | 0 | 0 | 0 | 364.37 | 0 | 123.5 | 123.5 | 364.37 | 123.5 | 0 | 123.5 | HR | 167 | 151.19 | 0 | 151.19 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0459-1020-C | IPCRP1 | IPCRP1 | 0459-1020 | CM - Formwork for Conc Security Wall | N | C |  | NR | P | 10851 | 4189.24 | 4189.24 | 4189.24 | 4189.24 | 100 | 0 | 0 | 0 | 0 | Y | 4189.24 | Y | 6661.76 | 0 | 0 | 10851 | 0 | 0 | 4189.24 | Y | 6661.76 | 0 | 0 | 10851 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4189.24 | 0 | 0 | 4189.24 | 0 | 0 | 0 | 0 | 0 | 0 | -4189.24 | 0 | 0 | 4189.24 | 4189.24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 74 | 0 | 74 | NA | 3020 | 2462 | 0 | 2462 | SF | 4189.24 | 0 | 4189.24 | 0
Y | IPCRP1-0459-1020-L | IPCRP1 | IPCRP1 | 0459-1020 | CM - Formwork for Conc Security Wall | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HR | 3020 | 2462 | 0 | 2462 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0460-0000-L | IPCRP1 | IPCRP1 | 0460-0000 | FIXED BOLLARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0460-0000-R | IPCRP1 | IPCRP1 | 0460-0000 | FIXED BOLLARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 369600 | 0 | 0 | 369600 | 0 | 369600 | 365200 | 0 | N | 369600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0461-0000-L | IPCRP1 | IPCRP1 | 0461-0000 | RETRACTABLE BOLLARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0461-0000-R | IPCRP1 | IPCRP1 | 0461-0000 | RETRACTABLE BOLLARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 45000 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 0 | N | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0461-1000-E | IPCRP1 | IPCRP1 | 0461-1000 | Install Bollards | N | E |  | NR | P | 21760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 21760 | 0 | 0 | 21760 | 0 | 0 | 0 | Y | 21760 | 0 | 0 | 21760 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 177 | 175 | 0 | 175 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0461-1000-L | IPCRP1 | IPCRP1 | 0461-1000 | Install Bollards | N | L |  | NR | P | 146718 | 110759.5 | 110759.5 | 110759.5 | 110759.5 | 100 | 0 | 0 | 0 | 0 | Y | 110759.5 | Y | 35958.5 | 0 | 0 | 146718 | 0 | 0 | 110759.5 | Y | 35958.5 | 0 | 0 | 146718 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -110759.5 | 0 | 0 | 110759.5 | 0 | 0 | 0 | 0 | 0 | 0 | -110759.5 | 0 | 0 | 110759.5 | 110759.5 | 0 | 0 | 0 | 1356.27 | 0 | 828.5 | 828.5 | 1356.27 | 828.5 | 0 | 828.5 | HR | 177 | 175 | 0 | 175 | EA | 0 | 0 | 0 | 0 | 166 fixed + 9 retractable = 175ea. Note we did purchase 168 fixed.
Y | IPCRP1-0461-1000-S | IPCRP1 | IPCRP1 | 0461-1000 | Install Bollards | N | S |  | UNIT | A | 0 | 3765.16 | 3765.16 | 3765.16 | 3765.16 | 100 | 0 | 0 | 0 | 0 | N | 3765.16 | N | -3765.16 | 0 | 0 | 0 | 0 | 0 | 3765.16 | N | -3765.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3765.16 | 0 | 0 | 3765.16 | 0 | 0 | 0 | 0 | 0 | 0 | -3765.16 | 0 | 0 | 3765.16 | 3765.16 | 0 | 0 | 0 | 0 | 0 | 29.5 | 29.5 | 0 | 29.5 | 0 | 29.5 | NA | 177 | 175 | 0 | 175 | EA | 3765.16 | 0 | 3765.16 | 0
Y | IPCRP1-0461-1005-L | IPCRP1 | IPCRP1 | 0461-1005 | Install & Strip Formwork for Bollards | N | L |  | UNIT | P | 0 | 225076.9 | 225076.9 | 225076.9 | 225076.9 | 100 | 0 | 0 | 0 | 0 | Y | 225076.9 | Y | -225076.9 | 0 | 0 | 0 | 0 | 0 | 225076.9 | Y | -225076.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -225076.9 | 0 | 0 | 225076.9 | 0 | 0 | 0 | 0 | 0 | 0 | -225076.9 | 0 | 0 | 225076.9 | 225076.9 | 0 | 0 | 0 | 0 | 0 | 1711 | 1711 | 0 | 1711 | 0 | 1711 | HR | 0 | 5059.55 | 0 | 5059.55 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0461-1005-S | IPCRP1 | IPCRP1 | 0461-1005 | Install & Strip Formwork for Bollards | N | S |  | UNIT | A | 0 | 2657.96 | 2657.96 | 2657.96 | 2657.96 | 100 | 0 | 0 | 0 | 0 | N | 2657.96 | N | -2657.96 | 0 | 0 | 0 | 0 | 0 | 2657.96 | N | -2657.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2657.96 | 0 | 0 | 2657.96 | 0 | 0 | 0 | 0 | 0 | 0 | -2657.96 | 0 | 0 | 2657.96 | 2657.96 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 22 | 0 | 22 | NA | 0 | 5059.55 | 0 | 5059.55 | SF | 2657.96 | 0 | 2657.96 | 0
Y | IPCRP1-0461-1010-L | IPCRP1 | IPCRP1 | 0461-1010 | Place Conc for WBB Fixed & Retract Bollards | N | L |  | NR | P | 45136.39 | 63752.02 | 63752.02 | 63752.02 | 63752.02 | 100 | 0 | 0 | 0 | 0 | Y | 63752.02 | Y | -18615.63 | 0 | 0 | 45136.39 | 0 | 0 | 63752.02 | Y | -18615.63 | 0 | 0 | 45136.39 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63752.02 | 0 | 0 | 63752.02 | 0 | 0 | 0 | 0 | 0 | 0 | -63752.02 | 0 | 0 | 63752.02 | 63752.02 | 0 | 0 | 0 | 448 | 0 | 519.5 | 519.5 | 448 | 519.5 | 0 | 519.5 | HR | 205 | 300.35 | 0 | 300.35 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0461-1020-L | IPCRP1 | IPCRP1 | 0461-1020 | PM - Fixed & Retractable Bollards | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 177 | 177 | 0 | 177 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0461-1020-M | IPCRP1 | IPCRP1 | 0461-1020 | PM - Fixed & Retractable Bollards | N | M |  | NR | P | 47912 | 1265016.86 | 1265016.86 | 1265012.5 | 1265016.86 | 100 | 0 | 0 | 0 | -4.36 | Y | 1265012.5 | Y | -1217100.5 | 0 | 0 | 47912 | 0 | 0 | 1265012.5 | Y | -1217100.5 | 0 | 0 | 47912 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1265012.5 | 0 | 0 | 1265012.5 | 0 | 0 | 0 | 0 | 0 | 0 | -1265012.5 | 0 | 0 | 1265012.5 | 1265012.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 180 | 0 | 180 | NA | 177 | 177 | 0 | 177 | EA | 1265016.86 | 4.36 | 1265012.5 | -4.36 | 168 fixed + 9 retractable = 177 total Retractable Bollards from US Koei increase cost by 820K (for 9ea Retractable Bollards).
Y | IPCRP1-0461-1030-C | IPCRP1 | IPCRP1 | 0461-1030 | CM - Formwork for Fixed & Retract Bollards | N | C |  | NR | P | 26828 | 2266.24 | 2266.24 | 2266.23 | 2266.24 | 100 | 0 | 0 | 0 | -0.01 | Y | 2266.23 | Y | 24561.77 | 0 | 0 | 26828 | 0 | 0 | 2266.23 | Y | 24561.77 | 0 | 0 | 26828 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2266.23 | 0 | 0 | 2266.23 | 0 | 0 | 0 | 0 | 0 | 0 | -2266.23 | 0 | 0 | 2266.23 | 2266.23 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 111 | 0 | 111 | NA | 7467 | 5059.55 | 0 | 5059.55 | SF | 2266.24 | 0.01 | 2266.23 | -0.01
Y | IPCRP1-0461-1030-L | IPCRP1 | IPCRP1 | 0461-1030 | CM - Formwork for Fixed & Retract Bollards | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 7467 | 5059.55 | 0 | 5059.55 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0462-0000-L | IPCRP1 | IPCRP1 | 0462-0000 | MARITIME LOAD-OUT FACILITY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0462-0000-R | IPCRP1 | IPCRP1 | 0462-0000 | MARITIME LOAD-OUT FACILITY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 35000 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0462-1000-C | IPCRP1 | IPCRP1 | 0462-1000 | Maritime Load Out Facility - Off Site | N | C |  | UNIT | U | 0 | 1544708.47 | 1544708.47 | 809864.3 | 1544708.47 | 52.4283 | 0 | 0 | 0 | 0 | Y | 1544708.47 | Y | -1544708.47 | 0 | 0 | 0 | 0 | 0 | 1544708.47 | Y | -1544708.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1544708.47 | 1950 | 675 | 1544708.47 | 0 | 0 | 0 | 0 | 0 | 0 | -1544708.47 | 0 | 0 | 1544708.47 | 1544708.47 | 0 | 0 | 0 | 0 | 0 | 18287.57 | 18287.57 | 0 | 18314.57 | -27 | 18287.57 | NA | 24 | 40 | 15 | 55 | MO | 1266408.47 | 734844.17 | 531564.3 | 0 | Trevcon Base PO IPCRP1-0418 @$620K. Bought out half of the item (12 months) with Trevcon and still need to buy the remaining 12 months (more than likely CME) for the same value. PMF (Consumable) = 1,240,000.00 and it will be a 1M hit
Y | IPCRP1-0462-1000-L | IPCRP1 | IPCRP1 | 0462-1000 | Maritime Load Out Facility - Off Site | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 24 | 40 | 15 | 55 | MO | 0 | 0 | 0 | 0 | 1) Includes Commitment 1.877M & PMF 4.272M for CME (Sub). 2) Includes Commitment & PMF 620K for CME (Consumable). 3) Includes Commitment & PMF 329K for Bay Crane NJ (Consumable). 4) P-Park rent gets <br>charged here. Commitment does not show up. 11K/mo x 24mo = 264K.
Y | IPCRP1-0462-1000-S | IPCRP1 | IPCRP1 | 0462-1000 | Maritime Load Out Facility - Off Site | N | S |  | NR | A | 240000 | 3431380 | 3431380 | 1196355.61 | 3431380 | 28.0046 | 0 | 0 | 0 | 840620 | Y | 4272000 | Y | -4032000 | 0 | 0 | 240000 | 0 | 0 | 4272000 | Y | -4032000 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4272000 | 0 | 0 | 4272000 | 0 | 0 | 0 | 0 | 1525000 | 0 | -4272000 | 0 | 0 | 4272000 | 4272000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 22272.27 | -22272.27 | 0 | NA | 24 | 40 | 15 | 55 | MO | 3431380 | 2235024.39 | 1196355.61 | 840620 | Trevcon PO under C category PLUG VALUE for cost to transload Alt Deck Bulb Tees, $5,272,000 . Break down further at a later date.
Y | IPCRP1-0463-0000-L | IPCRP1 | IPCRP1 | 0463-0000 | INSPECTION BOAT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0463-0000-R | IPCRP1 | IPCRP1 | 0463-0000 | INSPECTION BOAT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 900000 | 0 | 0 | 900000 | 0 | 900000 | 0 | 0 | N | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0463-1000-L | IPCRP1 | IPCRP1 | 0463-1000 | INSPECTION BOAT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 30 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0463-1000-S | IPCRP1 | IPCRP1 | 0463-1000 | INSPECTION BOAT | N | S |  | NR | A | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 600000 | 0 | 0 | 600000 | 0 | 0 | 0 | Y | 600000 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1994100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | NA | 30 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0 | Potential Underrun which benefits us since it was bid low. No start date. North American Marine(Inspection Boat) @ $1,994,100.00 Chances are we will never use this item. Cost is in the report based on our subcontract amount to NAM. Revenue is significantly lower (900K) so we will make money if we don’t use it. Will keep both in our report until we get half-way thru Phase 2, and we are 100% sure, DDC doesn’t change their mind about its use. To answer your question – we don’t have a start date, it is dictated by the Owner, who currently does not want to use the inspection boat.
Y | IPCRP1-0464-0000-L | IPCRP1 | IPCRP1 | 0464-0000 | TUG BOAT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0464-0000-R | IPCRP1 | IPCRP1 | 0464-0000 | TUG BOAT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000000 | 0 | 0 | 12000000 | 0 | 12000000 | 18450000 | 0 | N | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0464-1000-L | IPCRP1 | IPCRP1 | 0464-1000 | Tug Boat, 24 Hrs | N | L |  | NR | P | 7605415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 7605415 | 0 | 0 | 7605415 | 0 | 0 | 0 | Y | 7605415 | 0 | 0 | 7605415 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55845 | 0 | 0 | 0 | 55845 | 0 | 0 | 0 | HR | 104 | 198 | 28 | 226 | WK | 0 | 0 | 0 | 0
Y | IPCRP1-0464-1000-S | IPCRP1 | IPCRP1 | 0464-1000 | Tug Boat, 24 Hrs | N | S |  | UNIT | A | 0 | 9781456.35 | 9781456.35 | 8275845.9 | 9781456.35 | 84.6075 | 0 | 0 | 0 | 0 | Y | 9781456.35 | Y | -9781456.35 | 0 | 0 | 0 | 0 | 0 | 9781456.35 | Y | -9781456.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9781456.35 | 187976.25 | 0 | 9781456.35 | 0 | 0 | 0 | 0 | 0 | 0 | -9781456.35 | 0 | 0 | 9781456.35 | 9781456.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2231.05 | -2231.05 | 0 | NA | 104 | 198 | 28 | 226 | WK | 9781456.35 | 1505610.45 | 8275845.9 | 0 | Breakwater Marine Base @$3,960,000 (Posillico Civil) 2. start date June 5, 2022
Y | IPCRP1-0464-1010-C | IPCRP1 | IPCRP1 | 0464-1010 | Tug Boat Rental | N | C |  | NR | P | 339706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 339706 | 0 | 0 | 339706 | 0 | 0 | 0 | N | 339706 | 0 | 0 | 339706 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 24 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0 | This code will not be used. PMF will be $0 in all codes. Code was originally set up if we were renting a boat (which we are not).
Y | IPCRP1-0464-1010-L | IPCRP1 | IPCRP1 | 0464-1010 | Tug Boat Rental | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 24 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0464-1010-S | IPCRP1 | IPCRP1 | 0464-1010 | Tug Boat Rental | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 0 | 720 | 0 | 720 | NA | 24 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0465-0000-L | IPCRP1 | IPCRP1 | 0465-0000 | WATERFRONT OPERATIONS FACILITY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0465-0000-R | IPCRP1 | IPCRP1 | 0465-0000 | WATERFRONT OPERATIONS FACILITY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000000 | 0 | 0 | 5000000 | 0 | 5000000 | 5656250 | 0 | N | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0465-1000-C | IPCRP1 | IPCRP1 | 0465-1000 | Off Load Fill From Barge | N | C |  | UNIT | U | 0 | 2477122.98 | 2477122.98 | 1860773.32 | 2477122.98 | 44.1741 | 0 | 0 | 0 | 1735244.02 | Y | 4212367 | Y | -4212367 | 0 | 0 | 0 | 0 | 0 | 4212367 | Y | -4212367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4212367 | 0 | 0 | 4212367 | 0 | 0 | 0 | 0 | 0 | 0 | -4212367 | 0 | 0 | 4212367 | 4212367 | 0 | 0 | 0 | 0 | 0 | 49190.33 | 49190.33 | 0 | 48595.14 | 595.19 | 49190.33 | NA | 490000 | 264561.56 | 225438.44 | 490000 | CY | 2477122.98 | 616349.66 | 1860773.32 | 1735244.02
Y | IPCRP1-0465-1000-E | IPCRP1 | IPCRP1 | 0465-1000 | Off Load Fill From Barge | N | E |  | NR | P | 392000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 392000 | 0 | 0 | 392000 | 0 | 0 | 0 | Y | 392000 | 0 | 0 | 392000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8.5 | -8.5 | 0 | NA | 490000 | 264561.56 | 225438.44 | 490000 | CY | 0 | 0 | 0 | 0 | Weeks Marine @$1,867,550.00
Y | IPCRP1-0465-1000-L | IPCRP1 | IPCRP1 | 0465-1000 | Off Load Fill From Barge | N | L |  | NR | P | 722343.3 | 233551.95 | 233551.95 | 233551.95 | 233551.95 | 71.0903 | 0 | 0 | 0 | 94976.69 | Y | 328528.64 | Y | 393814.66 | 0 | 0 | 722343.3 | 0 | 0 | 328528.64 | Y | 393814.66 | 0 | 0 | 722343.3 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -328528.64 | 0 | 0 | 328528.64 | 0 | 0 | 0 | 0 | 0 | 0 | -328528.64 | 0 | 0 | 328528.64 | 328528.64 | 0 | 0 | 0 | 5880 | 0 | 2250 | 2250 | 5880 | 1546.5 | 703.5 | 2250 | HR | 490000 | 264561.56 | 225438.44 | 490000 | CY | 0 | 0 | 0 | 94976.69 | Weeks Marine @$1,867,550.00
Y | IPCRP1-0465-1000-S | IPCRP1 | IPCRP1 | 0465-1000 | Off Load Fill From Barge | N | S |  | UNIT | A | 0 | 856502.09 | 856502.09 | 557907.09 | 856502.09 | 65.1379 | 0 | 0 | 0 | 0 | Y | 856502.09 | Y | -856502.09 | 0 | 0 | 0 | 0 | 0 | 856502.09 | Y | -856502.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -856502.09 | 0 | 0 | 856502.09 | 0 | 0 | 0 | 0 | 0 | 0 | -856502.09 | 0 | 0 | 856502.09 | 856502.09 | 0 | 0 | 0 | 0 | 0 | 364 | 364 | 0 | 534 | -170 | 364 | NA | 490000 | 264561.56 | 225438.44 | 490000 | CY | 856502.09 | 298595 | 557907.09 | 0 | 1) Weeks Marine subcontract terminated Aug 23, final CV = $506,775.00, 76,121 CY, (6.65/CY avg) 2) Using Carver to unload after this. Hold 1.5M in cost for this purpose. Weeks Marine @$1,867,550.00 Weeks Marine subcontract cancelled. Leaving PMF value in place until new arrangements are finalized. As of 10/31/24 Carver costing $5.85/cy. Adjusted PMF (Consum) to match. 3. CTD (Quant) from actual CA Fill value (not 85%) + Andrews LW Fill quantity (45,089 cy)
Y | IPCRP1-0465-1010-E | IPCRP1 | IPCRP1 | 0465-1010 | Off Load Other Materials | N | E |  | NR | P | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 320000 | 0 | 0 | 320000 | 0 | 0 | 0 | Y | 320000 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 100 | 35 | 65 | 100 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0465-1010-L | IPCRP1 | IPCRP1 | 0465-1010 | Off Load Other Materials | N | L |  | NR | P | 1156244 | 141710.98 | 141710.98 | 141710.98 | 141710.98 | 12.2561 | 0 | 0 | 0 | 1014533.02 | N | 1156244 | N | 0 | 0 | 0 | 1156244 | 0 | 0 | 1156244 | N | 0 | 0 | 0 | 1156244 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1156244 | 1858.01 | 0 | 1156244 | 0 | 0 | 0 | 0 | 0 | 0 | -1156244 | 0 | 0 | 1156244 | 1156244 | 0 | 0 | 0 | 9600 | 0 | 9600 | 9600 | 9600 | 925.5 | 8674.5 | 9600 | HR | 100 | 35 | 65 | 100 | SH | 0 | 0 | 0 | 1014533.02
Y | IPCRP1-0465-1020-C | IPCRP1 | IPCRP1 | 0465-1020 | Waterfront Operations Facility | N | C |  | UNIT | U | 0 | 1829980.65 | 1829980.65 | 1481995.73 | 1829980.65 | 80.9842 | 0 | 0 | 0 | 0 | Y | 1829980.65 | Y | -1829980.65 | 0 | 0 | 0 | 0 | 0 | 1829980.65 | Y | -1829980.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1829980.65 | 21775 | 21775 | 1829980.65 | 0 | 0 | 0 | 0 | 0 | 0 | -1829980.65 | 0 | 0 | 1829980.65 | 1829980.65 | 0 | 0 | 0 | 0 | 0 | 135944.22 | 135944.22 | 0 | 135948.22 | -4 | 135944.22 | NA | 40 | 45.25 | 7.65 | 52.9 | MO | 1837601.97 | 347984.92 | 1489617.05 | 0 | HUGHES MARINE PO @522,600.00
Y | IPCRP1-0465-1020-E | IPCRP1 | IPCRP1 | 0465-1020 | Waterfront Operations Facility | N | E |  | UNIT | A | 0 | 637032.58 | 637032.58 | 428298.5 | 637032.58 | 83.8104 | 0 | 0 | 0 | -126000 | Y | 511032.58 | Y | -511032.58 | 0 | 0 | 0 | 0 | 0 | 511032.58 | Y | -511032.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -511032.58 | 0 | 7621.25 | 511032.58 | 0 | 0 | 0 | 0 | 0 | 0 | -511032.58 | 0 | 0 | 511032.58 | 511032.58 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 64.38 | -63.38 | 1 | NA | 40 | 45.25 | 7.65 | 52.9 | MO | 637032.58 | 208734.08 | 428298.5 | -126000 | Breakwater Base PO #221 @$364,060
Y | IPCRP1-0465-1020-L | IPCRP1 | IPCRP1 | 0465-1020 | Waterfront Operations Facility | N | L |  | UNIT | P | 0 | 73995.22 | 73995.22 | 73995.22 | 73995.22 | 100 | 0 | 0 | 0 | 0 | Y | 73995.22 | Y | -73995.22 | 0 | 0 | 0 | 0 | 0 | 73995.22 | Y | -73995.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -73995.22 | 0 | 0 | 73995.22 | 0 | 0 | 0 | 0 | 0 | 0 | -73995.22 | 0 | 0 | 73995.22 | 73995.22 | 0 | 0 | 0 | 0 | 0 | 510.5 | 510.5 | 0 | 510.5 | 0 | 510.5 | HR | 40 | 45.25 | 7.65 | 52.9 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0465-1020-S | IPCRP1 | IPCRP1 | 0465-1020 | Waterfront Operations Facility | N | S |  | NR | A | 1000000 | 64281.34 | 64281.34 | 16831.34 | 64281.34 | 3.5708 | 0 | 0 | 0 | 407076.1 | Y | 471357.44 | Y | 528642.56 | 0 | 0 | 1000000 | 0 | 0 | 471357.44 | Y | 528642.56 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -471357.44 | 0 | 0 | 471357.44 | 0 | 0 | 0 | 0 | 0 | 0 | -471357.44 | 0 | 0 | 471357.44 | 471357.44 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6 | -6 | 0 | NA | 40 | 45.25 | 7.65 | 52.9 | MO | 64281.34 | 47450 | 16831.34 | 407076.1
Y | IPCRP1-0465-1030-C | IPCRP1 | IPCRP1 | 0465-1030 | Barge Moves | N | C |  | UNIT | U | 0 | 645690.61 | 645690.61 | 320927.59 | 645690.61 | 49.725 | 0 | 0 | 0 | -285.36 | Y | 645405.25 | Y | -645405.25 | 0 | 0 | 0 | 0 | 0 | 645405.25 | Y | -645405.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -645405.25 | 0 | 285.36 | 645405.25 | 0 | 0 | 0 | 0 | 0 | 0 | -645405.25 | 0 | 0 | 645405.25 | 645405.25 | 0 | 0 | 0 | 0 | 0 | 548 | 548 | 0 | 22774.14 | -22226.14 | 548 | NA | 20 | 11 | 9 | 20 | SH | 645405.25 | 324763.02 | 320642.23 | -285.36 | Millers Launch PO #247 @$250.025
Y | IPCRP1-0465-1030-L | IPCRP1 | IPCRP1 | 0465-1030 | Barge Moves | N | L |  | UNIT | P | 0 | 5452.55 | 5452.55 | 5452.55 | 5452.55 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.5 | -41.5 | 0 | HR | 20 | 11 | 9 | 20 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0465-1030-M | IPCRP1 | IPCRP1 | 0465-1030 | Barge Moves | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 20 | 11 | 9 | 20 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0465-1030-S | IPCRP1 | IPCRP1 | 0465-1030 | Barge Moves | N | S |  | NR | A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | Y | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 20 | 11 | 9 | 20 | SH | 0 | 0 | 0 | 0 | PMF matches to the budget.
Y | IPCRP1-0466-0000-L | IPCRP1 | IPCRP1 | 0466-0000 | CONTROLLED LOW STRENGTH MATERIAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0466-0000-R | IPCRP1 | IPCRP1 | 0466-0000 | CONTROLLED LOW STRENGTH MATERIAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 217000 | 0 | 0 | 217000 | 0 | 217000 | 2247 | 0 | N | 217000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0466-1000-E | IPCRP1 | IPCRP1 | 0466-1000 | Controlled Low Strength Materials | N | E |  | NR | P | 16532.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16532.5 | 0 | 0 | 16532.5 | 0 | 0 | 0 | Y | 16532.5 | 0 | 0 | 16532.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 620 | 6.42 | 613.58 | 620 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0466-1000-L | IPCRP1 | IPCRP1 | 0466-1000 | Controlled Low Strength Materials | N | L |  | NR | P | 57141.97 | 44.98 | 44.98 | 44.98 | 44.98 | 0.078716 | 0 | 0 | 0 | 57096.99 | N | 57141.97 | N | 0 | 0 | 0 | 57141.97 | 0 | 0 | 57141.97 | N | 0 | 0 | 0 | 57141.97 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -57141.97 | 0 | -837.11 | 57141.97 | 0 | 0 | 0 | 0 | 0 | 0 | -57141.97 | 0 | 0 | 57141.97 | 57141.97 | 0 | 0 | 0 | 529.06 | 0 | 529.06 | 529.06 | 529.06 | 0 | 529.06 | 529.06 | HR | 620 | 6.42 | 613.58 | 620 | CY | 0 | 0 | 0 | 57096.99
Y | IPCRP1-0467-0000-L | IPCRP1 | IPCRP1 | 0467-0000 | CONST REPORT FOR REACH A | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0467-0000-R | IPCRP1 | IPCRP1 | 0467-0000 | CONST REPORT FOR REACH A | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0468-0000-L | IPCRP1 | IPCRP1 | 0468-0000 | CONST REPORT FOR REACH B | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0468-0000-R | IPCRP1 | IPCRP1 | 0468-0000 | CONST REPORT FOR REACH B | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0469-0000-L | IPCRP1 | IPCRP1 | 0469-0000 | CONST REPORT FOR REACH C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0469-0000-R | IPCRP1 | IPCRP1 | 0469-0000 | CONST REPORT FOR REACH C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0470-0000-L | IPCRP1 | IPCRP1 | 0470-0000 | CONST REPORT FOR REACH D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0470-0000-R | IPCRP1 | IPCRP1 | 0470-0000 | CONST REPORT FOR REACH D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0471-0000-L | IPCRP1 | IPCRP1 | 0471-0000 | CONST REPORT FOR REACH E | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0471-0000-R | IPCRP1 | IPCRP1 | 0471-0000 | CONST REPORT FOR REACH E | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0472-0000-L | IPCRP1 | IPCRP1 | 0472-0000 | CONST REPORT FOR W-BURG BRIDGE FOOT (REACH E) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0472-0000-R | IPCRP1 | IPCRP1 | 0472-0000 | CONST REPORT FOR W-BURG BRIDGE FOOT (REACH E) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0473-0000-L | IPCRP1 | IPCRP1 | 0473-0000 | CONST REPORT FOR REACH F | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0473-0000-R | IPCRP1 | IPCRP1 | 0473-0000 | CONST REPORT FOR REACH F | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0474-0000-L | IPCRP1 | IPCRP1 | 0474-0000 | CONST REPORT FOR REACH G | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0474-0000-R | IPCRP1 | IPCRP1 | 0474-0000 | CONST REPORT FOR REACH G | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0475-0000-L | IPCRP1 | IPCRP1 | 0475-0000 | CONST REPORT FOR REACH H | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0475-0000-R | IPCRP1 | IPCRP1 | 0475-0000 | CONST REPORT FOR REACH H | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0476-0000-L | IPCRP1 | IPCRP1 | 0476-0000 | CONST REPORT FOR REACH I | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0476-0000-R | IPCRP1 | IPCRP1 | 0476-0000 | CONST REPORT FOR REACH I | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0477-0000-L | IPCRP1 | IPCRP1 | 0477-0000 | CONST REPORT FOR REACH J | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0477-0000-R | IPCRP1 | IPCRP1 | 0477-0000 | CONST REPORT FOR REACH J | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0478-0000-L | IPCRP1 | IPCRP1 | 0478-0000 | CONST REPORT FOR REACH K | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0478-0000-R | IPCRP1 | IPCRP1 | 0478-0000 | CONST REPORT FOR REACH K | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0479-0000-L | IPCRP1 | IPCRP1 | 0479-0000 | CONST REPORT FOR CE B-CONVEY TUNNEL (REACH K) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0479-0000-R | IPCRP1 | IPCRP1 | 0479-0000 | CONST REPORT FOR CE B-CONVEY TUNNEL (REACH K) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0480-0000-L | IPCRP1 | IPCRP1 | 0480-0000 | CONST REPORT FOR MTA L-TRAIN TUNNEL (REACH K) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0480-0000-R | IPCRP1 | IPCRP1 | 0480-0000 | CONST REPORT FOR MTA L-TRAIN TUNNEL (REACH K) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0481-0000-L | IPCRP1 | IPCRP1 | 0481-0000 | MONITOR & POST-CONST REPORT - REACH A | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0481-0000-R | IPCRP1 | IPCRP1 | 0481-0000 | MONITOR & POST-CONST REPORT - REACH A | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0482-0000-L | IPCRP1 | IPCRP1 | 0482-0000 | MONITOR & POST-CONST REPORT - REACH B | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0482-0000-R | IPCRP1 | IPCRP1 | 0482-0000 | MONITOR & POST-CONST REPORT - REACH B | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 3000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0483-0000-L | IPCRP1 | IPCRP1 | 0483-0000 | MONITOR & POST-CONST REPORT - REACH C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0483-0000-R | IPCRP1 | IPCRP1 | 0483-0000 | MONITOR & POST-CONST REPORT - REACH C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 3000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0484-0000-L | IPCRP1 | IPCRP1 | 0484-0000 | MONITOR & POST-CONST REPORT - REACH D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0484-0000-R | IPCRP1 | IPCRP1 | 0484-0000 | MONITOR & POST-CONST REPORT - REACH D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 3000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0485-0000-L | IPCRP1 | IPCRP1 | 0485-0000 | MONITOR & POST-CONST REPORT - REACH E | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0485-0000-R | IPCRP1 | IPCRP1 | 0485-0000 | MONITOR & POST-CONST REPORT - REACH E | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0486-0000-L | IPCRP1 | IPCRP1 | 0486-0000 | MONITOR & POST-CONST REPORT - W-BURG BRIDGE FOOT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0486-0000-R | IPCRP1 | IPCRP1 | 0486-0000 | MONITOR & POST-CONST REPORT - W-BURG BRIDGE FOOT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0487-0000-L | IPCRP1 | IPCRP1 | 0487-0000 | MONITOR & POST-CONST REPORT - REACH F | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0487-0000-R | IPCRP1 | IPCRP1 | 0487-0000 | MONITOR & POST-CONST REPORT - REACH F | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0488-0000-L | IPCRP1 | IPCRP1 | 0488-0000 | MONITOR & POST-CONST REPORT - REACH G | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0488-0000-R | IPCRP1 | IPCRP1 | 0488-0000 | MONITOR & POST-CONST REPORT - REACH G | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0489-0000-L | IPCRP1 | IPCRP1 | 0489-0000 | MONITOR & POST-CONST REPORT - REACH H | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0489-0000-R | IPCRP1 | IPCRP1 | 0489-0000 | MONITOR & POST-CONST REPORT - REACH H | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0490-0000-L | IPCRP1 | IPCRP1 | 0490-0000 | MONITOR & POST-CONST REPORT - REACH I | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0490-0000-R | IPCRP1 | IPCRP1 | 0490-0000 | MONITOR & POST-CONST REPORT - REACH I | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0491-0000-L | IPCRP1 | IPCRP1 | 0491-0000 | MONITOR & POST-CONST REPORT - REACH J | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0491-0000-R | IPCRP1 | IPCRP1 | 0491-0000 | MONITOR & POST-CONST REPORT - REACH J | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0492-0000-L | IPCRP1 | IPCRP1 | 0492-0000 | MONITOR & POST-CONST REPORT - REACH K | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0492-0000-R | IPCRP1 | IPCRP1 | 0492-0000 | MONITOR & POST-CONST REPORT - REACH K | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0493-0000-L | IPCRP1 | IPCRP1 | 0493-0000 | MON & POST-CONST REP - CE B-CONVEY TUNNEL (K) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0493-0000-R | IPCRP1 | IPCRP1 | 0493-0000 | MON & POST-CONST REP - CE B-CONVEY TUNNEL (K) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0494-0000-L | IPCRP1 | IPCRP1 | 0494-0000 | MON & POST-CONST REP - MTA L-TRAIN TUNNEL (K) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0494-0000-R | IPCRP1 | IPCRP1 | 0494-0000 | MON & POST-CONST REP - MTA L-TRAIN TUNNEL (K) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0494-1000-L | IPCRP1 | IPCRP1 | 0494-1000 | Motinoring Sub (SA Engineering) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.74 | 0.26 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0494-1000-M | IPCRP1 | IPCRP1 | 0494-1000 | Motinoring Sub (SA Engineering) | N | M |  | UNIT | U | 0 | 20336.9 | 20336.9 | 19846.15 | 20336.9 | 152.8775 | 0 | 0 | 0 | 0 | N | 12981.73 | N | -12981.73 | 0 | 0 | 0 | 0 | 0 | 12981.73 | N | -12981.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12981.73 | 0 | 0 | 12981.73 | 0 | 0 | 0 | 0 | 0 | 0 | -12981.73 | 0 | 0 | 12981.73 | 12981.73 | 0 | 0 | 0 | 0 | 0 | 142 | 142 | 0 | 209 | -67 | 142 | NA | 1 | 0.74 | 0.26 | 1 | LS | 20691.72 | 490.75 | 20200.97 | 0
Y | IPCRP1-0494-1000-S | IPCRP1 | IPCRP1 | 0494-1000 | Motinoring Sub (SA Engineering) | N | S |  | NR | A | 1005571 | 1790162 | 1790162 | 1262142 | 1790162 | 70.6346 | 0 | 0 | 0 | -3300 | Y | 1786862 | Y | -781291 | 0 | 0 | 1005571 | 0 | 0 | 1786862 | Y | -781291 | 0 | 0 | 1005571 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1786862 | 0 | 12820 | 1786862 | 0 | 0 | 0 | 0 | 3000 | 0 | -1786862 | 0 | 0 | 1786862 | 1786862 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1542 | 189.47 | 1731.47 | NA | 1 | 0.74 | 0.26 | 1 | LS | 1790162 | 528020 | 1262142 | -3300 | SA ENGINEERING Base @$899,600.00 CO@$2,626. Air Quality Monitoring CO for SA Eng @$174,200
Y | IPCRP1-0495-0000-L | IPCRP1 | IPCRP1 | 0495-0000 | ECO ARMOR BLOCK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0495-0000-R | IPCRP1 | IPCRP1 | 0495-0000 | ECO ARMOR BLOCK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 592000 | 0 | 0 | 592000 | 0 | 592000 | 345600 | 0 | N | 592000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0495-1000-L | IPCRP1 | IPCRP1 | 0495-1000 | ECO ARMOR BLOCK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 185 | 108 | 108 | 216 | EA | 0 | 0 | 0 | 0 | Installation moved to cc: 0446-1010 Marine Demo sub (Trevcon) EcoBlock (490K), Iron Horse Transport (69K), Amoruso (10K) = 568K
Y | IPCRP1-0495-1000-M | IPCRP1 | IPCRP1 | 0495-1000 | ECO ARMOR BLOCK | N | M |  | UNIT | U | 0 | 401476.12 | 401476.12 | 401476.12 | 401476.12 | 99.9328 | 0 | 0 | 0 | 270 | Y | 401746.12 | Y | -401746.12 | 0 | 0 | 0 | 0 | 0 | 401746.12 | Y | -401746.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -401746.12 | 0 | 0 | 401746.12 | 0 | 0 | 0 | 0 | 0 | 0 | -401746.12 | 0 | 0 | 401746.12 | 401746.12 | 0 | 0 | 0 | 0 | 0 | 1465.06 | 1465.06 | 0 | 1464.36 | 0.7 | 1465.06 | NA | 185 | 108 | 108 | 216 | EA | 401476.12 | 0 | 401476.12 | 270 | Change PMF (Mat) from $418,617.00 to $401,476.12, matching CTD
Y | IPCRP1-0495-1000-S | IPCRP1 | IPCRP1 | 0495-1000 | ECO ARMOR BLOCK | N | S |  | NR | A | 548183.36 | 8925 | 8925 | 8925 | 8925 | 100 | 0 | 0 | 0 | 0 | Y | 8925 | Y | 539258.36 | 0 | 0 | 548183.36 | 0 | 0 | 8925 | Y | 539258.36 | 0 | 0 | 548183.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8925 | 0 | 0 | 8925 | 0 | 0 | 0 | 0 | 0 | 0 | -8925 | 0 | 0 | 8925 | 8925 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7 | -7 | 0 | NA | 185 | 108 | 108 | 216 | EA | 8925 | 0 | 8925 | 0
Y | IPCRP1-0496-0000-L | IPCRP1 | IPCRP1 | 0496-0000 | ECO TIDAL POOL ARMOR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0496-0000-R | IPCRP1 | IPCRP1 | 0496-0000 | ECO TIDAL POOL ARMOR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 155000 | 0 | 0 | 155000 | 0 | 155000 | 60000 | 0 | N | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0496-1000-L | IPCRP1 | IPCRP1 | 0496-1000 | ECO TIDAL POOL ARMOR | N | L |  | UNIT | P | 0 | 13194.83 | 13194.83 | 13194.83 | 13194.83 | 33.9462 | 0 | 0 | 0 | 25675 | Y | 38869.83 | Y | -38869.83 | 0 | 0 | 0 | 0 | 0 | 38869.83 | Y | -38869.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -38869.83 | 0 | 0 | 38869.83 | 0 | 0 | 0 | 0 | 0 | 0 | -38869.83 | 0 | 0 | 38869.83 | 38869.83 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 102.5 | 197.5 | 300 | HR | 31 | 12 | 18 | 30 | EA | 0 | 0 | 0 | 25675 | Installation moved to cc: 0446-1010 Marine Demo sub (Trevcon). Negative CO will delete Trevcon's scope. Converted to self-perform in Jan-24. 31 bought out in case of damage.
Y | IPCRP1-0496-1000-M | IPCRP1 | IPCRP1 | 0496-1000 | ECO TIDAL POOL ARMOR | N | M |  | UNIT | U | 0 | 49401 | 49401 | 49401 | 49401 | 100 | 0 | 0 | 0 | 0 | N | 49401 | N | -49401 | 0 | 0 | 0 | 0 | 0 | 49401 | N | -49401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -49401 | 0 | 0 | 49401 | 0 | 0 | 0 | 0 | 0 | 0 | -49401 | 0 | 0 | 49401 | 49401 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 0 | 66 | 0 | 66 | NA | 31 | 12 | 18 | 30 | EA | 49401 | 0 | 49401 | 0
Y | IPCRP1-0496-1000-S | IPCRP1 | IPCRP1 | 0496-1000 | ECO TIDAL POOL ARMOR | N | S |  | NR | A | 148555.52 | 0 | -29780.73 | -29780.73 | 0 | 100 | 0 | 0 | 0 | -29780.73 | Y | -29780.73 | Y | 178336.25 | 0 | 0 | 148555.52 | 0 | 0 | -29780.73 | Y | 178336.25 | 0 | 0 | 148555.52 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 29780.73 | 0 | 0 | -29780.73 | 0 | 0 | 0 | 0 | 0 | 0 | 29780.73 | 0 | 0 | -29780.73 | -29780.73 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 34.04 | -34.04 | 0 | NA | 31 | 12 | 18 | 30 | EA | 0 | 29780.73 | -29780.73 | -29780.73 | Change PMF (Sub) from $20,587.77 to $0.00, matching Commitment
Y | IPCRP1-0497-0000-L | IPCRP1 | IPCRP1 | 0497-0000 | ECO SEA PILLAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0497-0000-R | IPCRP1 | IPCRP1 | 0497-0000 | ECO SEA PILLAR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750000 | 0 | 0 | 750000 | 0 | 750000 | 450000 | 0 | N | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0497-1000-L | IPCRP1 | IPCRP1 | 0497-1000 | ECO SEA PILLAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 30 | 18 | 12 | 30 | EA | 0 | 0 | 0 | 0 | Installation moved to cc: 0446-1010 Marine Demo sub (Trevcon). re-entered on 1-12-2024
Y | IPCRP1-0497-1000-M | IPCRP1 | IPCRP1 | 0497-1000 | ECO SEA PILLAR | N | M |  | UNIT | U | 0 | 319102.59 | 319102.59 | 319102.59 | 319102.59 | 100 | 0 | 0 | 0 | 0 | Y | 319102.59 | Y | -319102.59 | 0 | 0 | 0 | 0 | 0 | 319102.59 | Y | -319102.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -319102.59 | 0 | 0 | 319102.59 | 0 | 0 | 0 | 0 | 0 | 0 | -319102.59 | 0 | 0 | 319102.59 | 319102.59 | 0 | 0 | 0 | 0 | 0 | 531.51 | 531.51 | 0 | 535.25 | -3.74 | 531.51 | NA | 30 | 18 | 12 | 30 | EA | 319102.59 | 0 | 319102.59 | 0 | Change PMF (Mat) from $321,277.57 to $319,102.59, matching CTD
Y | IPCRP1-0497-1000-S | IPCRP1 | IPCRP1 | 0497-1000 | ECO SEA PILLAR | N | S |  | NR | A | 687712.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 687712.85 | 0 | 0 | 687712.85 | 0 | 0 | 0 | Y | 687712.85 | 0 | 0 | 687712.85 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 30 | 18 | 12 | 30 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0498-0000-L | IPCRP1 | IPCRP1 | 0498-0000 | HAUL, TRANSP & DISPOSE, NON-HAZ CONTAM SOIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0498-0000-R | IPCRP1 | IPCRP1 | 0498-0000 | HAUL, TRANSP & DISPOSE, NON-HAZ CONTAM SOIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 180000 | 0 | 0 | 180000 | 0 | 180000 | 36690788.7 | 0 | N | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0498-1000-C | IPCRP1 | IPCRP1 | 0498-1000 | Haul, Transp & Disp, Non-Haz Contam Soil | N | C |  | UNIT | P | 0 | 30797794.35 | 30797794.35 | 12912742.98 | 30797794.35 | 101.1398 | 0 | 0 | 0 | -18030575.07 | Y | 12767219.28 | Y | -12767219.28 | 0 | 0 | 0 | 0 | 0 | 12767219.28 | Y | -12767219.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12767219.28 | 145523.7 | 168904.42 | 12767219.28 | 0 | 0 | 0 | 0 | 4500 | 0 | -12767219.28 | 0 | 0 | 12767219.28 | 12767219.28 | 0 | 0 | 0 | 0 | 0 | 418583.8 | 418583.8 | 0 | 423424.61 | -4840.81 | 418583.8 | NA | 2000 | 407675.43 | 0 | 407675.43 | TN | 30799566.47 | 17885051.37 | 12914515.1 | -18030575.07 | BAYSHORE SOIL MANAGEMENT LLC@$28,683,499.38 , and, CLEAN EARTH OF CARTERET, LLC@$14,451.25 , and, MUNOZ TRUCKING CORP@$1,491,399.86 , Total commitment is @$30,189,350.49 needs to be cleaned up and tied to revenue increase.
Y | IPCRP1-0498-1000-L | IPCRP1 | IPCRP1 | 0498-1000 | Haul, Transp & Disp, Non-Haz Contam Soil | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HR | 2000 | 407675.43 | 0 | 407675.43 | TN | 0 | 0 | 0 | 0 | Base contract quantity (2,000 T) + OR CO#02 (+121,500 T) + OR CO#05 (+190,500 T) =New total = 314,000 T. PMF (Sub) based on $25.00/T. PMF (Consumable) based on $32/T. New Revenue Total = 314,000 T @ $90/T = $28,260,000.00
Y | IPCRP1-0498-1000-S | IPCRP1 | IPCRP1 | 0498-1000 | Haul, Transp & Disp, Non-Haz Contam Soil | N | S |  | NR | A | 154660 | 7245226.44 | 7245226.44 | 6636198.55 | 7245226.44 | 84.5376 | 0 | 0 | 0 | 604773.56 | Y | 7850000 | Y | -7695340 | 0 | 0 | 154660 | 0 | 0 | 7850000 | Y | -7695340 | 0 | 0 | 154660 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7850000 | 0 | 26382.96 | 7850000 | 0 | 0 | 0 | 0 | 0 | 0 | -7850000 | 0 | 0 | 7850000 | 7850000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 267078.54 | -267078.54 | 0 | NA | 2000 | 407675.43 | 0 | 407675.43 | TN | 7245226.44 | 609027.89 | 6636198.55 | 604773.56 | Registered CO qty is 121,500. New Total is 123,500 (2,000 + 121,500). Subcontract forecast is $3,087,500 @$25/TON, and Consumable forecast is $3,952,000 @$32/TON
Y | IPCRP1-0498-1010-L | IPCRP1 | IPCRP1 | 0498-1010 | Screening & Loading of Contam & Non-Contam Soils | N | L |  | UNIT | P | 0 | 294775.69 | 294775.69 | 294775.69 | 294775.69 | 61.4108 | 0 | 0 | 0 | 185230.46 | Y | 480006.15 | Y | -480006.15 | 0 | 0 | 0 | 0 | 0 | 480006.15 | Y | -480006.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -480006.15 | 4904.73 | 10834.59 | 480006.15 | 0 | 0 | 0 | 0 | 0 | 0 | -480006.15 | 0 | 0 | 480006.15 | 480006.15 | 0 | 0 | 0 | 0 | 0 | 3200 | 3200 | 0 | 1969.5 | 1230.5 | 3200 | HR | 0 | 274 | 126 | 400 | DY | 0 | 0 | 0 | 185230.46
Y | IPCRP1-0498-1010-S | IPCRP1 | IPCRP1 | 0498-1010 | Screening & Loading of Contam & Non-Contam Soils | N | S |  | UNIT | A | 0 | 68622.65 | 68622.65 | 13622.65 | 68622.65 | 20.343 | 0 | 0 | 0 | 0 | N | 66964.77 | N | -66964.77 | 0 | 0 | 0 | 0 | 0 | 66964.77 | N | -66964.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -66964.77 | 387.4 | 0 | 66964.77 | 0 | 0 | 0 | 0 | 387.4 | 0 | -66964.77 | 0 | 0 | 66964.77 | 66964.77 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 27.54 | -1.54 | 26 | NA | 0 | 274 | 126 | 400 | DY | 68622.65 | 55000 | 13622.65 | 0
Y | IPCRP1-0498-1015-L | IPCRP1 | IPCRP1 | 0498-1015 | Prep and Set Up for Haz Material Stor/Handling | N | L |  | UNIT | P | 0 | 16373.62 | 16373.62 | 16373.62 | 16373.62 | 55.1754 | 0 | 0 | 0 | 13301.96 | N | 29675.58 | N | -29675.58 | 0 | 0 | 0 | 0 | 0 | 29675.58 | N | -29675.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -29675.58 | 1245.43 | 0 | 29675.58 | 0 | 0 | 0 | 0 | 0 | 0 | -29675.58 | 0 | 0 | 29675.58 | 29675.58 | 0 | 0 | 0 | 0 | 0 | 231.11 | 231.11 | 0 | 124.5 | 106.61 | 231.11 | HR | 0 | 0.9 | 1.1 | 2 | EA | 0 | 0 | 0 | 13301.96
Y | IPCRP1-0498-1015-S | IPCRP1 | IPCRP1 | 0498-1015 | Prep and Set Up for Haz Material Stor/Handling | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0.9 | 1.1 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0499-0000-L | IPCRP1 | IPCRP1 | 0499-0000 | HAUL, TRANSP & DISPOSE, NON-HAZ MGP CONTAM SOIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0499-0000-R | IPCRP1 | IPCRP1 | 0499-0000 | HAUL, TRANSP & DISPOSE, NON-HAZ MGP CONTAM SOIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 220000 | 0 | 0 | 220000 | 0 | 220000 | 369465.8 | 0 | N | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0499-1000-L | IPCRP1 | IPCRP1 | 0499-1000 | Haul, Trans & Disp, Non-Haz MGP Contam Soil | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2000 | 3358.78 | 0 | 3358.78 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0499-1000-S | IPCRP1 | IPCRP1 | 0499-1000 | Haul, Trans & Disp, Non-Haz MGP Contam Soil | N | S |  | NR | A | 191240 | 1000.78 | 1000.78 | 1000.78 | 1000.78 | 0.52331 | 0 | 0 | 0 | 190239.22 | N | 191240 | N | 0 | 0 | 0 | 191240 | 0 | 0 | 191240 | N | 0 | 0 | 0 | 191240 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -191240 | 0 | 0 | 191240 | 0 | 0 | 0 | 0 | 0 | 0 | -191240 | 0 | 0 | 191240 | 191240 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8 | -8 | 0 | NA | 2000 | 3358.78 | 0 | 3358.78 | TN | 1000.78 | 0 | 1000.78 | 190239.22
Y | IPCRP1-0500-0000-L | IPCRP1 | IPCRP1 | 0500-0000 | SAMPLE & TEST CONTAM/POTENT HAZ SOIL DISPOSE PURP | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0500-0000-R | IPCRP1 | IPCRP1 | 0500-0000 | SAMPLE & TEST CONTAM/POTENT HAZ SOIL DISPOSE PURP | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 137800 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0501-0000-L | IPCRP1 | IPCRP1 | 0501-0000 | HANDLE, TRANSPORT & DISP OF HAZ SOIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0501-0000-R | IPCRP1 | IPCRP1 | 0501-0000 | HANDLE, TRANSPORT & DISP OF HAZ SOIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 500000 | 0 | 0 | 500000 | 0 | 500000 | 361602.5 | 0 | N | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0501-1000-C | IPCRP1 | IPCRP1 | 0501-1000 | HANDLE, TRANSPORT & DISP OF HAZ SOIL | N | C |  | UNIT | U | 0 | 556840.71 | 556840.71 | 478113.24 | 556840.71 | 72.2225 | 0 | 0 | 0 | 105159.29 | Y | 662000 | Y | -662000 | 0 | 0 | 0 | 0 | 0 | 662000 | Y | -662000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -662000 | 0 | 145922.93 | 662000 | 0 | 0 | 0 | 0 | 145922.91 | 0 | -662000 | 0 | 0 | 662000 | 662000 | 0 | 0 | 0 | 0 | 0 | 142914.23 | 142914.23 | 0 | 142914.23 | 0 | 142914.23 | NA | 2000 | 1446.41 | 553.59 | 2000 | TN | 505750.51 | 78727.47 | 427023.04 | 105159.29 | Change PMF (Consumable) from $167,023.70 to $590,000.00
Y | IPCRP1-0501-1000-L | IPCRP1 | IPCRP1 | 0501-1000 | HANDLE, TRANSPORT & DISP OF HAZ SOIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2000 | 1446.41 | 553.59 | 2000 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0501-1000-S | IPCRP1 | IPCRP1 | 0501-1000 | HANDLE, TRANSPORT & DISP OF HAZ SOIL | N | S |  | NR | A | 410800 | 461580 | 461580 | 461579.8 | 461580 | 72.3479 | 0 | 0 | 0 | 176420 | Y | 638000 | Y | -227200 | 0 | 0 | 410800 | 0 | 0 | 638000 | Y | -227200 | 0 | 0 | 410800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -638000 | 0 | 0 | 638000 | 0 | 0 | 0 | 0 | 0 | 0 | -638000 | 0 | 0 | 638000 | 638000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7693 | -7693 | 0 | NA | 2000 | 1446.41 | 553.59 | 2000 | TN | 461580 | 0.2 | 461579.8 | 176420 | Change PMF (Sub) from $270,800.00 to $120,000.00
Y | IPCRP1-0502-0000-L | IPCRP1 | IPCRP1 | 0502-0000 | HEALTH & SAFETY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0502-0000-R | IPCRP1 | IPCRP1 | 0502-0000 | HEALTH & SAFETY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 150000 | 0 | 0 | 150000 | 0 | 150000 | 99000 | 0 | N | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0502-1000-L | IPCRP1 | IPCRP1 | 0502-1000 | Sample, Test, HASP Sub (AES) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.7 | 0.3 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0502-1000-S | IPCRP1 | IPCRP1 | 0502-1000 | Sample, Test, HASP Sub (AES) | N | S |  | NR | A | 139500 | 2771930 | 2771930 | 1940240 | 2771930 | 70.3768 | 0 | 0 | 0 | -15000 | Y | 2756930 | Y | -2617430 | 0 | 0 | 139500 | 0 | 0 | 2756930 | Y | -2617430 | 0 | 0 | 139500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2756930 | 0 | 0 | 2756930 | 0 | 0 | 0 | 0 | 0 | 0 | -2756930 | 0 | 0 | 2756930 | 2756930 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1828.81 | -1827.81 | 1 | NA | 1 | 0.7 | 0.3 | 1 | LS | 2771930 | 831690 | 1940240 | -15000 | American Environmental Solutions - base contract 362.5K, all other sub costs are ES CO's. American Environmental Solutions (Env. Sample & Testing) $ 362,500.00. AES CO's: Prepare Investigative HASP @750.00, Lab analysis of soil samples @$17.5K, Env. Sample & Testing @$5,750.00
Y | IPCRP1-0503-0000-L | IPCRP1 | IPCRP1 | 0503-0000 | REM, TREAT & DISCHARGE/DISP OF CONTAM WATER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | DY | 0 | 0 | 0 | 0
Y | IPCRP1-0503-0000-R | IPCRP1 | IPCRP1 | 0503-0000 | REM, TREAT & DISCHARGE/DISP OF CONTAM WATER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1412950 | 0 | 0 | 1412950 | 0 | 1412950 | 369600 | 0 | N | 1412950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | DY | 0 | 0 | 0 | 0
Y | IPCRP1-0503-1000-L | IPCRP1 | IPCRP1 | 0503-1000 | Operate Water Treatment System, All Shifts | N | L |  | NR | P | 946199.4 | -16.15 | -16.15 | -16.15 | -16.15 | -0.0017068 | 0 | 0 | 0 | 946215.55 | N | 946199.4 | N | 0 | 0 | 0 | 946199.4 | 0 | 0 | 946199.4 | N | 0 | 0 | 0 | 946199.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -946199.4 | 0 | -7216.79 | 946199.4 | 0 | 0 | 0 | 0 | 0 | 0 | -946199.4 | 0 | 0 | 946199.4 | 946199.4 | 0 | 0 | 0 | 8808 | 0 | 8808 | 8808 | 8808 | 0 | 8808 | 8808 | HR | 1101 | 0 | 1101 | 1101 | SH | 0 | 0 | 0 | 946215.55
Y | IPCRP1-0503-1010-L | IPCRP1 | IPCRP1 | 0503-1010 | Operate Dewatering System, Land Side | N | L |  | NR | P | 3249532 | 4610408.13 | 4610408.13 | 4610408.13 | 4610408.13 | 90.2069 | 0 | 0 | 0 | 500518.4 | Y | 5110926.53 | Y | -1861394.53 | 0 | 0 | 3249532 | 0 | 0 | 5110926.53 | Y | -1861394.53 | 0 | 0 | 3249532 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5110926.53 | 25391.12 | 53199.41 | 5110926.53 | 0 | 0 | 0 | 0 | 0 | 0 | -5110926.53 | 0 | 0 | 5110926.53 | 5110926.53 | 0 | 0 | 0 | 24800 | 0 | 34768 | 34768 | 24800 | 31393 | 3375 | 34768 | HR | 3100 | 4026.5 | 319.5 | 4346 | SH | 0 | 0 | 0 | 500518.4
Y | IPCRP1-0503-1010-S | IPCRP1 | IPCRP1 | 0503-1010 | Operate Dewatering System, Land Side | N | S |  | UNIT | A | 0 | 343.91 | 343.91 | 343.91 | 343.91 | 100 | 0 | 0 | 0 | 0 | Y | 343.91 | Y | -343.91 | 0 | 0 | 0 | 0 | 0 | 343.91 | Y | -343.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -343.91 | 0 | 0 | 343.91 | 0 | 0 | 0 | 0 | 0 | 0 | -343.91 | 0 | 0 | 343.91 | 343.91 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 0 | 3 | NA | 3100 | 4026.5 | 319.5 | 4346 | SH | 343.91 | 0 | 343.91 | 0 | Will be in next cycle: Transfer $343.91 (KMA) CTD & Commitment to cc: 0503-1030 Dewater/ Deep Well Sub Support.
Y | IPCRP1-0503-1015-L | IPCRP1 | IPCRP1 | 0503-1015 | Operate Dewatering System (Water Side at Cofferdam | N | L |  | UNIT | P | 0 | 587968.31 | 587968.31 | 587968.31 | 587968.31 | 71.8858 | 0 | 0 | 0 | 229951.69 | Y | 817920 | Y | -817920 | 0 | 0 | 0 | 0 | 0 | 817920 | Y | -817920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -817920 | 5629.38 | 0 | 817920 | 0 | 0 | 0 | 0 | 0 | 0 | -817920 | 0 | 0 | 817920 | 817920 | 0 | 0 | 0 | 0 | 0 | 5776.04 | 5776.04 | 0 | 4553 | 1223.04 | 5776.04 | HR | 0 | 561 | 159 | 720 | SH | 0 | 0 | 0 | 229951.69
Y | IPCRP1-0503-1020-C | IPCRP1 | IPCRP1 | 0503-1020 | Dewater/ Water Treat/ Deep Well Sub (Tri-State) | N | C |  | UNIT | U | 0 | 409931.88 | 409931.88 | 277961.11 | 409931.88 | 67.8067 | 0 | 0 | 0 | 0 | Y | 409931.88 | Y | -409931.88 | 0 | 0 | 0 | 0 | 0 | 409931.88 | Y | -409931.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -409931.88 | 0 | 0 | 409931.88 | 0 | 0 | 0 | 0 | 0 | 0 | -409931.88 | 0 | 0 | 409931.88 | 409931.88 | 0 | 0 | 0 | 0 | 0 | 3568.47 | 3568.47 | 0 | 3808.13 | -239.66 | 3568.47 | NA | 1 | 0.56 | 0.44 | 1 | LS | 417190.81 | 131970.77 | 285220.04 | 0 | Applemon PO@$111,000
Y | IPCRP1-0503-1020-L | IPCRP1 | IPCRP1 | 0503-1020 | Dewater/ Water Treat/ Deep Well Sub (Tri-State) | N | L |  | UNIT | P | 0 | 3812.62 | 3812.62 | 3812.62 | 3812.62 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | -29 | 0 | HR | 1 | 0.56 | 0.44 | 1 | LS | 0 | 0 | 0 | 0 | Tri State = 2.128M (base) + 335 + 137 = 2.6M (sub). Consumable = Applemon (279K) + multiple pipe suppliers = 334K
Y | IPCRP1-0503-1020-S | IPCRP1 | IPCRP1 | 0503-1020 | Dewater/ Water Treat/ Deep Well Sub (Tri-State) | N | S |  | NR | A | 2834910 | 2602331 | 2602331 | 1224119 | 2602331 | 47.0334 | 0 | 0 | 0 | 330 | Y | 2602661 | Y | 232249 | 0 | 0 | 2834910 | 0 | 0 | 2602661 | Y | 232249 | 0 | 0 | 2834910 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2602661 | 0 | 6059.98 | 2602661 | 0 | 0 | 0 | 0 | 0 | 0 | -2602661 | 0 | 0 | 2602661 | 2602661 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3525.32 | 17953.92 | 21479.24 | NA | 1 | 0.56 | 0.44 | 1 | LS | 2602331 | 1378212 | 1224119 | 330 | Tri-State Groundwater Solutions LLC $ 2,128,370.00, Applemon Base PO@$111k. Tri-state CO Dewatering Additional Pumps @$248,100
Y | IPCRP1-0503-1030-C | IPCRP1 | IPCRP1 | 0503-1030 | Dewater/Deep Well Sub Support | N | C |  | NR | P | 137550 | 254273.6 | 254273.6 | 252052.84 | 254273.6 | 72.0151 | 0 | 0 | 0 | 95726.4 | Y | 350000 | Y | -212450 | 0 | 0 | 137550 | 0 | 0 | 350000 | Y | -212450 | 0 | 0 | 137550 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -350000 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | -350000 | 0 | 0 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5748 | 1855.78 | 7603.78 | NA | 2942 | 2311 | 89 | 2400 | HR | 254273.6 | 2220.76 | 252052.84 | 95726.4
Y | IPCRP1-0503-1030-E | IPCRP1 | IPCRP1 | 0503-1030 | Dewater/Deep Well Sub Support | N | E |  | NR | P | 1045414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1045414 | 0 | 0 | 1045414 | 0 | 0 | 0 | N | 1045414 | 0 | 0 | 1045414 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5 | -5 | 0 | NA | 2942 | 2311 | 89 | 2400 | HR | 0 | 0 | 0 | 0 | Reduced self-perform sub support work, and included in subcontractor scope (see 0503-1020)
Y | IPCRP1-0503-1030-L | IPCRP1 | IPCRP1 | 0503-1030 | Dewater/Deep Well Sub Support | N | L |  | NR | P | 352752 | 316100.25 | 316100.25 | 316100.25 | 316100.25 | 100.3481 | 0 | 0 | 0 | -1096.4 | Y | 315003.85 | Y | 37748.15 | 0 | 0 | 352752 | 0 | 0 | 315003.85 | Y | 37748.15 | 0 | 0 | 352752 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -315003.85 | 1805.17 | 12402.26 | 315003.85 | 0 | 0 | 0 | 0 | 0 | 0 | -315003.85 | 0 | 0 | 315003.85 | 315003.85 | 0 | 0 | 0 | 2939.6 | 0 | 2400 | 2400 | 2939.6 | 2393.5 | 6.5 | 2400 | HR | 2942 | 2311 | 89 | 2400 | HR | 0 | 0 | 0 | -1096.4
Y | IPCRP1-0503-1030-S | IPCRP1 | IPCRP1 | 0503-1030 | Dewater/Deep Well Sub Support | N | S |  | UNIT | A | 0 | 7207.17 | 7207.17 | 7207.17 | 7207.17 | 101.8244 | 0 | 0 | 0 | -129.13 | Y | 7078.04 | Y | -7078.04 | 0 | 0 | 0 | 0 | 0 | 7078.04 | Y | -7078.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7078.04 | 129.13 | 262.11 | 7078.04 | 0 | 0 | 0 | 0 | 129.13 | 0 | -7078.04 | 0 | 0 | 7078.04 | 7078.04 | 0 | 0 | 0 | 0 | 0 | 34.5 | 34.5 | 0 | 54 | -19.5 | 34.5 | NA | 2942 | 2311 | 89 | 2400 | HR | 7207.17 | 0 | 7207.17 | -129.13
Y | IPCRP1-0503-1040-E | IPCRP1 | IPCRP1 | 0503-1040 | Fuel Support for Deep Well Sub | N | E |  | NR | P | 31360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 31360 | 0 | 0 | 31360 | 0 | 0 | 0 | N | 31360 | 0 | 0 | 31360 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 7840 | 0 | 0 | 0 | GL | 0 | 0 | 0 | 0
Y | IPCRP1-0503-1040-L | IPCRP1 | IPCRP1 | 0503-1040 | Fuel Support for Deep Well Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 7840 | 0 | 0 | 0 | GL | 0 | 0 | 0 | 0
Y | IPCRP1-0504-0000-L | IPCRP1 | IPCRP1 | 0504-0000 | NYCDEP - SAMPLE & TEST OF CONTAM WATER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0504-0000-R | IPCRP1 | IPCRP1 | 0504-0000 | NYCDEP - SAMPLE & TEST OF CONTAM WATER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0505-0000-L | IPCRP1 | IPCRP1 | 0505-0000 | TEMP PEDESTRIAN BRIDGE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0505-0000-R | IPCRP1 | IPCRP1 | 0505-0000 | TEMP PEDESTRIAN BRIDGE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10000000 | 0 | 0 | 10000000 | 0 | 10000000 | 10000000 | 0 | N | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0505-1000-C | IPCRP1 | IPCRP1 | 0505-1000 | Temp Ped Bridge, Abutments & Footings | N | C |  | UNIT | U | 0 | 417187.76 | 417187.76 | 417187.76 | 417187.76 | 99.3304 | 0 | 0 | 0 | 2812.24 | Y | 420000 | Y | -420000 | 0 | 0 | 0 | 0 | 0 | 420000 | Y | -420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -420000 | 0 | 0 | 420000 | 0 | 0 | 0 | 0 | 35.25 | 0 | -420000 | 0 | 0 | 420000 | 420000 | 0 | 0 | 0 | 0 | 0 | 157 | 157 | 0 | 13171.53 | -13014.53 | 157 | NA | 1 | 1 | 0 | 1 | LS | 410503.02 | -1939.09 | 412442.11 | 2812.24 | IDEAL GROUP IDEAL FOUNATION SY PO @$45,372.08 New commitments issued in June'22: CMF, Colony, Feldman, Ferrera, Rapid, Siegel, Triboro, Auster Rubber, CFS, Richard Dudgeon, Eagle Fence Total @$109,186.92 (as of 6-29-2022)
Y | IPCRP1-0505-1000-E | IPCRP1 | IPCRP1 | 0505-1000 | Temp Ped Bridge, Abutments & Footings | N | E |  | NR | P | 19983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 19983 | 0 | 0 | 19983 | 0 | 0 | 0 | Y | 19983 | 0 | 0 | 19983 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17 | -17 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0505-1000-L | IPCRP1 | IPCRP1 | 0505-1000 | Temp Ped Bridge, Abutments & Footings | N | L |  | NR | P | 130013.91 | 422360.18 | 422360.18 | 422360.18 | 422360.18 | 100.4427 | 0 | 0 | 0 | -1861.46 | Y | 420498.72 | Y | -290484.81 | 0 | 0 | 130013.91 | 0 | 0 | 420498.72 | Y | -290484.81 | 0 | 0 | 130013.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -420498.72 | 1861.45 | 0 | 420498.72 | 0 | 0 | 0 | 0 | 0 | 0 | -420498.72 | 0 | 0 | 420498.72 | 420498.72 | 0 | 0 | 0 | 1199 | 0 | 3444.5 | 3444.5 | 1199 | 3460.5 | -16 | 3444.5 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | -1861.46 | Remove Ramps/Shoring/Etc, crew of 6, 8hr/day x 15 days = 720 MHs. Remove Concrete Foundations, crew of 2, 5 days = 80 Mhs.Monthly Maintenance, crew of 3, 1 day/month x 12 months = 288 MHs. Total Man Hours = 1088 Mhs
Y | IPCRP1-0505-1000-S | IPCRP1 | IPCRP1 | 0505-1000 | Temp Ped Bridge, Abutments & Footings | N | S |  | UNIT | A | 0 | 6174.24 | 6174.24 | 6174.24 | 6174.24 | 106.6945 | 0 | 0 | 0 | 0 | N | 5786.84 | N | -5786.84 | 0 | 0 | 0 | 0 | 0 | 5786.84 | N | -5786.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5786.84 | 387.4 | 0 | 5786.84 | 0 | 0 | 0 | 0 | 387.4 | 0 | -5786.84 | 0 | 0 | 5786.84 | 5786.84 | 0 | 0 | 0 | 0 | 0 | 45.5 | 45.5 | 0 | 45.5 | 0 | 45.5 | NA | 1 | 1 | 0 | 1 | LS | 6174.24 | 0 | 6174.24 | 0
Y | IPCRP1-0506-0000-L | IPCRP1 | IPCRP1 | 0506-0000 | SSVS WORK-COMFORT STATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0506-0000-R | IPCRP1 | IPCRP1 | 0506-0000 | SSVS WORK-COMFORT STATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 150000 | 0 | 0 | 150000 | 0 | 150000 | 3000 | 0 | N | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0507-0000-L | IPCRP1 | IPCRP1 | 0507-0000 | SSVS WORK-M&O 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0507-0000-R | IPCRP1 | IPCRP1 | 0507-0000 | SSVS WORK-M&O 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 6000 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0508-0000-L | IPCRP1 | IPCRP1 | 0508-0000 | SSVS WORK-M&O 3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0508-0000-R | IPCRP1 | IPCRP1 | 0508-0000 | SSVS WORK-M&O 3 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 6000 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0509-0000-L | IPCRP1 | IPCRP1 | 0509-0000 | SSVS WORK-TENNIS BLDG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0509-0000-R | IPCRP1 | IPCRP1 | 0509-0000 | SSVS WORK-TENNIS BLDG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 0 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0510-0000-L | IPCRP1 | IPCRP1 | 0510-0000 | SSVS WORK-TRACK BLDG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0510-0000-R | IPCRP1 | IPCRP1 | 0510-0000 | SSVS WORK-TRACK BLDG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750000 | 0 | 0 | 750000 | 0 | 750000 | 0 | 0 | N | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0510-1000-L | IPCRP1 | IPCRP1 | 0510-1000 | Mech/HVAC/FS/ SSVS Sub (Welkin) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0510-1000-S | IPCRP1 | IPCRP1 | 0510-1000 | Mech/HVAC/FS/ SSVS Sub (Welkin) | N | S |  | NR | A | 1482600 | 1660000 | 1660000 | 65400 | 1660000 | 3.9398 | 0 | 0 | 0 | 0 | Y | 1660000 | Y | -177400 | 0 | 0 | 1482600 | 0 | 0 | 1660000 | Y | -177400 | 0 | 0 | 1482600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1660000 | 0 | 0 | 1660000 | 0 | 0 | 0 | 0 | 0 | 0 | -1660000 | 0 | 0 | 1660000 | 1660000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.85 | 0.15 | 1 | NA | 1 | 0 | 1 | 1 | LS | 1660000 | 1594600 | 65400 | 0 | Budget= $1,482,600; Subcontract=$1,820,000; Loss=($-337,400)
Y | IPCRP1-0511-0000-L | IPCRP1 | IPCRP1 | 0511-0000 | F, D & I CE PIPE-TO-WALL PENETRATION SEAL, COMPL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0511-0000-R | IPCRP1 | IPCRP1 | 0511-0000 | F, D & I CE PIPE-TO-WALL PENETRATION SEAL, COMPL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 270000 | 0 | 0 | 270000 | 0 | 270000 | 0 | 0 | N | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0511-1000-L | IPCRP1 | IPCRP1 | 0511-1000 | F, D & I CE Pipe to Wall Penetration Seal, Compl | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 54 | 0 | 54 | 54 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0511-1000-S | IPCRP1 | IPCRP1 | 0511-1000 | F, D & I CE Pipe to Wall Penetration Seal, Compl | N | S |  | NR | A | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | N | 270000 | N | 0 | 0 | 0 | 270000 | 0 | 0 | 270000 | N | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -270000 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | -270000 | 0 | 0 | 270000 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 54 | 0 | 54 | 54 | EA | 0 | 0 | 0 | 270000
Y | IPCRP1-0512-0000-L | IPCRP1 | IPCRP1 | 0512-0000 | TEMP MEASURES REQD BY PHASING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0512-0000-R | IPCRP1 | IPCRP1 | 0512-0000 | TEMP MEASURES REQD BY PHASING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4500000 | 0 | 0 | 4500000 | 0 | 4500000 | 2834957.2 | 0 | N | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0512-1000-C | IPCRP1 | IPCRP1 | 0512-1000 | Temp Measures Required by Phasing | N | C |  | NR | P | 274208 | 177520.19 | 177520.19 | 175832.86 | 177520.19 | 98.3714 | 0 | 0 | 0 | 1223.75 | Y | 178743.94 | Y | 95464.06 | 0 | 0 | 274208 | 0 | 0 | 178743.94 | Y | 95464.06 | 0 | 0 | 274208 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -178743.94 | 0 | 0 | 178743.94 | 0 | 0 | 0 | 0 | 0 | 0 | -178743.94 | 0 | 0 | 178743.94 | 178743.94 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12580.56 | -7688.39 | 4892.17 | NA | 1 | 0.64 | 0.36 | 1 | LS | 178743.94 | 1687.33 | 177056.61 | 1223.75 | CARTER, MILCHMAN & FRANK, INC; SIEGEL BROS; J.H. FISCHER AND SON
Y | IPCRP1-0512-1000-E | IPCRP1 | IPCRP1 | 0512-1000 | Temp Measures Required by Phasing | N | E |  | NR | P | 18000 | 0 | -114.77 | -114.77 | 0 | 100 | 0 | 0 | 0 | -114.77 | Y | -114.77 | Y | 18114.77 | 0 | 0 | 18000 | 0 | 0 | -114.77 | Y | 18114.77 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 114.77 | 0 | 0 | -114.77 | 0 | 0 | 0 | 0 | 0 | 0 | 114.77 | 0 | 0 | -114.77 | -114.77 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5 | 0 | 5 | NA | 1 | 0.64 | 0.36 | 1 | LS | 0 | 114.77 | -114.77 | -114.77 | Consumable cost is sheeting purchased for work at CE MH#7 on FDR Requested to transfer equipment costs to 2000-1230 Job Site Bare Equipment code Check going forward labor rate. Check remaining man-hours. Compare PMF MH to budgeted hours.
Y | IPCRP1-0512-1000-L | IPCRP1 | IPCRP1 | 0512-1000 | Temp Measures Required by Phasing | N | L |  | NR | P | 294153 | 401199.24 | 401199.24 | 401199.24 | 401199.24 | 71.5327 | 0 | 0 | 0 | 159661.76 | Y | 560861 | Y | -266708 | 0 | 0 | 294153 | 0 | 0 | 560861 | Y | -266708 | 0 | 0 | 294153 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -560861 | 0 | 0 | 560861 | 0 | 0 | 0 | 0 | 0 | 0 | -560861 | 0 | 0 | 560861 | 560861 | 0 | 0 | 0 | 2760 | 0 | 4685.98 | 4685.98 | 2760 | 3311 | 1374.98 | 4685.98 | HR | 1 | 0.64 | 0.36 | 1 | LS | 0 | 0 | 0 | 159661.76
Y | IPCRP1-0512-1000-M | IPCRP1 | IPCRP1 | 0512-1000 | Temp Measures Required by Phasing | N | M |  | NR | P | 102500 | 63894.85 | 63894.85 | 62276.22 | 63894.85 | 97.4667 | 0 | 0 | 0 | 0 | Y | 63894.85 | Y | 38605.15 | 0 | 0 | 102500 | 0 | 0 | 63894.85 | Y | 38605.15 | 0 | 0 | 102500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63894.85 | 0 | 0 | 63894.85 | 0 | 0 | 0 | 0 | 0 | 0 | -63894.85 | 0 | 0 | 63894.85 | 63894.85 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2478 | -2477.96 | 0.04 | NA | 1 | 0.64 | 0.36 | 1 | LS | 63894.85 | 1618.63 | 62276.22 | 0
Y | IPCRP1-0512-1000-S | IPCRP1 | IPCRP1 | 0512-1000 | Temp Measures Required by Phasing | N | S |  | NR | A | 90000 | 17250.66 | 17250.66 | 17250.66 | 17250.66 | 100 | 0 | 0 | 0 | 0 | Y | 17250.66 | Y | 72749.34 | 0 | 0 | 90000 | 0 | 0 | 17250.66 | Y | 72749.34 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17250.66 | 0 | 0 | 17250.66 | 0 | 0 | 0 | 0 | 0 | 0 | -17250.66 | 0 | 0 | 17250.66 | 17250.66 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 140 | -140 | 0 | NA | 1 | 0.64 | 0.36 | 1 | LS | 17250.66 | 0 | 17250.66 | 0
Y | IPCRP1-0513-0000-L | IPCRP1 | IPCRP1 | 0513-0000 | ALLOW FOR MAX INCENTIVE EARLY COMPLETION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0513-0000-R | IPCRP1 | IPCRP1 | 0513-0000 | ALLOW FOR MAX INCENTIVE EARLY COMPLETION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4500000 | 0 | 0 | 4500000 | 0 | 4500000 | 0 | 0 | N | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0513-1000-C | IPCRP1 | IPCRP1 | 0513-1000 | ALLOW FOR MAX INCENTIVE EARLY COMPLETION | N | C |  | NR | P | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | N | 4500000 | N | 0 | 0 | 0 | 4500000 | 0 | 0 | 4500000 | N | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4500000 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | -4500000 | 0 | 0 | 4500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 4500000
Y | IPCRP1-0513-1000-L | IPCRP1 | IPCRP1 | 0513-1000 | ALLOW FOR MAX INCENTIVE EARLY COMPLETION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0514-0000-L | IPCRP1 | IPCRP1 | 0514-0000 | ALLOW FOR CITY WORK ACCELERATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0514-0000-R | IPCRP1 | IPCRP1 | 0514-0000 | ALLOW FOR CITY WORK ACCELERATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10500000 | 0 | 0 | 10500000 | 0 | 10500000 | 4168622.46 | 0 | N | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0514-1000-C | IPCRP1 | IPCRP1 | 0514-1000 | ALLOW FOR CITY WORK ACCELERATION | N | C |  | NR | P | 9200000 | 14772.96 | 14772.96 | 14772.96 | 14772.96 | 0.27874 | 0 | 0 | 0 | 5285227.04 | Y | 5300000 | Y | 3900000 | 0 | 0 | 9200000 | 0 | 0 | 5300000 | Y | 3900000 | 0 | 0 | 9200000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5300000 | 0 | 0 | 5300000 | 0 | 0 | 0 | 0 | 0 | 0 | -5300000 | 0 | 0 | 5300000 | 5300000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 10000 | 1149 | 8851 | 10000 | HR | 0 | 0 | 0 | 5285227.04 | NYC DOT @$10,500.00. Thru Sep 2025, invoiced $3,484,198.14, which leaves $7,015,801.86, but $528,959.63 is temporary, leaving $7,544,761.49 left to invoice
Y | IPCRP1-0514-1000-L | IPCRP1 | IPCRP1 | 0514-1000 | ALLOW FOR CITY WORK ACCELERATION | N | L |  | UNIT | P | 1300000 | 146197.33 | 146197.33 | 146197.33 | 146197.33 | 11.2459 | 0 | 0 | 0 | 1153802.67 | Y | 1300000 | Y | 0 | 0 | 0 | 1300000 | 0 | 0 | 1300000 | Y | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1300000 | 20010.71 | 5879.27 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | -1300000 | 0 | 0 | 1300000 | 1300000 | 0 | 0 | 0 | 10000 | 0 | 10023.57 | 10023.57 | 10000 | 1187 | 8836.57 | 10023.57 | HR | 10000 | 1149 | 8851 | 10000 | HR | 0 | 0 | 0 | 1153802.67
Y | IPCRP1-0514-1000-S | IPCRP1 | IPCRP1 | 0514-1000 | ALLOW FOR CITY WORK ACCELERATION | N | S |  | UNIT | A | 0 | 127255.15 | 127255.15 | 126635.15 | 127255.15 | 63.3176 | 0 | 0 | 0 | 72744.85 | Y | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200000 | 4713.41 | 5070 | 200000 | 0 | 0 | 0 | 0 | 4713.41 | 0 | -200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 74.5 | -62.5 | 12 | NA | 10000 | 1149 | 8851 | 10000 | HR | 127255.15 | 620 | 126635.15 | 72744.85 | KMA CO
Y | IPCRP1-0515-0000-L | IPCRP1 | IPCRP1 | 0515-0000 | ALLOW FOR EXTRA WORK, ARCHAEOLOGICAL DISCOVERY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0515-0000-R | IPCRP1 | IPCRP1 | 0515-0000 | ALLOW FOR EXTRA WORK, ARCHAEOLOGICAL DISCOVERY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 1000000 | 260777.55 | 0 | N | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0515-1000-C | IPCRP1 | IPCRP1 | 0515-1000 | ALLOW FOR EXTRA WORK, ARCHAEOLOGICAL DISCOVERY | N | C |  | NR | P | 1000000 | 1653.2 | 1653.2 | 1653.2 | 1653.2 | 1.6532 | 0 | 0 | 0 | 98346.8 | N | 100000 | N | 900000 | 0 | 0 | 1000000 | 0 | 0 | 100000 | N | 900000 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 22 | -22 | 0 | NA | 5919.41 | 1380.5 | 4319.5 | 5700 | HR | 1653.2 | 0 | 1653.2 | 98346.8
Y | IPCRP1-0515-1000-E | IPCRP1 | IPCRP1 | 0515-1000 | ALLOW FOR EXTRA WORK, ARCHAEOLOGICAL DISCOVERY | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 5919.41 | 1380.5 | 4319.5 | 5700 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-0515-1000-L | IPCRP1 | IPCRP1 | 0515-1000 | ALLOW FOR EXTRA WORK, ARCHAEOLOGICAL DISCOVERY | N | L |  | UNIT | P | 0 | 157042.88 | 157042.88 | 157042.88 | 157042.88 | 24.1604 | 0 | 0 | 0 | 492957.12 | Y | 650000 | Y | -650000 | 0 | 0 | 0 | 0 | 0 | 650000 | Y | -650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -650000 | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | -650000 | 0 | 0 | 650000 | 650000 | 0 | 0 | 0 | 0 | 0 | 5713.33 | 5713.33 | 0 | 1380.5 | 4332.83 | 5713.33 | HR | 5919.41 | 1380.5 | 4319.5 | 5700 | HR | 0 | 0 | 0 | 492957.12 | Budget split to 800K on Labor and 200K on Consumable.
Y | IPCRP1-0515-1000-S | IPCRP1 | IPCRP1 | 0515-1000 | ALLOW FOR EXTRA WORK, ARCHAEOLOGICAL DISCOVERY | N | S |  | UNIT | A | 0 | 368.64 | 368.64 | 368.64 | 368.64 | 314.1104 | 0 | 0 | 0 | 0 | N | 117.36 | N | -117.36 | 0 | 0 | 0 | 0 | 0 | 117.36 | N | -117.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -117.36 | 0 | 0 | 117.36 | 0 | 0 | 0 | 0 | 0 | 0 | -117.36 | 0 | 0 | 117.36 | 117.36 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | -2 | 1 | NA | 5919.41 | 1380.5 | 4319.5 | 5700 | HR | 368.64 | 0 | 368.64 | 0
Y | IPCRP1-0516-0000-L | IPCRP1 | IPCRP1 | 0516-0000 | ALLOW FOR WAYFINDING TOTEMS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0516-0000-R | IPCRP1 | IPCRP1 | 0516-0000 | ALLOW FOR WAYFINDING TOTEMS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 111600 | 0 | 0 | 111600 | 0 | 111600 | 0 | 0 | N | 111600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0516-1000-C | IPCRP1 | IPCRP1 | 0516-1000 | ALLOW FOR WAYFINDING TOTEMS | N | C |  | NR | P | 111600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111600 | N | 111600 | N | 0 | 0 | 0 | 111600 | 0 | 0 | 111600 | N | 0 | 0 | 0 | 111600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -111600 | 0 | 0 | 111600 | 0 | 0 | 0 | 0 | 0 | 0 | -111600 | 0 | 0 | 111600 | 111600 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 111600
Y | IPCRP1-0516-1000-L | IPCRP1 | IPCRP1 | 0516-1000 | ALLOW FOR WAYFINDING TOTEMS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0517-0000-L | IPCRP1 | IPCRP1 | 0517-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T1) &/OR TEST P | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0517-0000-R | IPCRP1 | IPCRP1 | 0517-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T1) &/OR TEST P | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | N | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0518-0000-L | IPCRP1 | IPCRP1 | 0518-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T1) &/OR TEST P | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0518-0000-R | IPCRP1 | IPCRP1 | 0518-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T1) &/OR TEST P | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8500 | 0 | 0 | 8500 | 0 | 8500 | 0 | 0 | N | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0519-0000-L | IPCRP1 | IPCRP1 | 0519-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T1) &/OR TEST P | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0519-0000-R | IPCRP1 | IPCRP1 | 0519-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T1) &/OR TEST P | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 850 | 0 | 0 | 850 | 0 | 850 | 0 | 0 | N | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0520-0000-L | IPCRP1 | IPCRP1 | 0520-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T2) &/OR TEST P | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0520-0000-R | IPCRP1 | IPCRP1 | 0520-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T2) &/OR TEST P | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5500 | 0 | 0 | 5500 | 0 | 5500 | 0 | 0 | N | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0521-0000-L | IPCRP1 | IPCRP1 | 0521-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T3) &/OR TEST P | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0521-0000-R | IPCRP1 | IPCRP1 | 0521-0000 | UTIL CROSS TRENCH, CB CHUTE CONN (T3) &/OR TEST P | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5400 | 0 | 0 | 5400 | 0 | 5400 | 0 | 0 | N | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0521-1000-E | IPCRP1 | IPCRP1 | 0521-1000 | Util Cross Trench, CB Chute Conn (All types) &/or | N | E |  | NR | P | 2284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2284 | 0 | 0 | 2284 | 0 | 0 | 0 | Y | 2284 | 0 | 0 | 2284 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 20 | 0 | 20 | 20 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0521-1000-L | IPCRP1 | IPCRP1 | 0521-1000 | Util Cross Trench, CB Chute Conn (All types) &/or | N | L |  | NR | P | 12457 | 57.37 | 57.37 | 57.37 | 57.37 | 0.46054 | 0 | 0 | 0 | 12399.63 | N | 12457 | N | 0 | 0 | 0 | 12457 | 0 | 0 | 12457 | N | 0 | 0 | 0 | 12457 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12457 | 0 | 0 | 12457 | 0 | 0 | 0 | 0 | 0 | 0 | -12457 | 0 | 0 | 12457 | 12457 | 0 | 0 | 0 | 98.66 | 0 | 98.66 | 98.66 | 98.66 | 0 | 98.66 | 98.66 | HR | 20 | 0 | 20 | 20 | EA | 0 | 0 | 0 | 12399.63
Y | IPCRP1-0522-0000-L | IPCRP1 | IPCRP1 | 0522-0000 | 6 in VERT OR ROLLED WM OFSHET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0522-0000-R | IPCRP1 | IPCRP1 | 0522-0000 | 6 in VERT OR ROLLED WM OFSHET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31200 | 0 | 0 | 31200 | 0 | 31200 | 0 | 0 | N | 31200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0523-0000-L | IPCRP1 | IPCRP1 | 0523-0000 | 8 in VERT OR ROLLED WM OFSHET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0523-0000-R | IPCRP1 | IPCRP1 | 0523-0000 | 8 in VERT OR ROLLED WM OFSHET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 23400 | 0 | 0 | 23400 | 0 | 23400 | 0 | 0 | N | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | IPCRP1-0523-1000-L | IPCRP1 | IPCRP1 | 0523-1000 | 6, 8, 12 IN Vert or Rolled Offset | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 9 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0523-1000-S | IPCRP1 | IPCRP1 | 0523-1000 | 6, 8, 12 IN Vert or Rolled Offset | N | S |  | NR | A | 78390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52260 | Y | 52260 | Y | 26130 | 0 | 0 | 78390 | 0 | 0 | 52260 | Y | 26130 | 0 | 0 | 78390 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -52260 | 0 | 0 | 52260 | 0 | 0 | 0 | 0 | 0 | 0 | -52260 | 0 | 0 | 52260 | 52260 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 9 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 52260
Y | IPCRP1-0524-0000-L | IPCRP1 | IPCRP1 | 0524-0000 | UTIL CROSS TRENCH, SEWER, +12 in -24 in Diame (T1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0524-0000-R | IPCRP1 | IPCRP1 | 0524-0000 | UTIL CROSS TRENCH, SEWER, +12 in -24 in Diame (T1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10500 | 0 | 0 | 10500 | 0 | 10500 | 0 | 0 | N | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0525-0000-L | IPCRP1 | IPCRP1 | 0525-0000 | UTIL CROSS TRENCH, SEWER, +12 in -24 in Diame (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0525-0000-R | IPCRP1 | IPCRP1 | 0525-0000 | UTIL CROSS TRENCH, SEWER, +12 in -24 in Diame (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9600 | 0 | 0 | 9600 | 0 | 9600 | 0 | 0 | N | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0526-0000-L | IPCRP1 | IPCRP1 | 0526-0000 | UTIL CROSS TRENCH, SEWER, +12 in -24 in Diame (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0526-0000-R | IPCRP1 | IPCRP1 | 0526-0000 | UTIL CROSS TRENCH, SEWER, +12 in -24 in Diame (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57200 | 0 | 0 | 57200 | 0 | 57200 | 0 | 0 | N | 57200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0526-1000-E | IPCRP1 | IPCRP1 | 0526-1000 | Util Cross Trench, Sewer, +12 in -24 in(All types) | N | E |  | NR | P | 8292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 8292 | 0 | 0 | 8292 | 0 | 0 | 0 | Y | 8292 | 0 | 0 | 8292 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0526-1000-L | IPCRP1 | IPCRP1 | 0526-1000 | Util Cross Trench, Sewer, +12 in -24 in(All types) | N | L |  | NR | P | 31746 | 6012.14 | 6012.14 | 6012.14 | 6012.14 | 18.9383 | 0 | 0 | 0 | 25733.86 | N | 31746 | N | 0 | 0 | 0 | 31746 | 0 | 0 | 31746 | N | 0 | 0 | 0 | 31746 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31746 | 0 | 0 | 31746 | 0 | 0 | 0 | 0 | 0 | 0 | -31746 | 0 | 0 | 31746 | 31746 | 0 | 0 | 0 | 260 | 0 | 260 | 260 | 260 | 47 | 213 | 260 | HR | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 25733.86
Y | IPCRP1-0527-0000-L | IPCRP1 | IPCRP1 | 0527-0000 | 12 in VERT OR ROLLED WM OFSHET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0527-0000-R | IPCRP1 | IPCRP1 | 0527-0000 | 12 in VERT OR ROLLED WM OFSHET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 47400 | 0 | 0 | 47400 | 0 | 47400 | 0 | 0 | N | 47400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0528-0000-L | IPCRP1 | IPCRP1 | 0528-0000 | UTIL CROSS TRENCH, SEWER, +12 in -36 in Diame (T1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0528-0000-R | IPCRP1 | IPCRP1 | 0528-0000 | UTIL CROSS TRENCH, SEWER, +12 in -36 in Diame (T1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3500 | 0 | 0 | 3500 | 0 | 3500 | 0 | 0 | N | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0529-0000-L | IPCRP1 | IPCRP1 | 0529-0000 | UTIL CROSS TRENCH, SEWER, +12 in -36 in Diame (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0529-0000-R | IPCRP1 | IPCRP1 | 0529-0000 | UTIL CROSS TRENCH, SEWER, +12 in -36 in Diame (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 14400 | 0 | 0 | 14400 | 0 | 14400 | 0 | 0 | N | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0530-0000-L | IPCRP1 | IPCRP1 | 0530-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0530-0000-R | IPCRP1 | IPCRP1 | 0530-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3500 | 0 | 0 | 3500 | 0 | 3500 | 0 | 0 | N | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0531-0000-L | IPCRP1 | IPCRP1 | 0531-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0531-0000-R | IPCRP1 | IPCRP1 | 0531-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0532-0000-L | IPCRP1 | IPCRP1 | 0532-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0532-0000-R | IPCRP1 | IPCRP1 | 0532-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57000 | 0 | 0 | 57000 | 0 | 57000 | 5700 | 0 | N | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0533-0000-L | IPCRP1 | IPCRP1 | 0533-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0533-0000-R | IPCRP1 | IPCRP1 | 0533-0000 | UTIL CROSS TRENCH, SEWER, +36-48 D (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57600 | 0 | 0 | 57600 | 0 | 57600 | 0 | 0 | N | 57600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0534-0000-L | IPCRP1 | IPCRP1 | 0534-0000 | UTIL CROSS TRENCH, SEWER, +54-60 D (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0534-0000-R | IPCRP1 | IPCRP1 | 0534-0000 | UTIL CROSS TRENCH, SEWER, +54-60 D (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7150 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | N | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0535-0000-L | IPCRP1 | IPCRP1 | 0535-0000 | UTIL CROSS TRENCH, SEWER, +54-60 D (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0535-0000-R | IPCRP1 | IPCRP1 | 0535-0000 | UTIL CROSS TRENCH, SEWER, +54-60 D (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19200 | 0 | 0 | 19200 | 0 | 19200 | 0 | 0 | N | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0536-0000-L | IPCRP1 | IPCRP1 | 0536-0000 | UTIL CROSS TRENCH, SEWER, +60-72 D (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0536-0000-R | IPCRP1 | IPCRP1 | 0536-0000 | UTIL CROSS TRENCH, SEWER, +60-72 D (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7150 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | N | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0537-0000-L | IPCRP1 | IPCRP1 | 0537-0000 | UTIL CROSS TRENCH, SEWER, +60-72 D (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0537-0000-R | IPCRP1 | IPCRP1 | 0537-0000 | UTIL CROSS TRENCH, SEWER, +60-72 D (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19200 | 0 | 0 | 19200 | 0 | 19200 | 0 | 0 | N | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0537-1000-E | IPCRP1 | IPCRP1 | 0537-1000 | Util Cross Trnch, Sewr, >24 in - 72 in (All types) | N | E |  | NR | P | 21469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 21469 | 0 | 0 | 21469 | 0 | 0 | 0 | Y | 21469 | 0 | 0 | 21469 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 30 | 1 | 25 | 26 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0537-1000-L | IPCRP1 | IPCRP1 | 0537-1000 | Util Cross Trnch, Sewr, >24 in - 72 in (All types) | N | L |  | NR | P | 82192 | 3529.69 | 3529.69 | 3529.69 | 3529.69 | 4.9551 | 0 | 0 | 0 | 67703.31 | Y | 71233 | Y | 10959 | 0 | 0 | 82192 | 0 | 0 | 71233 | Y | 10959 | 0 | 0 | 82192 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -71233 | 0 | 0 | 71233 | 0 | 0 | 0 | 0 | 0 | 0 | -71233 | 0 | 0 | 71233 | 71233 | 0 | 0 | 0 | 673.16 | 0 | 581.13 | 581.13 | 673.16 | 27 | 554.13 | 581.13 | HR | 30 | 1 | 25 | 26 | EA | 0 | 0 | 0 | 67703.31
Y | IPCRP1-0537-1000-S | IPCRP1 | IPCRP1 | 0537-1000 | Util Cross Trnch, Sewr, >24 in - 72 in (All types) | N | S |  | UNIT | A | 0 | 227.64 | 227.64 | 227.64 | 227.64 | 100 | 0 | 0 | 0 | 0 | N | 227.64 | N | -227.64 | 0 | 0 | 0 | 0 | 0 | 227.64 | N | -227.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -227.64 | 0 | 0 | 227.64 | 0 | 0 | 0 | 0 | 0 | 0 | -227.64 | 0 | 0 | 227.64 | 227.64 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 30 | 1 | 25 | 26 | EA | 227.64 | 0 | 227.64 | 0
Y | IPCRP1-0538-0000-L | IPCRP1 | IPCRP1 | 0538-0000 | UTIL CROSS TRENCH, WM, UP TO 12 D (T1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0538-0000-R | IPCRP1 | IPCRP1 | 0538-0000 | UTIL CROSS TRENCH, WM, UP TO 12 D (T1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8190 | 0 | 0 | 8190 | 0 | 8190 | 8190 | 0 | N | 8190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0539-0000-L | IPCRP1 | IPCRP1 | 0539-0000 | UTIL CROSS TRENCH, WM, UP TO 12 D (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0539-0000-R | IPCRP1 | IPCRP1 | 0539-0000 | UTIL CROSS TRENCH, WM, UP TO 12 D (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12400 | 0 | 0 | 12400 | 0 | 12400 | 1550 | 0 | N | 12400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0540-0000-L | IPCRP1 | IPCRP1 | 0540-0000 | UTIL CROSS TRENCH, WM, UP TO 12 D (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0540-0000-R | IPCRP1 | IPCRP1 | 0540-0000 | UTIL CROSS TRENCH, WM, UP TO 12 D (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 32500 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | N | 32500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0540-1000-E | IPCRP1 | IPCRP1 | 0540-1000 | Util Cross Trench, WM, Up to 12in (All types) | N | E |  | NR | P | 4319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4319 | 0 | 0 | 4319 | 0 | 0 | 0 | Y | 4319 | 0 | 0 | 4319 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 28 | 10 | 12 | 22 | EA | 0 | 0 | 0 | 0 | As per NM (8/26) BS still has to invoice CE for 1 more. Capped out quantity paid by DDC (7ea - JB108.1). TTD Quantity as of 6/17/24 = 8ea, w/ balance paid by CE.
Y | IPCRP1-0540-1000-L | IPCRP1 | IPCRP1 | 0540-1000 | Util Cross Trench, WM, Up to 12in (All types) | N | L |  | NR | P | 26950 | 2630.9 | 2630.9 | 2630.9 | 2630.9 | 12.4246 | 0 | 0 | 0 | 18544.1 | Y | 21175 | Y | 5775 | 0 | 0 | 26950 | 0 | 0 | 21175 | Y | 5775 | 0 | 0 | 26950 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21175 | 0 | 0 | 21175 | 0 | 0 | 0 | 0 | 0 | 0 | -21175 | 0 | 0 | 21175 | 21175 | 0 | 0 | 0 | 218.3 | 0 | 169.25 | 169.25 | 218.3 | 19.5 | 149.75 | 169.25 | HR | 28 | 10 | 12 | 22 | EA | 0 | 0 | 0 | 18544.1
Y | IPCRP1-0540-1000-S | IPCRP1 | IPCRP1 | 0540-1000 | Util Cross Trench, WM, Up to 12in (All types) | N | S |  | UNIT | A | 0 | 348.44 | 348.44 | 348.44 | 348.44 | 100 | 0 | 0 | 0 | 0 | N | 348.44 | N | -348.44 | 0 | 0 | 0 | 0 | 0 | 348.44 | N | -348.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -348.44 | 0 | 0 | 348.44 | 0 | 0 | 0 | 0 | 0 | 0 | -348.44 | 0 | 0 | 348.44 | 348.44 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 0 | 3 | NA | 28 | 10 | 12 | 22 | EA | 348.44 | 0 | 348.44 | 0
Y | IPCRP1-0541-0000-L | IPCRP1 | IPCRP1 | 0541-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0541-0000-R | IPCRP1 | IPCRP1 | 0541-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0542-0000-L | IPCRP1 | IPCRP1 | 0542-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0542-0000-R | IPCRP1 | IPCRP1 | 0542-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 480000 | 0 | 0 | 480000 | 0 | 480000 | 0 | 0 | N | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0543-0000-L | IPCRP1 | IPCRP1 | 0543-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0543-0000-R | IPCRP1 | IPCRP1 | 0543-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0544-0000-L | IPCRP1 | IPCRP1 | 0544-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T4) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0544-0000-R | IPCRP1 | IPCRP1 | 0544-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T4) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0545-0000-L | IPCRP1 | IPCRP1 | 0545-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T5) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0545-0000-R | IPCRP1 | IPCRP1 | 0545-0000 | UTIL CROSS SHT PILES, FLOOD WALL/GATE (T5) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0546-0000-L | IPCRP1 | IPCRP1 | 0546-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0546-0000-R | IPCRP1 | IPCRP1 | 0546-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 520000 | 0 | 0 | 520000 | 0 | 520000 | 0 | 0 | N | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0547-0000-L | IPCRP1 | IPCRP1 | 0547-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0547-0000-R | IPCRP1 | IPCRP1 | 0547-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 320000 | 0 | 0 | 320000 | 0 | 320000 | 0 | 0 | N | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0548-0000-L | IPCRP1 | IPCRP1 | 0548-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0548-0000-R | IPCRP1 | IPCRP1 | 0548-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0549-0000-L | IPCRP1 | IPCRP1 | 0549-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0549-0000-R | IPCRP1 | IPCRP1 | 0549-0000 | UTIL CROSS ST PIPE PILES, FLOOD WALL/GATE (T3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0549-1000-E | IPCRP1 | IPCRP1 | 0549-1000 | Util Cross Sheet Pile/Flood Gate (All types) | N | E |  | NR | P | 223714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 223714 | 0 | 0 | 223714 | 0 | 0 | 0 | Y | 223714 | 0 | 0 | 223714 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 43 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0549-1000-L | IPCRP1 | IPCRP1 | 0549-1000 | Util Cross Sheet Pile/Flood Gate (All types) | N | L |  | NR | P | 743788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 743788 | 0 | 0 | 743788 | 0 | 0 | 0 | N | 743788 | 0 | 0 | 743788 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6548 | 0 | 0 | 0 | 6548 | 0 | 0 | 0 | HR | 43 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0549-1000-M | IPCRP1 | IPCRP1 | 0549-1000 | Util Cross Sheet Pile/Flood Gate (All types) | N | M |  | NR | P | 322500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 322490 | 0 | 0 | 322500 | 0 | 0 | 10 | Y | 322490 | 0 | 0 | 322500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 43 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 10
Y | IPCRP1-0550-0000-L | IPCRP1 | IPCRP1 | 0550-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0550-0000-R | IPCRP1 | IPCRP1 | 0550-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 40000 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0551-0000-L | IPCRP1 | IPCRP1 | 0551-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0551-0000-R | IPCRP1 | IPCRP1 | 0551-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0552-0000-L | IPCRP1 | IPCRP1 | 0552-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0552-0000-R | IPCRP1 | IPCRP1 | 0552-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T3 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0553-0000-L | IPCRP1 | IPCRP1 | 0553-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T4 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0553-0000-R | IPCRP1 | IPCRP1 | 0553-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T4 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0554-0000-L | IPCRP1 | IPCRP1 | 0554-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T5 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0554-0000-R | IPCRP1 | IPCRP1 | 0554-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON SHT PILES (T5 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0555-0000-L | IPCRP1 | IPCRP1 | 0555-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0555-0000-R | IPCRP1 | IPCRP1 | 0555-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0556-0000-L | IPCRP1 | IPCRP1 | 0556-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0556-0000-R | IPCRP1 | IPCRP1 | 0556-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0557-0000-L | IPCRP1 | IPCRP1 | 0557-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0557-0000-R | IPCRP1 | IPCRP1 | 0557-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0558-0000-L | IPCRP1 | IPCRP1 | 0558-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0558-0000-R | IPCRP1 | IPCRP1 | 0558-0000 | UTIL CROSS THRU FLOOD WALL/GATES ON ST PIPE PILES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0558-1000-E | IPCRP1 | IPCRP1 | 0558-1000 | Util Cross Thru Flood Wall/Gates on Sht Piles (Al | N | E |  | NR | P | 57232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 57232 | 0 | 0 | 57232 | 0 | 0 | 0 | Y | 57232 | 0 | 0 | 57232 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 11 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0558-1000-L | IPCRP1 | IPCRP1 | 0558-1000 | Util Cross Thru Flood Wall/Gates on Sht Piles (Al | N | L |  | NR | P | 190280 | 1356.16 | 1356.16 | 1356.16 | 1356.16 | 100 | 0 | 0 | 0 | 0 | N | 1356.16 | N | 188923.84 | 0 | 0 | 190280 | 0 | 0 | 1356.16 | N | 188923.84 | 0 | 0 | 190280 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1356.16 | 0 | 0 | 1356.16 | 0 | 0 | 0 | 0 | 0 | 0 | -1356.16 | 0 | 0 | 1356.16 | 1356.16 | 0 | 0 | 0 | 1675 | 0 | 0 | 0 | 1675 | 9.5 | -9.5 | 0 | HR | 11 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0558-1000-M | IPCRP1 | IPCRP1 | 0558-1000 | Util Cross Thru Flood Wall/Gates on Sht Piles (Al | N | M |  | NR | P | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 82500 | 0 | 0 | 82500 | 0 | 0 | 0 | Y | 82500 | 0 | 0 | 82500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 11 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0559-0000-L | IPCRP1 | IPCRP1 | 0559-0000 | INCREM COST MGP CONTAM/HAND/DISPOSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0559-0000-R | IPCRP1 | IPCRP1 | 0559-0000 | INCREM COST MGP CONTAM/HAND/DISPOSE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 163500 | 0 | 0 | 163500 | 0 | 163500 | 0 | 0 | N | 163500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0559-1000-C | IPCRP1 | IPCRP1 | 0559-1000 | INCREM COST MGP CONTAM/HAND/DISPOSE | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4927.14 | N | 4927.14 | N | -4927.14 | 0 | 0 | 0 | 0 | 0 | 4927.14 | N | -4927.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4927.14 | -4525.5 | 0 | 4927.14 | 0 | 0 | 0 | -4927.14 | 0 | 0 | -4927.14 | 0 | 0 | 4927.14 | 4927.14 | 0 | 0 | 0 | 0 | 0 | 4093.5 | 4093.5 | 0 | 4093.5 | 0 | 4093.5 | NA | 1090 | 1794.9 | 0 | 1794.9 | CY | 0 | 0 | 0 | 4927.14
Y | IPCRP1-0559-1000-E | IPCRP1 | IPCRP1 | 0559-1000 | INCREM COST MGP CONTAM/HAND/DISPOSE | N | E |  | NR | P | 15309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 15309 | 0 | 0 | 15309 | 0 | 0 | 0 | Y | 15309 | 0 | 0 | 15309 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1090 | 1794.9 | 0 | 1794.9 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0559-1000-L | IPCRP1 | IPCRP1 | 0559-1000 | INCREM COST MGP CONTAM/HAND/DISPOSE | N | L |  | NR | P | 58608.62 | 53398.21 | 53398.21 | 53398.21 | 53398.21 | 91.1098 | 0 | 0 | 0 | 5210.41 | Y | 58608.62 | Y | 0 | 0 | 0 | 58608.62 | 0 | 0 | 58608.62 | Y | 0 | 0 | 0 | 58608.62 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -58608.62 | 326.51 | 0 | 58608.62 | 0 | 0 | 0 | 0 | 0 | 0 | -58608.62 | 0 | 0 | 58608.62 | 58608.62 | 0 | 0 | 0 | 480 | 0 | 511.98 | 511.98 | 480 | 378.5 | 133.48 | 511.98 | HR | 1090 | 1794.9 | 0 | 1794.9 | CY | 0 | 0 | 0 | 5210.41
Y | IPCRP1-0559-1010-L | IPCRP1 | IPCRP1 | 0559-1010 | Truck & Dispose $200/ton - $300/cy | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1090 | 0 | 1090 | 1090 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0559-1010-S | IPCRP1 | IPCRP1 | 0559-1010 | Truck & Dispose $200/ton - $300/cy | N | S |  | NR | A | 327000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327000 | N | 327000 | N | 0 | 0 | 0 | 327000 | 0 | 0 | 327000 | N | 0 | 0 | 0 | 327000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -327000 | 0 | 0 | 327000 | 0 | 0 | 0 | 0 | 0 | 0 | -327000 | 0 | 0 | 327000 | 327000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1090 | 0 | 1090 | 1090 | CY | 0 | 0 | 0 | 327000
Y | IPCRP1-0560-0000-L | IPCRP1 | IPCRP1 | 0560-0000 | INST COMP CARB FIBER SYST ENCAP UG TRANS FEED/RET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0560-0000-R | IPCRP1 | IPCRP1 | 0560-0000 | INST COMP CARB FIBER SYST ENCAP UG TRANS FEED/RET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 48000000 | 0 | 0 | 48000000 | 0 | 48000000 | 48000000 | 0 | N | 48000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0560-1000-C | IPCRP1 | IPCRP1 | 0560-1000 | Carbon Fiber Excavation & Support | N | C |  | NR | P | 80000 | 41010.16 | 41010.16 | 41010.16 | 41010.16 | 100 | 0 | 0 | 0 | 0 | Y | 41010.16 | Y | 38989.84 | 0 | 0 | 80000 | 0 | 0 | 41010.16 | Y | 38989.84 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -41010.16 | 0 | 0 | 41010.16 | 0 | 0 | 0 | 0 | 0 | 0 | -41010.16 | 0 | 0 | 41010.16 | 41010.16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 538 | 0 | 538 | NA | 250 | 183 | 0 | 183 | DY | 19117.27 | -16280.44 | 35397.71 | 0
Y | IPCRP1-0560-1000-E | IPCRP1 | IPCRP1 | 0560-1000 | Carbon Fiber Excavation & Support | N | E |  | NR | P | 365391 | 0 | -1457.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 365391 | 0 | 0 | 365391 | 0 | 0 | 0 | Y | 365391 | 0 | 0 | 365391 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 145 | 0 | 145 | NA | 250 | 183 | 0 | 183 | DY | -1457.64 | -1457.64 | 0 | 0 | This note will be deleted when NASSAU SLING PO will be removed from category E to C.
Y | IPCRP1-0560-1000-L | IPCRP1 | IPCRP1 | 0560-1000 | Carbon Fiber Excavation & Support | N | L |  | NR | P | 1786721 | 30029.05 | 30029.05 | 30029.05 | 30029.05 | 100 | 0 | 0 | 0 | 0 | Y | 30029.05 | Y | 1756691.95 | 0 | 0 | 1786721 | 0 | 0 | 30029.05 | Y | 1756691.95 | 0 | 0 | 1786721 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30029.05 | 0 | 0 | 30029.05 | 0 | 0 | 0 | 0 | 0 | 0 | -30029.05 | 0 | 0 | 30029.05 | 30029.05 | 0 | 0 | 0 | 16600 | 0 | 263.5 | 263.5 | 16600 | 263.5 | 0 | 263.5 | HR | 250 | 183 | 0 | 183 | DY | 0 | 0 | 0 | 0 | PMF reduced to 3750 MH and $450K total cost for labor, $80K for Consumable ($530K total) on May'22 forecast.
Y | IPCRP1-0560-1010-L | IPCRP1 | IPCRP1 | 0560-1010 | Carbon Fiber Wrap Sub (CTI) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2000 | 2000 | 0 | 2000 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0560-1010-S | IPCRP1 | IPCRP1 | 0560-1010 | Carbon Fiber Wrap Sub (CTI) | N | S |  | NR | A | 38368425 | 28657196.26 | 28657196.26 | 28657196.26 | 28657196.26 | 100 | 0 | 0 | 0 | 0 | Y | 28657196.26 | Y | 9711228.74 | 0 | 0 | 38368425 | 0 | 0 | 28657196.26 | Y | 9711228.74 | 0 | 0 | 38368425 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28657196.26 | 0 | 0 | 28657196.26 | 0 | 0 | 0 | 0 | 0 | 0 | -28657196.26 | 0 | 0 | 28657196.26 | 28657196.26 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4700 | -1448.44 | 3251.56 | NA | 2000 | 2000 | 0 | 2000 | LF | 28657196.26 | 0 | 28657196.26 | 0 | Composite Technology & Infrastructure, (CTI) (Carbon Fiber Wrap) $ 295M + CO @$17,830.98 under JB 900 CE (seq#0663), Pinnacle Environmental @$170,948.80 Pinnacle CO Additional ACM scope requested by ConEd (T&M) to be paid under JB item
Y | IPCRP1-0561-0000-L | IPCRP1 | IPCRP1 | 0561-0000 | EXTRA DEPTH EXCAV OF CB CHUTE CONN PIPES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0561-0000-R | IPCRP1 | IPCRP1 | 0561-0000 | EXTRA DEPTH EXCAV OF CB CHUTE CONN PIPES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16500 | 0 | 0 | 16500 | 0 | 16500 | 0 | 0 | N | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0561-1000-E | IPCRP1 | IPCRP1 | 0561-1000 | Extra Depth Excav of CB Chute Conn Pipes | N | E |  | NR | P | 1481.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1481.69 | 0 | 0 | 1481.69 | 0 | 0 | 0 | Y | 1481.69 | 0 | 0 | 1481.69 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 110 | 0 | 110 | 110 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0561-1000-L | IPCRP1 | IPCRP1 | 0561-1000 | Extra Depth Excav of CB Chute Conn Pipes | N | L |  | NR | P | 8080.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8080.48 | N | 8080.48 | N | 0 | 0 | 0 | 8080.48 | 0 | 0 | 8080.48 | N | 0 | 0 | 0 | 8080.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8080.48 | 0 | 0 | 8080.48 | 0 | 0 | 0 | 0 | 0 | 0 | -8080.48 | 0 | 0 | 8080.48 | 8080.48 | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 64 | 0 | 64 | 64 | HR | 110 | 0 | 110 | 110 | LF | 0 | 0 | 0 | 8080.48
Y | IPCRP1-0562-0000-L | IPCRP1 | IPCRP1 | 0562-0000 | INST & REM OF CB W/ UTIL INTERFERENCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0562-0000-R | IPCRP1 | IPCRP1 | 0562-0000 | INST & REM OF CB W/ UTIL INTERFERENCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 28400 | 0 | 0 | 28400 | 0 | 28400 | 0 | 0 | N | 28400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0562-1000-E | IPCRP1 | IPCRP1 | 0562-1000 | Inst & Rem of CB w/Util Interference | N | E |  | NR | P | 2963.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2963.38 | 0 | 0 | 2963.38 | 0 | 0 | 0 | Y | 2963.38 | 0 | 0 | 2963.38 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 4 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0562-1000-L | IPCRP1 | IPCRP1 | 0562-1000 | Inst & Rem of CB w/Util Interference | N | L |  | NR | P | 16160.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8080.47 | Y | 8080.47 | Y | 8080.47 | 0 | 0 | 16160.94 | 0 | 0 | 8080.47 | Y | 8080.47 | 0 | 0 | 16160.94 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8080.47 | 0 | 0 | 8080.47 | 0 | 0 | 0 | 0 | 0 | 0 | -8080.47 | 0 | 0 | 8080.47 | 8080.47 | 0 | 0 | 0 | 128 | 0 | 64 | 64 | 128 | 0 | 64 | 64 | HR | 4 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 8080.47
Y | IPCRP1-0563-0000-L | IPCRP1 | IPCRP1 | 0563-0000 | INST OF CB W/ UTIL INTERFERENCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0563-0000-R | IPCRP1 | IPCRP1 | 0563-0000 | INST OF CB W/ UTIL INTERFERENCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 14100 | 0 | 0 | 14100 | 0 | 14100 | 0 | 0 | N | 14100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0563-1000-E | IPCRP1 | IPCRP1 | 0563-1000 | Inst of CB w/Util Interference | N | E |  | NR | P | 1481.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1481.69 | 0 | 0 | 1481.69 | 0 | 0 | 0 | Y | 1481.69 | 0 | 0 | 1481.69 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3 | 0 | 3 | 3 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0563-1000-L | IPCRP1 | IPCRP1 | 0563-1000 | Inst of CB w/Util Interference | N | L |  | NR | P | 8080.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8080.48 | N | 8080.48 | N | 0 | 0 | 0 | 8080.48 | 0 | 0 | 8080.48 | N | 0 | 0 | 0 | 8080.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8080.48 | 0 | 0 | 8080.48 | 0 | 0 | 0 | 0 | 0 | 0 | -8080.48 | 0 | 0 | 8080.48 | 8080.48 | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 64 | 0 | 64 | 64 | HR | 3 | 0 | 3 | 3 | EA | 0 | 0 | 0 | 8080.48
Y | IPCRP1-0564-0000-L | IPCRP1 | IPCRP1 | 0564-0000 | SPECIAL CARE EXCAV & BACKFILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0564-0000-R | IPCRP1 | IPCRP1 | 0564-0000 | SPECIAL CARE EXCAV & BACKFILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 187600 | 0 | 0 | 187600 | 0 | 187600 | 7764.4 | 0 | N | 187600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0564-1000-E | IPCRP1 | IPCRP1 | 0564-1000 | SPECIAL CARE EXCAV & BACKFILL | N | E |  | NR | P | 15824.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 15824.5 | 0 | 0 | 15824.5 | 0 | 0 | 0 | Y | 15824.5 | 0 | 0 | 15824.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 670 | 27.74 | 321.12 | 348.86 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0564-1000-L | IPCRP1 | IPCRP1 | 0564-1000 | SPECIAL CARE EXCAV & BACKFILL | N | L |  | NR | P | 98748.99 | 2869.6 | 2869.6 | 2869.6 | 2869.6 | 5.581 | 0 | 0 | 0 | 48547.4 | Y | 51417 | Y | 47331.99 | 0 | 0 | 98748.99 | 0 | 0 | 51417 | Y | 47331.99 | 0 | 0 | 98748.99 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -51417 | 0 | 0 | 51417 | 0 | 0 | 0 | 0 | 0 | 0 | -51417 | 0 | 0 | 51417 | 51417 | 0 | 0 | 0 | 800 | 0 | 415.81 | 415.81 | 800 | 23 | 392.81 | 415.81 | HR | 670 | 27.74 | 321.12 | 348.86 | CY | 0 | 0 | 0 | 48547.4
Y | IPCRP1-0564-1000-S | IPCRP1 | IPCRP1 | 0564-1000 | SPECIAL CARE EXCAV & BACKFILL | N | S |  | UNIT | A | 0 | 231.8 | 231.8 | 231.8 | 231.8 | 100 | 0 | 0 | 0 | 0 | N | 231.8 | N | -231.8 | 0 | 0 | 0 | 0 | 0 | 231.8 | N | -231.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -231.8 | 0 | 0 | 231.8 | 0 | 0 | 0 | 0 | 0 | 0 | -231.8 | 0 | 0 | 231.8 | 231.8 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 670 | 27.74 | 321.12 | 348.86 | CY | 231.8 | 0 | 231.8 | 0
Y | IPCRP1-0565-0000-L | IPCRP1 | IPCRP1 | 0565-0000 | SPECIAL CARE EXCAV & BACKFILL, OIL O-STATIC PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0565-0000-R | IPCRP1 | IPCRP1 | 0565-0000 | SPECIAL CARE EXCAV & BACKFILL, OIL O-STATIC PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1538310 | 0 | 0 | 1538310 | 0 | 1538310 | 45876.7 | 0 | N | 1538310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1538310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0565-1000-E | IPCRP1 | IPCRP1 | 0565-1000 | SPECIAL CARE EXCAV & BACKFILL, OIL O-STATIC PIPE | N | E |  | NR | P | 122472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 122472 | 0 | 0 | 122472 | 0 | 0 | 0 | Y | 122472 | 0 | 0 | 122472 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3273 | 97.61 | 515.82 | 613.43 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0565-1000-L | IPCRP1 | IPCRP1 | 0565-1000 | SPECIAL CARE EXCAV & BACKFILL, OIL O-STATIC PIPE | N | L |  | NR | P | 468859.01 | 5816.94 | 5816.94 | 5816.94 | 5816.94 | 7.1845 | 0 | 0 | 0 | 75148.21 | Y | 80965.15 | Y | 387893.86 | 0 | 0 | 468859.01 | 0 | 0 | 80965.15 | Y | 387893.86 | 0 | 0 | 468859.01 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -80965.15 | 0 | 0 | 80965.15 | 0 | 0 | 0 | 0 | 0 | 0 | -80965.15 | 0 | 0 | 80965.15 | 80965.15 | 0 | 0 | 0 | 3840 | 0 | 613.43 | 613.43 | 3840 | 45 | 568.43 | 613.43 | HR | 3273 | 97.61 | 515.82 | 613.43 | CY | 0 | 0 | 0 | 75148.21 | CE transferred 1M in funding to JB900 (0663-1000) which equates to deduction of 2,127.66cy
N | IPCRP1-0565-1000-S | IPCRP1 | IPCRP1 | 0565-1000 | SPECIAL CARE EXCAV & BACKFILL, OIL O-STATIC PIPE | N | S |  | UNIT | A | 0 | 393.16 | 393.16 | 393.16 | 393.16 | 100 | 0 | 0 | 0 | 0 | N | 393.16 | N | -393.16 | 0 | 0 | 0 | 0 | 0 | 393.16 | N | -393.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -393.16 | 0 | 393.16 | 393.16 | 0 | 0 | 0 | 0 | 0 | 0 | -393.16 | 0 | 0 | 393.16 | 393.16 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | NA | 3273 | 97.61 | 515.82 | 613.43 | CY | 393.16 | 0 | 393.16 | 0
Y | IPCRP1-0566-0000-L | IPCRP1 | IPCRP1 | 0566-0000 | FIELD COAT OF OIL O-STATIC FEEDER PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0566-0000-R | IPCRP1 | IPCRP1 | 0566-0000 | FIELD COAT OF OIL O-STATIC FEEDER PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 412888 | 0 | 0 | 412888 | 0 | 412888 | 0 | 0 | N | 412888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0566-1000-L | IPCRP1 | IPCRP1 | 0566-1000 | Field Coat of Oil O-Static Feeder Pipe | N | L |  | NR | P | 314832.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 314832.63 | 0 | 0 | 314832.63 | 0 | 0 | 0 | Y | 314832.63 | 0 | 0 | 314832.63 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | HR | 7373 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | CE transferred $412,888.00 in funding to JB900 (0663-1000) for entire activity/bid item
Y | IPCRP1-0567-0000-L | IPCRP1 | IPCRP1 | 0567-0000 | F, D & I TYPE 3/8 CLEAN SAND BACKFILL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0567-0000-R | IPCRP1 | IPCRP1 | 0567-0000 | F, D & I TYPE 3/8 CLEAN SAND BACKFILL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1879920 | 0 | 0 | 1879920 | 0 | 1879920 | 1443688.8 | 0 | N | 1879920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0567-1000-E | IPCRP1 | IPCRP1 | 0567-1000 | F, D & I TYPE 3/8 CLEAN SAND BACKFILL | N | E |  | NR | P | 122472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 122472 | 0 | 0 | 122472 | 0 | 0 | 0 | N | 122472 | 0 | 0 | 122472 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 7833 | 6015.4 | 494.6 | 6510 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0567-1000-L | IPCRP1 | IPCRP1 | 0567-1000 | F, D & I TYPE 3/8 CLEAN SAND BACKFILL | N | L |  | NR | P | 468869.01 | 316712.2 | 316712.2 | 316712.2 | 316712.2 | 90.23 | 0 | 0 | 0 | 34293.23 | Y | 351005.43 | Y | 117863.58 | 0 | 0 | 468869.01 | 0 | 0 | 351005.43 | Y | 117863.58 | 0 | 0 | 468869.01 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -351005.43 | 0 | 0 | 351005.43 | 0 | 0 | 0 | 0 | 0 | 0 | -351005.43 | 0 | 0 | 351005.43 | 351005.43 | 0 | 0 | 0 | 3840 | 0 | 2750.22 | 2750.22 | 3840 | 2507.5 | 242.72 | 2750.22 | HR | 7833 | 6015.4 | 494.6 | 6510 | CY | 0 | 0 | 0 | 34293.23
Y | IPCRP1-0567-1000-S | IPCRP1 | IPCRP1 | 0567-1000 | F, D & I TYPE 3/8 CLEAN SAND BACKFILL | N | S |  | UNIT | A | 0 | 1836.42 | 1836.42 | 1836.42 | 1836.42 | 100 | 0 | 0 | 0 | 0 | Y | 1836.42 | Y | -1836.42 | 0 | 0 | 0 | 0 | 0 | 1836.42 | Y | -1836.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1836.42 | 0 | 0 | 1836.42 | 0 | 0 | 0 | 0 | 0 | 0 | -1836.42 | 0 | 0 | 1836.42 | 1836.42 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 15 | -13 | 2 | NA | 7833 | 6015.4 | 494.6 | 6510 | CY | 1836.42 | 0 | 1836.42 | 0
Y | IPCRP1-0568-0000-L | IPCRP1 | IPCRP1 | 0568-0000 | SUPP/PROT ELEC & GAS FACIL (T.1) DURING CITY TREN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0568-0000-R | IPCRP1 | IPCRP1 | 0568-0000 | SUPP/PROT ELEC & GAS FACIL (T.1) DURING CITY TREN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 64600 | 0 | 0 | 64600 | 0 | 64600 | 1768 | 0 | N | 64600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0569-0000-L | IPCRP1 | IPCRP1 | 0569-0000 | SUPP/PROT ELEC & GAS FACIL (T.2) DURING CITY TREN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0569-0000-R | IPCRP1 | IPCRP1 | 0569-0000 | SUPP/PROT ELEC & GAS FACIL (T.2) DURING CITY TREN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 289870 | 0 | 0 | 289870 | 0 | 289870 | 1640 | 0 | N | 289870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0570-0000-L | IPCRP1 | IPCRP1 | 0570-0000 | SUPP/PROT ELEC & GAS FACIL (T.3) DURING CITY TREN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0570-0000-R | IPCRP1 | IPCRP1 | 0570-0000 | SUPP/PROT ELEC & GAS FACIL (T.3) DURING CITY TREN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 187500 | 0 | 0 | 187500 | 0 | 187500 | 2500 | 0 | N | 187500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0571-0000-L | IPCRP1 | IPCRP1 | 0571-0000 | SUPP/PROT ELEC & GAS FACIL (T.4) DURING CITY TREN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0571-0000-R | IPCRP1 | IPCRP1 | 0571-0000 | SUPP/PROT ELEC & GAS FACIL (T.4) DURING CITY TREN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 23375 | 0 | 0 | 23375 | 0 | 23375 | 6171 | 0 | N | 23375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0571-1000-E | IPCRP1 | IPCRP1 | 0571-1000 | Supp/ Prot Elec & Gas Fac (T1 - T4) During City T | N | E |  | NR | P | 47854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 47854 | 0 | 0 | 47854 | 0 | 0 | 0 | Y | 47854 | 0 | 0 | 47854 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 6110 | 130 | 4150.73 | 4280.73 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0571-1000-L | IPCRP1 | IPCRP1 | 0571-1000 | Supp/ Prot Elec & Gas Fac (T1 - T4) During City T | N | L |  | NR | P | 298623 | 19224.13 | 19224.13 | 19224.13 | 19224.13 | 9.1885 | 0 | 0 | 0 | 189994.27 | Y | 209218.4 | Y | 89404.6 | 0 | 0 | 298623 | 0 | 0 | 209218.4 | Y | 89404.6 | 0 | 0 | 298623 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -209218.4 | 0 | 0 | 209218.4 | 0 | 0 | 0 | 0 | 0 | 0 | -209218.4 | 0 | 0 | 209218.4 | 209218.4 | 0 | 0 | 0 | 2419.3 | 0 | 1682.8 | 1682.8 | 2419.3 | 143.5 | 1539.3 | 1682.8 | HR | 6110 | 130 | 4150.73 | 4280.73 | LF | 0 | 0 | 0 | 189994.27
Y | IPCRP1-0571-1000-S | IPCRP1 | IPCRP1 | 0571-1000 | Supp/ Prot Elec & Gas Fac (T1 - T4) During City T | N | S |  | UNIT | A | 0 | 1956.36 | 1956.36 | 1956.36 | 1956.36 | 100 | 0 | 0 | 0 | 0 | N | 1956.36 | N | -1956.36 | 0 | 0 | 0 | 0 | 0 | 1956.36 | N | -1956.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1956.36 | 0 | 0 | 1956.36 | 0 | 0 | 0 | 0 | 0 | 0 | -1956.36 | 0 | 0 | 1956.36 | 1956.36 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 16 | 0 | 16 | NA | 6110 | 130 | 4150.73 | 4280.73 | LF | 1956.36 | 0 | 1956.36 | 0
Y | IPCRP1-0572-0000-L | IPCRP1 | IPCRP1 | 0572-0000 | TEST PITS FOR UTIL FACILITIES | N | L |  | UNIT | P | 0 | 30 | 30 | 30 | 30 | 100 | 0 | 0 | 0 | 0 | Y | 30 | Y | -30 | 0 | 0 | 0 | 0 | 0 | 30 | Y | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | Main office and CMiC are unable to move this after numerous attempts.
Y | IPCRP1-0572-0000-R | IPCRP1 | IPCRP1 | 0572-0000 | TEST PITS FOR UTIL FACILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 89100 | 0 | 0 | 89100 | 0 | 89100 | 89100 | 0 | N | 89100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0573-0000-L | IPCRP1 | IPCRP1 | 0573-0000 | TEST PITS FOR UTIL FACILITIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0573-0000-R | IPCRP1 | IPCRP1 | 0573-0000 | TEST PITS FOR UTIL FACILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3000 | 0 | 0 | 3000 | 0 | 3000 | 3000 | 0 | N | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0573-1000-E | IPCRP1 | IPCRP1 | 0573-1000 | TEST PITS FOR UTIL FACILITIES | N | E |  | NR | P | 8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 8063 | 0 | 0 | 8063 | 0 | 0 | 0 | N | 8063 | 0 | 0 | 8063 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 340 | 605.4 | 0 | 605.4 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0573-1000-L | IPCRP1 | IPCRP1 | 0573-1000 | TEST PITS FOR UTIL FACILITIES | N | L |  | NR | P | 48024 | 167744.99 | 167744.99 | 167744.99 | 167744.99 | 100 | 0 | 0 | 0 | -0.01 | Y | 167744.98 | Y | -119720.98 | 0 | 0 | 48024 | 0 | 0 | 167744.98 | Y | -119720.98 | 0 | 0 | 48024 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -167744.98 | 0 | 0 | 167744.98 | 0 | 0 | 0 | 0 | 0 | 0 | -167744.98 | 0 | 0 | 167744.98 | 167744.98 | 0 | 0 | 0 | 413.35 | 0 | 1448.5 | 1448.5 | 413.35 | 1448.5 | 0 | 1448.5 | HR | 340 | 605.4 | 0 | 605.4 | CY | 0 | 0 | 0 | -0.01 | Capped out quantity paid by DDC is 330 CY. Capped out quantity paid by DDC for 0572 CE (330cy) and 0573 ECS (10cy). TTD quantity as of 5/17/24 = 605.40cy, with balance (265.40cy) paid by CE. Capped out quantity paid by DDC is 330 CY. TTD quantity as of 1/10/24 is 579.97 CY, 10 cy paid from ECS. Capped out quantity paid by DDC for 0572 CE (330cy) and 0573 ECS (10cy). TTD quantity as of 5/17/24 = 605.40cy, with balance (265.40cy) paid by CE.
Y | IPCRP1-0573-1000-S | IPCRP1 | IPCRP1 | 0573-1000 | TEST PITS FOR UTIL FACILITIES | N | S |  | UNIT | A | 0 | 4375.73 | 4375.73 | 4375.73 | 4375.73 | 100 | 0 | 0 | 0 | 0 | Y | 4375.73 | Y | -4375.73 | 0 | 0 | 0 | 0 | 0 | 4375.73 | Y | -4375.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4375.73 | 0 | 0 | 4375.73 | 0 | 0 | 0 | 0 | 0 | 0 | -4375.73 | 0 | 0 | 4375.73 | 4375.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | -38 | 0 | NA | 340 | 605.4 | 0 | 605.4 | CY | 4375.73 | 0 | 4375.73 | 0
Y | IPCRP1-0574-0000-L | IPCRP1 | IPCRP1 | 0574-0000 | SURVEY/DRAFT TEST PITS FOR UTIL FACILITIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0574-0000-R | IPCRP1 | IPCRP1 | 0574-0000 | SURVEY/DRAFT TEST PITS FOR UTIL FACILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 172200 | 0 | 0 | 172200 | 0 | 172200 | 172200 | 0 | N | 172200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0574-1000-E | IPCRP1 | IPCRP1 | 0574-1000 | SURVEY/DRAFT TEST PITS FOR UTIL FACILITIES | N | E |  | NR | P | 10923.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 10923.64 | 0 | 0 | 10923.64 | 0 | 0 | 0 | Y | 10923.64 | 0 | 0 | 10923.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 420 | 574.08 | 185.92 | 760 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0574-1000-L | IPCRP1 | IPCRP1 | 0574-1000 | SURVEY/DRAFT TEST PITS FOR UTIL FACILITIES | N | L |  | NR | P | 65064.23 | 153657.31 | 153657.31 | 153657.31 | 153657.31 | 67.8703 | 0 | 0 | 0 | 72741.2 | Y | 226398.51 | Y | -161334.28 | 0 | 0 | 65064.23 | 0 | 0 | 226398.51 | Y | -161334.28 | 0 | 0 | 65064.23 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -226398.51 | 0 | 0 | 226398.51 | 0 | 0 | 0 | 0 | 0 | 0 | -226398.51 | 0 | 0 | 226398.51 | 226398.51 | 0 | 0 | 0 | 560 | 0 | 1900.43 | 1900.43 | 560 | 1318.5 | 581.93 | 1900.43 | HR | 420 | 574.08 | 185.92 | 760 | CY | 0 | 0 | 0 | 72741.2
Y | IPCRP1-0574-1000-S | IPCRP1 | IPCRP1 | 0574-1000 | SURVEY/DRAFT TEST PITS FOR UTIL FACILITIES | N | S |  | UNIT | A | 0 | 1793.42 | 1793.42 | 1793.42 | 1793.42 | 100 | 0 | 0 | 0 | 0 | Y | 1793.42 | Y | -1793.42 | 0 | 0 | 0 | 0 | 0 | 1793.42 | Y | -1793.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1793.42 | 0 | 0 | 1793.42 | 0 | 0 | 0 | 0 | 0 | 0 | -1793.42 | 0 | 0 | 1793.42 | 1793.42 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 15 | -10 | 5 | NA | 420 | 574.08 | 185.92 | 760 | CY | 1793.42 | 0 | 1793.42 | 0 | Capped out quantity paid by DDC is 420 CY. TTD quantity as of 8/31/25 is 574.08 CY w/ balance paid for by CE. Capped out quantity paid by DDC is 420 CY. TTD quantity as of 3/28/23 is 531.42 CY w/ balance paid for by CE. KMA CO posted in April '23.
Y | IPCRP1-0575-0000-L | IPCRP1 | IPCRP1 | 0575-0000 | TRENCH EX FOR ADJUST OF UTIL FACILITIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0575-0000-R | IPCRP1 | IPCRP1 | 0575-0000 | TRENCH EX FOR ADJUST OF UTIL FACILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 45269 | 0 | 0 | 45269 | 0 | 45269 | 0 | 0 | N | 45269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0576-0000-L | IPCRP1 | IPCRP1 | 0576-0000 | TRENCH EX FOR ADJUST OF UTIL FACILITIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0576-0000-R | IPCRP1 | IPCRP1 | 0576-0000 | TRENCH EX FOR ADJUST OF UTIL FACILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3023040 | 0 | 0 | 3023040 | 0 | 3023040 | 100467.2 | 0 | N | 3023040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0577-0000-L | IPCRP1 | IPCRP1 | 0577-0000 | TRENCH EX FOR ADJUST OF UTIL FACILITIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0577-0000-R | IPCRP1 | IPCRP1 | 0577-0000 | TRENCH EX FOR ADJUST OF UTIL FACILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15410 | 0 | 0 | 15410 | 0 | 15410 | 15002.9 | 0 | N | 15410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0577-1000-E | IPCRP1 | IPCRP1 | 0577-1000 | Trench Ex for Adjust of Utility Facilities (All T | N | E |  | NR | P | 138462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 138462 | 0 | 0 | 138462 | 0 | 0 | 0 | Y | 138462 | 0 | 0 | 138462 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 9670 | 408.19 | 1359.81 | 1768 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0577-1000-L | IPCRP1 | IPCRP1 | 0577-1000 | Trench Ex for Adjust of Utility Facilities (All T | N | L |  | NR | P | 778521 | 76218.46 | 76218.46 | 76218.46 | 76218.46 | 53.5468 | 0 | 0 | 0 | 66121.54 | Y | 142340 | Y | 636181 | 0 | 0 | 778521 | 0 | 0 | 142340 | Y | 636181 | 0 | 0 | 778521 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -142340 | 2515.43 | 0 | 142340 | 0 | 0 | 0 | 0 | 0 | 0 | -142340 | 0 | 0 | 142340 | 142340 | 0 | 0 | 0 | 6724 | 0 | 1159.12 | 1159.12 | 6724 | 586.5 | 572.62 | 1159.12 | HR | 9670 | 408.19 | 1359.81 | 1768 | CY | 0 | 0 | 0 | 66121.54 | CE transferred 1.5M in funding to JB900 (0663-1000) which equates to deduction of 4,687.50cy
N | IPCRP1-0577-1000-S | IPCRP1 | IPCRP1 | 0577-1000 | Trench Ex for Adjust of Utility Facilities (All T | N | S |  | UNIT | A | 0 | 516.54 | 516.54 | 516.54 | 516.54 | 100 | 0 | 0 | 0 | 0 | N | 516.54 | N | -516.54 | 0 | 0 | 0 | 0 | 0 | 516.54 | N | -516.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -516.54 | 516.54 | 0 | 516.54 | 0 | 0 | 0 | 0 | 516.54 | 0 | -516.54 | 0 | 0 | 516.54 | 516.54 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | NA | 9670 | 408.19 | 1359.81 | 1768 | CY | 516.54 | 0 | 516.54 | 0
Y | IPCRP1-0578-0000-L | IPCRP1 | IPCRP1 | 0578-0000 | EXIST CONC ENC COND IN FINAL POS W/O CONC ENC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0578-0000-R | IPCRP1 | IPCRP1 | 0578-0000 | EXIST CONC ENC COND IN FINAL POS W/O CONC ENC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 72000 | 0 | 0 | 72000 | 0 | 72000 | 0 | 0 | N | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0578-1000-E | IPCRP1 | IPCRP1 | 0578-1000 | EXIST CONC ENC COND IN FINAL POS W/O CONC ENC | N | E |  | NR | P | 6242.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6242.08 | 0 | 0 | 6242.08 | 0 | 0 | 0 | Y | 6242.08 | 0 | 0 | 6242.08 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 800 | 0 | 400 | 400 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0578-1000-L | IPCRP1 | IPCRP1 | 0578-1000 | EXIST CONC ENC COND IN FINAL POS W/O CONC ENC | N | L |  | NR | P | 37179.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18589.78 | Y | 18589.78 | Y | 18589.78 | 0 | 0 | 37179.56 | 0 | 0 | 18589.78 | Y | 18589.78 | 0 | 0 | 37179.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18589.78 | 0 | 0 | 18589.78 | 0 | 0 | 0 | 0 | 0 | 0 | -18589.78 | 0 | 0 | 18589.78 | 18589.78 | 0 | 0 | 0 | 320 | 0 | 160 | 160 | 320 | 0 | 160 | 160 | HR | 800 | 0 | 400 | 400 | LF | 0 | 0 | 0 | 18589.78
Y | IPCRP1-0579-0000-L | IPCRP1 | IPCRP1 | 0579-0000 | EXIST CONC ENC COND IN FINAL POS W/ CONC ENC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0579-0000-R | IPCRP1 | IPCRP1 | 0579-0000 | EXIST CONC ENC COND IN FINAL POS W/ CONC ENC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 147200 | 0 | 0 | 147200 | 0 | 147200 | 0 | 0 | N | 147200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0579-1000-E | IPCRP1 | IPCRP1 | 0579-1000 | EXIST CONC ENC COND IN FINAL POS W/ CONC ENC | N | E |  | NR | P | 12484.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 12484.16 | 0 | 0 | 12484.16 | 0 | 0 | 0 | Y | 12484.16 | 0 | 0 | 12484.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1600 | 0 | 800 | 800 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0579-1000-L | IPCRP1 | IPCRP1 | 0579-1000 | EXIST CONC ENC COND IN FINAL POS W/ CONC ENC | N | L |  | NR | P | 74359.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37342.6 | Y | 37342.6 | Y | 37016.51 | 0 | 0 | 74359.11 | 0 | 0 | 37342.6 | Y | 37016.51 | 0 | 0 | 74359.11 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37342.6 | 0 | 0 | 37342.6 | 0 | 0 | 0 | 0 | 0 | 0 | -37342.6 | 0 | 0 | 37342.6 | 37342.6 | 0 | 0 | 0 | 640 | 0 | 319.99 | 319.99 | 640 | 0 | 319.99 | 319.99 | HR | 1600 | 0 | 800 | 800 | LF | 0 | 0 | 0 | 37342.6
Y | IPCRP1-0580-0000-L | IPCRP1 | IPCRP1 | 0580-0000 | EXIST NON-CONC ENC COND IN FINAL POS W/OUT CONC E | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0580-0000-R | IPCRP1 | IPCRP1 | 0580-0000 | EXIST NON-CONC ENC COND IN FINAL POS W/OUT CONC E | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 97760 | 0 | 0 | 97760 | 0 | 97760 | 97760 | 0 | N | 97760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0580-1000-E | IPCRP1 | IPCRP1 | 0580-1000 | EXIST NON-CONC ENC COND IN FINAL POS W/OUT CONC E | N | E |  | NR | P | 8582.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 8582.86 | 0 | 0 | 8582.86 | 0 | 0 | 0 | N | 8582.86 | 0 | 0 | 8582.86 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1880 | 4286 | 0 | 4286 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0580-1000-L | IPCRP1 | IPCRP1 | 0580-1000 | EXIST NON-CONC ENC COND IN FINAL POS W/OUT CONC E | N | L |  | NR | P | 51121.89 | 5664.61 | 5664.61 | 5664.61 | 5664.61 | 100 | 0 | 0 | 0 | 0 | Y | 5664.61 | Y | 45457.28 | 0 | 0 | 51121.89 | 0 | 0 | 5664.61 | Y | 45457.28 | 0 | 0 | 51121.89 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5664.61 | 0 | 0 | 5664.61 | 0 | 0 | 0 | 0 | 0 | 0 | -5664.61 | 0 | 0 | 5664.61 | 5664.61 | 0 | 0 | 0 | 440 | 0 | 40 | 40 | 440 | 40 | 0 | 40 | HR | 1880 | 4286 | 0 | 4286 | LF | 0 | 0 | 0 | 0 | Capped out quantity paid by DDC = 1,880 LF. QTD thru (8/31/25) = 4,286, with balance paid directly by CE. Capped out quantity piad by DDC at 1,880 LF. Balance of Quantity to Date as of Nov 2023 is 3,290 LF.
Y | IPCRP1-0581-0000-L | IPCRP1 | IPCRP1 | 0581-0000 | EXIST NON-CONC ENC COND IN FINAL POS W/ CONC ENC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0581-0000-R | IPCRP1 | IPCRP1 | 0581-0000 | EXIST NON-CONC ENC COND IN FINAL POS W/ CONC ENC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 551640 | 0 | 0 | 551640 | 0 | 551640 | 0 | 0 | N | 551640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0581-1000-E | IPCRP1 | IPCRP1 | 0581-1000 | Exist Non-Conc Enc Conc in Final Pos w/ Conc Enc | N | E |  | NR | P | 46815.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 46815.6 | 0 | 0 | 46815.6 | 0 | 0 | 0 | Y | 46815.6 | 0 | 0 | 46815.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 9194 | 0 | 2527.33 | 2527.33 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0581-1000-L | IPCRP1 | IPCRP1 | 0581-1000 | Exist Non-Conc Enc Conc in Final Pos w/ Conc Enc | N | L |  | NR | P | 278846.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76651.9 | Y | 76651.9 | Y | 202194.79 | 0 | 0 | 278846.69 | 0 | 0 | 76651.9 | Y | 202194.79 | 0 | 0 | 278846.69 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -76651.9 | 0 | 0 | 76651.9 | 0 | 0 | 0 | 0 | 0 | 0 | -76651.9 | 0 | 0 | 76651.9 | 76651.9 | 0 | 0 | 0 | 2400 | 0 | 659.99 | 659.99 | 2400 | 0 | 659.99 | 659.99 | HR | 9194 | 0 | 2527.33 | 2527.33 | LF | 0 | 0 | 0 | 76651.9
Y | IPCRP1-0582-0000-L | IPCRP1 | IPCRP1 | 0582-0000 | EXIST TRANS FACIL, UP TO 6 in D, ADJ 0-6in ANY DIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0582-0000-R | IPCRP1 | IPCRP1 | 0582-0000 | EXIST TRANS FACIL, UP TO 6 in D, ADJ 0-6in ANY DIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 665395 | 0 | 0 | 665395 | 0 | 665395 | 665395 | 0 | N | 665395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0582-1000-E | IPCRP1 | IPCRP1 | 0582-1000 | Exist Transmis Facil, up to 6 D, Adj 0-6in Any D | N | E |  | NR | P | 54618.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 54618.2 | 0 | 0 | 54618.2 | 0 | 0 | 0 | N | 54618.2 | 0 | 0 | 54618.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 9115 | 10108 | 1061 | 11169 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0582-1000-L | IPCRP1 | IPCRP1 | 0582-1000 | Exist Transmis Facil, up to 6 D, Adj 0-6in Any D | N | L |  | NR | P | 457105.04 | 3481.97 | 3481.97 | 3481.97 | 3481.97 | 4 | 0 | 0 | 0 | 83568 | Y | 87049.97 | Y | 370055.07 | 0 | 0 | 457105.04 | 0 | 0 | 87049.97 | Y | 370055.07 | 0 | 0 | 457105.04 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -87049.97 | 0 | 0 | 87049.97 | 0 | 0 | 0 | 0 | 0 | 0 | -87049.97 | 0 | 0 | 87049.97 | 87049.97 | 0 | 0 | 0 | 4060 | 0 | 500 | 500 | 4060 | 20 | 480 | 500 | HR | 9115 | 10108 | 1061 | 11169 | LF | 0 | 0 | 0 | 83568 | Capped out quantity paid by DDC is 9,115 LF. TTD quantity as of 4/19/23 is 10,108 LF w/ balance paid for by CE.
Y | IPCRP1-0583-0000-L | IPCRP1 | IPCRP1 | 0583-0000 | EXIST TRANS FACIL, 6-12 D, ADJ 0-6in ANY DIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0583-0000-R | IPCRP1 | IPCRP1 | 0583-0000 | EXIST TRANS FACIL, 6-12 D, ADJ 0-6in ANY DIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 681440 | 0 | 0 | 681440 | 0 | 681440 | 35680 | 0 | N | 681440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 681440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0583-1000-E | IPCRP1 | IPCRP1 | 0583-1000 | Exist Transmis Facil, 6-12 D, Adj 0-6in Any Dir | N | E |  | NR | P | 55298.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 55298.46 | 0 | 0 | 55298.46 | 0 | 0 | 0 | Y | 55298.46 | 0 | 0 | 55298.46 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8518 | 446 | 2161 | 2607 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0583-1000-L | IPCRP1 | IPCRP1 | 0583-1000 | Exist Transmis Facil, 6-12 D, Adj 0-6in Any Dir | N | L |  | NR | P | 463735.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141930 | Y | 141930 | Y | 321805.12 | 0 | 0 | 463735.12 | 0 | 0 | 141930 | Y | 321805.12 | 0 | 0 | 463735.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -141930 | 0 | 0 | 141930 | 0 | 0 | 0 | 0 | 0 | 0 | -141930 | 0 | 0 | 141930 | 141930 | 0 | 0 | 0 | 4118 | 0 | 1260.04 | 1260.04 | 4118 | 0 | 1260.04 | 1260.04 | HR | 8518 | 446 | 2161 | 2607 | LF | 0 | 0 | 0 | 141930 | CE transferred 300K in funding to JB900 (0663-1000) which equates to 3,750.00 LF
Y | IPCRP1-0584-0000-L | IPCRP1 | IPCRP1 | 0584-0000 | EXIST TRANS FACIL, UP TO 6in D, ADJ +6-9 ANY DIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0584-0000-R | IPCRP1 | IPCRP1 | 0584-0000 | EXIST TRANS FACIL, UP TO 6in D, ADJ +6-9 ANY DIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 736185 | 0 | 0 | 736185 | 0 | 736185 | 258400 | 0 | N | 736185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0584-1000-E | IPCRP1 | IPCRP1 | 0584-1000 | Exist Transmis Facil, up to 6in D, Adj +6- 9 Any | N | E |  | NR | P | 60080.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 60080.02 | 0 | 0 | 60080.02 | 0 | 0 | 0 | Y | 60080.02 | 0 | 0 | 60080.02 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8661 | 3040 | 1634.03 | 4674.03 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0584-1000-L | IPCRP1 | IPCRP1 | 0584-1000 | Exist Transmis Facil, up to 6in D, Adj +6- 9 Any | N | L |  | NR | P | 502815.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271351.46 | Y | 271351.46 | Y | 231464.09 | 0 | 0 | 502815.55 | 0 | 0 | 271351.46 | Y | 231464.09 | 0 | 0 | 502815.55 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -271351.46 | 0 | 0 | 271351.46 | 0 | 0 | 0 | 0 | 0 | 0 | -271351.46 | 0 | 0 | 271351.46 | 271351.46 | 0 | 0 | 0 | 4466 | 0 | 2410.08 | 2410.08 | 4466 | 0 | 2410.08 | 2410.08 | HR | 8661 | 3040 | 1634.03 | 4674.03 | LF | 0 | 0 | 0 | 271351.46 | CE transferred 200K in funding to JB900 (0663-1000) which equates to 2,352.94 LF
Y | IPCRP1-0585-0000-L | IPCRP1 | IPCRP1 | 0585-0000 | EXIST TRANS FACIL, 6-12in D, ADJ +6-9 ANY DIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0585-0000-R | IPCRP1 | IPCRP1 | 0585-0000 | EXIST TRANS FACIL, 6-12in D, ADJ +6-9 ANY DIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1249703 | 0 | 0 | 1249703 | 0 | 1249703 | 36946 | 0 | N | 1249703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0585-1000-E | IPCRP1 | IPCRP1 | 0585-1000 | Exist Transmis Facil, 6-12in D, Adj +6- 9 Any D | N | E |  | NR | P | 102214.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 102214.06 | 0 | 0 | 102214.06 | 0 | 0 | 0 | Y | 102214.06 | 0 | 0 | 102214.06 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 13733 | 406 | 2267.89 | 2673.89 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0585-1000-L | IPCRP1 | IPCRP1 | 0585-1000 | Exist Transmis Facil, 6-12in D, Adj +6- 9 Any D | N | L |  | NR | P | 855439.43 | 1984.94 | 1984.94 | 1984.94 | 1984.94 | 1.1917 | 0 | 0 | 0 | 164574.06 | Y | 166559 | Y | 688880.43 | 0 | 0 | 855439.43 | 0 | 0 | 166559 | Y | 688880.43 | 0 | 0 | 855439.43 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -166559 | 0 | 0 | 166559 | 0 | 0 | 0 | 0 | 0 | 0 | -166559 | 0 | 0 | 166559 | 166559 | 0 | 0 | 0 | 7598 | 0 | 1479.32 | 1479.32 | 7598 | 18 | 1461.32 | 1479.32 | HR | 13733 | 406 | 2267.89 | 2673.89 | LF | 0 | 0 | 0 | 164574.06 | CE transferred 800K in funding to JB900 (0663-1000) which equates to 8,791.21 LF
Y | IPCRP1-0586-0000-L | IPCRP1 | IPCRP1 | 0586-0000 | EXIST TRANS FACIL, UP TO 6in D, ADJ +9-12 ANY DI | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0586-0000-R | IPCRP1 | IPCRP1 | 0586-0000 | EXIST TRANS FACIL, UP TO 6in D, ADJ +9-12 ANY DI | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 482976 | 0 | 0 | 482976 | 0 | 482976 | 195072 | 0 | N | 482976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0586-1000-E | IPCRP1 | IPCRP1 | 0586-1000 | Exist Transmis Facil, up to 6in D, Adj +9-12 Any | N | E |  | NR | P | 30611.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 30611.7 | 0 | 0 | 30611.7 | 0 | 0 | 0 | Y | 30611.7 | 0 | 0 | 30611.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5031 | 2032 | 655.25 | 2687.25 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0586-1000-L | IPCRP1 | IPCRP1 | 0586-1000 | Exist Transmis Facil, up to 6in D, Adj +9-12 Any | N | L |  | NR | P | 342065.58 | 12952.98 | 12952.98 | 12952.98 | 12952.98 | 7.0894 | 0 | 0 | 0 | 169757.02 | Y | 182710 | Y | 159355.58 | 0 | 0 | 342065.58 | 0 | 0 | 182710 | Y | 159355.58 | 0 | 0 | 342065.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -182710 | 0 | 0 | 182710 | 0 | 0 | 0 | 0 | 0 | 0 | -182710 | 0 | 0 | 182710 | 182710 | 0 | 0 | 0 | 2970 | 0 | 1585.59 | 1585.59 | 2970 | 112 | 1473.59 | 1585.59 | HR | 5031 | 2032 | 655.25 | 2687.25 | LF | 0 | 0 | 0 | 169757.02 | CE transferred 100K in funding to JB900 (0663-1000) which equates to 1,041.67 LF
Y | IPCRP1-0587-0000-L | IPCRP1 | IPCRP1 | 0587-0000 | EXIST TRANS FACIL, 6-12in D, ADJ +9-12 ANY DIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0587-0000-R | IPCRP1 | IPCRP1 | 0587-0000 | EXIST TRANS FACIL, 6-12in D, ADJ +9-12 ANY DIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 897851 | 0 | 0 | 897851 | 0 | 897851 | 15141 | 0 | N | 897851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0587-1000-E | IPCRP1 | IPCRP1 | 0587-1000 | Exist Transmis Facil, 6-12in D, Adj +9- 12 Any | N | E |  | NR | P | 64761.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 64761.58 | 0 | 0 | 64761.58 | 0 | 0 | 0 | Y | 64761.58 | 0 | 0 | 64761.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8717 | 147 | 1171.94 | 1318.94 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0587-1000-L | IPCRP1 | IPCRP1 | 0587-1000 | Exist Transmis Facil, 6-12in D, Adj +9- 12 Any | N | L |  | NR | P | 622620.95 | 258.35 | 258.35 | 258.35 | 258.35 | 0.27424 | 0 | 0 | 0 | 93948.65 | Y | 94207 | Y | 528413.95 | 0 | 0 | 622620.95 | 0 | 0 | 94207 | Y | 528413.95 | 0 | 0 | 622620.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -94207 | 0 | 0 | 94207 | 0 | 0 | 0 | 0 | 0 | 0 | -94207 | 0 | 0 | 94207 | 94207 | 0 | 0 | 0 | 5478 | 0 | 828.72 | 828.72 | 5478 | 2 | 826.72 | 828.72 | HR | 8717 | 147 | 1171.94 | 1318.94 | LF | 0 | 0 | 0 | 93948.65 | CE transferred 500K in funding to JB900 (0663-1000) which equates to 4,854.37 LF
Y | IPCRP1-0588-0000-L | IPCRP1 | IPCRP1 | 0588-0000 | EXIST CONC ENC TELECOM COND IN FINAL POS W/ CONC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0588-0000-R | IPCRP1 | IPCRP1 | 0588-0000 | EXIST CONC ENC TELECOM COND IN FINAL POS W/ CONC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10340 | 0 | 0 | 10340 | 0 | 10340 | 0 | 0 | N | 10340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0589-0000-L | IPCRP1 | IPCRP1 | 0589-0000 | EXIST CONC ENC TELECOM COND IN FINAL POS W/ CONC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0589-0000-R | IPCRP1 | IPCRP1 | 0589-0000 | EXIST CONC ENC TELECOM COND IN FINAL POS W/ CONC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5120 | 0 | 0 | 5120 | 0 | 5120 | 0 | 0 | N | 5120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0590-0000-L | IPCRP1 | IPCRP1 | 0590-0000 | EXIST NON-CONC ENC TELECOM COND IN FINAL POS W/ C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0590-0000-R | IPCRP1 | IPCRP1 | 0590-0000 | EXIST NON-CONC ENC TELECOM COND IN FINAL POS W/ C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2960 | 0 | 0 | 2960 | 0 | 2960 | 2960 | 0 | N | 2960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0591-0000-L | IPCRP1 | IPCRP1 | 0591-0000 | EXIST NON-CONC ENC ST/IRON COND IN FINAL POS W/ C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0591-0000-R | IPCRP1 | IPCRP1 | 0591-0000 | EXIST NON-CONC ENC ST/IRON COND IN FINAL POS W/ C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4800 | 0 | 0 | 4800 | 0 | 4800 | 0 | 0 | N | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0592-0000-L | IPCRP1 | IPCRP1 | 0592-0000 | EXIST VAC CONC ENC TELECOM COND IN F.P. W/ CONC E | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0592-0000-R | IPCRP1 | IPCRP1 | 0592-0000 | EXIST VAC CONC ENC TELECOM COND IN F.P. W/ CONC E | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4200 | 0 | 0 | 4200 | 0 | 4200 | 4200 | 0 | N | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0593-0000-L | IPCRP1 | IPCRP1 | 0593-0000 | EXIST VAC NON-CONC ENC COND IN F.P. W/ CONC ENC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0593-0000-R | IPCRP1 | IPCRP1 | 0593-0000 | EXIST VAC NON-CONC ENC COND IN F.P. W/ CONC ENC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4120 | 0 | 0 | 4120 | 0 | 4120 | 0 | 0 | N | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0593-1000-E | IPCRP1 | IPCRP1 | 0593-1000 | Exist Cond Placed in Final Position w/ Conc Encas | N | E |  | NR | P | 2536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2536 | 0 | 0 | 2536 | 0 | 0 | 0 | Y | 2536 | 0 | 0 | 2536 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 460 | 397 | 63 | 460 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0593-1000-L | IPCRP1 | IPCRP1 | 0593-1000 | Exist Cond Placed in Final Position w/ Conc Encas | N | L |  | NR | P | 15104 | 12400.54 | 12400.54 | 12400.54 | 12400.54 | 82.101 | 0 | 0 | 0 | 2703.46 | N | 15104 | N | 0 | 0 | 0 | 15104 | 0 | 0 | 15104 | N | 0 | 0 | 0 | 15104 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15104 | 583.58 | 0 | 15104 | 0 | 0 | 0 | 0 | 0 | 0 | -15104 | 0 | 0 | 15104 | 15104 | 0 | 0 | 0 | 130 | 0 | 130 | 130 | 130 | 100 | 30 | 130 | HR | 460 | 397 | 63 | 460 | LF | 0 | 0 | 0 | 2703.46 | This activity combines 1ea Cablevision + 5ea ECS items. We have overrun 2ea ECS items (seq #590 & #593).
Y | IPCRP1-0593-1000-M | IPCRP1 | IPCRP1 | 0593-1000 | Exist Cond Placed in Final Position w/ Conc Encas | N | M |  | UNIT | U | 0 | 435.5 | 435.5 | 435.5 | 435.5 | 100 | 0 | 0 | 0 | 0 | N | 435.5 | N | -435.5 | 0 | 0 | 0 | 0 | 0 | 435.5 | N | -435.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -435.5 | 0 | 0 | 435.5 | 0 | 0 | 0 | 0 | 0 | 0 | -435.5 | 0 | 0 | 435.5 | 435.5 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 17 | 0 | 17 | NA | 460 | 397 | 63 | 460 | LF | 435.5 | 0 | 435.5 | 0
Y | IPCRP1-0594-0000-L | IPCRP1 | IPCRP1 | 0594-0000 | PLACE ST PROT PLATES FOR UTILITY FACILITIES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0594-0000-R | IPCRP1 | IPCRP1 | 0594-0000 | PLACE ST PROT PLATES FOR UTILITY FACILITIES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10400 | 0 | 0 | 10400 | 0 | 10400 | 182.34 | 0 | N | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0594-1000-L | IPCRP1 | IPCRP1 | 0594-1000 | PLACE ST PROT PLATES FOR UTILITY FACILITIES | N | L |  | NR | P | 8230.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8230.42 | N | 8230.42 | N | 0 | 0 | 0 | 8230.42 | 0 | 0 | 8230.42 | N | 0 | 0 | 0 | 8230.42 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8230.42 | 0 | 0 | 8230.42 | 0 | 0 | 0 | 0 | 0 | 0 | -8230.42 | 0 | 0 | 8230.42 | 8230.42 | 0 | 0 | 0 | 80 | 0 | 80 | 80 | 80 | 0 | 80 | 80 | HR | 4000 | 70.13 | 3929.87 | 4000 | SF | 0 | 0 | 0 | 8230.42 | CTD (Quantity)is 70.13 (March 2024)
Y | IPCRP1-0595-0000-L | IPCRP1 | IPCRP1 | 0595-0000 | PIER & PLATE METH, PROT DI WM & OTHER SHALLOW FAC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0595-0000-R | IPCRP1 | IPCRP1 | 0595-0000 | PIER & PLATE METH, PROT DI WM & OTHER SHALLOW FAC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42000 | 0 | 0 | 42000 | 0 | 42000 | 0 | 0 | N | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0595-1000-E | IPCRP1 | IPCRP1 | 0595-1000 | PIER & PLATE METH, PROT DI WM & OTHER SHALLOW FAC | N | E |  | NR | P | 3121.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3121.04 | 0 | 0 | 3121.04 | 0 | 0 | 0 | Y | 3121.04 | 0 | 0 | 3121.04 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0595-1000-L | IPCRP1 | IPCRP1 | 0595-1000 | PIER & PLATE METH, PROT DI WM & OTHER SHALLOW FAC | N | L |  | NR | P | 18589.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18589.79 | N | 18589.79 | N | 0 | 0 | 0 | 18589.79 | 0 | 0 | 18589.79 | N | 0 | 0 | 0 | 18589.79 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18589.79 | 0 | 0 | 18589.79 | 0 | 0 | 0 | 0 | 0 | 0 | -18589.79 | 0 | 0 | 18589.79 | 18589.79 | 0 | 0 | 0 | 160 | 0 | 160 | 160 | 160 | 0 | 160 | 160 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 18589.79
Y | IPCRP1-0595-1010-L | IPCRP1 | IPCRP1 | 0595-1010 | PM - Plate & Beams for Shallow Protection | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5780 | 0 | 5780 | 5780 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0595-1010-M | IPCRP1 | IPCRP1 | 0595-1010 | PM - Plate & Beams for Shallow Protection | N | M |  | NR | P | 4489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4489 | N | 4489 | N | 0 | 0 | 0 | 4489 | 0 | 0 | 4489 | N | 0 | 0 | 0 | 4489 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4489 | 0 | 0 | 4489 | 0 | 0 | 0 | 0 | 0 | 0 | -4489 | 0 | 0 | 4489 | 4489 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5780 | 0 | 5780 | 5780 | LB | 0 | 0 | 0 | 4489
Y | IPCRP1-0596-0000-L | IPCRP1 | IPCRP1 | 0596-0000 | PERM SUP ALLOW OF CRIT UTIL FACIL, SIGNIF SETTLEM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0596-0000-R | IPCRP1 | IPCRP1 | 0596-0000 | PERM SUP ALLOW OF CRIT UTIL FACIL, SIGNIF SETTLEM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 500000 | 0 | 0 | 500000 | 0 | 500000 | 0 | 0 | N | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0596-1000-C | IPCRP1 | IPCRP1 | 0596-1000 | Perm Support Allow of Crit Util Facility, Settlem | N | C |  | NR | P | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | N | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0596-1000-L | IPCRP1 | IPCRP1 | 0596-1000 | Perm Support Allow of Crit Util Facility, Settlem | N | L |  | UNIT | P | 0 | 45.07 | 45.07 | 45.07 | 45.07 | 100 | 0 | 0 | 0 | 0 | N | 45.07 | N | -45.07 | 0 | 0 | 0 | 0 | 0 | 45.07 | N | -45.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45.07 | 0 | 0 | 45.07 | 0 | 0 | 0 | 0 | 0 | 0 | -45.07 | 0 | 0 | 45.07 | 45.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0 | CE transferred $500,000.00 in funding to JB900 (0663-1000) for entire activity/bid item
Y | IPCRP1-0596-1000-S | IPCRP1 | IPCRP1 | 0596-1000 | Perm Support Allow of Crit Util Facility, Settlem | N | S |  | UNIT | A | 0 | 446.35 | 446.35 | 446.35 | 446.35 | 100 | 0 | 0 | 0 | 0 | N | 446.35 | N | -446.35 | 0 | 0 | 0 | 0 | 0 | 446.35 | N | -446.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -446.35 | 0 | 0 | 446.35 | 0 | 0 | 0 | 0 | 0 | 0 | -446.35 | 0 | 0 | 446.35 | 446.35 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 1 | 0 | 0 | 0 | FP | 446.35 | 0 | 446.35 | 0
Y | IPCRP1-0597-0000-L | IPCRP1 | IPCRP1 | 0597-0000 | TRENCH EX, INSTALL UTIL FACIL W/ DEPTH <5ft | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0597-0000-R | IPCRP1 | IPCRP1 | 0597-0000 | TRENCH EX, INSTALL UTIL FACIL W/ DEPTH <5ft | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 362960 | 0 | 0 | 362960 | 0 | 362960 | 327818.4 | 0 | N | 362960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0597-1000-E | IPCRP1 | IPCRP1 | 0597-1000 | Trench Ex, Install Util Facil w/ Depth <5 Ft | N | E |  | NR | P | 20248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20248 | 0 | 0 | 20248 | 0 | 0 | 0 | Y | 20248 | 0 | 0 | 20248 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1396 | 1260.84 | 135.16 | 1396 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0597-1000-L | IPCRP1 | IPCRP1 | 0597-1000 | Trench Ex, Install Util Facil w/ Depth <5 Ft | N | L |  | NR | P | 80805 | 259328.35 | 259328.35 | 259328.35 | 259328.35 | 90.2412 | 0 | 0 | 0 | 28044.01 | Y | 287372.36 | Y | -206567.36 | 0 | 0 | 80805 | 0 | 0 | 287372.36 | Y | -206567.36 | 0 | 0 | 80805 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -287372.36 | 0 | 0 | 287372.36 | 0 | 0 | 0 | 0 | 0 | 0 | -287372.36 | 0 | 0 | 287372.36 | 287372.36 | 0 | 0 | 0 | 640 | 0 | 2332.07 | 2332.07 | 640 | 2104.5 | 227.57 | 2332.07 | HR | 1396 | 1260.84 | 135.16 | 1396 | CY | 0 | 0 | 0 | 28044.01 | As / NM (6/16/25) accept DDC QTD = 1,260.82 thru Mar 2025
Y | IPCRP1-0597-1000-S | IPCRP1 | IPCRP1 | 0597-1000 | Trench Ex, Install Util Facil w/ Depth <5 Ft | N | S |  | UNIT | A | 0 | 12150.08 | 12150.08 | 12150.08 | 12150.08 | 100 | 0 | 0 | 0 | 0 | Y | 12150.08 | Y | -12150.08 | 0 | 0 | 0 | 0 | 0 | 12150.08 | Y | -12150.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12150.08 | 0 | 0 | 12150.08 | 0 | 0 | 0 | 0 | 0 | 0 | -12150.08 | 0 | 0 | 12150.08 | 12150.08 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 0 | 98.5 | -94 | 4.5 | NA | 1396 | 1260.84 | 135.16 | 1396 | CY | 12150.08 | 0 | 12150.08 | 0
Y | IPCRP1-0597-1010-L | IPCRP1 | IPCRP1 | 0597-1010 | Aggregate Fill (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1396 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0597-1010-M | IPCRP1 | IPCRP1 | 0597-1010 | Aggregate Fill (CLOSED) | N | M |  | NR | P | 17450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 17450 | 0 | 0 | 17450 | 0 | 0 | 0 | N | 17450 | 0 | 0 | 17450 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1396 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0598-0000-L | IPCRP1 | IPCRP1 | 0598-0000 | TRENCH EX, INSTALL UTIL FACIL W/ DEPTH >5ft, REQD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0598-0000-R | IPCRP1 | IPCRP1 | 0598-0000 | TRENCH EX, INSTALL UTIL FACIL W/ DEPTH >5ft, REQD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 399000 | 0 | 0 | 399000 | 0 | 399000 | 122986.6 | 0 | N | 399000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0598-1000-E | IPCRP1 | IPCRP1 | 0598-1000 | Trench Ex, Install Util Facil w/ Depth >5ft | N | E |  | NR | P | 20546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20546 | 0 | 0 | 20546 | 0 | 0 | 0 | Y | 20546 | 0 | 0 | 20546 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1050 | 322.07 | 727.93 | 1050 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0598-1000-L | IPCRP1 | IPCRP1 | 0598-1000 | Trench Ex, Install Util Facil w/ Depth >5ft | N | L |  | NR | P | 111916 | 44627.32 | 44627.32 | 44627.32 | 44627.32 | 39.8757 | 0 | 0 | 0 | 67288.68 | N | 111916 | N | 0 | 0 | 0 | 111916 | 0 | 0 | 111916 | N | 0 | 0 | 0 | 111916 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -111916 | 0 | 0 | 111916 | 0 | 0 | 0 | 0 | 0 | 0 | -111916 | 0 | 0 | 111916 | 111916 | 0 | 0 | 0 | 912 | 0 | 912 | 912 | 912 | 376.5 | 535.5 | 912 | HR | 1050 | 322.07 | 727.93 | 1050 | CY | 0 | 0 | 0 | 67288.68 | As / NM (6/16/25) accept DDC QTD = 322.072 thru Mar 2025
Y | IPCRP1-0599-0000-L | IPCRP1 | IPCRP1 | 0599-0000 | TRENCH EX, CARBON FIBER WRAP EXIST UTIL FACILITIE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0599-0000-R | IPCRP1 | IPCRP1 | 0599-0000 | TRENCH EX, CARBON FIBER WRAP EXIST UTIL FACILITIE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3276722.6 | 0 | 0 | 4293640 | 0 | 3276722.6 | 3276722.6 | 0 | N | 3276722.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3276722.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0599-1000-E | IPCRP1 | IPCRP1 | 0599-1000 | TRENCH EX, CARBON FIBER WRAP EXIST UTIL FACILITIE | N | E |  | NR | P | 120450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 120450 | 0 | 0 | 120450 | 0 | 0 | 0 | N | 120450 | 0 | 0 | 120450 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8320 | -8320 | 0 | NA | 9334 | 7123.31 | 0 | 7123.31 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0599-1000-L | IPCRP1 | IPCRP1 | 0599-1000 | TRENCH EX, CARBON FIBER WRAP EXIST UTIL FACILITIE | N | L |  | NR | P | 1325155 | 707116.32 | 707116.32 | 707116.32 | 707116.32 | 100 | 0 | 0 | 0 | 0 | Y | 707116.32 | Y | 618038.68 | 0 | 0 | 1325155 | 0 | 0 | 707116.32 | Y | 618038.68 | 0 | 0 | 1325155 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -707116.32 | 0 | 0 | 707116.32 | 0 | 0 | 0 | 0 | 0 | 0 | -707116.32 | 0 | 0 | 707116.32 | 707116.32 | 0 | 0 | 0 | 9680 | 0 | 5841.5 | 5841.5 | 9680 | 5841.5 | 0 | 5841.5 | HR | 9334 | 7123.31 | 0 | 7123.31 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0599-1010-C | IPCRP1 | IPCRP1 | 0599-1010 | CM - Slings | N | C |  | NR | P | 80000 | 8019.17 | 8019.17 | 8019.17 | 8019.17 | 100 | 0 | 0 | 0 | 0 | Y | 8019.17 | Y | 71980.83 | 0 | 0 | 80000 | 0 | 0 | 8019.17 | Y | 71980.83 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8019.17 | 0 | 0 | 8019.17 | 0 | 0 | 0 | 0 | 0 | 0 | -8019.17 | 0 | 0 | 8019.17 | 8019.17 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 401 | -401 | 0 | NA | 1600 | 160 | 0 | 160 | EA | 8019.17 | 0 | 8019.17 | 0
Y | IPCRP1-0599-1010-L | IPCRP1 | IPCRP1 | 0599-1010 | CM - Slings | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1600 | 160 | 0 | 160 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0600-0000-L | IPCRP1 | IPCRP1 | 0600-0000 | EXCAV FOR UTIL STRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0600-0000-R | IPCRP1 | IPCRP1 | 0600-0000 | EXCAV FOR UTIL STRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 285390 | 0 | 0 | 285390 | 0 | 285390 | 99445.5 | 0 | N | 285390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0600-1000-E | IPCRP1 | IPCRP1 | 0600-1000 | Excavate for Util Structure | N | E |  | NR | P | 14684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 14684 | 0 | 0 | 14684 | 0 | 0 | 0 | Y | 14684 | 0 | 0 | 14684 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 906 | 315.7 | 352.2 | 667.9 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0600-1000-L | IPCRP1 | IPCRP1 | 0600-1000 | Excavate for Util Structure | N | L |  | NR | P | 89697 | 77754.29 | 77754.29 | 77754.29 | 77754.29 | 47.2961 | 0 | 0 | 0 | 86644.71 | Y | 164399 | Y | -74702 | 0 | 0 | 89697 | 0 | 0 | 164399 | Y | -74702 | 0 | 0 | 89697 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -164399 | 0 | 0 | 164399 | 0 | 0 | 0 | 0 | 0 | 0 | -164399 | 0 | 0 | 164399 | 164399 | 0 | 0 | 0 | 728 | 0 | 1449.16 | 1449.16 | 728 | 685.5 | 763.66 | 1449.16 | HR | 906 | 315.7 | 352.2 | 667.9 | CY | 0 | 0 | 0 | 86644.71
Y | IPCRP1-0600-1000-S | IPCRP1 | IPCRP1 | 0600-1000 | Excavate for Util Structure | N | S |  | UNIT | A | 0 | 761.61 | 761.61 | 761.58 | 761.61 | 99.9961 | 0 | 0 | 0 | 0 | Y | 761.61 | Y | -761.61 | 0 | 0 | 0 | 0 | 0 | 761.61 | Y | -761.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -761.61 | 0 | 0 | 761.61 | 0 | 0 | 0 | 0 | 0 | 0 | -761.61 | 0 | 0 | 761.61 | 761.61 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 7 | -4 | 3 | NA | 906 | 315.7 | 352.2 | 667.9 | CY | 761.61 | 0.03 | 761.58 | 0
Y | IPCRP1-0601-0000-L | IPCRP1 | IPCRP1 | 0601-0000 | MASS TRENCH EX (T.1) FOR UTIL FACIL, UP TO 20% | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0601-0000-R | IPCRP1 | IPCRP1 | 0601-0000 | MASS TRENCH EX (T.1) FOR UTIL FACIL, UP TO 20% | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 324300 | 0 | 0 | 324300 | 0 | 324300 | 27213.6 | 0 | N | 324300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0601-1000-E | IPCRP1 | IPCRP1 | 0601-1000 | Mass Trench Ex (T.1) for Util Facility, Up to 20% | N | E |  | NR | P | 18222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 18222 | 0 | 0 | 18222 | 0 | 0 | 0 | Y | 18222 | 0 | 0 | 18222 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 940 | 78.88 | 0 | 78.88 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0601-1000-L | IPCRP1 | IPCRP1 | 0601-1000 | Mass Trench Ex (T.1) for Util Facility, Up to 20% | N | L |  | NR | P | 87357 | 6027.43 | 6027.43 | 6027.43 | 6027.43 | 100 | 0 | 0 | 0 | 0 | Y | 6027.43 | Y | 81329.57 | 0 | 0 | 87357 | 0 | 0 | 6027.43 | Y | 81329.57 | 0 | 0 | 87357 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6027.43 | 0 | 0 | 6027.43 | 0 | 0 | 0 | 0 | 0 | 0 | -6027.43 | 0 | 0 | 6027.43 | 6027.43 | 0 | 0 | 0 | 656 | 0 | 51.5 | 51.5 | 656 | 51.5 | 0 | 51.5 | HR | 940 | 78.88 | 0 | 78.88 | CY | 0 | 0 | 0 | 0 | CE transferred balance of funding to JB900 (0663-1000) which equates to deduction of 861.12cy
Y | IPCRP1-0602-0000-L | IPCRP1 | IPCRP1 | 0602-0000 | MASS TRENCH EX (T.2) FOR UTIL FACIL, >20% UP TO 4 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0602-0000-R | IPCRP1 | IPCRP1 | 0602-0000 | MASS TRENCH EX (T.2) FOR UTIL FACIL, >20% UP TO 4 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 593400 | 0 | 0 | 593400 | 0 | 593400 | 0 | 0 | N | 593400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0602-1000-E | IPCRP1 | IPCRP1 | 0602-1000 | Mass Trench Ex (T.2) for Util Facility, >20% up t | N | E |  | NR | P | 33834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 33834 | 0 | 0 | 33834 | 0 | 0 | 0 | Y | 33834 | 0 | 0 | 33834 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1720 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0602-1000-L | IPCRP1 | IPCRP1 | 0602-1000 | Mass Trench Ex (T.2) for Util Facility, >20% up t | N | L |  | NR | P | 163178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 163178 | 0 | 0 | 163178 | 0 | 0 | 0 | N | 163178 | 0 | 0 | 163178 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344 | 0 | 0 | 0 | 1344 | 0 | 0 | 0 | HR | 1720 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CE transferred $593,400.00 in funding to JB900 (0663-1000) for entire activity/bid item.
Y | IPCRP1-0603-0000-L | IPCRP1 | IPCRP1 | 0603-0000 | CONST FIELD SUPPORT, SURVEY CREW (T .1) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0603-0000-R | IPCRP1 | IPCRP1 | 0603-0000 | CONST FIELD SUPPORT, SURVEY CREW (T .1) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 128400 | 0 | 0 | 128400 | 0 | 128400 | 24300 | 0 | N | 128400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0603-1000-E | IPCRP1 | IPCRP1 | 0603-1000 | Const Field Support, Survey Crew (T .1) | N | E |  | NR | P | 26750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 26750 | 0 | 0 | 26750 | 0 | 0 | 0 | Y | 26750 | 0 | 0 | 26750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 428 | 81 | 347 | 428 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0603-1000-L | IPCRP1 | IPCRP1 | 0603-1000 | Const Field Support, Survey Crew (T .1) | N | L |  | NR | P | 108085.5 | 1017.35 | 1017.35 | 1017.35 | 1017.35 | 0.94125 | 0 | 0 | 0 | 107068.15 | Y | 108085.5 | Y | 0 | 0 | 0 | 108085.5 | 0 | 0 | 108085.5 | Y | 0 | 0 | 0 | 108085.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -108085.5 | 0 | 0 | 108085.5 | 0 | 0 | 0 | 0 | 0 | 0 | -108085.5 | 0 | 0 | 108085.5 | 108085.5 | 0 | 0 | 0 | 856 | 0 | 856.67 | 856.67 | 856 | 8 | 848.67 | 856.67 | HR | 428 | 81 | 347 | 428 | CH | 0 | 0 | 0 | 107068.15
Y | IPCRP1-0603-1000-S | IPCRP1 | IPCRP1 | 0603-1000 | Const Field Support, Survey Crew (T .1) | N | S |  | UNIT | A | 0 | 2405.92 | 2405.92 | 2405.92 | 2405.92 | 100 | 0 | 0 | 0 | 0 | N | 2405.92 | N | -2405.92 | 0 | 0 | 0 | 0 | 0 | 2405.92 | N | -2405.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2405.92 | 0 | 0 | 2405.92 | 0 | 0 | 0 | 0 | 0 | 0 | -2405.92 | 0 | 0 | 2405.92 | 2405.92 | 0 | 0 | 0 | 0 | 0 | 20.5 | 20.5 | 0 | 20.5 | 0 | 20.5 | NA | 428 | 81 | 347 | 428 | CH | 2405.92 | 0 | 2405.92 | 0
Y | IPCRP1-0604-0000-L | IPCRP1 | IPCRP1 | 0604-0000 | CONST FIELD SUPPORT, SM SIZE CREW (T .2) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0604-0000-R | IPCRP1 | IPCRP1 | 0604-0000 | CONST FIELD SUPPORT, SM SIZE CREW (T .2) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 723000 | 0 | 0 | 723000 | 0 | 723000 | 37800 | 0 | N | 723000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0604-1000-L | IPCRP1 | IPCRP1 | 0604-1000 | Const Field Support, Sm Size Crew (T .2) | N | L |  | NR | P | 789195.58 | 43862.23 | 43862.23 | 43862.23 | 43862.23 | 19.5968 | 0 | 0 | 0 | 179961.77 | Y | 223824 | Y | 565371.58 | 0 | 0 | 789195.58 | 0 | 0 | 223824 | Y | 565371.58 | 0 | 0 | 789195.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -223824 | 0 | 3196.28 | 223824 | 0 | 0 | 0 | 0 | 0 | 0 | -223824 | 0 | 0 | 223824 | 223824 | 0 | 0 | 0 | 7230 | 0 | 1973.89 | 1973.89 | 7230 | 324 | 1649.89 | 1973.89 | HR | 2410 | 144 | 539.5 | 683.5 | CH | 0 | 0 | 0 | 179961.77
N | IPCRP1-0604-1000-S | IPCRP1 | IPCRP1 | 0604-1000 | Const Field Support, Sm Size Crew (T .2) | N | S |  | UNIT | A | 0 | 1310.53 | 1310.53 | 1310.53 | 1310.53 | 100 | 0 | 0 | 0 | 0 | N | 1310.53 | N | -1310.53 | 0 | 0 | 0 | 0 | 0 | 1310.53 | N | -1310.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1310.53 | 0 | 1310.53 | 1310.53 | 0 | 0 | 0 | 0 | 0 | 0 | -1310.53 | 0 | 0 | 1310.53 | 1310.53 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | NA | 2410 | 144 | 539.5 | 683.5 | CH | 1310.53 | 0 | 1310.53 | 0
Y | IPCRP1-0605-0000-L | IPCRP1 | IPCRP1 | 0605-0000 | CONST FIELD SUPPORT, MED SIZE CREW (T .3) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0605-0000-R | IPCRP1 | IPCRP1 | 0605-0000 | CONST FIELD SUPPORT, MED SIZE CREW (T .3) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2968000 | 0 | 0 | 2968000 | 0 | 2968000 | 2410800 | 0 | N | 2968000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2968000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0605-1000-E | IPCRP1 | IPCRP1 | 0605-1000 | Const Field Support, Med Size Crew (T .3) | N | E |  | NR | P | 361845.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 361845.58 | 0 | 0 | 361845.58 | 0 | 0 | 0 | Y | 361845.58 | 0 | 0 | 361845.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3710 | 3013.5 | 696.5 | 3710 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0605-1000-L | IPCRP1 | IPCRP1 | 0605-1000 | Const Field Support, Med Size Crew (T .3) | N | L |  | NR | P | 2536938.28 | 1365862.28 | 1365862.28 | 1365862.28 | 1365862.28 | 80.3448 | 0 | 0 | 0 | 334137.72 | Y | 1700000 | Y | 836938.28 | 0 | 0 | 2536938.28 | 0 | 0 | 1700000 | Y | 836938.28 | 0 | 0 | 2536938.28 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1700000 | 8216.88 | 0 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | -1700000 | 0 | 0 | 1700000 | 1700000 | 0 | 0 | 0 | 22260 | 0 | 12000.03 | 12000.03 | 22260 | 9675 | 2325.03 | 12000.03 | HR | 3710 | 3013.5 | 696.5 | 3710 | CH | 0 | 0 | 0 | 334137.72 | As / NM (6/16/25) accept DDC QTD = 2,582.50 (thru Apr) + est 35' in May = 2,617.50
Y | IPCRP1-0605-1000-S | IPCRP1 | IPCRP1 | 0605-1000 | Const Field Support, Med Size Crew (T .3) | N | S |  | UNIT | A | 0 | 6229.83 | 6229.83 | 6229.83 | 6229.83 | 100 | 0 | 0 | 0 | 0 | Y | 6229.83 | Y | -6229.83 | 0 | 0 | 0 | 0 | 0 | 6229.83 | Y | -6229.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6229.83 | 0 | 0 | 6229.83 | 0 | 0 | 0 | 0 | 0 | 0 | -6229.83 | 0 | 0 | 6229.83 | 6229.83 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 52 | -44 | 8 | NA | 3710 | 3013.5 | 696.5 | 3710 | CH | 6229.83 | 0 | 6229.83 | 0
Y | IPCRP1-0606-0000-L | IPCRP1 | IPCRP1 | 0606-0000 | CONST FIELD SUPPORT, PIPE RIPPING (T 5) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0606-0000-R | IPCRP1 | IPCRP1 | 0606-0000 | CONST FIELD SUPPORT, PIPE RIPPING (T 5) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10400 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | N | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CH | 0 | 0 | 0 | 0
Y | IPCRP1-0606-1000-L | IPCRP1 | IPCRP1 | 0606-1000 | CONST FIELD SUPPORT, PIPE RIPPING (T 5) | N | L |  | NR | P | 8531.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8531.64 | N | 8531.64 | N | 0 | 0 | 0 | 8531.64 | 0 | 0 | 8531.64 | N | 0 | 0 | 0 | 8531.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8531.64 | 0 | 0 | 8531.64 | 0 | 0 | 0 | 0 | 0 | 0 | -8531.64 | 0 | 0 | 8531.64 | 8531.64 | 0 | 0 | 0 | 80 | 0 | 80 | 80 | 80 | 0 | 80 | 80 | HR | 16 | 0 | 16 | 16 | CH | 0 | 0 | 0 | 8531.64
Y | IPCRP1-0607-0000-L | IPCRP1 | IPCRP1 | 0607-0000 | REM ABAND UTIL COND (NON-CONC ENC) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0607-0000-R | IPCRP1 | IPCRP1 | 0607-0000 | REM ABAND UTIL COND (NON-CONC ENC) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 47061 | 0 | 0 | 47061 | 0 | 47061 | 396 | 0 | N | 47061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0608-0000-L | IPCRP1 | IPCRP1 | 0608-0000 | REM ABAND UTIL COND (NON-CONC ENC) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0608-0000-R | IPCRP1 | IPCRP1 | 0608-0000 | REM ABAND UTIL COND (NON-CONC ENC) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 900 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | N | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0609-0000-L | IPCRP1 | IPCRP1 | 0609-0000 | REM ABAND MASONRY FOR UTIL FACIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0609-0000-R | IPCRP1 | IPCRP1 | 0609-0000 | REM ABAND MASONRY FOR UTIL FACIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35700 | 0 | 0 | 35700 | 0 | 35700 | 0 | 0 | N | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0610-0000-L | IPCRP1 | IPCRP1 | 0610-0000 | REM ABAND MASONRY FOR UTIL FACIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0610-0000-R | IPCRP1 | IPCRP1 | 0610-0000 | REM ABAND MASONRY FOR UTIL FACIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2150 | 0 | 0 | 2150 | 0 | 2150 | 0 | 0 | N | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0610-1000-E | IPCRP1 | IPCRP1 | 0610-1000 | Rem Aband Util Cond or Aband Mason for Util Facil | N | E |  | NR | P | 8189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 8189 | 0 | 0 | 8189 | 0 | 0 | 0 | Y | 8189 | 0 | 0 | 8189 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 10508 | 88 | 10420 | 10508 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0610-1000-L | IPCRP1 | IPCRP1 | 0610-1000 | Rem Aband Util Cond or Aband Mason for Util Facil | N | L |  | NR | P | 45540 | 1525.97 | 1525.97 | 1525.97 | 1525.97 | 3.3508 | 0 | 0 | 0 | 44014.03 | N | 45540 | N | 0 | 0 | 0 | 45540 | 0 | 0 | 45540 | N | 0 | 0 | 0 | 45540 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45540 | 0 | 0 | 45540 | 0 | 0 | 0 | 0 | 0 | 0 | -45540 | 0 | 0 | 45540 | 45540 | 0 | 0 | 0 | 363 | 0 | 363 | 363 | 363 | 12 | 351 | 363 | HR | 10508 | 88 | 10420 | 10508 | LF | 0 | 0 | 0 | 44014.03
Y | IPCRP1-0611-0000-L | IPCRP1 | IPCRP1 | 0611-0000 | INSTALL UTIL COND W/O CONC ENCASE IN F.P. | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0611-0000-R | IPCRP1 | IPCRP1 | 0611-0000 | INSTALL UTIL COND W/O CONC ENCASE IN F.P. | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 56100 | 0 | 0 | 56100 | 0 | 56100 | 56100 | 0 | N | 56100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0611-1000-E | IPCRP1 | IPCRP1 | 0611-1000 | Install Util Cond w/o Conc Encase in Final Positi | N | E |  | NR | P | 7912.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 7912.25 | 0 | 0 | 7912.25 | 0 | 0 | 0 | Y | 7912.25 | 0 | 0 | 7912.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5100 | 15510.5 | 0 | 15510.5 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0611-1000-L | IPCRP1 | IPCRP1 | 0611-1000 | Install Util Cond w/o Conc Encase in Final Positi | N | L |  | NR | P | 36287.15 | 125955.67 | 125955.67 | 125955.67 | 125955.67 | 100 | 0 | 0 | 0 | 0 | Y | 125955.67 | Y | -89668.52 | 0 | 0 | 36287.15 | 0 | 0 | 125955.67 | Y | -89668.52 | 0 | 0 | 36287.15 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -125955.67 | 0 | 0 | 125955.67 | 0 | 0 | 0 | 0 | 0 | 0 | -125955.67 | 0 | 0 | 125955.67 | 125955.67 | 0 | 0 | 0 | 280 | 0 | 1061.5 | 1061.5 | 280 | 1061.5 | 0 | 1061.5 | HR | 5100 | 15510.5 | 0 | 15510.5 | LF | 0 | 0 | 0 | 0 | BS (6/13/25 confirmed QTD thru Mar 25 = 15,015.50 LF Capped out quantity paid by DDC at 5,100.00 LF. TTD Quantity as of 11/5/25 is 15,510.50 LF with balance paid directly by CE
Y | IPCRP1-0611-1000-S | IPCRP1 | IPCRP1 | 0611-1000 | Install Util Cond w/o Conc Encase in Final Positi | N | S |  | UNIT | A | 0 | 2722.1 | 2722.1 | 2722.1 | 2722.1 | 100 | 0 | 0 | 0 | 0 | N | 2722.1 | N | -2722.1 | 0 | 0 | 0 | 0 | 0 | 2722.1 | N | -2722.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2722.1 | 0 | 0 | 2722.1 | 0 | 0 | 0 | 0 | 0 | 0 | -2722.1 | 0 | 0 | 2722.1 | 2722.1 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 22 | 0 | 22 | NA | 5100 | 15510.5 | 0 | 15510.5 | LF | 2722.1 | 0 | 2722.1 | 0
Y | IPCRP1-0612-0000-L | IPCRP1 | IPCRP1 | 0612-0000 | INSTALL UTIL COND W/CONC ENCASE IN F.P. | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0612-0000-R | IPCRP1 | IPCRP1 | 0612-0000 | INSTALL UTIL COND W/CONC ENCASE IN F.P. | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 107900 | 0 | 0 | 107900 | 0 | 107900 | 2288 | 0 | N | 107900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0612-1000-E | IPCRP1 | IPCRP1 | 0612-1000 | Install Util Cond w/ Conc Encase in Final Positio | N | E |  | NR | P | 12876.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 12876.8 | 0 | 0 | 12876.8 | 0 | 0 | 0 | Y | 12876.8 | 0 | 0 | 12876.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8300 | 176 | 8124 | 8300 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0612-1000-L | IPCRP1 | IPCRP1 | 0612-1000 | Install Util Cond w/ Conc Encase in Final Positio | N | L |  | NR | P | 59055.56 | 4641.5 | 4641.5 | 4641.5 | 4641.5 | 7.8595 | 0 | 0 | 0 | 54414.06 | N | 59055.56 | N | 0 | 0 | 0 | 59055.56 | 0 | 0 | 59055.56 | N | 0 | 0 | 0 | 59055.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -59055.56 | 0 | 0 | 59055.56 | 0 | 0 | 0 | 0 | 0 | 0 | -59055.56 | 0 | 0 | 59055.56 | 59055.56 | 0 | 0 | 0 | 455.7 | 0 | 455.7 | 455.7 | 455.7 | 46.5 | 409.2 | 455.7 | HR | 8300 | 176 | 8124 | 8300 | LF | 0 | 0 | 0 | 54414.06
Y | IPCRP1-0613-0000-L | IPCRP1 | IPCRP1 | 0613-0000 | 12 in D ST GAS PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0613-0000-R | IPCRP1 | IPCRP1 | 0613-0000 | 12 in D ST GAS PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 130240 | 0 | 0 | 130240 | 0 | 130240 | 0 | 0 | N | 130240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0614-0000-L | IPCRP1 | IPCRP1 | 0614-0000 | 24 in D ST GAS PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0614-0000-R | IPCRP1 | IPCRP1 | 0614-0000 | 24 in D ST GAS PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 179520 | 0 | 0 | 179520 | 0 | 179520 | 0 | 0 | N | 179520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0615-0000-L | IPCRP1 | IPCRP1 | 0615-0000 | 3 in D ST GAS PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0615-0000-R | IPCRP1 | IPCRP1 | 0615-0000 | 3 in D ST GAS PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 113520 | 0 | 0 | 113520 | 0 | 113520 | 111047.5 | 0 | N | 113520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0616-0000-L | IPCRP1 | IPCRP1 | 0616-0000 | 8 in D ST GAS PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0616-0000-R | IPCRP1 | IPCRP1 | 0616-0000 | 8 in D ST GAS PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 200610 | 0 | 0 | 200610 | 0 | 200610 | 57915 | 0 | N | 200610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0617-0000-L | IPCRP1 | IPCRP1 | 0617-0000 | 12 in D ST GAS PIPE FITTING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0617-0000-R | IPCRP1 | IPCRP1 | 0617-0000 | 12 in D ST GAS PIPE FITTING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 56000 | 0 | 0 | 56000 | 0 | 56000 | 0 | 0 | N | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0618-0000-L | IPCRP1 | IPCRP1 | 0618-0000 | 24 in D ST GAS PIPE FITTING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0618-0000-R | IPCRP1 | IPCRP1 | 0618-0000 | 24 in D ST GAS PIPE FITTING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 132300 | 0 | 0 | 132300 | 0 | 132300 | 0 | 0 | N | 132300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0619-0000-L | IPCRP1 | IPCRP1 | 0619-0000 | 3 in D ST GAS PIPE FITTING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0619-0000-R | IPCRP1 | IPCRP1 | 0619-0000 | 3 in D ST GAS PIPE FITTING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 37260 | 0 | 0 | 37260 | 0 | 37260 | 37260 | 0 | N | 37260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0620-0000-L | IPCRP1 | IPCRP1 | 0620-0000 | 8 in D ST GAS PIPE FITTING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0620-0000-R | IPCRP1 | IPCRP1 | 0620-0000 | 8 in D ST GAS PIPE FITTING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 94500 | 0 | 0 | 94500 | 0 | 94500 | 94500 | 0 | N | 94500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0620-1000-E | IPCRP1 | IPCRP1 | 0620-1000 | Inst St Gas Pipe (3 - 24) in Complete w/ Test & Ti | N | E |  | NR | P | 102713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 102713 | 0 | 0 | 102713 | 0 | 0 | 0 | Y | 102713 | 0 | 0 | 102713 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1854 | 731 | 0 | 731 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0620-1000-L | IPCRP1 | IPCRP1 | 0620-1000 | Inst St Gas Pipe (3 - 24) in Complete w/ Test & Ti | N | L |  | NR | P | 428289 | 93902.29 | 93902.29 | 93902.29 | 93902.29 | 100 | 0 | 0 | 0 | 0 | Y | 93902.29 | Y | 334386.71 | 0 | 0 | 428289 | 0 | 0 | 93902.29 | Y | 334386.71 | 0 | 0 | 428289 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -93902.29 | 0 | 0 | 93902.29 | 0 | 0 | 0 | 0 | 0 | 0 | -93902.29 | 0 | 0 | 93902.29 | 93902.29 | 0 | 0 | 0 | 2494.67 | 0 | 726.5 | 726.5 | 2494.67 | 726.5 | 0 | 726.5 | HR | 1854 | 731 | 0 | 731 | LF | 0 | 0 | 0 | 0 | Lg Gas Work at E10th St deleted as per CE email dated 9/11/24
Y | IPCRP1-0620-1010-L | IPCRP1 | IPCRP1 | 0620-1010 | Hot Coating | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0620-1010-S | IPCRP1 | IPCRP1 | 0620-1010 | Hot Coating | N | S |  | NR | A | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16000 | 0 | 0 | 16000 | 0 | 0 | 0 | Y | 16000 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | Lg Gas Work at E10th St deleted as per CE email dated 9/11/24
Y | IPCRP1-0621-0000-L | IPCRP1 | IPCRP1 | 0621-0000 | INSTALL PLASTIC GAS PIPE - 12in D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0621-0000-R | IPCRP1 | IPCRP1 | 0621-0000 | INSTALL PLASTIC GAS PIPE - 12in D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 72930 | 0 | 0 | 72930 | 0 | 72930 | 72930 | 0 | N | 72930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0622-0000-L | IPCRP1 | IPCRP1 | 0622-0000 | INSTALL PLASTIC GAS PIPE - 3in D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0622-0000-R | IPCRP1 | IPCRP1 | 0622-0000 | INSTALL PLASTIC GAS PIPE - 3in D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15080 | 0 | 0 | 15080 | 0 | 15080 | 0 | 0 | N | 15080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0623-0000-L | IPCRP1 | IPCRP1 | 0623-0000 | INSTALL PLASTIC GAS PIPE - 8in D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0623-0000-R | IPCRP1 | IPCRP1 | 0623-0000 | INSTALL PLASTIC GAS PIPE - 8in D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57200 | 0 | 0 | 57200 | 0 | 57200 | 57200 | 0 | N | 57200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0624-0000-L | IPCRP1 | IPCRP1 | 0624-0000 | INSTALL PLASTIC GAS PIPE FITTING - 12in D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0624-0000-R | IPCRP1 | IPCRP1 | 0624-0000 | INSTALL PLASTIC GAS PIPE FITTING - 12in D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7800 | 0 | 0 | 7800 | 0 | 7800 | 7800 | 0 | N | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0625-0000-L | IPCRP1 | IPCRP1 | 0625-0000 | INSTALL PLASTIC GAS PIPE FITTING - 3in D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0625-0000-R | IPCRP1 | IPCRP1 | 0625-0000 | INSTALL PLASTIC GAS PIPE FITTING - 3in D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1610 | 0 | 0 | 1610 | 0 | 1610 | 0 | 0 | N | 1610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0626-0000-L | IPCRP1 | IPCRP1 | 0626-0000 | INSTALL PLASTIC GAS PIPE FITTING - 8in D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0626-0000-R | IPCRP1 | IPCRP1 | 0626-0000 | INSTALL PLASTIC GAS PIPE FITTING - 8in D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2340 | 0 | 0 | 2340 | 0 | 2340 | 2340 | 0 | N | 2340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0626-1000-E | IPCRP1 | IPCRP1 | 0626-1000 | Install Plastic Gas Pipe (3, 8, 12)in & Fittings | N | E |  | NR | P | 14497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 14497 | 0 | 0 | 14497 | 0 | 0 | 0 | Y | 14497 | 0 | 0 | 14497 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 629 | 584.5 | 44.5 | 629 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0626-1000-L | IPCRP1 | IPCRP1 | 0626-1000 | Install Plastic Gas Pipe (3, 8, 12)in & Fittings | N | L |  | NR | P | 65145 | 25784.62 | 25784.62 | 25784.62 | 25784.62 | 39.5804 | 0 | 0 | 0 | 39360.38 | Y | 65145 | Y | 0 | 0 | 0 | 65145 | 0 | 0 | 65145 | Y | 0 | 0 | 0 | 65145 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -65145 | 0 | 0 | 65145 | 0 | 0 | 0 | 0 | 0 | 0 | -65145 | 0 | 0 | 65145 | 65145 | 0 | 0 | 0 | 441.79 | 0 | 441.78 | 441.78 | 441.79 | 209.5 | 232.28 | 441.78 | HR | 629 | 584.5 | 44.5 | 629 | LF | 0 | 0 | 0 | 39360.38
Y | IPCRP1-0627-0000-L | IPCRP1 | IPCRP1 | 0627-0000 | INSTALL 24in D STEAM PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0627-0000-R | IPCRP1 | IPCRP1 | 0627-0000 | INSTALL 24in D STEAM PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 815100 | 0 | 0 | 815100 | 0 | 815100 | 0 | 0 | N | 815100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0628-0000-L | IPCRP1 | IPCRP1 | 0628-0000 | INSTALL 24in D STEAM PIPE FITTING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0628-0000-R | IPCRP1 | IPCRP1 | 0628-0000 | INSTALL 24in D STEAM PIPE FITTING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 460000 | 0 | 0 | 460000 | 0 | 460000 | 0 | 0 | N | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0628-1000-E | IPCRP1 | IPCRP1 | 0628-1000 | Inst 24in D Steam Pipe - Complete | N | E |  | NR | P | 91692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 91692 | 0 | 0 | 91692 | 0 | 0 | 0 | Y | 91692 | 0 | 0 | 91692 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 418 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0628-1000-L | IPCRP1 | IPCRP1 | 0628-1000 | Inst 24in D Steam Pipe - Complete | N | L |  | NR | P | 473912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | Y | 130 | Y | 473782 | 0 | 0 | 473912 | 0 | 0 | 130 | Y | 473782 | 0 | 0 | 473912 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | -130 | 0 | 0 | 130 | 130 | 0 | 0 | 0 | 3952.51 | 0 | 1 | 1 | 3952.51 | 0 | 1 | 1 | HR | 418 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 130 | Steam Work at E10th St deleted as per CE email dated 9/11/24. CE transferred $1,415,100.00 in funding to JB900 (0663-1000) for entire activity/bid item (0627, 0628, 0632).
Y | IPCRP1-0629-0000-L | IPCRP1 | IPCRP1 | 0629-0000 | F, D & I 36in STR ST STEAM CASING PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0629-0000-R | IPCRP1 | IPCRP1 | 0629-0000 | F, D & I 36in STR ST STEAM CASING PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 224000 | 0 | 0 | 224000 | 0 | 224000 | 0 | 0 | N | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0630-0000-L | IPCRP1 | IPCRP1 | 0630-0000 | F, D & I 48 STR ST STEAM CASING PIPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0630-0000-R | IPCRP1 | IPCRP1 | 0630-0000 | F, D & I 48 STR ST STEAM CASING PIPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 312000 | 0 | 0 | 312000 | 0 | 312000 | 0 | 0 | N | 312000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0630-1000-E | IPCRP1 | IPCRP1 | 0630-1000 | Inst Steam Casing Pipe, Housing, & Supports | N | E |  | NR | P | 29027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 29027 | 0 | 0 | 29027 | 0 | 0 | 0 | Y | 29027 | 0 | 0 | 29027 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 160 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0630-1000-L | IPCRP1 | IPCRP1 | 0630-1000 | Inst Steam Casing Pipe, Housing, & Supports | N | L |  | NR | P | 148826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | Y | 130 | Y | 148696 | 0 | 0 | 148826 | 0 | 0 | 130 | Y | 148696 | 0 | 0 | 148826 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | -130 | 0 | 0 | 130 | 130 | 0 | 0 | 0 | 1075.9 | 0 | 1 | 1 | 1075.9 | 0 | 1 | 1 | HR | 160 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 130 | Steam Work at E10th St deleted as per CE email dated 9/11/24. CE transferred $536,000.00 in funding to JB900 (0663-1000) for entire activity/bid item.
Y | IPCRP1-0630-1010-L | IPCRP1 | IPCRP1 | 0630-1010 | PM-Straight St Steam Casing Pipe, 36in & 48in Dia | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 160 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0630-1010-M | IPCRP1 | IPCRP1 | 0630-1010 | PM-Straight St Steam Casing Pipe, 36in & 48in Dia | N | M |  | NR | P | 35100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 35100 | 0 | 0 | 35100 | 0 | 0 | 0 | Y | 35100 | 0 | 0 | 35100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 160 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Steam Work at E10th St deleted as per CE email dated 9/11/24
Y | IPCRP1-0631-0000-L | IPCRP1 | IPCRP1 | 0631-0000 | STEAM VALVE ASSEMBLY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0631-0000-R | IPCRP1 | IPCRP1 | 0631-0000 | STEAM VALVE ASSEMBLY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 14900 | 0 | 0 | 14900 | 0 | 14900 | 0 | 0 | N | 14900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0632-0000-L | IPCRP1 | IPCRP1 | 0632-0000 | INSTALL STEAM ANCHOR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0632-0000-R | IPCRP1 | IPCRP1 | 0632-0000 | INSTALL STEAM ANCHOR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 140000 | 0 | 0 | 140000 | 0 | 140000 | 0 | 0 | N | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0633-0000-L | IPCRP1 | IPCRP1 | 0633-0000 | INSTALL STEAM MANHOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0633-0000-R | IPCRP1 | IPCRP1 | 0633-0000 | INSTALL STEAM MANHOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 196000 | 0 | 0 | 196000 | 0 | 196000 | 0 | 0 | N | 196000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0633-1000-E | IPCRP1 | IPCRP1 | 0633-1000 | Install Anchor Base Form & Pour | N | E |  | NR | P | 9687.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 9687.36 | 0 | 0 | 9687.36 | 0 | 0 | 0 | Y | 9687.36 | 0 | 0 | 9687.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0633-1000-L | IPCRP1 | IPCRP1 | 0633-1000 | Install Anchor Base Form & Pour | N | L |  | NR | P | 42779.07 | 28.93 | 28.93 | 28.93 | 28.93 | 100 | 0 | 0 | 0 | 0 | Y | 28.93 | Y | 42750.14 | 0 | 0 | 42779.07 | 0 | 0 | 28.93 | Y | 42750.14 | 0 | 0 | 42779.07 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28.93 | 0 | 0 | 28.93 | 0 | 0 | 0 | 0 | 0 | 0 | -28.93 | 0 | 0 | 28.93 | 28.93 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | Steam Work at E10th St deleted as per CE email dated 9/11/24. CE transferred $196,000.00 in funding to JB900 (0663-1000) for entire activity/bid item
Y | IPCRP1-0634-0000-L | IPCRP1 | IPCRP1 | 0634-0000 | ADJUST UTIL HARDWARE (< 7) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0634-0000-R | IPCRP1 | IPCRP1 | 0634-0000 | ADJUST UTIL HARDWARE (< 7) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4100 | 0 | 0 | 4100 | 0 | 4100 | 0 | 0 | N | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0635-0000-L | IPCRP1 | IPCRP1 | 0635-0000 | ADJUST UTIL HARDWARE (7 - <14) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0635-0000-R | IPCRP1 | IPCRP1 | 0635-0000 | ADJUST UTIL HARDWARE (7 - <14) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3280 | 0 | 0 | 3280 | 0 | 3280 | 0 | 0 | N | 3280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0636-0000-L | IPCRP1 | IPCRP1 | 0636-0000 | ADJUST UTIL HARDWARE (14 - <30) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0636-0000-R | IPCRP1 | IPCRP1 | 0636-0000 | ADJUST UTIL HARDWARE (14 - <30) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5280 | 0 | 0 | 5280 | 0 | 5280 | 0 | 0 | N | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0637-0000-L | IPCRP1 | IPCRP1 | 0637-0000 | ADJUST UTIL HARDWARE (30 - <34) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0637-0000-R | IPCRP1 | IPCRP1 | 0637-0000 | ADJUST UTIL HARDWARE (30 - <34) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 24030 | 0 | 0 | 24030 | 0 | 24030 | 0 | 0 | N | 24030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0638-0000-L | IPCRP1 | IPCRP1 | 0638-0000 | ADJUST UTIL HARDWARE (34 - <41) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0638-0000-R | IPCRP1 | IPCRP1 | 0638-0000 | ADJUST UTIL HARDWARE (34 - <41) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1760 | 0 | 0 | 1760 | 0 | 1760 | 0 | 0 | N | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0639-0000-L | IPCRP1 | IPCRP1 | 0639-0000 | ADJUST UTIL HARDWARE (34 - <41) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0639-0000-R | IPCRP1 | IPCRP1 | 0639-0000 | ADJUST UTIL HARDWARE (34 - <41) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1760 | 0 | 0 | 1760 | 0 | 1760 | 0 | 0 | N | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0640-0000-L | IPCRP1 | IPCRP1 | 0640-0000 | ADJUST UTIL HARDWARE (34 - <41) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0640-0000-R | IPCRP1 | IPCRP1 | 0640-0000 | ADJUST UTIL HARDWARE (34 - <41) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9500 | 0 | 0 | 9500 | 0 | 9500 | 0 | 0 | N | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0641-0000-L | IPCRP1 | IPCRP1 | 0641-0000 | ADJUST UTIL HARDWARE (41 - <75) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0641-0000-R | IPCRP1 | IPCRP1 | 0641-0000 | ADJUST UTIL HARDWARE (41 - <75) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 2400 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0642-0000-L | IPCRP1 | IPCRP1 | 0642-0000 | ADJUST UTIL HARDWARE (75 - <125) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0642-0000-R | IPCRP1 | IPCRP1 | 0642-0000 | ADJUST UTIL HARDWARE (75 - <125) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13500 | 0 | 0 | 13500 | 0 | 13500 | 0 | 0 | N | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0643-0000-L | IPCRP1 | IPCRP1 | 0643-0000 | ADJUST UTIL HARDWARE (125 - <170) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0643-0000-R | IPCRP1 | IPCRP1 | 0643-0000 | ADJUST UTIL HARDWARE (125 - <170) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13500 | 0 | 0 | 13500 | 0 | 13500 | 0 | 0 | N | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0643-1000-L | IPCRP1 | IPCRP1 | 0643-1000 | Adjust Util Hardware (All Heights) | N | L |  | NR | P | 46611 | 2349.44 | 2349.44 | 2349.44 | 2349.44 | 5.0405 | 0 | 0 | 0 | 44261.56 | N | 46611 | N | 0 | 0 | 0 | 46611 | 0 | 0 | 46611 | N | 0 | 0 | 0 | 46611 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -46611 | 0 | 0 | 46611 | 0 | 0 | 0 | 0 | 0 | 0 | -46611 | 0 | 0 | 46611 | 46611 | 0 | 0 | 0 | 432 | 0 | 432 | 432 | 432 | 20 | 412 | 432 | HR | 93 | 2 | 91 | 93 | EA | 0 | 0 | 0 | 44261.56
Y | IPCRP1-0644-0000-L | IPCRP1 | IPCRP1 | 0644-0000 | MODIF WORK METH TO ACCOM UTIL HARDWARE (30 - <34 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0644-0000-R | IPCRP1 | IPCRP1 | 0644-0000 | MODIF WORK METH TO ACCOM UTIL HARDWARE (30 - <34 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2250 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | N | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0645-0000-L | IPCRP1 | IPCRP1 | 0645-0000 | MODIF WORK METH TO ACCOM UTIL HARDWARE (34 - <41 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0645-0000-R | IPCRP1 | IPCRP1 | 0645-0000 | MODIF WORK METH TO ACCOM UTIL HARDWARE (34 - <41 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2250 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | N | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0646-0000-L | IPCRP1 | IPCRP1 | 0646-0000 | MODIF WORK METH TO ACCOM UTIL HARDWARE (41 - <75 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0646-0000-R | IPCRP1 | IPCRP1 | 0646-0000 | MODIF WORK METH TO ACCOM UTIL HARDWARE (41 - <75 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2250 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | N | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0646-1000-L | IPCRP1 | IPCRP1 | 0646-1000 | Modif Work Meth to Accom Util Hardware (30 to 75 | N | L |  | NR | P | 5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179 | N | 5179 | N | 0 | 0 | 0 | 5179 | 0 | 0 | 5179 | N | 0 | 0 | 0 | 5179 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5179 | 0 | 0 | 5179 | 0 | 0 | 0 | 0 | 0 | 0 | -5179 | 0 | 0 | 5179 | 5179 | 0 | 0 | 0 | 48 | 0 | 48 | 48 | 48 | 0 | 48 | 48 | HR | 30 | 0 | 30 | 30 | EA | 0 | 0 | 0 | 5179
Y | IPCRP1-0647-0000-L | IPCRP1 | IPCRP1 | 0647-0000 | REPAIR TO UTIL STRUCTURES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0647-0000-R | IPCRP1 | IPCRP1 | 0647-0000 | REPAIR TO UTIL STRUCTURES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 85500 | 0 | 0 | 85500 | 0 | 85500 | 0 | 0 | N | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0647-1000-E | IPCRP1 | IPCRP1 | 0647-1000 | Repair to Utilily Structures | N | E |  | NR | P | 3870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3870 | 0 | 0 | 3870 | 0 | 0 | 0 | Y | 3870 | 0 | 0 | 3870 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 180 | 0 | 95.79 | 95.79 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0647-1000-L | IPCRP1 | IPCRP1 | 0647-1000 | Repair to Utilily Structures | N | L |  | NR | P | 27752.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14769 | Y | 14769 | Y | 12983.38 | 0 | 0 | 27752.38 | 0 | 0 | 14769 | Y | 12983.38 | 0 | 0 | 27752.38 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14769 | 0 | 0 | 14769 | 0 | 0 | 0 | 0 | 0 | 0 | -14769 | 0 | 0 | 14769 | 14769 | 0 | 0 | 0 | 240 | 0 | 128 | 128 | 240 | 0 | 128 | 128 | HR | 180 | 0 | 95.79 | 95.79 | CY | 0 | 0 | 0 | 14769
Y | IPCRP1-0647-1000-S | IPCRP1 | IPCRP1 | 0647-1000 | Repair to Utilily Structures | N | S |  | UNIT | A | 0 | 870.03 | 870.03 | 870.03 | 870.03 | 100 | 0 | 0 | 0 | 0 | N | 870.03 | N | -870.03 | 0 | 0 | 0 | 0 | 0 | 870.03 | N | -870.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -870.03 | 0 | 0 | 870.03 | 0 | 0 | 0 | 0 | 0 | 0 | -870.03 | 0 | 0 | 870.03 | 870.03 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 7 | NA | 180 | 0 | 95.79 | 95.79 | CY | 870.03 | 0 | 870.03 | 0
Y | IPCRP1-0648-0000-L | IPCRP1 | IPCRP1 | 0648-0000 | CONC COLLAR AROUND STEAM CASTINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0648-0000-R | IPCRP1 | IPCRP1 | 0648-0000 | CONC COLLAR AROUND STEAM CASTINGS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0648-1000-C | IPCRP1 | IPCRP1 | 0648-1000 | CONC COLLAR AROUND STEAM CASTINGS | N | C |  | NR | P | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | N | 50 | N | 0 | 0 | 0 | 50 | 0 | 0 | 50 | N | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | -50 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 500 | 0 | 500 | 500 | SF | 0 | 0 | 0 | 50
Y | IPCRP1-0648-1000-E | IPCRP1 | IPCRP1 | 0648-1000 | CONC COLLAR AROUND STEAM CASTINGS | N | E |  | NR | P | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 100 | 0 | 0 | 100 | 0 | 0 | 0 | Y | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 500 | 0 | 500 | 500 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0648-1000-L | IPCRP1 | IPCRP1 | 0648-1000 | CONC COLLAR AROUND STEAM CASTINGS | N | L |  | NR | P | 6980.49 | 1210.81 | 1210.81 | 1210.81 | 1210.81 | 17.3456 | 0 | 0 | 0 | 5769.68 | N | 6980.49 | N | 0 | 0 | 0 | 6980.49 | 0 | 0 | 6980.49 | N | 0 | 0 | 0 | 6980.49 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6980.49 | 0 | 0 | 6980.49 | 0 | 0 | 0 | 0 | 0 | 0 | -6980.49 | 0 | 0 | 6980.49 | 6980.49 | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 64 | 9 | 55 | 64 | HR | 500 | 0 | 500 | 500 | SF | 0 | 0 | 0 | 5769.68
Y | IPCRP1-0649-0000-L | IPCRP1 | IPCRP1 | 0649-0000 | INSTALL FIELD CONSTRUCTED UTIL STRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0649-0000-R | IPCRP1 | IPCRP1 | 0649-0000 | INSTALL FIELD CONSTRUCTED UTIL STRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 311100 | 0 | 0 | 311100 | 0 | 311100 | 77611.8 | 0 | N | 311100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0649-1000-E | IPCRP1 | IPCRP1 | 0649-1000 | INSTALL FIELD CONSTRUCTED UTIL STRUCTURE | N | E |  | NR | P | 47738.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 47738.98 | 0 | 0 | 47738.98 | 0 | 0 | 0 | Y | 47738.98 | 0 | 0 | 47738.98 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 305 | 76.09 | 228.91 | 305 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0649-1000-L | IPCRP1 | IPCRP1 | 0649-1000 | INSTALL FIELD CONSTRUCTED UTIL STRUCTURE | N | L |  | NR | P | 150059.74 | 79683.41 | 79683.41 | 79683.41 | 79683.41 | 53.1011 | 0 | 0 | 0 | 70376.32 | Y | 150059.73 | Y | 0.01 | 0 | 0 | 150059.74 | 0 | 0 | 150059.73 | Y | 0.01 | 0 | 0 | 150059.74 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -150059.73 | 0 | 0 | 150059.73 | 0 | 0 | 0 | 0 | 0 | 0 | -150059.73 | 0 | 0 | 150059.73 | 150059.73 | 0 | 0 | 0 | 1220 | 0 | 1240.17 | 1240.17 | 1220 | 668 | 572.17 | 1240.17 | HR | 305 | 76.09 | 228.91 | 305 | CY | 0 | 0 | 0 | 70376.32
Y | IPCRP1-0649-1000-S | IPCRP1 | IPCRP1 | 0649-1000 | INSTALL FIELD CONSTRUCTED UTIL STRUCTURE | N | S |  | UNIT | A | 0 | 960 | 960 | 960 | 960 | 100 | 0 | 0 | 0 | 0 | N | 960 | N | -960 | 0 | 0 | 0 | 0 | 0 | 960 | N | -960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -960 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | -960 | 0 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 305 | 76.09 | 228.91 | 305 | CY | 960 | 0 | 960 | 0
Y | IPCRP1-0650-0000-L | IPCRP1 | IPCRP1 | 0650-0000 | BREAK OUT & REM UTIL STRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0650-0000-R | IPCRP1 | IPCRP1 | 0650-0000 | BREAK OUT & REM UTIL STRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 670000 | 0 | 0 | 670000 | 0 | 670000 | 9120 | 0 | N | 670000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0650-1000-E | IPCRP1 | IPCRP1 | 0650-1000 | Break Out & Rem Utility Structure | N | E |  | NR | P | 48677 | 48.69 | 48.69 | 48.69 | 48.69 | 100 | 0 | 0 | 0 | 0 | Y | 48.69 | Y | 48628.31 | 0 | 0 | 48677 | 0 | 0 | 48.69 | Y | 48628.31 | 0 | 0 | 48677 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -48.69 | 0 | 0 | 48.69 | 0 | 0 | 0 | 0 | 0 | 0 | -48.69 | 0 | 0 | 48.69 | 48.69 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3 | -3 | 0 | NA | 670 | 9.12 | 660.88 | 670 | CY | 48.59 | -0.1 | 48.69 | 0
Y | IPCRP1-0650-1000-L | IPCRP1 | IPCRP1 | 0650-1000 | Break Out & Rem Utility Structure | N | L |  | NR | P | 333719.88 | 5206.36 | 5206.36 | 5206.36 | 5206.36 | 1.5601 | 0 | 0 | 0 | 328513.52 | Y | 333719.88 | Y | 0 | 0 | 0 | 333719.88 | 0 | 0 | 333719.88 | Y | 0 | 0 | 0 | 333719.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -333719.88 | 0 | 0 | 333719.88 | 0 | 0 | 0 | 0 | 0 | 0 | -333719.88 | 0 | 0 | 333719.88 | 333719.88 | 0 | 0 | 0 | 2800 | 0 | 2803.72 | 2803.72 | 2800 | 47.5 | 2756.22 | 2803.72 | HR | 670 | 9.12 | 660.88 | 670 | CY | 0 | 0 | 0 | 328513.52
Y | IPCRP1-0651-0000-L | IPCRP1 | IPCRP1 | 0651-0000 | SPEC MODIF OF WORK TO ACCOM U.G. FACIL W/LMT COVE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0651-0000-R | IPCRP1 | IPCRP1 | 0651-0000 | SPEC MODIF OF WORK TO ACCOM U.G. FACIL W/LMT COVE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 41400 | 0 | 0 | 41400 | 0 | 41400 | 0 | 0 | N | 41400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0652-0000-L | IPCRP1 | IPCRP1 | 0652-0000 | SPEC MODIF OF WORK TO ACCOM U.G. FACIL W/LMT COVE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0652-0000-R | IPCRP1 | IPCRP1 | 0652-0000 | SPEC MODIF OF WORK TO ACCOM U.G. FACIL W/LMT COVE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6900 | 0 | 0 | 6900 | 0 | 6900 | 0 | 0 | N | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0652-1000-C | IPCRP1 | IPCRP1 | 0652-1000 | Spec Modif of Work to Accom UG Facil w/ Limited C | N | C |  | NR | P | 3482 | 36106.37 | 36106.37 | 33163.14 | 36106.37 | 91.8484 | 0 | 0 | 0 | 0 | Y | 36106.37 | Y | -32624.37 | 0 | 0 | 3482 | 0 | 0 | 36106.37 | Y | -32624.37 | 0 | 0 | 3482 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36106.37 | 0 | 0 | 36106.37 | 0 | 0 | 0 | 0 | 0 | 0 | -36106.37 | 0 | 0 | 36106.37 | 36106.37 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 27484 | -27484 | 0 | NA | 210 | 0 | 210 | 210 | CY | 36106.37 | 2943.23 | 33163.14 | 0
Y | IPCRP1-0652-1000-E | IPCRP1 | IPCRP1 | 0652-1000 | Spec Modif of Work to Accom UG Facil w/ Limited C | N | E |  | NR | P | 580.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 580.28 | 0 | 0 | 580.28 | 0 | 0 | 0 | Y | 580.28 | 0 | 0 | 580.28 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 210 | 0 | 210 | 210 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0652-1000-L | IPCRP1 | IPCRP1 | 0652-1000 | Spec Modif of Work to Accom UG Facil w/ Limited C | N | L |  | NR | P | 13527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13527 | N | 13527 | N | 0 | 0 | 0 | 13527 | 0 | 0 | 13527 | N | 0 | 0 | 0 | 13527 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13527 | 0 | 0 | 13527 | 0 | 0 | 0 | 0 | 0 | 0 | -13527 | 0 | 0 | 13527 | 13527 | 0 | 0 | 0 | 112 | 0 | 112 | 112 | 112 | 0 | 112 | 112 | HR | 210 | 0 | 210 | 210 | CY | 0 | 0 | 0 | 13527 | Consumable cost is sheeting purchased for work at CE MH#7 on FDR
Y | IPCRP1-0653-0000-L | IPCRP1 | IPCRP1 | 0653-0000 | REM ABAND UTIL ST/CI/PLASTIC PIPE, UP TO 12 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0653-0000-R | IPCRP1 | IPCRP1 | 0653-0000 | REM ABAND UTIL ST/CI/PLASTIC PIPE, UP TO 12 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31825 | 0 | 0 | 31825 | 0 | 31825 | 4959 | 0 | N | 31825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0654-0000-L | IPCRP1 | IPCRP1 | 0654-0000 | REM ABAND UTIL ST/CI PIPE, STRUCT OPENINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0654-0000-R | IPCRP1 | IPCRP1 | 0654-0000 | REM ABAND UTIL ST/CI PIPE, STRUCT OPENINGS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11600 | 0 | 0 | 11600 | 0 | 11600 | 0 | 0 | N | 11600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0654-1000-E | IPCRP1 | IPCRP1 | 0654-1000 | Rem Aband Util Pipe (up to 12) All Types | N | E |  | NR | P | 3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3121 | 0 | 0 | 3121 | 0 | 0 | 0 | Y | 3121 | 0 | 0 | 3121 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1875 | 261 | 1614 | 1875 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0654-1000-L | IPCRP1 | IPCRP1 | 0654-1000 | Rem Aband Util Pipe (up to 12) All Types | N | L |  | NR | P | 18590 | 8606.73 | 8606.73 | 8606.73 | 8606.73 | 46.2976 | 0 | 0 | 0 | 9983.27 | N | 18590 | N | 0 | 0 | 0 | 18590 | 0 | 0 | 18590 | N | 0 | 0 | 0 | 18590 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18590 | 0 | 0 | 18590 | 0 | 0 | 0 | 0 | 0 | 0 | -18590 | 0 | 0 | 18590 | 18590 | 0 | 0 | 0 | 160 | 0 | 160 | 160 | 160 | 66.5 | 93.5 | 160 | HR | 1875 | 261 | 1614 | 1875 | LF | 0 | 0 | 0 | 9983.27
Y | IPCRP1-0655-0000-L | IPCRP1 | IPCRP1 | 0655-0000 | USE SHEETING LINE AS FORM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0655-0000-R | IPCRP1 | IPCRP1 | 0655-0000 | USE SHEETING LINE AS FORM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19758 | 0 | 0 | 19758 | 0 | 19758 | 0 | 0 | N | 19758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0655-1000-L | IPCRP1 | IPCRP1 | 0655-1000 | Use Sheeting Line as Form (3 Timber Lagging) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3293 | 0 | 3293 | 3293 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0655-1000-M | IPCRP1 | IPCRP1 | 0655-1000 | Use Sheeting Line as Form (3 Timber Lagging) | N | M |  | NR | P | 14818.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14818.5 | N | 14818.5 | N | 0 | 0 | 0 | 14818.5 | 0 | 0 | 14818.5 | N | 0 | 0 | 0 | 14818.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14818.5 | 0 | 0 | 14818.5 | 0 | 0 | 0 | 0 | 0 | 0 | -14818.5 | 0 | 0 | 14818.5 | 14818.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3293 | 0 | 3293 | 3293 | SF | 0 | 0 | 0 | 14818.5
Y | IPCRP1-0656-0000-L | IPCRP1 | IPCRP1 | 0656-0000 | MODIF TROLLEY STRUCT REM WHEN X-ING UTIL FACIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0656-0000-R | IPCRP1 | IPCRP1 | 0656-0000 | MODIF TROLLEY STRUCT REM WHEN X-ING UTIL FACIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0657-0000-L | IPCRP1 | IPCRP1 | 0657-0000 | MODIF TROLLEY STRUCT REM PARALLEL TO UTIL FACIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0657-0000-R | IPCRP1 | IPCRP1 | 0657-0000 | MODIF TROLLEY STRUCT REM PARALLEL TO UTIL FACIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 48000 | 0 | 0 | 48000 | 0 | 48000 | 0 | 0 | N | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0657-1000-E | IPCRP1 | IPCRP1 | 0657-1000 | Mofify Trolley Structure at Util Facility | N | E |  | NR | P | 9284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 9284 | 0 | 0 | 9284 | 0 | 0 | 0 | Y | 9284 | 0 | 0 | 9284 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 450 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | IPCRP1-0657-1000-L | IPCRP1 | IPCRP1 | 0657-1000 | Mofify Trolley Structure at Util Facility | N | L |  | NR | P | 33954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 33954 | 0 | 0 | 33954 | 0 | 0 | 0 | Y | 33954 | 0 | 0 | 33954 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | HR | 450 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0658-0000-L | IPCRP1 | IPCRP1 | 0658-0000 | LINE CUT BY PNEUMATIC TOOLS W/ RDWY REM (ASPH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0658-0000-R | IPCRP1 | IPCRP1 | 0658-0000 | LINE CUT BY PNEUMATIC TOOLS W/ RDWY REM (ASPH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3000 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | N | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0659-0000-L | IPCRP1 | IPCRP1 | 0659-0000 | LINE CUT BY PNEUMATIC TOOLS W/ RDWY REM (ASPH/CON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0659-0000-R | IPCRP1 | IPCRP1 | 0659-0000 | LINE CUT BY PNEUMATIC TOOLS W/ RDWY REM (ASPH/CON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 54000 | 0 | 0 | 54000 | 0 | 54000 | 17310 | 0 | N | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0660-0000-L | IPCRP1 | IPCRP1 | 0660-0000 | LINE CUT ANY COMBO (ASPH/CONC/BEL BLOCK) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0660-0000-R | IPCRP1 | IPCRP1 | 0660-0000 | LINE CUT ANY COMBO (ASPH/CONC/BEL BLOCK) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9600 | 0 | 0 | 9600 | 0 | 9600 | 0 | 0 | N | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0660-1000-E | IPCRP1 | IPCRP1 | 0660-1000 | Line Cut By Pneumatic Tools, All Types of Roadway | N | E |  | NR | P | 19463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 19463 | 0 | 0 | 19463 | 0 | 0 | 0 | Y | 19463 | 0 | 0 | 19463 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 6500 | 1731 | 4769 | 6500 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0660-1000-L | IPCRP1 | IPCRP1 | 0660-1000 | Line Cut By Pneumatic Tools, All Types of Roadway | N | L |  | NR | P | 36214 | 39698.8 | 39698.8 | 39698.8 | 39698.8 | 109.6228 | 0 | 0 | 0 | 0 | N | 36214 | N | 0 | 0 | 0 | 36214 | 0 | 0 | 36214 | N | 0 | 0 | 0 | 36214 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36214 | 0 | 0 | 36214 | 0 | 0 | 0 | 0 | 0 | 0 | -36214 | 0 | 0 | 36214 | 36214 | 0 | 0 | 0 | 352 | 0 | 352 | 352 | 352 | 316.5 | 35.5 | 352 | HR | 6500 | 1731 | 4769 | 6500 | LF | 0 | 0 | 0 | 0 | 205 LF was completed in April '22 with minimal hours coded to 0663 budget.
Y | IPCRP1-0660-1000-S | IPCRP1 | IPCRP1 | 0660-1000 | Line Cut By Pneumatic Tools, All Types of Roadway | N | S |  | UNIT | A | 0 | 3840 | 3840 | 3840 | 3840 | 100 | 0 | 0 | 0 | 0 | N | 3840 | N | -3840 | 0 | 0 | 0 | 0 | 0 | 3840 | N | -3840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3840 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | -3840 | 0 | 0 | 3840 | 3840 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 32 | 0 | 32 | NA | 6500 | 1731 | 4769 | 6500 | LF | 3840 | 0 | 3840 | 0
Y | IPCRP1-0661-0000-L | IPCRP1 | IPCRP1 | 0661-0000 | PLACE RUBBER SHEETS FOR UTIL FACIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0661-0000-R | IPCRP1 | IPCRP1 | 0661-0000 | PLACE RUBBER SHEETS FOR UTIL FACIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10725 | 0 | 0 | 10725 | 0 | 10725 | 0 | 0 | N | 10725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0661-1000-L | IPCRP1 | IPCRP1 | 0661-1000 | Place Rubber Sheets for Util Facility | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2750 | 0 | 2750 | 2750 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0661-1000-S | IPCRP1 | IPCRP1 | 0661-1000 | Place Rubber Sheets for Util Facility | N | S |  | NR | A | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | N | 8250 | N | 0 | 0 | 0 | 8250 | 0 | 0 | 8250 | N | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8250 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | -8250 | 0 | 0 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 2750 | 0 | 2750 | 2750 | SF | 0 | 0 | 0 | 8250
Y | IPCRP1-0662-0000-L | IPCRP1 | IPCRP1 | 0662-0000 | EXTRA UTIL WORK COSTS ALLOWANCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0662-0000-R | IPCRP1 | IPCRP1 | 0662-0000 | EXTRA UTIL WORK COSTS ALLOWANCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5814.72 | 0 | 0 | 5814.72 | 0 | 5814.72 | 0 | 0 | N | 5814.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5814.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0662-1000-C | IPCRP1 | IPCRP1 | 0662-1000 | Extra Utility Work Costs Allowance (CABV) | N | C |  | NR | P | 5814.72 | 7525.44 | 7525.44 | 0 | 7525.44 | 0 | 0 | 0 | 0 | -7525.44 | Y | 0 | Y | 5814.72 | 0 | 0 | 5814.72 | 0 | 0 | 0 | Y | 5814.72 | 0 | 0 | 5814.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3634.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 129 | 0 | 129 | NA | 1 | 0 | 1 | 1 | FP | 7525.44 | 7525.44 | 0 | -7525.44
Y | IPCRP1-0662-1000-L | IPCRP1 | IPCRP1 | 0662-1000 | Extra Utility Work Costs Allowance (CABV) | N | L |  | UNIT | P | 0 | 4609.82 | 4609.82 | 4609.82 | 4609.82 | 88.6504 | 0 | 0 | 0 | 590.18 | Y | 5200 | Y | -5200 | 0 | 0 | 0 | 0 | 0 | 5200 | Y | -5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5200 | 2096.24 | 2513.58 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | -5200 | 0 | 0 | 5200 | 5200 | 0 | 0 | 0 | 0 | 0 | 40.67 | 40.67 | 0 | 38 | 2.67 | 40.67 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 590.18
Y | IPCRP1-0663-0000-L | IPCRP1 | IPCRP1 | 0663-0000 | EXTRA UTIL WORK COSTS ALLOWANCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0663-0000-R | IPCRP1 | IPCRP1 | 0663-0000 | EXTRA UTIL WORK COSTS ALLOWANCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 16690000 | 0 | 0 | 16690000 | 0 | 16690000 | 16690000 | 0 | N | 16690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0663-1000-C | IPCRP1 | IPCRP1 | 0663-1000 | Extra Utility Work Costs Allowance (CE) | N | C |  | NR | P | 16690000 | 74941.79 | 74941.79 | 74941.79 | 74941.79 | 74.9418 | 0 | 0 | 0 | 25058.21 | Y | 100000 | Y | 16590000 | 0 | 0 | 16690000 | 0 | 0 | 100000 | Y | 16590000 | 0 | 0 | 16690000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 363 | 279.31 | 642.31 | NA | 101520 | 90818 | 12982 | 103800 | HR | 50309.92 | -494.64 | 50804.56 | 25058.21
Y | IPCRP1-0663-1000-E | IPCRP1 | IPCRP1 | 0663-1000 | Extra Utility Work Costs Allowance (CE) | N | E |  | UNIT | A | 0 | 50052.02 | 50052.02 | 49257.23 | 50052.02 | 82.0954 | 0 | 0 | 0 | 9947.98 | Y | 60000 | Y | -60000 | 0 | 0 | 0 | 0 | 0 | 60000 | Y | -60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60000 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | -60000 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | -131 | 0 | NA | 101520 | 90818 | 12982 | 103800 | HR | 50052.02 | 794.79 | 49257.23 | 9947.98 | Allowance Equipment Budget
Y | IPCRP1-0663-1000-L | IPCRP1 | IPCRP1 | 0663-1000 | Extra Utility Work Costs Allowance (CE) | N | L |  | UNIT | P | 0 | 11658285.27 | 11658285.27 | 11658285.27 | 11658285.27 | 87.7222 | 0 | 0 | 0 | 1631714.73 | Y | 13290000 | Y | -13290000 | 0 | 0 | 0 | 0 | 0 | 13290000 | Y | -13290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13290000 | 99539.67 | 171028.59 | 13290000 | 0 | 0 | 0 | 0 | 0 | 0 | -13290000 | 0 | 0 | 13290000 | 13290000 | 0 | 0 | 0 | 0 | 0 | 103978.28 | 103978.28 | 0 | 91166 | 12812.28 | 103978.28 | HR | 101520 | 90818 | 12982 | 103800 | HR | 0 | 0 | 0 | 1631714.73 | null
Y | IPCRP1-0663-1000-M | IPCRP1 | IPCRP1 | 0663-1000 | Extra Utility Work Costs Allowance (CE) | N | M |  | UNIT | U | 0 | 145747.16 | 145747.16 | 136234.16 | 145747.16 | 64.4212 | 0 | 0 | 0 | 65727 | Y | 211474.16 | Y | -211474.16 | 0 | 0 | 0 | 0 | 0 | 211474.16 | Y | -211474.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -211474.16 | 0 | 0 | 211474.16 | 0 | 0 | 0 | 0 | 0 | 0 | -211474.16 | 0 | 0 | 211474.16 | 211474.16 | 0 | 0 | 0 | 0 | 0 | 403 | 403 | 0 | 403 | 0 | 403 | NA | 101520 | 90818 | 12982 | 103800 | HR | 145747.16 | 9513 | 136234.16 | 65727
Y | IPCRP1-0663-1000-S | IPCRP1 | IPCRP1 | 0663-1000 | Extra Utility Work Costs Allowance (CE) | N | S |  | UNIT | A | 0 | 1263277.2 | 1263277.2 | 1263277.09 | 1263277.2 | 90.2341 | 0 | 0 | 0 | 136722.8 | Y | 1400000 | Y | -1400000 | 0 | 0 | 0 | 0 | 0 | 1400000 | Y | -1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1400000 | 33575 | 27979.9 | 1400000 | 0 | 0 | 0 | 0 | 33575 | 0 | -1400000 | 0 | 0 | 1400000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8846 | -8846 | 0 | NA | 101520 | 90818 | 12982 | 103800 | HR | 1263277.2 | 0.11 | 1263277.09 | 136722.8
Y | IPCRP1-0664-0000-L | IPCRP1 | IPCRP1 | 0664-0000 | EXTRA UTIL WORK COSTS ALLOWANCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0664-0000-R | IPCRP1 | IPCRP1 | 0664-0000 | EXTRA UTIL WORK COSTS ALLOWANCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0664-1000-C | IPCRP1 | IPCRP1 | 0664-1000 | Extra Utility Work Costs Allowance (ECS) | N | C |  | NR | P | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | Y | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 153.85 | 103 | 0 | 103 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-0664-1000-L | IPCRP1 | IPCRP1 | 0664-1000 | Extra Utility Work Costs Allowance (ECS) | N | L |  | UNIT | P | 0 | 14295.93 | 14295.93 | 14295.93 | 14295.93 | 100 | 0 | 0 | 0 | 0 | Y | 14295.93 | Y | -14295.93 | 0 | 0 | 0 | 0 | 0 | 14295.93 | Y | -14295.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14295.93 | 0 | 0 | 14295.93 | 0 | 0 | 0 | 0 | 0 | 0 | -14295.93 | 0 | 0 | 14295.93 | 14295.93 | 0 | 0 | 0 | 0 | 0 | 103 | 103 | 0 | 103 | 0 | 103 | HR | 153.85 | 103 | 0 | 103 | HR | 0 | 0 | 0 | 0 | Capped out quantity paid by DDC at $20,000.00. TTD = $44,365,77, with balance paid directly by ECS.
Y | IPCRP1-0664-1000-S | IPCRP1 | IPCRP1 | 0664-1000 | Extra Utility Work Costs Allowance (ECS) | N | S |  | UNIT | A | 0 | 897.67 | 897.67 | 897.67 | 897.67 | 100 | 0 | 0 | 0 | 0 | Y | 897.67 | Y | -897.67 | 0 | 0 | 0 | 0 | 0 | 897.67 | Y | -897.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -897.67 | 0 | 0 | 897.67 | 0 | 0 | 0 | 0 | 0 | 0 | -897.67 | 0 | 0 | 897.67 | 897.67 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 8 | -5 | 3 | NA | 153.85 | 103 | 0 | 103 | HR | 897.67 | 0 | 897.67 | 0 | KMA CO
Y | IPCRP1-0665-0000-L | IPCRP1 | IPCRP1 | 0665-0000 | METAL ARCH MESH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0665-0000-R | IPCRP1 | IPCRP1 | 0665-0000 | METAL ARCH MESH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2000000 | 0 | 0 | 2000000 | 0 | 2000000 | 0 | 0 | N | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0666-0000-L | IPCRP1 | IPCRP1 | 0666-0000 | BROKEN STONE, LOOSE MEASURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0666-0000-R | IPCRP1 | IPCRP1 | 0666-0000 | BROKEN STONE, LOOSE MEASURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 288260 | 0 | 0 | 288260 | 0 | 288260 | 69854.4 | 0 | N | 288260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0667-0000-L | IPCRP1 | IPCRP1 | 0667-0000 | FOUND MATERIAL FOR CONC (TRUCK MEASURED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0667-0000-R | IPCRP1 | IPCRP1 | 0667-0000 | FOUND MATERIAL FOR CONC (TRUCK MEASURED) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 41820 | 0 | 0 | 41820 | 0 | 41820 | 0 | 0 | N | 41820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0667-1000-L | IPCRP1 | IPCRP1 | 0667-1000 | Found Material for Conc (Truck Measure) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 246 | 0 | 246 | 246 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0667-1000-S | IPCRP1 | IPCRP1 | 0667-1000 | Found Material for Conc (Truck Measure) | N | S |  | NR | A | 31011.69 | 437.84 | 437.84 | 437.84 | 437.84 | 1.4119 | 0 | 0 | 0 | 30573.85 | N | 31011.69 | N | 0 | 0 | 0 | 31011.69 | 0 | 0 | 31011.69 | N | 0 | 0 | 0 | 31011.69 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31011.69 | 0 | 0 | 31011.69 | 0 | 0 | 0 | 0 | 0 | 0 | -31011.69 | 0 | 0 | 31011.69 | 31011.69 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.5 | -3.5 | 0 | NA | 246 | 0 | 246 | 246 | CY | 437.84 | 0 | 437.84 | 30573.85
Y | IPCRP1-0668-0000-L | IPCRP1 | IPCRP1 | 0668-0000 | GRANITE BLOCK ON SAND - ACCESSIBLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0668-0000-R | IPCRP1 | IPCRP1 | 0668-0000 | GRANITE BLOCK ON SAND - ACCESSIBLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 180560 | 0 | 0 | 180560 | 0 | 180560 | 0 | 0 | N | 180560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0669-0000-L | IPCRP1 | IPCRP1 | 0669-0000 | CHAIN LINK FENCE 8ft-0in HT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0669-0000-R | IPCRP1 | IPCRP1 | 0669-0000 | CHAIN LINK FENCE 8ft-0in HT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300390 | 0 | 0 | 300390 | 0 | 300390 | 112689.6 | 0 | N | 300390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0670-0000-L | IPCRP1 | IPCRP1 | 0670-0000 | CHAIN LINK FENCE 12ft-0in HT, 2in MESH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0670-0000-R | IPCRP1 | IPCRP1 | 0670-0000 | CHAIN LINK FENCE 12ft-0in HT, 2in MESH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 203490 | 0 | 0 | 203490 | 0 | 203490 | 22800 | 0 | N | 203490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0671-0000-L | IPCRP1 | IPCRP1 | 0671-0000 | SINGLE GATE CLF, 8ft HT & OVER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0671-0000-R | IPCRP1 | IPCRP1 | 0671-0000 | SINGLE GATE CLF, 8ft HT & OVER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 146200 | 0 | 0 | 146200 | 0 | 146200 | 60200 | 0 | N | 146200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0672-0000-L | IPCRP1 | IPCRP1 | 0672-0000 | DOUBLE GATE CLF, 8ft HT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0672-0000-R | IPCRP1 | IPCRP1 | 0672-0000 | DOUBLE GATE CLF, 8ft HT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16000 | 0 | 0 | 16000 | 0 | 16000 | 16000 | 0 | N | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0673-0000-L | IPCRP1 | IPCRP1 | 0673-0000 | DOUBLE GATE CLF, 10ft HT & OVER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0673-0000-R | IPCRP1 | IPCRP1 | 0673-0000 | DOUBLE GATE CLF, 10ft HT & OVER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 100000 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0674-0000-L | IPCRP1 | IPCRP1 | 0674-0000 | TEMPORARY SHEETING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0674-0000-R | IPCRP1 | IPCRP1 | 0674-0000 | TEMPORARY SHEETING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 289500 | 0 | 0 | 289500 | 0 | 289500 | 32040.64 | 0 | N | 289500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0674-1000-L | IPCRP1 | IPCRP1 | 0674-1000 | Temp Sheeting - Self Perform/ All Other Subs | N | L |  | UNIT | P | 0 | 207499.57 | 207499.57 | 207499.57 | 207499.57 | 119.413 | 0 | 0 | 0 | -33733.19 | Y | 173766.38 | Y | -173766.38 | 0 | 0 | 0 | 0 | 0 | 173766.38 | Y | -173766.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -173766.38 | 12974.34 | 20758.86 | 173766.38 | 0 | 0 | 0 | 0 | 0 | 0 | -173766.38 | 0 | 0 | 173766.38 | 173766.38 | 0 | 0 | 0 | 0 | 0 | 1175.5 | 1175.5 | 0 | 1405.5 | -230 | 1175.5 | HR | 144750 | 6738.4 | 1770.31 | 8508.71 | SF | 0 | 0 | 0 | -33733.19 | Scope included in cc: 0832-1000, Parks Utility Sub (Akela) re-entered on 1-12-2024. IPC installed sheets behind Esplanade Demo
Y | IPCRP1-0674-1000-S | IPCRP1 | IPCRP1 | 0674-1000 | Temp Sheeting - Self Perform/ All Other Subs | N | S |  | NR | A | 1520671 | 1588.46 | 1588.46 | 1588.46 | 1588.46 | 286.0132 | 0 | 0 | 0 | -1033.08 | Y | 555.38 | Y | 1520115.62 | 0 | 0 | 1520671 | 0 | 0 | 555.38 | Y | 1520115.62 | 0 | 0 | 1520671 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -555.38 | 1033.08 | 0 | 555.38 | 0 | 0 | 0 | 0 | 1033.08 | 0 | -555.38 | 0 | 0 | 555.38 | 555.38 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4.5 | -4.5 | 0 | NA | 144750 | 6738.4 | 1770.31 | 8508.71 | SF | 1588.46 | 0 | 1588.46 | -1033.08
Y | IPCRP1-0675-0000-L | IPCRP1 | IPCRP1 | 0675-0000 | PARKS LEAF MH F&C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0675-0000-R | IPCRP1 | IPCRP1 | 0675-0000 | PARKS LEAF MH F&C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 59500 | 0 | 0 | 59500 | 0 | 59500 | 32300 | 0 | N | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0676-0000-L | IPCRP1 | IPCRP1 | 0676-0000 | PARKS LEAF CB F&C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0676-0000-R | IPCRP1 | IPCRP1 | 0676-0000 | PARKS LEAF CB F&C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42500 | 0 | 0 | 42500 | 0 | 42500 | 23800 | 0 | N | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0677-0000-L | IPCRP1 | IPCRP1 | 0677-0000 | DI SEWER PIPE - 12 DIA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0677-0000-R | IPCRP1 | IPCRP1 | 0677-0000 | DI SEWER PIPE - 12 DIA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13750 | 0 | 0 | 13750 | 0 | 13750 | 8294 | 0 | N | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0678-0000-L | IPCRP1 | IPCRP1 | 0678-0000 | DI SEWER PIPE - 8 DIA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0678-0000-R | IPCRP1 | IPCRP1 | 0678-0000 | DI SEWER PIPE - 8 DIA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 591750 | 0 | 0 | 591750 | 0 | 591750 | 294750 | 0 | N | 591750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0679-0000-L | IPCRP1 | IPCRP1 | 0679-0000 | DI SEWER PIPE - 4 DIA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0679-0000-R | IPCRP1 | IPCRP1 | 0679-0000 | DI SEWER PIPE - 4 DIA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50625 | 0 | 0 | 50625 | 0 | 50625 | 38022.75 | 0 | N | 50625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0680-0000-L | IPCRP1 | IPCRP1 | 0680-0000 | DI SEWER PIPE - 6 DIA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0680-0000-R | IPCRP1 | IPCRP1 | 0680-0000 | DI SEWER PIPE - 6 DIA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 87750 | 0 | 0 | 87750 | 0 | 87750 | 41600 | 0 | N | 87750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0681-0000-L | IPCRP1 | IPCRP1 | 0681-0000 | POLYETHYLENE CORRUGATED PIPE (18) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0681-0000-R | IPCRP1 | IPCRP1 | 0681-0000 | POLYETHYLENE CORRUGATED PIPE (18) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1820475 | 0 | 0 | 1820475 | 0 | 1820475 | 663525 | 0 | N | 1820475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1820475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0682-0000-L | IPCRP1 | IPCRP1 | 0682-0000 | POLYETHYLENE CORRUGATED PIPE (24) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0682-0000-R | IPCRP1 | IPCRP1 | 0682-0000 | POLYETHYLENE CORRUGATED PIPE (24) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 811250 | 0 | 0 | 811250 | 0 | 811250 | 0 | 0 | N | 811250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 811250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0683-0000-L | IPCRP1 | IPCRP1 | 0683-0000 | HYDRODYNAMIC SEPARATOR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0683-0000-R | IPCRP1 | IPCRP1 | 0683-0000 | HYDRODYNAMIC SEPARATOR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 416000 | 0 | 0 | 416000 | 0 | 416000 | 96000 | 0 | N | 416000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0684-0000-L | IPCRP1 | IPCRP1 | 0684-0000 | 5 CONC SW W/ SPEC SCORE & EXPOSED AGG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0684-0000-R | IPCRP1 | IPCRP1 | 0684-0000 | 5 CONC SW W/ SPEC SCORE & EXPOSED AGG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3407822 | 0 | 0 | 3407822 | 0 | 3407822 | 901621.38 | 0 | N | 3407822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3407822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0685-0000-L | IPCRP1 | IPCRP1 | 0685-0000 | 6 CONC SW W/ SPEC SCORE & EXPOSED AGG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0685-0000-R | IPCRP1 | IPCRP1 | 0685-0000 | 6 CONC SW W/ SPEC SCORE & EXPOSED AGG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3319623 | 0 | 0 | 3319623 | 0 | 3319623 | 1527332.76 | 0 | N | 3319623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3319623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0685-1000-L | IPCRP1 | IPCRP1 | 0685-1000 | 5 & 6 Exposed Aggregate Sidewalk (Prima Paving) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 277850 | 97550.67 | 180299.33 | 277850 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0685-1000-S | IPCRP1 | IPCRP1 | 0685-1000 | 5 & 6 Exposed Aggregate Sidewalk (Prima Paving) | N | S |  | NR | A | 6483609 | 7191280.24 | 7191280.24 | 2598571.84 | 7191280.24 | 36.2919 | 0 | 0 | 0 | 0 | N | 7160196 | N | -676587 | 0 | 0 | 6483609 | 0 | 0 | 7160196 | N | -676587 | 0 | 0 | 6483609 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7160196 | 0 | 0 | 7160196 | 0 | 0 | 0 | 0 | 0 | 0 | -7160196 | 0 | 0 | 7160196 | 7160196 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 97554.67 | -97553.67 | 1 | NA | 277850 | 97550.67 | 180299.33 | 277850 | SF | 7191280.24 | 4592708.4 | 2598571.84 | 0 | PRIMA PAVING @$7,160,196.00
Y | IPCRP1-0686-0000-L | IPCRP1 | IPCRP1 | 0686-0000 | GALVANIZED ESPLANADE SEA RAIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0686-0000-R | IPCRP1 | IPCRP1 | 0686-0000 | GALVANIZED ESPLANADE SEA RAIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5499000 | 0 | 0 | 5499000 | 0 | 5499000 | 3085596 | 0 | N | 5499000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5499000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0687-0000-L | IPCRP1 | IPCRP1 | 0687-0000 | ST SLAT DOUBLE SWING GATE, 8ft HT X 35ft W | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0687-0000-R | IPCRP1 | IPCRP1 | 0687-0000 | ST SLAT DOUBLE SWING GATE, 8ft HT X 35ft W | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42000 | 0 | 0 | 42000 | 0 | 42000 | 0 | 0 | N | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0687-1000-C | IPCRP1 | IPCRP1 | 0687-1000 | Sign-Rail-Fence Subcontractors (Multiple Subs) | N | C |  | UNIT | U | 0 | 19134 | 19134 | 19134 | 19134 | 100 | 0 | 0 | 0 | 0 | Y | 19134 | Y | -19134 | 0 | 0 | 0 | 0 | 0 | 19134 | Y | -19134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19134 | 0 | 0 | 19134 | 0 | 0 | 0 | 0 | 0 | 0 | -19134 | 0 | 0 | 19134 | 19134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | LS | 1 | 0.4 | 0.6 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0687-1000-L | IPCRP1 | IPCRP1 | 0687-1000 | Sign-Rail-Fence Subcontractors (Multiple Subs) | N | L |  | UNIT | P | 0 | 2841.47 | 2841.47 | 2841.47 | 2841.47 | 21.8575 | 0 | 0 | 0 | 10158.53 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 24 | 76 | 100 | HR | 1 | 0.4 | 0.6 | 1 | LS | 0 | 0 | 0 | 10158.53 | Change PMF (Sub) from $13,304,455.31 to $13, 504,455.31
Y | IPCRP1-0687-1000-S | IPCRP1 | IPCRP1 | 0687-1000 | Sign-Rail-Fence Subcontractors (Multiple Subs) | N | S |  | NR | A | 20159392 | 13661511.39 | 13661511.39 | 5376974.95 | 13661511.39 | 39.3586 | 0 | 0 | 0 | 0 | Y | 13661511.39 | Y | 6497880.61 | 0 | 0 | 20159392 | 0 | 0 | 13661511.39 | Y | 6497880.61 | 0 | 0 | 20159392 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13661511.39 | 16800 | 374171.25 | 13661511.39 | 0 | 0 | 0 | 0 | 0 | 0 | -13661511.39 | 0 | 0 | 13661511.39 | 13661511.39 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 55745.25 | 11279.8 | 67025.05 | NA | 1 | 0.4 | 0.6 | 1 | LS | 13661511.39 | 8284536.44 | 5376974.95 | 0 | 1. Eagle Fence ($100,000.00) East End Solutions ($6,594,275.00, thru SCO#3), National const Rentals ($136,021.06), United Fence & Guard Rail (#1,358,426.00), Yaboo Fence ($4,598,926,54, thru SCO#21). Total =$12,838,117.22. 2. Hold $200,000.00 for Traffic Signs (TBD). Change PMF (Sub) from $13,304,455.31 to $13, 504,455.31
Y | IPCRP1-0687-1010-L | IPCRP1 | IPCRP1 | 0687-1010 | F&I Perm Traffic Signs & Posts | N | L |  | UNIT | P | 0 | 4231 | 4231 | 4231 | 4231 | 6.5092 | 0 | 0 | 0 | 60769 | Y | 65000 | Y | -65000 | 0 | 0 | 0 | 0 | 0 | 65000 | Y | -65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -65000 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | -65000 | 0 | 0 | 65000 | 65000 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 38 | 462 | 500 | HR | 0 | 13 | 37 | 50 | EA | 0 | 0 | 0 | 60769
Y | IPCRP1-0687-1010-M | IPCRP1 | IPCRP1 | 0687-1010 | F&I Perm Traffic Signs & Posts | N | M |  | UNIT | U | 0 | 21722.56 | 21722.56 | 21722.56 | 21722.56 | 86.8902 | 0 | 0 | 0 | 3277.44 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | -760 | 0 | NA | 0 | 13 | 37 | 50 | EA | 20492.19 | -14.14 | 20506.33 | 3277.44 | This will cover all work associated with eight (8ea) contract items 6.83AA, 6.AB, 6.83AR, 6.83BA, 6.83 BB, 6.86 AA, 6.86 AB, 6.86 BA, 6.86 BB.
Y | IPCRP1-0687-1010-S | IPCRP1 | IPCRP1 | 0687-1010 | F&I Perm Traffic Signs & Posts | N | S |  | UNIT | A | 0 | 1512.58 | 1512.58 | 1512.58 | 1512.58 | 100 | 0 | 0 | 0 | 0 | N | 1512.58 | N | -1512.58 | 0 | 0 | 0 | 0 | 0 | 1512.58 | N | -1512.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1512.58 | 0 | 0 | 1512.58 | 0 | 0 | 0 | 0 | 0 | 0 | -1512.58 | 0 | 0 | 1512.58 | 1512.58 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 12 | NA | 0 | 13 | 37 | 50 | EA | 1512.58 | 0 | 1512.58 | 0
Y | IPCRP1-0688-0000-L | IPCRP1 | IPCRP1 | 0688-0000 | ST BLEACHER TYPE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0688-0000-R | IPCRP1 | IPCRP1 | 0688-0000 | ST BLEACHER TYPE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 104000 | 0 | 0 | 104000 | 0 | 104000 | 0 | 0 | N | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0689-0000-L | IPCRP1 | IPCRP1 | 0689-0000 | ST BLEACHER TYPE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0689-0000-R | IPCRP1 | IPCRP1 | 0689-0000 | ST BLEACHER TYPE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 176000 | 0 | 0 | 176000 | 0 | 176000 | 88000 | 0 | N | 176000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0689-1000-C | IPCRP1 | IPCRP1 | 0689-1000 | Steel Bleachers, Type 1 & Type 2 | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 16 | 4 | 12 | 16 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0689-1000-L | IPCRP1 | IPCRP1 | 0689-1000 | Steel Bleachers, Type 1 & Type 2 | N | L |  | UNIT | P | 0 | 6267 | 6267 | 6267 | 6267 | 7.5325 | 0 | 0 | 0 | 76933 | Y | 83200 | Y | -83200 | 0 | 0 | 0 | 0 | 0 | 83200 | Y | -83200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -83200 | 0 | 0 | 83200 | 0 | 0 | 0 | 0 | 0 | 0 | -83200 | 0 | 0 | 83200 | 83200 | 0 | 0 | 0 | 0 | 0 | 640 | 640 | 0 | 43.5 | 596.5 | 640 | HR | 16 | 4 | 12 | 16 | EA | 0 | 0 | 0 | 76933 | Refer to InProduction PO#3732. VS assuming 1 crew day (5 men) per bleacher
Y | IPCRP1-0689-1000-M | IPCRP1 | IPCRP1 | 0689-1000 | Steel Bleachers, Type 1 & Type 2 | N | M |  | UNIT | U | 0 | 438615 | 438615 | 254680 | 438615 | 58.0646 | 0 | 0 | 0 | 0 | Y | 438615 | Y | -438615 | 0 | 0 | 0 | 0 | 0 | 438615 | Y | -438615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -438615 | 0 | 0 | 438615 | 0 | 0 | 0 | 0 | 0 | 0 | -438615 | 0 | 0 | 438615 | 438615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.85 | -10.85 | 0 | NA | 16 | 4 | 12 | 16 | EA | 438615 | 183935 | 254680 | 0
Y | IPCRP1-0689-1000-S | IPCRP1 | IPCRP1 | 0689-1000 | Steel Bleachers, Type 1 & Type 2 | N | S |  | NR | A | 268936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 268936 | 0 | 0 | 268936 | 0 | 0 | 0 | Y | 268936 | 0 | 0 | 268936 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 16 | 4 | 12 | 16 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0690-0000-L | IPCRP1 | IPCRP1 | 0690-0000 | STONE TYPE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0690-0000-R | IPCRP1 | IPCRP1 | 0690-0000 | STONE TYPE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 582500 | 0 | 0 | 582500 | 0 | 582500 | 323425 | 0 | N | 582500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0691-0000-L | IPCRP1 | IPCRP1 | 0691-0000 | STONE TYPE 3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0691-0000-R | IPCRP1 | IPCRP1 | 0691-0000 | STONE TYPE 3 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2844000 | 0 | 0 | 2844000 | 0 | 2844000 | 1274000 | 0 | N | 2844000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2844000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0692-0000-L | IPCRP1 | IPCRP1 | 0692-0000 | BOULDER TYPE 4 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0692-0000-R | IPCRP1 | IPCRP1 | 0692-0000 | BOULDER TYPE 4 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 79200 | 0 | 0 | 79200 | 0 | 79200 | 40488 | 0 | N | 79200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-0693-0000-L | IPCRP1 | IPCRP1 | 0693-0000 | STONE VENEER TYPE 5A | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0693-0000-R | IPCRP1 | IPCRP1 | 0693-0000 | STONE VENEER TYPE 5A | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 61600 | 0 | 0 | 61600 | 0 | 61600 | 115121.95 | 0 | N | 61600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0694-0000-L | IPCRP1 | IPCRP1 | 0694-0000 | STONE VENEER TYPE 5B | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0694-0000-R | IPCRP1 | IPCRP1 | 0694-0000 | STONE VENEER TYPE 5B | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6475 | 0 | 0 | 6475 | 0 | 6475 | 53471.25 | 0 | N | 6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0695-0000-L | IPCRP1 | IPCRP1 | 0695-0000 | STONE VENEER TYPE 5C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0695-0000-R | IPCRP1 | IPCRP1 | 0695-0000 | STONE VENEER TYPE 5C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30100 | 0 | 0 | 30100 | 0 | 30100 | 47311.25 | 0 | N | 30100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0696-0000-L | IPCRP1 | IPCRP1 | 0696-0000 | STONE VENEER TYPE 5D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0696-0000-R | IPCRP1 | IPCRP1 | 0696-0000 | STONE VENEER TYPE 5D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2450 | 0 | 0 | 2450 | 0 | 2450 | 8435 | 0 | N | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0697-0000-L | IPCRP1 | IPCRP1 | 0697-0000 | ESPLANADE PC CONC SEATWALL MODULE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0697-0000-R | IPCRP1 | IPCRP1 | 0697-0000 | ESPLANADE PC CONC SEATWALL MODULE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 226000 | 0 | 0 | 226000 | 0 | 226000 | 74000 | 0 | N | 226000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0698-0000-L | IPCRP1 | IPCRP1 | 0698-0000 | ESPLANADE PC CONC SEATWALL MODULE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0698-0000-R | IPCRP1 | IPCRP1 | 0698-0000 | ESPLANADE PC CONC SEATWALL MODULE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 847000 | 0 | 0 | 847000 | 0 | 847000 | 292600 | 0 | N | 847000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0699-0000-L | IPCRP1 | IPCRP1 | 0699-0000 | ESPLANADE PC CONC SEATWALL MODULE 3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0699-0000-R | IPCRP1 | IPCRP1 | 0699-0000 | ESPLANADE PC CONC SEATWALL MODULE 3 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 84000 | 0 | 0 | 84000 | 0 | 84000 | 50400 | 0 | N | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0700-0000-L | IPCRP1 | IPCRP1 | 0700-0000 | ESPLANADE PC CONC SEATWALL MODULE 4 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0700-0000-R | IPCRP1 | IPCRP1 | 0700-0000 | ESPLANADE PC CONC SEATWALL MODULE 4 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 292000 | 0 | 0 | 292000 | 0 | 292000 | 172000 | 0 | N | 292000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0701-0000-L | IPCRP1 | IPCRP1 | 0701-0000 | ESPLANADE PC CONC SEATWALL MODULE 5 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0701-0000-R | IPCRP1 | IPCRP1 | 0701-0000 | ESPLANADE PC CONC SEATWALL MODULE 5 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 172800 | 0 | 0 | 172800 | 0 | 172800 | 46800 | 0 | N | 172800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0702-0000-L | IPCRP1 | IPCRP1 | 0702-0000 | ESPLANADE PC CONC SEATWALL MODULE 6 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0702-0000-R | IPCRP1 | IPCRP1 | 0702-0000 | ESPLANADE PC CONC SEATWALL MODULE 6 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 61200 | 0 | 0 | 61200 | 0 | 61200 | 34000 | 0 | N | 61200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0703-0000-L | IPCRP1 | IPCRP1 | 0703-0000 | ESPLANADE PC CONC SEATWALL MODULE 9 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0703-0000-R | IPCRP1 | IPCRP1 | 0703-0000 | ESPLANADE PC CONC SEATWALL MODULE 9 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 48600 | 0 | 0 | 48600 | 0 | 48600 | 48600 | 0 | N | 48600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0704-0000-L | IPCRP1 | IPCRP1 | 0704-0000 | ESPLANADE PC CONC SEATWALL MODULE 10 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0704-0000-R | IPCRP1 | IPCRP1 | 0704-0000 | ESPLANADE PC CONC SEATWALL MODULE 10 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 71400 | 0 | 0 | 71400 | 0 | 71400 | 71400 | 0 | N | 71400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0705-0000-L | IPCRP1 | IPCRP1 | 0705-0000 | ESPLANADE PC CONC SEATWALL MODULE 7 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0705-0000-R | IPCRP1 | IPCRP1 | 0705-0000 | ESPLANADE PC CONC SEATWALL MODULE 7 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40800 | 0 | 0 | 40800 | 0 | 40800 | 13600 | 0 | N | 40800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0706-0000-L | IPCRP1 | IPCRP1 | 0706-0000 | ESPLANADE PC CONC MODULE 8 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0706-0000-R | IPCRP1 | IPCRP1 | 0706-0000 | ESPLANADE PC CONC MODULE 8 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16800 | 0 | 0 | 16800 | 0 | 16800 | 5600 | 0 | N | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0706-1000-C | IPCRP1 | IPCRP1 | 0706-1000 | Conc Pavers & Stone Work Sub (VIF Corp) | N | C |  | UNIT | U | 0 | 2258497.28 | 2258497.28 | 437481.37 | 2258497.28 | 17.499 | 0 | 0 | 0 | 241544.72 | Y | 2500042 | Y | -2500042 | 0 | 0 | 0 | 0 | 0 | 2500042 | Y | -2500042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2500042 | 9591.25 | -3388 | 2500042 | 0 | 0 | 0 | 10442.47 | 0 | 0 | -2500042 | 0 | 0 | 2500042 | 2500042 | 0 | 0 | 0 | 0 | 0 | 86090.17 | 86090.17 | 0 | 65299.19 | 20790.98 | 86090.17 | NA | 891 | 0.57 | 0.43 | 1 | LS | 2249926.78 | 1821015.91 | 428910.87 | 241544.72
Y | IPCRP1-0706-1000-L | IPCRP1 | IPCRP1 | 0706-1000 | Conc Pavers & Stone Work Sub (VIF Corp) | N | L |  | UNIT | P | 0 | 168281.12 | 168281.12 | 168281.12 | 168281.12 | 37.0493 | 0 | 0 | 0 | 285927.74 | N | 454208.86 | N | -454208.86 | 0 | 0 | 0 | 0 | 0 | 454208.86 | N | -454208.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -454208.86 | 223.84 | 0 | 454208.86 | 0 | 0 | 0 | 0 | 0 | 0 | -454208.86 | 0 | 0 | 454208.86 | 454208.86 | 0 | 0 | 0 | 0 | 0 | 3232.43 | 3232.43 | 0 | 1199.5 | 2032.93 | 3232.43 | HR | 891 | 0.57 | 0.43 | 1 | LS | 0 | 0 | 0 | 285927.74
Y | IPCRP1-0706-1000-S | IPCRP1 | IPCRP1 | 0706-1000 | Conc Pavers & Stone Work Sub (VIF Corp) | N | S |  | NR | A | 12175609 | 8050451.06 | 8050451.06 | 5811415.12 | 8050451.06 | 67.0367 | 0 | 0 | 621125 | -2574.16 | Y | 8047876.9 | Y | 4127732.1 | 0 | 621125 | 12796734 | 0 | 621125 | 8669001.9 | Y | 4127732.1 | 0 | 0 | 11554484 | 0 | 621125 | 0 | 0 | 0 | N | 0 | 0 | -8669001.9 | 0 | 110247.14 | 8047876.9 | 0 | 0 | 0 | 0 | 0 | 0 | -8669001.9 | 0 | 0 | 8047876.9 | 8047876.9 | 0 | 0 | 0 | 890 | 0 | 0 |  | 1780 | 400193.66 | -363743.13 | 36450.53 | NA | 1781 | 0.57 | 0.43 | 1 | LS | 8050451.06 | 2239035.94 | 5811415.12 | 618550.84 | VIF SC (5.036M), United Pavers SC (3.01M) VIF Base Contract @$10,106,201.76
Y | IPCRP1-0706-1005-L | IPCRP1 | IPCRP1 | 0706-1005 | Self-Perform Esplanade Seat-Wall Mods 1-10 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327037.5 | Y | 327037.5 | Y | -327037.5 | 0 | 0 | 0 | 0 | 0 | 327037.5 | Y | -327037.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -327037.5 | 0 | 0 | 327037.5 | 0 | 0 | 0 | 0 | 0 | 0 | -327037.5 | 0 | 0 | 327037.5 | 327037.5 | 0 | 0 | 0 | 0 | 0 | 2422.5 | 2422.5 | 0 | 0 | 2422.5 | 2422.5 | HR | 0 | 0 | 510 | 510 | EA | 0 | 0 | 0 | 327037.5 | 0.5 MH to unload, 4.0 MH to set. 0.25 MH to caulk joints = 4.75 MH/ea total (see Winston email 12/5/25 for takeoff)
Y | IPCRP1-0706-1006-L | IPCRP1 | IPCRP1 | 0706-1006 | Self-Perform Stone Types 2-3-4 (post VIF) | N | L |  | UNIT | P | 0 | 47970.89 | 47970.89 | 47970.89 | 47970.89 | 7.9054 | 0 | 0 | 0 | 558838.2 | Y | 606809.09 | Y | -606809.09 | 0 | 0 | 0 | 0 | 0 | 606809.09 | Y | -606809.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -606809.09 | 21986.61 | 2287.66 | 606809.09 | 0 | 0 | 0 | 0 | 0 | 0 | -606809.09 | 0 | 0 | 606809.09 | 606809.09 | 0 | 0 | 0 | 0 | 0 | 4508 | 4508 | 0 | 526 | 3982 | 4508 | HR | 0 | 29 | 615 | 644 | EA | 0 | 0 | 0 | 558838.2 | 1.0 MH to unload, 4.0 MH to set. 2.0 MH to caulk joints = 7.0 MH/ea total (see Winston email 12/5/25 for takeoff)
N | IPCRP1-0706-1006-M | IPCRP1 | IPCRP1 | 0706-1006 | Self-Perform Stone Types 2-3-4 (post VIF) | N | M |  | UNIT | U | 0 | 6118.7 | 6118.7 | 3604.64 | 6118.7 | 58.9119 | 0 | 0 | 0 | 0 | N | 6118.7 | N | -6118.7 | 0 | 0 | 0 | 0 | 0 | 6118.7 | N | -6118.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6118.7 | 3604.64 | 0 | 0 | -6118.7 | 0 | 0 | 6118.7 | 0 | 0 | -6118.7 | 0 | 0 | 6118.7 | 6118.7 | 0 | 0 | 0 | 0 | 0 | 190 | 190 | 0 | 172 | 18 | 190 | NA | 0 | 29 | 615 | 644 | EA | 6118.7 | 2514.06 | 3604.64 | 0
Y | IPCRP1-0706-1006-S | IPCRP1 | IPCRP1 | 0706-1006 | Self-Perform Stone Types 2-3-4 (post VIF) | N | S |  | UNIT | A | 0 | 1774.06 | 1774.06 | 1774.06 | 1774.06 | 100 | 0 | 0 | 0 | 0 | N | 1774.06 | N | -1774.06 | 0 | 0 | 0 | 0 | 0 | 1774.06 | N | -1774.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1774.06 | 0 | 0 | 1774.06 | 0 | 0 | 0 | 0 | 0 | 0 | -1774.06 | 0 | 0 | 1774.06 | 1774.06 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 14 | 0 | 14 | NA | 0 | 29 | 615 | 644 | EA | 1774.06 | 0 | 1774.06 | 0
Y | IPCRP1-0706-1010-C | IPCRP1 | IPCRP1 | 0706-1010 | Heat Support for VIF Work | N | C |  | UNIT | U | 0 | 8279.95 | 8279.95 | 8279.75 | 8279.95 | 99.9976 | 0 | 0 | 0 | 0 | Y | 8279.95 | Y | -8279.95 | 0 | 0 | 0 | 0 | 0 | 8279.95 | Y | -8279.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8279.95 | 0 | 0 | 8279.95 | 0 | 0 | 0 | 0 | 0 | 0 | -8279.95 | 0 | 0 | 8279.95 | 8279.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 34 | 0 | 34 | SH | 8279.95 | 0.2 | 8279.75 | 0
Y | IPCRP1-0706-1010-L | IPCRP1 | IPCRP1 | 0706-1010 | Heat Support for VIF Work | N | L |  | UNIT | P | 0 | 84124.07 | 84124.07 | 84124.07 | 84124.07 | 100 | 0 | 0 | 0 | 0 | Y | 84124.07 | Y | -84124.07 | 0 | 0 | 0 | 0 | 0 | 84124.07 | Y | -84124.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -84124.07 | 0 | 0 | 84124.07 | 0 | 0 | 0 | 0 | 0 | 0 | -84124.07 | 0 | 0 | 84124.07 | 84124.07 | 0 | 0 | 0 | 0 | 0 | 745.5 | 745.5 | 0 | 745.5 | 0 | 745.5 | HR | 0 | 34 | 0 | 34 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-0706-1010-S | IPCRP1 | IPCRP1 | 0706-1010 | Heat Support for VIF Work | N | S |  | UNIT | A | 0 | 3473.35 | 3473.35 | 3473.35 | 3473.35 | 100 | 0 | 0 | 0 | 0 | N | 3473.35 | N | -3473.35 | 0 | 0 | 0 | 0 | 0 | 3473.35 | N | -3473.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3473.35 | 0 | 0 | 3473.35 | 0 | 0 | 0 | 0 | 0 | 0 | -3473.35 | 0 | 0 | 3473.35 | 3473.35 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 28 | 36 | 64 | NA | 0 | 34 | 0 | 34 | SH | 3473.35 | 0 | 3473.35 | 0
Y | IPCRP1-0707-0000-L | IPCRP1 | IPCRP1 | 0707-0000 | BENCH, 1939 WF RPL SLATS, 4ft LENGTH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0707-0000-R | IPCRP1 | IPCRP1 | 0707-0000 | BENCH, 1939 WF RPL SLATS, 4ft LENGTH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18000 | 0 | 0 | 18000 | 0 | 18000 | 18000 | 0 | N | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0708-0000-L | IPCRP1 | IPCRP1 | 0708-0000 | PNEUMATIC EXCAV AROUND TREES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0708-0000-R | IPCRP1 | IPCRP1 | 0708-0000 | PNEUMATIC EXCAV AROUND TREES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12375 | 0 | 0 | 12375 | 0 | 12375 | 3370.5 | 0 | N | 12375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0709-0000-L | IPCRP1 | IPCRP1 | 0709-0000 | CIRCULAR TABLES & CHAIRS TYPE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0709-0000-R | IPCRP1 | IPCRP1 | 0709-0000 | CIRCULAR TABLES & CHAIRS TYPE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 44400 | 0 | 0 | 44400 | 0 | 44400 | 28990 | 0 | N | 44400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0710-0000-L | IPCRP1 | IPCRP1 | 0710-0000 | CIRCULAR TABLE & CHAIRS TYPE 1, ACCESSIBLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0710-0000-R | IPCRP1 | IPCRP1 | 0710-0000 | CIRCULAR TABLE & CHAIRS TYPE 1, ACCESSIBLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 29600 | 0 | 0 | 29600 | 0 | 29600 | 18813 | 0 | N | 29600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0711-0000-L | IPCRP1 | IPCRP1 | 0711-0000 | CIRCULAR TABLES & CHAIRS TYPE 1, W/UMBRELLA HOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0711-0000-R | IPCRP1 | IPCRP1 | 0711-0000 | CIRCULAR TABLES & CHAIRS TYPE 1, W/UMBRELLA HOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 198000 | 0 | 0 | 198000 | 0 | 198000 | 171477 | 0 | N | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0712-0000-L | IPCRP1 | IPCRP1 | 0712-0000 | CIRCULAR TABLES & CHAIRS TYPE 1, ACCESS, W/UMB HO | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0712-0000-R | IPCRP1 | IPCRP1 | 0712-0000 | CIRCULAR TABLES & CHAIRS TYPE 1, ACCESS, W/UMB HO | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 99000 | 0 | 0 | 99000 | 0 | 99000 | 85318 | 0 | N | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0713-0000-L | IPCRP1 | IPCRP1 | 0713-0000 | ST UMBRELLA SURFACE MOUNT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0713-0000-R | IPCRP1 | IPCRP1 | 0713-0000 | ST UMBRELLA SURFACE MOUNT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 413400 | 0 | 0 | 413400 | 0 | 413400 | 363760 | 0 | N | 413400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0714-0000-L | IPCRP1 | IPCRP1 | 0714-0000 | ST UMBRELLA SLEEVE & BRACKET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0714-0000-R | IPCRP1 | IPCRP1 | 0714-0000 | ST UMBRELLA SLEEVE & BRACKET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 74200 | 0 | 0 | 74200 | 0 | 74200 | 74200 | 0 | N | 74200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0715-0000-L | IPCRP1 | IPCRP1 | 0715-0000 | ST UMBRELLA SURFACE TABLE MOUNT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0715-0000-R | IPCRP1 | IPCRP1 | 0715-0000 | ST UMBRELLA SURFACE TABLE MOUNT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 190800 | 0 | 0 | 190800 | 0 | 190800 | 170028 | 0 | N | 190800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0716-0000-L | IPCRP1 | IPCRP1 | 0716-0000 | BIGBELLY BIN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0716-0000-R | IPCRP1 | IPCRP1 | 0716-0000 | BIGBELLY BIN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 462300 | 0 | 0 | 462300 | 0 | 462300 | 351982.54 | 0 | N | 462300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0717-0000-L | IPCRP1 | IPCRP1 | 0717-0000 | M+O PRE-FABRICATED BUILDING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0717-0000-R | IPCRP1 | IPCRP1 | 0717-0000 | M+O PRE-FABRICATED BUILDING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2000000 | 0 | 0 | 2000000 | 0 | 2000000 | 1074350 | 0 | N | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1000-E | IPCRP1 | IPCRP1 | 0717-1000 | Excavate for M&O Pre-Fab Bldg | N | E |  | NR | P | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3200 | 0 | 0 | 3200 | 0 | 0 | 0 | Y | 3200 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 600 | 135.71 | 0 | 135.71 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1000-L | IPCRP1 | IPCRP1 | 0717-1000 | Excavate for M&O Pre-Fab Bldg | N | L |  | NR | P | 11097.52 | 12710.83 | 12710.83 | 12710.83 | 12710.83 | 121.1937 | 0 | 0 | 0 | -2222.8 | Y | 10488.03 | Y | 609.49 | 0 | 0 | 11097.52 | 0 | 0 | 10488.03 | Y | 609.49 | 0 | 0 | 11097.52 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10488.03 | 2222.8 | 4359.97 | 10488.03 | 0 | 0 | 0 | 0 | 0 | 0 | -10488.03 | 0 | 0 | 10488.03 | 10488.03 | 0 | 0 | 0 | 96 | 0 | 90 | 90 | 96 | 111 | -21 | 90 | HR | 600 | 135.71 | 0 | 135.71 | CY | 0 | 0 | 0 | -2222.8
N | IPCRP1-0717-1000-S | IPCRP1 | IPCRP1 | 0717-1000 | Excavate for M&O Pre-Fab Bldg | N | S |  | UNIT | A | 0 | 391.24 | 391.24 | 391.24 | 391.24 | 100 | 0 | 0 | 0 | 0 | N | 391.24 | N | -391.24 | 0 | 0 | 0 | 0 | 0 | 391.24 | N | -391.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -391.24 | 129.13 | 262.11 | 391.24 | 0 | 0 | 0 | 0 | 129.13 | 0 | -391.24 | 0 | 0 | 391.24 | 391.24 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | NA | 600 | 135.71 | 0 | 135.71 | CY | 391.24 | 0 | 391.24 | 0
Y | IPCRP1-0717-1010-L | IPCRP1 | IPCRP1 | 0717-1010 | Form & Strip for M&O Pre-Fab Bldg | N | L |  | NR | P | 48776.67 | 110877.08 | 110877.08 | 110877.08 | 110877.08 | 129.4945 | 0 | 0 | 0 | -25254.09 | Y | 85622.99 | Y | -36846.32 | 0 | 0 | 48776.67 | 0 | 0 | 85622.99 | Y | -36846.32 | 0 | 0 | 48776.67 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -85622.99 | 25254.09 | 15428.38 | 85622.99 | 0 | 0 | 0 | 0 | 0 | 0 | -85622.99 | 0 | 0 | 85622.99 | 85622.99 | 0 | 0 | 0 | 412.8 | 0 | 661 | 661 | 412.8 | 898.5 | -237.5 | 661 | HR | 2064 | 2471.12 | 0 | 2471.12 | SF | 0 | 0 | 0 | -25254.09
Y | IPCRP1-0717-1010-S | IPCRP1 | IPCRP1 | 0717-1010 | Form & Strip for M&O Pre-Fab Bldg | N | S |  | UNIT | A | 0 | 2531.74 | 2531.74 | 2531.74 | 2531.74 | 129.7909 | 0 | 0 | 0 | 0 | N | 1950.63 | N | -1950.63 | 0 | 0 | 0 | 0 | 0 | 1950.63 | N | -1950.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1950.63 | 581.11 | 0 | 1950.63 | 0 | 0 | 0 | 0 | 581.11 | 0 | -1950.63 | 0 | 0 | 1950.63 | 1950.63 | 0 | 0 | 0 | 0 | 0 | 15.5 | 15.5 | 0 | 15.5 | 0 | 15.5 | NA | 2064 | 2471.12 | 0 | 2471.12 | SF | 2531.74 | 0 | 2531.74 | 0
Y | IPCRP1-0717-1020-E | IPCRP1 | IPCRP1 | 0717-1020 | Place Conc Found for M&O Pre-Fab Bldg | N | E |  | NR | P | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | Y | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 166 | 102.09 | 0 | 102.09 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1020-L | IPCRP1 | IPCRP1 | 0717-1020 | Place Conc Found for M&O Pre-Fab Bldg | N | L |  | NR | P | 15428.56 | 25810.21 | 25810.21 | 25810.21 | 25810.21 | 117.267 | 0 | 0 | 0 | -3800.43 | Y | 22009.78 | Y | -6581.22 | 0 | 0 | 15428.56 | 0 | 0 | 22009.78 | Y | -6581.22 | 0 | 0 | 15428.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22009.78 | 3800.43 | 3911.98 | 22009.78 | 0 | 0 | 0 | 0 | 0 | 0 | -22009.78 | 0 | 0 | 22009.78 | 22009.78 | 0 | 0 | 0 | 144 | 0 | 170 | 170 | 144 | 205 | -35 | 170 | HR | 166 | 102.09 | 0 | 102.09 | CY | 0 | 0 | 0 | -3800.43
Y | IPCRP1-0717-1020-S | IPCRP1 | IPCRP1 | 0717-1020 | Place Conc Found for M&O Pre-Fab Bldg | N | S |  | UNIT | A | 0 | 646.08 | 646.08 | 646.08 | 646.08 | 124.9792 | 0 | 0 | 0 | 0 | N | 516.95 | N | -516.95 | 0 | 0 | 0 | 0 | 0 | 516.95 | N | -516.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -516.95 | 129.13 | 0 | 516.95 | 0 | 0 | 0 | 0 | 129.13 | 0 | -516.95 | 0 | 0 | 516.95 | 516.95 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 166 | 102.09 | 0 | 102.09 | CY | 646.08 | 0 | 646.08 | 0
Y | IPCRP1-0717-1030-E | IPCRP1 | IPCRP1 | 0717-1030 | Place Backfill Material for M&O Pre-Fab Bldg | N | E |  | NR | P | 5852.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5852.8 | 0 | 0 | 5852.8 | 0 | 0 | 0 | Y | 5852.8 | 0 | 0 | 5852.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 472 | 180.23 | 291.77 | 472 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1030-L | IPCRP1 | IPCRP1 | 0717-1030 | Place Backfill Material for M&O Pre-Fab Bldg | N | L |  | NR | P | 23995.06 | 29314.48 | 29314.48 | 29314.48 | 29314.48 | 122.1688 | 0 | 0 | 0 | 0 | N | 23995.06 | N | 0 | 0 | 0 | 23995.06 | 0 | 0 | 23995.06 | N | 0 | 0 | 0 | 23995.06 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23995.06 | 9167.69 | 0 | 23995.06 | 0 | 0 | 0 | 0 | 0 | 0 | -23995.06 | 0 | 0 | 23995.06 | 23995.06 | 0 | 0 | 0 | 226.56 | 0 | 226.56 | 226.56 | 226.56 | 237 | -10.44 | 226.56 | HR | 472 | 180.23 | 291.77 | 472 | CY | 0 | 0 | 0 | 0
N | IPCRP1-0717-1030-S | IPCRP1 | IPCRP1 | 0717-1030 | Place Backfill Material for M&O Pre-Fab Bldg | N | S |  | UNIT | A | 0 | 516.54 | 516.54 | 516.54 | 516.54 | 100 | 0 | 0 | 0 | 0 | N | 516.54 | N | -516.54 | 0 | 0 | 0 | 0 | 0 | 516.54 | N | -516.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -516.54 | 516.54 | 0 | 516.54 | 0 | 0 | 0 | 0 | 516.54 | 0 | -516.54 | 0 | 0 | 516.54 | 516.54 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | NA | 472 | 180.23 | 291.77 | 472 | CY | 516.54 | 0 | 516.54 | 0
Y | IPCRP1-0717-1040-E | IPCRP1 | IPCRP1 | 0717-1040 | Install Doors at M&O#2 | N | E |  | NR | P | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | Y | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 16 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1040-L | IPCRP1 | IPCRP1 | 0717-1040 | Install Doors at M&O#2 | N | L |  | NR | P | 12832 | 16449.49 | 16449.49 | 16449.49 | 16449.49 | 48.9568 | 0 | 0 | 0 | 17150.51 | Y | 33600 | Y | -20768 | 0 | 0 | 12832 | 0 | 0 | 33600 | Y | -20768 | 0 | 0 | 12832 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -33600 | 0 | 0 | 33600 | 0 | 0 | 0 | 0 | 0 | 0 | -33600 | 0 | 0 | 33600 | 33600 | 0 | 0 | 0 | 116 | 0 | 240.01 | 240.01 | 116 | 115 | 125.01 | 240.01 | HR | 16 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 17150.51
Y | IPCRP1-0717-1050-C | IPCRP1 | IPCRP1 | 0717-1050 | Furn Forms for M&O Pre-Fab Bldg Foundation | N | C |  | NR | P | 6742 | 37057.2 | 37057.2 | 36448.13 | 37057.2 | 100 | 0 | 0 | 0 | -609.07 | Y | 36448.13 | Y | -29706.13 | 0 | 0 | 6742 | 0 | 0 | 36448.13 | Y | -29706.13 | 0 | 0 | 6742 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36448.13 | 0 | 8590.13 | 36448.13 | 0 | 0 | 0 | 0 | 1768.13 | 0 | -36448.13 | 0 | 0 | 36448.13 | 36448.13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4568.28 | 0 | 4568.28 | NA | 2064 | 2064 | 0 | 2064 | SF | 37057.2 | 609.07 | 36448.13 | -609.07
Y | IPCRP1-0717-1050-L | IPCRP1 | IPCRP1 | 0717-1050 | Furn Forms for M&O Pre-Fab Bldg Foundation | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2064 | 2064 | 0 | 2064 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1060-L | IPCRP1 | IPCRP1 | 0717-1060 | Furn Doors | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 4 | 4 | 0 | 4 | EA | 0 | 0 | 0 | 0 | AT (12/12) confirmed by Jbo, these doors for M&O Bldg
Y | IPCRP1-0717-1060-M | IPCRP1 | IPCRP1 | 0717-1060 | Furn Doors | N | M |  | NR | P | 14111 | 40415.14 | 40415.14 | 28923.2 | 40415.14 | 71.5653 | 0 | 0 | 0 | 0 | Y | 40415.14 | Y | -26304.14 | 0 | 0 | 14111 | 0 | 0 | 40415.14 | Y | -26304.14 | 0 | 0 | 14111 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -40415.14 | 0 | 0 | 40415.14 | 0 | 0 | 0 | 0 | 0 | 0 | -40415.14 | 0 | 0 | 40415.14 | 40415.14 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 14432.2 | -10166.1 | 4266.1 | NA | 4 | 4 | 0 | 4 | EA | 40415.14 | 11491.94 | 28923.2 | 0
Y | IPCRP1-0717-1070-L | IPCRP1 | IPCRP1 | 0717-1070 | Furn St Pipe Bollards | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 24 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | This cc: can be closed (LV (6/16/25). All Building Bollards were coded and will be included for payment under item/cc = 0914-1000/ PK-ESCR 737/ 0914-1000 - St Pipe Bollards.
Y | IPCRP1-0717-1070-M | IPCRP1 | IPCRP1 | 0717-1070 | Furn St Pipe Bollards | N | M |  | NR | P | 69000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 68990 | 0 | 0 | 69000 | 0 | 0 | 10 | Y | 68990 | 0 | 0 | 69000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 24 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 10
Y | IPCRP1-0717-1080-L | IPCRP1 | IPCRP1 | 0717-1080 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1080-S | IPCRP1 | IPCRP1 | 0717-1080 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | S |  | NR | P | 37895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 37895 | 0 | 0 | 37895 | 0 | 0 | 0 | N | 37895 | 0 | 0 | 37895 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | Work included in Sheet Applied Waterproofing Membrane Sub (D-Star), cost code 0178-1000
Y | IPCRP1-0717-1090-L | IPCRP1 | IPCRP1 | 0717-1090 | Painting/ Lead Abatement Sub (Crossroads) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.63 | 0.37 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1090-S | IPCRP1 | IPCRP1 | 0717-1090 | Painting/ Lead Abatement Sub (Crossroads) | N | S |  | NR | A | 6000 | 1372522.72 | 1372522.72 | 716528.79 | 1372522.72 | 72.2698 | 0 | 0 | 0 | -381059 | Y | 991463.72 | Y | -985463.72 | 0 | 0 | 6000 | 0 | 0 | 991463.72 | Y | -985463.72 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -991463.72 | 0 | 0 | 991463.72 | 0 | 0 | 0 | 372702 | 0 | 0 | -991463.72 | 0 | 0 | 991463.72 | 991463.72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 27230.65 | -27229.65 | 1 | NA | 1 | 0.63 | 0.37 | 1 | LS | 1372522.72 | 655993.93 | 716528.79 | -381059 | CROSSROADS Base Contract @$450,000.00
Y | IPCRP1-0717-1100-C | IPCRP1 | IPCRP1 | 0717-1100 | OH Door Sub | N | C |  | UNIT | U | 0 | 2475 | 2475 | 2475 | 2475 | 100 | 0 | 0 | 0 | 0 | N | 2475 | N | -2475 | 0 | 0 | 0 | 0 | 0 | 2475 | N | -2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2475 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | -2475 | 0 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 2 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1100-L | IPCRP1 | IPCRP1 | 0717-1100 | OH Door Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0717-1100-S | IPCRP1 | IPCRP1 | 0717-1100 | OH Door Sub | N | S |  | NR | A | 45500 | 169900 | 169900 | 84950 | 169900 | 50 | 0 | 0 | 0 | 0 | Y | 169900 | Y | -124400 | 0 | 0 | 45500 | 0 | 0 | 169900 | Y | -124400 | 0 | 0 | 45500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -169900 | 0 | 0 | 169900 | 0 | 0 | 0 | 0 | 0 | 0 | -169900 | 0 | 0 | 169900 | 169900 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | -1 | 1 | NA | 2 | 2 | 2 | 4 | EA | 169900 | 84950 | 84950 | 0 | Need to delete Able Rolling Steel Door subcontract (99K). PMF is for new sub, City Store Gate (169.9K), as Able could not fabricate to spec.
Y | IPCRP1-0717-1110-L | IPCRP1 | IPCRP1 | 0717-1110 | Caulking for M&O Building PC Joints | N | L |  | UNIT | P | 0 | 442.82 | 442.82 | 442.82 | 442.82 | 100 | 0 | 0 | 0 | 0 | Y | 442.82 | Y | -442.82 | 0 | 0 | 0 | 0 | 0 | 442.82 | Y | -442.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -442.82 | 0 | 0 | 442.82 | 0 | 0 | 0 | 0 | 0 | 0 | -442.82 | 0 | 0 | 442.82 | 442.82 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | sub is Schnell Contracting
Y | IPCRP1-0717-1110-S | IPCRP1 | IPCRP1 | 0717-1110 | Caulking for M&O Building PC Joints | N | S |  | UNIT | A | 0 | 36000 | 36000 | 13500 | 36000 | 37.5 | 0 | 0 | 0 | 0 | N | 36000 | N | -36000 | 0 | 0 | 0 | 0 | 0 | 36000 | N | -36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36000 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | -36000 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0.38 | 0.62 | 1 | NA | 0 | 0 | 1 | 1 | LS | 36000 | 22500 | 13500 | 0
Y | IPCRP1-0717-1120-L | IPCRP1 | IPCRP1 | 0717-1120 | F&I Flashing at M&O Buildings 2 & 3 | N | L |  | UNIT | P | 0 | 6140.55 | 6140.55 | 6140.55 | 6140.55 | 37.9046 | 0 | 0 | 0 | 10059.45 | Y | 16200 | Y | -16200 | 0 | 0 | 0 | 0 | 0 | 16200 | Y | -16200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16200 | 0 | 0 | 16200 | 0 | 0 | 0 | 0 | 0 | 0 | -16200 | 0 | 0 | 16200 | 16200 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 45 | 75 | 120 | HR | 0 | 1 | 1 | 2 | EA | 0 | 0 | 0 | 10059.45
Y | IPCRP1-0717-1120-M | IPCRP1 | IPCRP1 | 0717-1120 | F&I Flashing at M&O Buildings 2 & 3 | N | M |  | UNIT | U | 0 | 8355.3 | 8355.3 | 8338.85 | 8355.3 | 100 | 0 | 0 | 0 | -16.45 | Y | 8338.85 | Y | -8338.85 | 0 | 0 | 0 | 0 | 0 | 8338.85 | Y | -8338.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8338.85 | 0 | 3648 | 8338.85 | 0 | 0 | 0 | 0 | 3648 | 0 | -8338.85 | 0 | 0 | 8338.85 | 8338.85 | 0 | 0 | 0 | 0 | 0 | 94.7 | 94.7 | 0 | 94.7 | 0 | 94.7 | NA | 0 | 1 | 1 | 2 | EA | 8355.3 | 16.45 | 8338.85 | -16.45
Y | IPCRP1-0717-1130-L | IPCRP1 | IPCRP1 | 0717-1130 | DOB Site Protection for Buildings (Up & Down) | N | L |  | UNIT | P | 0 | 10520.5 | 10520.5 | 10520.5 | 10520.5 | 20.2317 | 0 | 0 | 0 | 41479.5 | Y | 52000 | Y | -52000 | 0 | 0 | 0 | 0 | 0 | 52000 | Y | -52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -52000 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | -52000 | 0 | 0 | 52000 | 52000 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 91.5 | 308.5 | 400 | HR | 0 | 0.5 | 3.5 | 4 | EA | 0 | 0 | 0 | 41479.5 | This was excluded from ASW work scope and not picked up in bid estimate.
Y | IPCRP1-0717-1140-L | IPCRP1 | IPCRP1 | 0717-1140 | F&I SIP Roof Decking at M&O 2 & 3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | Y | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 30000 | Y | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 200 | 200 | HR | 0 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 30000 | This was excluded from ASW work scope and not picked up in bid estimate.
Y | IPCRP1-0717-1140-M | IPCRP1 | IPCRP1 | 0717-1140 | F&I SIP Roof Decking at M&O 2 & 3 | N | M |  | UNIT | U | 0 | 41536.5 | 41536.5 | 41536.5 | 41536.5 | 100 | 0 | 0 | 0 | 0 | Y | 41536.5 | Y | -41536.5 | 0 | 0 | 0 | 0 | 0 | 41536.5 | Y | -41536.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -41536.5 | 0 | 0 | 41536.5 | 0 | 0 | 0 | 0 | 0 | 0 | -41536.5 | 0 | 0 | 41536.5 | 41536.5 | 0 | 0 | 0 | 0 | 0 | 2849 | 2849 | 0 | 2849 | 0 | 2849 | NA | 0 | 0 | 2 | 2 | EA | 41536.5 | 0 | 41536.5 | 0
Y | IPCRP1-0718-0000-L | IPCRP1 | IPCRP1 | 0718-0000 | M+O FUEL STORAGE CABINET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0718-0000-R | IPCRP1 | IPCRP1 | 0718-0000 | M+O FUEL STORAGE CABINET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19200 | 0 | 0 | 19200 | 0 | 19200 | 0 | 0 | N | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0718-1000-L | IPCRP1 | IPCRP1 | 0718-1000 | M+O FUEL STORAGE CABINET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 12 | 0 | 12 | 12 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0718-1000-S | IPCRP1 | IPCRP1 | 0718-1000 | M+O FUEL STORAGE CABINET | N | S |  | NR | A | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | N | 18000 | N | 0 | 0 | 0 | 18000 | 0 | 0 | 18000 | N | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18000 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | -18000 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 12 | 0 | 12 | 12 | EA | 0 | 0 | 0 | 18000
Y | IPCRP1-0719-0000-L | IPCRP1 | IPCRP1 | 0719-0000 | CHAIN LINK FENCE 16ft HT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0719-0000-R | IPCRP1 | IPCRP1 | 0719-0000 | CHAIN LINK FENCE 16ft HT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 624000 | 0 | 0 | 624000 | 0 | 624000 | 266812.5 | 0 | N | 624000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0720-0000-L | IPCRP1 | IPCRP1 | 0720-0000 | SINGLE GATE FOR CLF, 4ft HT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0720-0000-R | IPCRP1 | IPCRP1 | 0720-0000 | SINGLE GATE FOR CLF, 4ft HT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 26000 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | N | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0721-0000-L | IPCRP1 | IPCRP1 | 0721-0000 | TREE REM (6 - 12 DBH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0721-0000-R | IPCRP1 | IPCRP1 | 0721-0000 | TREE REM (6 - 12 DBH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 125400 | 0 | 0 | 125400 | 0 | 125400 | 324500 | 0 | N | 125400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0722-0000-L | IPCRP1 | IPCRP1 | 0722-0000 | STUMP REM 6- 12 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0722-0000-R | IPCRP1 | IPCRP1 | 0722-0000 | STUMP REM 6- 12 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9900 | 0 | 0 | 9900 | 0 | 9900 | 1100 | 0 | N | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0723-0000-L | IPCRP1 | IPCRP1 | 0723-0000 | DOUBLE GATE FOR CLF, 4ft HT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0723-0000-R | IPCRP1 | IPCRP1 | 0723-0000 | DOUBLE GATE FOR CLF, 4ft HT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 24000 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | N | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0724-0000-L | IPCRP1 | IPCRP1 | 0724-0000 | CLAY STORAGE BOX | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0724-0000-R | IPCRP1 | IPCRP1 | 0724-0000 | CLAY STORAGE BOX | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 33000 | 0 | 0 | 33000 | 0 | 33000 | 0 | 0 | N | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0725-0000-L | IPCRP1 | IPCRP1 | 0725-0000 | SAFETY SURFACE 10ft FALL HT, OTHER COLOR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0725-0000-R | IPCRP1 | IPCRP1 | 0725-0000 | SAFETY SURFACE 10ft FALL HT, OTHER COLOR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 768130 | 0 | 0 | 768130 | 0 | 768130 | 0 | 0 | N | 768130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0726-0000-L | IPCRP1 | IPCRP1 | 0726-0000 | PLAY EQUIPMENT - 10TH ST. | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0726-0000-R | IPCRP1 | IPCRP1 | 0726-0000 | PLAY EQUIPMENT - 10TH ST. | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 200000 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | N | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0727-0000-L | IPCRP1 | IPCRP1 | 0727-0000 | SIGNAGE & WAYFINDING (BIKEWAY) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0727-0000-R | IPCRP1 | IPCRP1 | 0727-0000 | SIGNAGE & WAYFINDING (BIKEWAY) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16000 | 0 | 0 | 16000 | 0 | 16000 | 0 | 0 | N | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0728-0000-L | IPCRP1 | IPCRP1 | 0728-0000 | THERMOPLASTIC EXTRUDED LINE 4 WIDTH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0728-0000-R | IPCRP1 | IPCRP1 | 0728-0000 | THERMOPLASTIC EXTRUDED LINE 4 WIDTH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 21977.5 | 0 | 0 | 21977.5 | 0 | 21977.5 | 3873.75 | 0 | N | 21977.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21977.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0729-0000-L | IPCRP1 | IPCRP1 | 0729-0000 | THERMOPLASTIC HFPRM LINES, SYMBOLS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0729-0000-R | IPCRP1 | IPCRP1 | 0729-0000 | THERMOPLASTIC HFPRM LINES, SYMBOLS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 54225 | 0 | 0 | 54225 | 0 | 54225 | 18450 | 0 | N | 54225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0729-1000-L | IPCRP1 | IPCRP1 | 0729-1000 | Pavement Marking Subcontractor | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.22 | 0.78 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0729-1000-S | IPCRP1 | IPCRP1 | 0729-1000 | Pavement Marking Subcontractor | N | S |  | NR | A | 183677 | 174706.75 | 174706.75 | 40198.98 | 174706.75 | 21.8857 | 0 | 0 | 0 | 8970.25 | N | 183677 | N | 0 | 0 | 0 | 183677 | 0 | 0 | 183677 | N | 0 | 0 | 0 | 183677 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -183677 | 0 | 0 | 183677 | 0 | 0 | 0 | 0 | 0 | 0 | -183677 | 0 | 0 | 183677 | 183677 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 38619.91 | 120712.38 | 159332.29 | NA | 1 | 0.22 | 0.78 | 1 | LS | 174706.75 | 134507.77 | 40198.98 | 8970.25
Y | IPCRP1-0730-0000-L | IPCRP1 | IPCRP1 | 0730-0000 | SOD NEW LAWN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0730-0000-R | IPCRP1 | IPCRP1 | 0730-0000 | SOD NEW LAWN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 404065 | 0 | 0 | 404065 | 0 | 404065 | 240537.51 | 0 | N | 404065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0731-0000-L | IPCRP1 | IPCRP1 | 0731-0000 | CONIFER TREE PLANTING 10 - 12 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0731-0000-R | IPCRP1 | IPCRP1 | 0731-0000 | CONIFER TREE PLANTING 10 - 12 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 95200 | 0 | 0 | 95200 | 0 | 95200 | 32200 | 0 | N | 95200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0732-0000-L | IPCRP1 | IPCRP1 | 0732-0000 | CONIFER TREE PLANTING 12 - 14 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0732-0000-R | IPCRP1 | IPCRP1 | 0732-0000 | CONIFER TREE PLANTING 12 - 14 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 138000 | 0 | 0 | 138000 | 0 | 138000 | 69600 | 0 | N | 138000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0733-0000-L | IPCRP1 | IPCRP1 | 0733-0000 | CONIFER TREE PLANTING 14 - 16 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0733-0000-R | IPCRP1 | IPCRP1 | 0733-0000 | CONIFER TREE PLANTING 14 - 16 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 61000 | 0 | 0 | 61000 | 0 | 61000 | 20000 | 0 | N | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0734-0000-L | IPCRP1 | IPCRP1 | 0734-0000 | CONIFER TREE PLANTING 8 - 10 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0734-0000-R | IPCRP1 | IPCRP1 | 0734-0000 | CONIFER TREE PLANTING 8 - 10 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 65250 | 0 | 0 | 65250 | 0 | 65250 | 15750 | 0 | N | 65250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0735-0000-L | IPCRP1 | IPCRP1 | 0735-0000 | SHRUB 18 - 24 IN. HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0735-0000-R | IPCRP1 | IPCRP1 | 0735-0000 | SHRUB 18 - 24 IN. HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 151830 | 0 | 0 | 151830 | 0 | 151830 | 24930 | 0 | N | 151830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0736-0000-L | IPCRP1 | IPCRP1 | 0736-0000 | SHRUB 18 - 24 IN. HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0736-0000-R | IPCRP1 | IPCRP1 | 0736-0000 | SHRUB 18 - 24 IN. HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 28700 | 0 | 0 | 28700 | 0 | 28700 | 6500 | 0 | N | 28700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0737-0000-L | IPCRP1 | IPCRP1 | 0737-0000 | SHRUB 2 GALLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0737-0000-R | IPCRP1 | IPCRP1 | 0737-0000 | SHRUB 2 GALLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 113295 | 0 | 0 | 113295 | 0 | 113295 | 44170 | 0 | N | 113295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0738-0000-L | IPCRP1 | IPCRP1 | 0738-0000 | SHRUB 30 - 36 IN. HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0738-0000-R | IPCRP1 | IPCRP1 | 0738-0000 | SHRUB 30 - 36 IN. HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 85875 | 0 | 0 | 85875 | 0 | 85875 | 8125 | 0 | N | 85875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0739-0000-L | IPCRP1 | IPCRP1 | 0739-0000 | SHRUB 3 GALLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0739-0000-R | IPCRP1 | IPCRP1 | 0739-0000 | SHRUB 3 GALLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 183400 | 0 | 0 | 183400 | 0 | 183400 | 204050 | 0 | N | 183400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0740-0000-L | IPCRP1 | IPCRP1 | 0740-0000 | SHRUB 5 GALLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0740-0000-R | IPCRP1 | IPCRP1 | 0740-0000 | SHRUB 5 GALLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1034110 | 0 | 0 | 1034110 | 0 | 1034110 | 238510 | 0 | N | 1034110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0741-0000-L | IPCRP1 | IPCRP1 | 0741-0000 | SHRUB 7 GALLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0741-0000-R | IPCRP1 | IPCRP1 | 0741-0000 | SHRUB 7 GALLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 79515 | 0 | 0 | 79515 | 0 | 79515 | 38610 | 0 | N | 79515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0742-0000-L | IPCRP1 | IPCRP1 | 0742-0000 | BULB | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0742-0000-R | IPCRP1 | IPCRP1 | 0742-0000 | BULB | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18072.25 | 0 | 0 | 18072.25 | 0 | 18072.25 | 157.5 | 0 | N | 18072.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18072.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0743-0000-L | IPCRP1 | IPCRP1 | 0743-0000 | MULTI-STEM TREE PLANTING 10 - 12 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0743-0000-R | IPCRP1 | IPCRP1 | 0743-0000 | MULTI-STEM TREE PLANTING 10 - 12 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 43000 | 0 | 0 | 43000 | 0 | 43000 | 10000 | 0 | N | 43000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0744-0000-L | IPCRP1 | IPCRP1 | 0744-0000 | MULTI-STEM TREE PLANTING 12 - 14 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0744-0000-R | IPCRP1 | IPCRP1 | 0744-0000 | MULTI-STEM TREE PLANTING 12 - 14 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 55900 | 0 | 0 | 55900 | 0 | 55900 | 19500 | 0 | N | 55900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0745-0000-L | IPCRP1 | IPCRP1 | 0745-0000 | MULTI-STEM TREE PLANTING 14 - 16 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0745-0000-R | IPCRP1 | IPCRP1 | 0745-0000 | MULTI-STEM TREE PLANTING 14 - 16 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 86000 | 0 | 0 | 86000 | 0 | 86000 | 48000 | 0 | N | 86000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0746-0000-L | IPCRP1 | IPCRP1 | 0746-0000 | MULTI-STEM TREE PLANTING 8 - 10 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0746-0000-R | IPCRP1 | IPCRP1 | 0746-0000 | MULTI-STEM TREE PLANTING 8 - 10 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 56700 | 0 | 0 | 56700 | 0 | 56700 | 35100 | 0 | N | 56700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0747-0000-L | IPCRP1 | IPCRP1 | 0747-0000 | ORNAMENTAL GRASS 1 GALLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0747-0000-R | IPCRP1 | IPCRP1 | 0747-0000 | ORNAMENTAL GRASS 1 GALLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 491850 | 0 | 0 | 491850 | 0 | 491850 | 91675 | 0 | N | 491850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0748-0000-L | IPCRP1 | IPCRP1 | 0748-0000 | ORNAMENTAL GRASS 1 QUART | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0748-0000-R | IPCRP1 | IPCRP1 | 0748-0000 | ORNAMENTAL GRASS 1 QUART | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 159511 | 0 | 0 | 159511 | 0 | 159511 | 126819 | 0 | N | 159511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0749-0000-L | IPCRP1 | IPCRP1 | 0749-0000 | PERENNIAL/GROUND COVER , 1 GALLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0749-0000-R | IPCRP1 | IPCRP1 | 0749-0000 | PERENNIAL/GROUND COVER , 1 GALLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 408986 | 0 | 0 | 408986 | 0 | 408986 | 77096 | 0 | N | 408986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0750-0000-L | IPCRP1 | IPCRP1 | 0750-0000 | TREE PLANTING 10 GAL CONTAINER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0750-0000-R | IPCRP1 | IPCRP1 | 0750-0000 | TREE PLANTING 10 GAL CONTAINER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7125 | 0 | 0 | 7125 | 0 | 7125 | 1750 | 0 | N | 7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0751-0000-L | IPCRP1 | IPCRP1 | 0751-0000 | TREE PLANTING 2.0 - 2.5 CALIPER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0751-0000-R | IPCRP1 | IPCRP1 | 0751-0000 | TREE PLANTING 2.0 - 2.5 CALIPER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6000 | 0 | 0 | 6000 | 0 | 6000 | 16800 | 0 | N | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0752-0000-L | IPCRP1 | IPCRP1 | 0752-0000 | TREE PLANTING 20 GAL CONTAINER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0752-0000-R | IPCRP1 | IPCRP1 | 0752-0000 | TREE PLANTING 20 GAL CONTAINER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 675 | 0 | 0 | 675 | 0 | 675 | 0 | 0 | N | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0753-0000-L | IPCRP1 | IPCRP1 | 0753-0000 | TREE PLANTING 2.5-3.0 CALIPER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0753-0000-R | IPCRP1 | IPCRP1 | 0753-0000 | TREE PLANTING 2.5-3.0 CALIPER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 266250 | 0 | 0 | 266250 | 0 | 266250 | 107250 | 0 | N | 266250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0754-0000-L | IPCRP1 | IPCRP1 | 0754-0000 | TREE PLANTING 3.0-3.5 CALIPER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0754-0000-R | IPCRP1 | IPCRP1 | 0754-0000 | TREE PLANTING 3.0-3.5 CALIPER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 946050 | 0 | 0 | 946050 | 0 | 946050 | 262500 | 0 | N | 946050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0755-0000-L | IPCRP1 | IPCRP1 | 0755-0000 | TREE PLANTING 5 GAL CONTAINER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0755-0000-R | IPCRP1 | IPCRP1 | 0755-0000 | TREE PLANTING 5 GAL CONTAINER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6900 | 0 | 0 | 6900 | 0 | 6900 | 2400 | 0 | N | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0756-0000-L | IPCRP1 | IPCRP1 | 0756-0000 | TREE PLANTING 6 - 8 FT HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0756-0000-R | IPCRP1 | IPCRP1 | 0756-0000 | TREE PLANTING 6 - 8 FT HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 700 | 0 | 0 | 700 | 0 | 700 | 0 | 0 | N | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0756-1000-L | IPCRP1 | IPCRP1 | 0756-1000 | Landscape Subcontractor (Eastern) | N | L |  | UNIT | P | 0 | 79303.92 | 79303.92 | 79303.92 | 79303.92 | 38.7775 | 0 | 0 | 0 | 125206.28 | Y | 204510.2 | Y | -204510.2 | 0 | 0 | 0 | 0 | 0 | 204510.2 | Y | -204510.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -204510.2 | 0 | 0 | 204510.2 | 0 | 0 | 0 | 0 | 0 | 0 | -204510.2 | 0 | 0 | 204510.2 | 204510.2 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 0 | 574.5 | 1025.5 | 1600 | HR | 1 | 0.37 | 0.63 | 1 | LS | 0 | 0 | 0 | 125206.28
Y | IPCRP1-0756-1000-S | IPCRP1 | IPCRP1 | 0756-1000 | Landscape Subcontractor (Eastern) | N | S |  | NR | A | 19873534 | 22078738.94 | 22078738.94 | 8052350.34 | 22078738.94 | 36.5703 | 0 | 0 | 0 | -59888.55 | Y | 22018850.39 | Y | -2145316.39 | 0 | 0 | 19873534 | 0 | 0 | 22018850.39 | Y | -2145316.39 | 0 | 0 | 19873534 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22018850.39 | 0 | 0 | 22018850.39 | 0 | 0 | 0 | 0 | 59888.55 | 0 | -22018850.39 | 0 | 0 | 22018850.39 | 22018850.39 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 720574.85 | 199625.9 | 920200.75 | LS | 1 | 0.37 | 0.63 | 1 | LS | 22078738.94 | 14026388.6 | 8052350.34 | -59888.55 | Eastern Base Contract @Base Contract @18,583,771.50 CO@$1,032,830.00
Y | IPCRP1-0756-1005-L | IPCRP1 | IPCRP1 | 0756-1005 | Backcharge to Eastern for Damages Caused by Easter | N | L |  | UNIT | P | 13000 | 11993.99 | 11993.99 | 11993.99 | 11993.99 | 47.9875 | 0 | 0 | 0 | 13000 | N | 24993.99 | N | -11993.99 | 0 | 0 | 13000 | 0 | 0 | 24993.99 | N | -11993.99 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24993.99 | 0 | 0 | 24993.99 | 0 | 0 | 0 | 0 | 0 | 0 | -24993.99 | 0 | 0 | 24993.99 | 24993.99 | 0 | 0 | 0 | 0 | 0 | 199 | 199 | 100 | 99 | 100 | 199 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 13000
Y | IPCRP1-0756-1005-S | IPCRP1 | IPCRP1 | 0756-1005 | Backcharge to Eastern for Damages Caused by Easter | N | S |  | UNIT | A | 0 | 3626.94 | 3626.94 | 3626.94 | 3626.94 | 100 | 0 | 0 | 0 | 0 | N | 3626.94 | N | -3626.94 | 0 | 0 | 0 | 0 | 0 | 3626.94 | N | -3626.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3626.94 | 0 | 0 | 3626.94 | 0 | 0 | 0 | 0 | 0 | 0 | -3626.94 | 0 | 0 | 3626.94 | 3626.94 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 0 | 29 | 0 | 29 | NA | 1 | 0 | 1 | 1 | LS | 3626.94 | 0 | 3626.94 | 0
Y | IPCRP1-0757-0000-L | IPCRP1 | IPCRP1 | 0757-0000 | SYNTHETIC TURF-INFILL TYPE ON STONE BASE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0757-0000-R | IPCRP1 | IPCRP1 | 0757-0000 | SYNTHETIC TURF-INFILL TYPE ON STONE BASE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3623578 | 0 | 0 | 3623578 | 0 | 3623578 | 1515012.79 | 0 | N | 3623578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3623578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0758-0000-L | IPCRP1 | IPCRP1 | 0758-0000 | TREE REM (12 - 18 DBH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0758-0000-R | IPCRP1 | IPCRP1 | 0758-0000 | TREE REM (12 - 18 DBH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 388500 | 0 | 0 | 388500 | 0 | 388500 | 315000 | 0 | N | 388500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0759-0000-L | IPCRP1 | IPCRP1 | 0759-0000 | COLOR SEAL COAT SYSTEM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0759-0000-R | IPCRP1 | IPCRP1 | 0759-0000 | COLOR SEAL COAT SYSTEM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 549133 | 0 | 0 | 549133 | 0 | 549133 | 501867.6 | 0 | N | 549133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0760-0000-L | IPCRP1 | IPCRP1 | 0760-0000 | PAINT LINES - 2 WIDTH - COLOR SEAL COAT AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0760-0000-R | IPCRP1 | IPCRP1 | 0760-0000 | PAINT LINES - 2 WIDTH - COLOR SEAL COAT AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9568.75 | 0 | 0 | 9568.75 | 0 | 9568.75 | 8896.25 | 0 | N | 9568.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0761-0000-L | IPCRP1 | IPCRP1 | 0761-0000 | LONG JUMP, LANDING & PIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0761-0000-R | IPCRP1 | IPCRP1 | 0761-0000 | LONG JUMP, LANDING & PIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 40000 | 0 | 0 | 40000 | 0 | 40000 | 0 | 0 | N | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0762-0000-L | IPCRP1 | IPCRP1 | 0762-0000 | GEOTEXTILES-DRAINAGE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0762-0000-R | IPCRP1 | IPCRP1 | 0762-0000 | GEOTEXTILES-DRAINAGE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2304.5 | 0 | 0 | 2304.5 | 0 | 2304.5 | 1402.69 | 0 | N | 2304.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2304.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0763-0000-L | IPCRP1 | IPCRP1 | 0763-0000 | GEOTEXTILES-SEPARATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0763-0000-R | IPCRP1 | IPCRP1 | 0763-0000 | GEOTEXTILES-SEPARATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31806.5 | 0 | 0 | 31806.5 | 0 | 31806.5 | 25737.43 | 0 | N | 31806.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31806.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0763-1000-L | IPCRP1 | IPCRP1 | 0763-1000 | Geotextile - Drainage & Seperation | N | L |  | UNIT | P | 0 | 2535.64 | 2535.64 | 2535.64 | 2535.64 | 15.7294 | 0 | 0 | 0 | 13584.78 | Y | 16120.42 | Y | -16120.42 | 0 | 0 | 0 | 0 | 0 | 16120.42 | Y | -16120.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16120.42 | 0 | 0 | 16120.42 | 0 | 0 | 0 | 0 | 0 | 0 | -16120.42 | 0 | 0 | 16120.42 | 16120.42 | 0 | 0 | 0 | 0 | 0 | 124 | 124 | 0 | 25 | 99 | 124 | HR | 6202 | 4679.53 | 1522.47 | 6202 | SY | 0 | 0 | 0 | 13584.78
Y | IPCRP1-0763-1000-M | IPCRP1 | IPCRP1 | 0763-1000 | Geotextile - Drainage & Seperation | N | M |  | UNIT | U | 0 | 6184.09 | 6184.09 | 5858.67 | 6184.09 | 35.5999 | 0 | 0 | 0 | 10272.91 | Y | 16457 | Y | -16457 | 0 | 0 | 0 | 0 | 0 | 16457 | Y | -16457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16457 | 0 | 0 | 16457 | 0 | 0 | 0 | 0 | 0 | 0 | -16457 | 0 | 0 | 16457 | 16457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | -25 | 0 | NA | 6202 | 4679.53 | 1522.47 | 6202 | SY | 6184.09 | 325.42 | 5858.67 | 10272.91
Y | IPCRP1-0763-1000-S | IPCRP1 | IPCRP1 | 0763-1000 | Geotextile - Drainage & Seperation | N | S |  | NR | A | 32577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 32577 | 0 | 0 | 32577 | 0 | 0 | 0 | Y | 32577 | 0 | 0 | 32577 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 6202 | 4679.53 | 1522.47 | 6202 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0764-0000-L | IPCRP1 | IPCRP1 | 0764-0000 | BENCH, 1964 WORLDS FAIR W/ RPL SLATS W/ ARMS 4ft | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0764-0000-R | IPCRP1 | IPCRP1 | 0764-0000 | BENCH, 1964 WORLDS FAIR W/ RPL SLATS W/ ARMS 4ft | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 113600 | 0 | 0 | 113600 | 0 | 113600 | 20800 | 0 | N | 113600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0765-0000-L | IPCRP1 | IPCRP1 | 0765-0000 | BENCH, TYPE C (SPORTS) W/ RPL SLATS - BACKLESS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0765-0000-R | IPCRP1 | IPCRP1 | 0765-0000 | BENCH, TYPE C (SPORTS) W/ RPL SLATS - BACKLESS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 220500 | 0 | 0 | 220500 | 0 | 220500 | 63000 | 0 | N | 220500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0766-0000-L | IPCRP1 | IPCRP1 | 0766-0000 | BICYCLE RACK -HOOP- | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0766-0000-R | IPCRP1 | IPCRP1 | 0766-0000 | BICYCLE RACK -HOOP- | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 159300 | 0 | 0 | 159300 | 0 | 159300 | 78300 | 0 | N | 159300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0767-0000-L | IPCRP1 | IPCRP1 | 0767-0000 | PICNIC TABLE - FIXED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0767-0000-R | IPCRP1 | IPCRP1 | 0767-0000 | PICNIC TABLE - FIXED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0768-0000-L | IPCRP1 | IPCRP1 | 0768-0000 | CHAIN LINK FENCE 12ft HT, 1.75in MESH (TENNIS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0768-0000-R | IPCRP1 | IPCRP1 | 0768-0000 | CHAIN LINK FENCE 12ft HT, 1.75in MESH (TENNIS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 369200 | 0 | 0 | 369200 | 0 | 369200 | 362714 | 0 | N | 369200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0769-0000-L | IPCRP1 | IPCRP1 | 0769-0000 | CHAIN LINK FENCE 4ft HT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0769-0000-R | IPCRP1 | IPCRP1 | 0769-0000 | CHAIN LINK FENCE 4ft HT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 183040 | 0 | 0 | 183040 | 0 | 183040 | 0 | 0 | N | 183040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0770-0000-L | IPCRP1 | IPCRP1 | 0770-0000 | ST FENCE 4ft HIGH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0770-0000-R | IPCRP1 | IPCRP1 | 0770-0000 | ST FENCE 4ft HIGH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1163250 | 0 | 0 | 1163250 | 0 | 1163250 | 8261 | 0 | N | 1163250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0771-0000-L | IPCRP1 | IPCRP1 | 0771-0000 | 2ft 6in HIGH ST FENCE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0771-0000-R | IPCRP1 | IPCRP1 | 0771-0000 | 2ft 6in HIGH ST FENCE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 66550 | 0 | 0 | 66550 | 0 | 66550 | 68156 | 0 | N | 66550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0772-0000-L | IPCRP1 | IPCRP1 | 0772-0000 | SINGLE GATE FOR ST FENCE 4ft-0 HIGH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0772-0000-R | IPCRP1 | IPCRP1 | 0772-0000 | SINGLE GATE FOR ST FENCE 4ft-0 HIGH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5200 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | N | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0773-0000-L | IPCRP1 | IPCRP1 | 0773-0000 | BASEBALL ACCESSORIES SET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0773-0000-R | IPCRP1 | IPCRP1 | 0773-0000 | BASEBALL ACCESSORIES SET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3300 | 0 | 0 | 3300 | 0 | 3300 | 2200 | 0 | N | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0774-0000-L | IPCRP1 | IPCRP1 | 0774-0000 | BASKETBALL BACKSTOP SINGLE POST (PC BACKBOARD) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0774-0000-R | IPCRP1 | IPCRP1 | 0774-0000 | BASKETBALL BACKSTOP SINGLE POST (PC BACKBOARD) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42400 | 0 | 0 | 42400 | 0 | 42400 | 21200 | 0 | N | 42400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0775-0000-L | IPCRP1 | IPCRP1 | 0775-0000 | HOODED BASEBALL BACKSTOP | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0775-0000-R | IPCRP1 | IPCRP1 | 0775-0000 | HOODED BASEBALL BACKSTOP | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 700000 | 0 | 0 | 700000 | 0 | 700000 | 200000 | 0 | N | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0776-0000-L | IPCRP1 | IPCRP1 | 0776-0000 | PREPARE SKINNED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0776-0000-R | IPCRP1 | IPCRP1 | 0776-0000 | PREPARE SKINNED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 450560 | 0 | 0 | 450560 | 0 | 450560 | 0 | 0 | N | 450560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0776-1000-L | IPCRP1 | IPCRP1 | 0776-1000 | Prepare Skinned Areas | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2816 | 0 | 2816 | 2816 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0776-1000-S | IPCRP1 | IPCRP1 | 0776-1000 | Prepare Skinned Areas | N | S |  | NR | A | 443744.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443744.72 | N | 443744.72 | N | 0 | 0 | 0 | 443744.72 | 0 | 0 | 443744.72 | N | 0 | 0 | 0 | 443744.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -443744.72 | 0 | 0 | 443744.72 | 0 | 0 | 0 | 0 | 0 | 0 | -443744.72 | 0 | 0 | 443744.72 | 443744.72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 2816 | 0 | 2816 | 2816 | SY | 0 | 0 | 0 | 443744.72
Y | IPCRP1-0777-0000-L | IPCRP1 | IPCRP1 | 0777-0000 | SOCCER GOALS - PORTABLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0777-0000-R | IPCRP1 | IPCRP1 | 0777-0000 | SOCCER GOALS - PORTABLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 39000 | 0 | 0 | 39000 | 0 | 39000 | 13000 | 0 | N | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0778-0000-L | IPCRP1 | IPCRP1 | 0778-0000 | SOCCER GOAL JUNIOR SIZE, PORTABLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0778-0000-R | IPCRP1 | IPCRP1 | 0778-0000 | SOCCER GOAL JUNIOR SIZE, PORTABLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13000 | 0 | 0 | 13000 | 0 | 13000 | 13000 | 0 | N | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0779-0000-L | IPCRP1 | IPCRP1 | 0779-0000 | TENNIS COURT ACCESSORIES SET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0779-0000-R | IPCRP1 | IPCRP1 | 0779-0000 | TENNIS COURT ACCESSORIES SET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 132000 | 0 | 0 | 132000 | 0 | 132000 | 132000 | 0 | N | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0780-0000-L | IPCRP1 | IPCRP1 | 0780-0000 | PAINT LINES 4 SYNTHETIC TURF | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0780-0000-R | IPCRP1 | IPCRP1 | 0780-0000 | PAINT LINES 4 SYNTHETIC TURF | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12337.5 | 0 | 0 | 12337.5 | 0 | 12337.5 | 11063.58 | 0 | N | 12337.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12337.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0781-0000-L | IPCRP1 | IPCRP1 | 0781-0000 | PERFORATED POLYETHYLENE CORR PIPE (12) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0781-0000-R | IPCRP1 | IPCRP1 | 0781-0000 | PERFORATED POLYETHYLENE CORR PIPE (12) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 281250 | 0 | 0 | 281250 | 0 | 281250 | 0 | 0 | N | 281250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0782-0000-L | IPCRP1 | IPCRP1 | 0782-0000 | POLYETHYLENE CORR PIPE (6) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0782-0000-R | IPCRP1 | IPCRP1 | 0782-0000 | POLYETHYLENE CORR PIPE (6) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6000 | 0 | 0 | 6000 | 0 | 6000 | 0 | 0 | N | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0783-0000-L | IPCRP1 | IPCRP1 | 0783-0000 | POLYETHYLENE CORR PIPE (12) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0783-0000-R | IPCRP1 | IPCRP1 | 0783-0000 | POLYETHYLENE CORR PIPE (12) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 286400 | 0 | 0 | 286400 | 0 | 286400 | 442154.14 | 0 | N | 286400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0784-0000-L | IPCRP1 | IPCRP1 | 0784-0000 | PERFORATED POLYETHYLENE CORR PIPE (6) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0784-0000-R | IPCRP1 | IPCRP1 | 0784-0000 | PERFORATED POLYETHYLENE CORR PIPE (6) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1332400 | 0 | 0 | 1332400 | 0 | 1332400 | 603362 | 0 | N | 1332400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0785-0000-L | IPCRP1 | IPCRP1 | 0785-0000 | TREE REM (18 - 24 DBH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0785-0000-R | IPCRP1 | IPCRP1 | 0785-0000 | TREE REM (18 - 24 DBH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 542500 | 0 | 0 | 542500 | 0 | 542500 | 672700 | 0 | N | 542500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0786-0000-L | IPCRP1 | IPCRP1 | 0786-0000 | ST SLAT ROLLING GATE, 8ft HT X 25ft W | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0786-0000-R | IPCRP1 | IPCRP1 | 0786-0000 | ST SLAT ROLLING GATE, 8ft HT X 25ft W | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 22000 | 0 | 0 | 22000 | 0 | 22000 | 0 | 0 | N | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0787-0000-L | IPCRP1 | IPCRP1 | 0787-0000 | PAINT LINES 4 INCH LAWN & CLAY AREAS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0787-0000-R | IPCRP1 | IPCRP1 | 0787-0000 | PAINT LINES 4 INCH LAWN & CLAY AREAS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1625 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | N | 1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0787-1000-L | IPCRP1 | IPCRP1 | 0787-1000 | Paint Lines 4 Lawn & Clay Areas | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 650 | 0 | 650 | 650 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0787-1000-S | IPCRP1 | IPCRP1 | 0787-1000 | Paint Lines 4 Lawn & Clay Areas | N | S |  | NR | A | 1365.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1365.72 | N | 1365.72 | N | 0 | 0 | 0 | 1365.72 | 0 | 0 | 1365.72 | N | 0 | 0 | 0 | 1365.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1365.72 | 0 | 0 | 1365.72 | 0 | 0 | 0 | 0 | 0 | 0 | -1365.72 | 0 | 0 | 1365.72 | 1365.72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 650 | 0 | 650 | 650 | LF | 0 | 0 | 0 | 1365.72
Y | IPCRP1-0788-0000-L | IPCRP1 | IPCRP1 | 0788-0000 | 1964 WORLDS FAIR BAR STOOL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0788-0000-R | IPCRP1 | IPCRP1 | 0788-0000 | 1964 WORLDS FAIR BAR STOOL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 70400 | 0 | 0 | 70400 | 0 | 70400 | 44000 | 0 | N | 70400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0789-0000-L | IPCRP1 | IPCRP1 | 0789-0000 | 1964 WORLDS FAIR CHAIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0789-0000-R | IPCRP1 | IPCRP1 | 0789-0000 | 1964 WORLDS FAIR CHAIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 28800 | 0 | 0 | 28800 | 0 | 28800 | 14400 | 0 | N | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0790-0000-L | IPCRP1 | IPCRP1 | 0790-0000 | HOT COAL BIN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0790-0000-R | IPCRP1 | IPCRP1 | 0790-0000 | HOT COAL BIN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 42400 | 0 | 0 | 42400 | 0 | 42400 | 21200 | 0 | N | 42400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0791-0000-L | IPCRP1 | IPCRP1 | 0791-0000 | STAINLESS ST HAND RAIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0791-0000-R | IPCRP1 | IPCRP1 | 0791-0000 | STAINLESS ST HAND RAIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 144600 | 0 | 0 | 144600 | 0 | 144600 | 111840 | 0 | N | 144600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0792-0000-L | IPCRP1 | IPCRP1 | 0792-0000 | TREE REM (24 - 30 DBH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0792-0000-R | IPCRP1 | IPCRP1 | 0792-0000 | TREE REM (24 - 30 DBH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 332100 | 0 | 0 | 332100 | 0 | 332100 | 431275 | 0 | N | 332100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0793-0000-L | IPCRP1 | IPCRP1 | 0793-0000 | TREE REM (30 - 36 DBH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0793-0000-R | IPCRP1 | IPCRP1 | 0793-0000 | TREE REM (30 - 36 DBH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 142600 | 0 | 0 | 142600 | 0 | 142600 | 105800 | 0 | N | 142600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0794-0000-L | IPCRP1 | IPCRP1 | 0794-0000 | TREE REM (36 - 42 DBH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0794-0000-R | IPCRP1 | IPCRP1 | 0794-0000 | TREE REM (36 - 42 DBH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25500 | 0 | 0 | 25500 | 0 | 25500 | 20400 | 0 | N | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0795-0000-L | IPCRP1 | IPCRP1 | 0795-0000 | RECONSTRUCT DRAINAGE STRUCT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0795-0000-R | IPCRP1 | IPCRP1 | 0795-0000 | RECONSTRUCT DRAINAGE STRUCT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11000 | 0 | 0 | 11000 | 0 | 11000 | 0 | 0 | N | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0796-0000-L | IPCRP1 | IPCRP1 | 0796-0000 | CB F&C W/ BALLAST SCREEN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0796-0000-R | IPCRP1 | IPCRP1 | 0796-0000 | CB F&C W/ BALLAST SCREEN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 144900 | 0 | 0 | 144900 | 0 | 144900 | 0 | 0 | N | 144900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0797-0000-L | IPCRP1 | IPCRP1 | 0797-0000 | DIP SEWER - 18 DIA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0797-0000-R | IPCRP1 | IPCRP1 | 0797-0000 | DIP SEWER - 18 DIA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1296000 | 0 | 0 | 1296000 | 0 | 1296000 | 565867.5 | 0 | N | 1296000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0798-0000-L | IPCRP1 | IPCRP1 | 0798-0000 | DIP SEWER - 24 DIA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0798-0000-R | IPCRP1 | IPCRP1 | 0798-0000 | DIP SEWER - 24 DIA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25200 | 0 | 0 | 25200 | 0 | 25200 | 8700 | 0 | N | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0799-0000-L | IPCRP1 | IPCRP1 | 0799-0000 | PRECAST CONC DRYWELL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0799-0000-R | IPCRP1 | IPCRP1 | 0799-0000 | PRECAST CONC DRYWELL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 36600 | 0 | 0 | 36600 | 0 | 36600 | 12200 | 0 | N | 36600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0800-0000-L | IPCRP1 | IPCRP1 | 0800-0000 | IP PTZ HDTV DOME CAMERA & MOUNTING ASSEMBLY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0800-0000-R | IPCRP1 | IPCRP1 | 0800-0000 | IP PTZ HDTV DOME CAMERA & MOUNTING ASSEMBLY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20700 | 0 | 0 | 20700 | 0 | 20700 | 0 | 0 | N | 20700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0801-0000-L | IPCRP1 | IPCRP1 | 0801-0000 | VEHICLE TRANSMIT TAG READER OSS-1 JACKSON AV | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0801-0000-R | IPCRP1 | IPCRP1 | 0801-0000 | VEHICLE TRANSMIT TAG READER OSS-1 JACKSON AV | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0802-0000-L | IPCRP1 | IPCRP1 | 0802-0000 | VEHICLE TRANSMIT TAG ANTENNA OSS-1 JACKSON AV | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0802-0000-R | IPCRP1 | IPCRP1 | 0802-0000 | VEHICLE TRANSMIT TAG ANTENNA OSS-1 JACKSON AV | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 32000 | 0 | 0 | 32000 | 0 | 32000 | 0 | 0 | N | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0803-0000-L | IPCRP1 | IPCRP1 | 0803-0000 | VEHICLE TRANSMIT TAG READER OSS-8N FDR NORTH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0803-0000-R | IPCRP1 | IPCRP1 | 0803-0000 | VEHICLE TRANSMIT TAG READER OSS-8N FDR NORTH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0804-0000-L | IPCRP1 | IPCRP1 | 0804-0000 | VEHICLE TRANSMIT TAG ANTENNA OSS-8N FDR NORTH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0804-0000-R | IPCRP1 | IPCRP1 | 0804-0000 | VEHICLE TRANSMIT TAG ANTENNA OSS-8N FDR NORTH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16000 | 0 | 0 | 16000 | 0 | 16000 | 0 | 0 | N | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0805-0000-L | IPCRP1 | IPCRP1 | 0805-0000 | VEHICLE TRANSMIT TAG READER OSS-8S FDR SOUTH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0805-0000-R | IPCRP1 | IPCRP1 | 0805-0000 | VEHICLE TRANSMIT TAG READER OSS-8S FDR SOUTH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0806-0000-L | IPCRP1 | IPCRP1 | 0806-0000 | VEHICLE TRANSMIT TAG ANTENNA OSS-8S FDR SOUTH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0806-0000-R | IPCRP1 | IPCRP1 | 0806-0000 | VEHICLE TRANSMIT TAG ANTENNA OSS-8S FDR SOUTH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16000 | 0 | 0 | 16000 | 0 | 16000 | 0 | 0 | N | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0807-0000-L | IPCRP1 | IPCRP1 | 0807-0000 | NEMA 3R ITS SIGNAL CABINETS, TYPE P44 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0807-0000-R | IPCRP1 | IPCRP1 | 0807-0000 | NEMA 3R ITS SIGNAL CABINETS, TYPE P44 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0808-0000-L | IPCRP1 | IPCRP1 | 0808-0000 | NEMA 3R ITS SIGNAL CABINETS, TYPE 344 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0808-0000-R | IPCRP1 | IPCRP1 | 0808-0000 | NEMA 3R ITS SIGNAL CABINETS, TYPE 344 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 92000 | 0 | 0 | 92000 | 0 | 92000 | 0 | 0 | N | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0809-0000-L | IPCRP1 | IPCRP1 | 0809-0000 | NEMA 3R ITS SIGNAL CABINETS, TYPE ATSC-8 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0809-0000-R | IPCRP1 | IPCRP1 | 0809-0000 | NEMA 3R ITS SIGNAL CABINETS, TYPE ATSC-8 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 32000 | 0 | 0 | 32000 | 0 | 32000 | 0 | 0 | N | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0810-0000-L | IPCRP1 | IPCRP1 | 0810-0000 | RADAR BASED TRAFFIC MEASURING SENSOR (RTMS) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0810-0000-R | IPCRP1 | IPCRP1 | 0810-0000 | RADAR BASED TRAFFIC MEASURING SENSOR (RTMS) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9900 | 0 | 0 | 9900 | 0 | 9900 | 0 | 0 | N | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0811-0000-L | IPCRP1 | IPCRP1 | 0811-0000 | ITS CAT 6 OUTDOOR ETHERNET CABLE-GEL FILLED | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0811-0000-R | IPCRP1 | IPCRP1 | 0811-0000 | ITS CAT 6 OUTDOOR ETHERNET CABLE-GEL FILLED | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6750 | 0 | 0 | 6750 | 0 | 6750 | 0 | 0 | N | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0812-0000-L | IPCRP1 | IPCRP1 | 0812-0000 | ITS REMOVALS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0812-0000-R | IPCRP1 | IPCRP1 | 0812-0000 | ITS REMOVALS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8900 | 0 | 0 | 8900 | 0 | 8900 | 8900 | 0 | N | 8900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0813-0000-L | IPCRP1 | IPCRP1 | 0813-0000 | LED FULL COLOR VARIABLE MESSAGE SIGN (VMS) - OSS- | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0813-0000-R | IPCRP1 | IPCRP1 | 0813-0000 | LED FULL COLOR VARIABLE MESSAGE SIGN (VMS) - OSS- | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0814-0000-L | IPCRP1 | IPCRP1 | 0814-0000 | LED FULL COLOR VARIABLE MESSAGE SIGN (VMS) - OSS- | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0814-0000-R | IPCRP1 | IPCRP1 | 0814-0000 | LED FULL COLOR VARIABLE MESSAGE SIGN (VMS) - OSS- | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 65000 | 0 | 0 | 65000 | 0 | 65000 | 0 | 0 | N | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0815-0000-L | IPCRP1 | IPCRP1 | 0815-0000 | TENNIS BUILDING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0815-0000-R | IPCRP1 | IPCRP1 | 0815-0000 | TENNIS BUILDING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5222271.75 | 0 | 0 | 5222271.75 | 0 | 5222271.75 | 2081674.83 | 0 | N | 5222271.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5222271.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1000-E | IPCRP1 | IPCRP1 | 0815-1000 | Excavate & Sheet for Tennis Bldg Footing | N | E |  | NR | P | 1387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1387 | 0 | 0 | 1387 | 0 | 0 | 0 | Y | 1387 | 0 | 0 | 1387 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 260 | 167.89 | 0 | 167.89 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1000-L | IPCRP1 | IPCRP1 | 0815-1000 | Excavate & Sheet for Tennis Bldg Footing | N | L |  | NR | P | 6066 | 7462.47 | 7462.47 | 7462.47 | 7462.47 | 131.8148 | 0 | 0 | 0 | -1801.14 | Y | 5661.33 | Y | 404.67 | 0 | 0 | 6066 | 0 | 0 | 5661.33 | Y | 404.67 | 0 | 0 | 6066 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5661.33 | 1801.14 | -297.33 | 5661.33 | 0 | 0 | 0 | 0 | 0 | 0 | -5661.33 | 0 | 0 | 5661.33 | 5661.33 | 0 | 0 | 0 | 51.6 | 0 | 44.5 | 44.5 | 51.6 | 60.5 | -16 | 44.5 | HR | 260 | 167.89 | 0 | 167.89 | CY | 0 | 0 | 0 | -1801.14
Y | IPCRP1-0815-1000-S | IPCRP1 | IPCRP1 | 0815-1000 | Excavate & Sheet for Tennis Bldg Footing | N | S |  | UNIT | A | 0 | 1376.62 | 1376.62 | 1376.62 | 1376.62 | 100 | 0 | 0 | 0 | 0 | N | 1376.62 | N | -1376.62 | 0 | 0 | 0 | 0 | 0 | 1376.62 | N | -1376.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1376.62 | 0 | 0 | 1376.62 | 0 | 0 | 0 | 0 | 0 | 0 | -1376.62 | 0 | 0 | 1376.62 | 1376.62 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 11 | 0 | 11 | NA | 260 | 167.89 | 0 | 167.89 | CY | 1376.62 | 0 | 1376.62 | 0
Y | IPCRP1-0815-1010-L | IPCRP1 | IPCRP1 | 0815-1010 | Form & Strip for Tennis Bldg Footing | N | L |  | NR | P | 150286.91 | 99161.99 | 99161.99 | 99161.99 | 99161.99 | 100 | 0 | 0 | 0 | 0 | Y | 99161.99 | Y | 51124.92 | 0 | 0 | 150286.91 | 0 | 0 | 99161.99 | Y | 51124.92 | 0 | 0 | 150286.91 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -99161.99 | 0 | 0 | 99161.99 | 0 | 0 | 0 | 0 | 0 | 0 | -99161.99 | 0 | 0 | 99161.99 | 99161.99 | 0 | 0 | 0 | 1271.89 | 0 | 0 | 0 | 1271.89 | 764.5 | -764.5 |  | HR | 2760 | 1648.46 | 0 | 1648.46 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1010-S | IPCRP1 | IPCRP1 | 0815-1010 | Form & Strip for Tennis Bldg Footing | N | S |  | UNIT | A | 0 | 961.68 | 961.68 | 961.68 | 961.68 | 100 | 0 | 0 | 0 | 0 | N | 961.68 | N | -961.68 | 0 | 0 | 0 | 0 | 0 | 961.68 | N | -961.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -961.68 | 0 | 0 | 961.68 | 0 | 0 | 0 | 0 | 0 | 0 | -961.68 | 0 | 0 | 961.68 | 961.68 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 0 | 7.5 | 0 | 7.5 | NA | 2760 | 1648.46 | 0 | 1648.46 | SF | 961.68 | 0 | 961.68 | 0 | Adjusted PMF as/ JBo email dated 8/27
Y | IPCRP1-0815-1020-E | IPCRP1 | IPCRP1 | 0815-1020 | Place Conc Found for Tennis Bldg Footing | N | E |  | NR | P | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | Y | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 184 | 132.26 | 0 | 132.26 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1020-L | IPCRP1 | IPCRP1 | 0815-1020 | Place Conc Found for Tennis Bldg Footing | N | L |  | NR | P | 15428.56 | 29008.84 | 29008.84 | 29008.84 | 29008.84 | 100 | 0 | 0 | 0 | 0 | Y | 29008.84 | Y | -13580.28 | 0 | 0 | 15428.56 | 0 | 0 | 29008.84 | Y | -13580.28 | 0 | 0 | 15428.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -29008.84 | 0 | 0 | 29008.84 | 0 | 0 | 0 | 0 | 0 | 0 | -29008.84 | 0 | 0 | 29008.84 | 29008.84 | 0 | 0 | 0 | 144 | 0 | 229 | 229 | 144 | 229 | 0 | 229 | HR | 184 | 132.26 | 0 | 132.26 | CY | 0 | 0 | 0 | 0 | Adjusted PMF as/ JBo email dated 8/27
Y | IPCRP1-0815-1020-S | IPCRP1 | IPCRP1 | 0815-1020 | Place Conc Found for Tennis Bldg Footing | N | S |  | UNIT | A | 0 | 635.33 | 635.33 | 635.33 | 635.33 | 100 | 0 | 0 | 0 | 0 | N | 635.33 | N | -635.33 | 0 | 0 | 0 | 0 | 0 | 635.33 | N | -635.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -635.33 | 0 | 0 | 635.33 | 0 | 0 | 0 | 0 | 0 | 0 | -635.33 | 0 | 0 | 635.33 | 635.33 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | NA | 184 | 132.26 | 0 | 132.26 | CY | 635.33 | 0 | 635.33 | 0
Y | IPCRP1-0815-1030-E | IPCRP1 | IPCRP1 | 0815-1030 | Backfill for Tennis Bldg Footing | N | E |  | NR | P | 1587.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1587.2 | 0 | 0 | 1587.2 | 0 | 0 | 0 | Y | 1587.2 | 0 | 0 | 1587.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 128 | 226.05 | 0 | 226.05 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1030-L | IPCRP1 | IPCRP1 | 0815-1030 | Backfill for Tennis Bldg Footing | N | L |  | NR | P | 5480.79 | 7999.76 | 7999.76 | 7999.76 | 7999.76 | 100 | 0 | 0 | 0 | 0 | Y | 7999.76 | Y | -2518.97 | 0 | 0 | 5480.79 | 0 | 0 | 7999.76 | Y | -2518.97 | 0 | 0 | 5480.79 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7999.76 | 0 | 0 | 7999.76 | 0 | 0 | 0 | 0 | 0 | 0 | -7999.76 | 0 | 0 | 7999.76 | 7999.76 | 0 | 0 | 0 | 51.2 | 0 | 58 | 58 | 51.2 | 58 | 0 | 58 | HR | 128 | 226.05 | 0 | 226.05 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1040-C | IPCRP1 | IPCRP1 | 0815-1040 | CM - Furn Forms & Sheeting, Tennis Bldg | N | C |  | NR | P | 9524 | 30776.26 | 30776.26 | 21760.68 | 30776.26 | 102.1922 | 0 | 0 | 0 | -9482.38 | Y | 21293.88 | Y | -11769.88 | 0 | 0 | 9524 | 0 | 0 | 21293.88 | Y | -11769.88 | 0 | 0 | 9524 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21293.88 | 466.8 | 7300.44 | 21293.88 | 0 | 0 | 0 | 466.8 | 15695.06 | 0 | -21293.88 | 0 | 0 | 21293.88 | 21293.88 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6881.34 | -36 | 6845.34 | NA | 2960 | 2960 | 0 | 2960 | SF | 30776.26 | 9015.58 | 21760.68 | -9482.38
Y | IPCRP1-0815-1040-L | IPCRP1 | IPCRP1 | 0815-1040 | CM - Furn Forms & Sheeting, Tennis Bldg | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2960 | 2960 | 0 | 2960 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1050-C | IPCRP1 | IPCRP1 | 0815-1050 | Building Sub - Tennis, Track, 10th St C.S. (Commo | N | C |  | UNIT | U | 0 | 352694.19 | 352694.19 | 172049.67 | 352694.19 | 53.4258 | 0 | 0 | 0 | -30659.65 | Y | 322034.54 | Y | -322034.54 | 0 | 0 | 0 | 0 | 0 | 322034.54 | Y | -322034.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -322034.54 | 1687.56 | 24062.94 | 322034.54 | 0 | 0 | 0 | 1687.56 | -13200.84 | 0 | -322034.54 | 0 | 0 | 322034.54 | 322034.54 | 0 | 0 | 0 | 0 | 0 | 1230.2 | 1230.2 | 0 | 122669.45 | -121439.25 | 1230.2 | NA | 1 | 0 | 1 | 1 | LS | 352694.19 | 180644.52 | 172049.67 | -30659.65
Y | IPCRP1-0815-1050-L | IPCRP1 | IPCRP1 | 0815-1050 | Building Sub - Tennis, Track, 10th St C.S. (Commo | N | L |  | UNIT | P | 0 | 176696.76 | 176696.76 | 176696.76 | 176696.76 | 217.9093 | 0 | 0 | 0 | -95609.46 | Y | 81087.3 | Y | -81087.3 | 0 | 0 | 0 | 0 | 0 | 81087.3 | Y | -81087.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -81087.3 | 95609.46 | 14723.49 | 81087.3 | 0 | 0 | 0 | 0 | 0 | 0 | -81087.3 | 0 | 0 | 81087.3 | 81087.3 | 0 | 0 | 0 | 0 | 0 | 647.5 | 647.5 | 0 | 1421.5 | -774 | 647.5 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | -95609.46
Y | IPCRP1-0815-1050-S | IPCRP1 | IPCRP1 | 0815-1050 | Building Sub - Tennis, Track, 10th St C.S. (Commo | N | S |  | NR | P | 11575749 | 11409309.47 | 11409309.47 | 564286.53 | 11409309.47 | 5.0694 | 0 | 0 | 0 | -277972.77 | Y | 11131336.7 | Y | 444412.3 | 0 | 0 | 11575749 | 0 | 0 | 11131336.7 | Y | 444412.3 | 0 | 0 | 11575749 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11131336.7 | 903.94 | 262.11 | 11131336.7 | 0 | 0 | 0 | 0 | 903.94 | 0 | -11131336.7 | 0 | 0 | 11131336.7 | 11131336.7 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 15.82 | -12 | 3.82 | NA | 1 | 0 | 1 | 1 | LS | 11409309.47 | 10845022.94 | 564286.53 | -277972.77 | COMMODORE Base Contract @$10,750,000.00 CO#1 Roofing at Canopy #1-2 and Pre-fab Bldg #1-2 @$221K,
Y | IPCRP1-0815-1055-L | IPCRP1 | IPCRP1 | 0815-1055 | CMU Installation Costs | N | L |  | UNIT | P | 0 | 153853.47 | 153853.47 | 153853.47 | 153853.47 | 91.575 | 0 | 0 | 0 | 14154.68 | Y | 168008.15 | Y | -168008.15 | 0 | 0 | 0 | 0 | 0 | 168008.15 | Y | -168008.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -168008.15 | 0 | 35764.26 | 168008.15 | 0 | 0 | 0 | 0 | 0 | 0 | -168008.15 | 0 | 0 | 168008.15 | 168008.15 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 1306 | -106 | 1200 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 14154.68 | Keeping track so this can be deducted from IBS Enterprise PO#6132
N | IPCRP1-0815-1055-S | IPCRP1 | IPCRP1 | 0815-1055 | CMU Installation Costs | N | S |  | UNIT | A | 0 | 1044.59 | 1044.59 | 1044.59 | 1044.59 | 100 | 0 | 0 | 0 | 0 | N | 1044.59 | N | -1044.59 | 0 | 0 | 0 | 0 | 0 | 1044.59 | N | -1044.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1044.59 | 258.27 | 786.32 | 1044.59 | 0 | 0 | 0 | 0 | 258.27 | 0 | -1044.59 | 0 | 0 | 1044.59 | 1044.59 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 8 | NA | 0 | 1 | 0 | 1 | LS | 1044.59 | 0 | 1044.59 | 0
Y | IPCRP1-0815-1060-L | IPCRP1 | IPCRP1 | 0815-1060 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1405 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0815-1060-S | IPCRP1 | IPCRP1 | 0815-1060 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | S |  | NR | P | 20091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20091.5 | 0 | 0 | 20091.5 | 0 | 0 | 0 | Y | 20091.5 | 0 | 0 | 20091.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1405 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work included in Sheet Applied Waterproofing Membrane Sub (D-Star), cost code 0178-1000
Y | IPCRP1-0815-1070-L | IPCRP1 | IPCRP1 | 0815-1070 | Furn & Inst Drainage Floor Hatches | N | L |  | UNIT | P | 0 | 1384.55 | 1384.55 | 1384.55 | 1384.55 | 16.4827 | 0 | 0 | 0 | 7015.45 | Y | 8400 | Y | -8400 | 0 | 0 | 0 | 0 | 0 | 8400 | Y | -8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8400 | 0 | 0 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | -8400 | 0 | 0 | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 10 | 50 | 60 | HR | 0 | 1 | 4 | 5 | EA | 0 | 0 | 0 | 7015.45
Y | IPCRP1-0815-1070-M | IPCRP1 | IPCRP1 | 0815-1070 | Furn & Inst Drainage Floor Hatches | N | M |  | UNIT | U | 0 | 5446.59 | 5446.59 | 5393.88 | 5446.59 | 99.0322 | 0 | 0 | 0 | 0 | N | 5446.59 | N | -5446.59 | 0 | 0 | 0 | 0 | 0 | 5446.59 | N | -5446.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5446.59 | 0 | 0 | 5446.59 | 0 | 0 | 0 | 0 | 0 | 0 | -5446.59 | 0 | 0 | 5446.59 | 5446.59 | 0 | 0 | 0 | 0 | 0 | 10.94 | 10.94 | 0 | 4 | 6.94 | 10.94 | NA | 0 | 1 | 4 | 5 | EA | 5446.59 | 52.71 | 5393.88 | 0
Y | IPCRP1-0816-0000-L | IPCRP1 | IPCRP1 | 0816-0000 | TRACK BUILDING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0816-0000-R | IPCRP1 | IPCRP1 | 0816-0000 | TRACK BUILDING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15000000 | 0 | 0 | 15000000 | 0 | 15000000 | 8100 | 0 | N | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | Work included in Sheet Applied Waterproofing Membrane Sub (D-Star), cost code 0178-1000
Y | IPCRP1-0816-1000-E | IPCRP1 | IPCRP1 | 0816-1000 | Excavate & Sheet for Track Bldg Footing | N | E |  | NR | P | 4171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4171 | 0 | 0 | 4171 | 0 | 0 | 0 | Y | 4171 | 0 | 0 | 4171 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 782 | 0 | 782 | 782 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0816-1000-L | IPCRP1 | IPCRP1 | 0816-1000 | Excavate & Sheet for Track Bldg Footing | N | L |  | NR | P | 15721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15721 | N | 15721 | N | 0 | 0 | 0 | 15721 | 0 | 0 | 15721 | N | 0 | 0 | 0 | 15721 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15721 | 0 | 0 | 15721 | 0 | 0 | 0 | 0 | 0 | 0 | -15721 | 0 | 0 | 15721 | 15721 | 0 | 0 | 0 | 135.12 | 0 | 135.12 | 135.12 | 135.12 | 0 | 135.12 | 135.12 | HR | 782 | 0 | 782 | 782 | CY | 0 | 0 | 0 | 15721
Y | IPCRP1-0816-1010-L | IPCRP1 | IPCRP1 | 0816-1010 | Form & Strip for Track Bldg Footing | N | L |  | NR | P | 522526.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522526.36 | N | 522526.36 | N | 0 | 0 | 0 | 522526.36 | 0 | 0 | 522526.36 | N | 0 | 0 | 0 | 522526.36 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -522526.36 | 0 | 0 | 522526.36 | 0 | 0 | 0 | 0 | 0 | 0 | -522526.36 | 0 | 0 | 522526.36 | 522526.36 | 0 | 0 | 0 | 4422.18 | 0 | 4422.18 | 4422.18 | 4422.18 | 0 | 4422.18 | 4422.18 | HR | 11365 | 0 | 11365 | 11365 | SF | 0 | 0 | 0 | 522526.36
Y | IPCRP1-0816-1020-E | IPCRP1 | IPCRP1 | 0816-1020 | Place Conc Found for Track Bldg Footing | N | E |  | NR | P | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | Y | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 560 | 0 | 560 | 560 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0816-1020-L | IPCRP1 | IPCRP1 | 0816-1020 | Place Conc Found for Track Bldg Footing | N | L |  | NR | P | 23142.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23142.84 | N | 23142.84 | N | 0 | 0 | 0 | 23142.84 | 0 | 0 | 23142.84 | N | 0 | 0 | 0 | 23142.84 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23142.84 | 0 | 0 | 23142.84 | 0 | 0 | 0 | 0 | 0 | 0 | -23142.84 | 0 | 0 | 23142.84 | 23142.84 | 0 | 0 | 0 | 216 | 0 | 216 | 216 | 216 | 0 | 216 | 216 | HR | 560 | 0 | 560 | 560 | CY | 0 | 0 | 0 | 23142.84
Y | IPCRP1-0816-1030-E | IPCRP1 | IPCRP1 | 0816-1030 | Backfill for Track Bldg Footing | N | E |  | NR | P | 3596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3596 | 0 | 0 | 3596 | 0 | 0 | 0 | Y | 3596 | 0 | 0 | 3596 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 290 | 0 | 290 | 290 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0816-1030-L | IPCRP1 | IPCRP1 | 0816-1030 | Backfill for Track Bldg Footing | N | L |  | NR | P | 12417.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12417.4 | N | 12417.4 | N | 0 | 0 | 0 | 12417.4 | 0 | 0 | 12417.4 | N | 0 | 0 | 0 | 12417.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12417.4 | 0 | 0 | 12417.4 | 0 | 0 | 0 | 0 | 0 | 0 | -12417.4 | 0 | 0 | 12417.4 | 12417.4 | 0 | 0 | 0 | 116 | 0 | 116 | 116 | 116 | 0 | 116 | 116 | HR | 290 | 0 | 290 | 290 | CY | 0 | 0 | 0 | 12417.4
Y | IPCRP1-0816-1040-C | IPCRP1 | IPCRP1 | 0816-1040 | CM - Furn Forms & Sheeting, Track Bldg | N | C |  | NR | P | 37632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37632 | N | 37632 | N | 0 | 0 | 0 | 37632 | 0 | 0 | 37632 | N | 0 | 0 | 0 | 37632 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -37632 | 0 | 0 | 37632 | 0 | 0 | 0 | 0 | 0 | 0 | -37632 | 0 | 0 | 37632 | 37632 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 11565 | 0 | 11565 | 11565 | SF | 0 | 0 | 0 | 37632
Y | IPCRP1-0816-1040-L | IPCRP1 | IPCRP1 | 0816-1040 | CM - Furn Forms & Sheeting, Track Bldg | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 11565 | 0 | 11565 | 11565 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0816-1050-L | IPCRP1 | IPCRP1 | 0816-1050 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5100 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0816-1050-S | IPCRP1 | IPCRP1 | 0816-1050 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | S |  | NR | P | 72930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 72930 | 0 | 0 | 72930 | 0 | 0 | 0 | N | 72930 | 0 | 0 | 72930 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5100 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work included in Sheet Applied Waterproofing Membrane Sub (D-Star), cost code 0178-1000
N | IPCRP1-0816-1060-L | IPCRP1 | IPCRP1 | 0816-1060 | Fire Protection Sub at Track & Field Building | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | IPCRP1-0816-1060-S | IPCRP1 | IPCRP1 | 0816-1060 | Fire Protection Sub at Track & Field Building | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | Y | 99000 | Y | -99000 | 0 | 0 | 0 | 0 | 0 | 99000 | Y | -99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -99000 | 0 | 0 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | -99000 | 0 | 0 | 99000 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 99000 | Original budget in bid was 30K. Was lumped together with Mech Sub scope and missed. Fire Protection Sub – RAEL Automatic Sprinkler Co.
Y | IPCRP1-0817-0000-L | IPCRP1 | IPCRP1 | 0817-0000 | 10TH STREET COMFORT STATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0817-0000-R | IPCRP1 | IPCRP1 | 0817-0000 | 10TH STREET COMFORT STATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4000000 | 0 | 0 | 4000000 | 0 | 4000000 | 1200 | 0 | N | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0817-1000-E | IPCRP1 | IPCRP1 | 0817-1000 | Excavate & Sheet for 10th St C.S. Footing | N | E |  | NR | P | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2053 | 0 | 0 | 2053 | 0 | 0 | 0 | Y | 2053 | 0 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 385 | 0 | 385 | 385 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0817-1000-L | IPCRP1 | IPCRP1 | 0817-1000 | Excavate & Sheet for 10th St C.S. Footing | N | L |  | NR | P | 14925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14925 | N | 14925 | N | 0 | 0 | 0 | 14925 | 0 | 0 | 14925 | N | 0 | 0 | 0 | 14925 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14925 | 0 | 0 | 14925 | 0 | 0 | 0 | 0 | 0 | 0 | -14925 | 0 | 0 | 14925 | 14925 | 0 | 0 | 0 | 123.7 | 0 | 123.7 | 123.7 | 123.7 | 0 | 123.7 | 123.7 | HR | 385 | 0 | 385 | 385 | CY | 0 | 0 | 0 | 14925
Y | IPCRP1-0817-1010-L | IPCRP1 | IPCRP1 | 0817-1010 | Form & Strip for 10th St C.S. Footing | N | L |  | NR | P | 222260.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222260.86 | N | 222260.86 | N | 0 | 0 | 0 | 222260.86 | 0 | 0 | 222260.86 | N | 0 | 0 | 0 | 222260.86 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -222260.86 | 0 | 0 | 222260.86 | 0 | 0 | 0 | 0 | 0 | 0 | -222260.86 | 0 | 0 | 222260.86 | 222260.86 | 0 | 0 | 0 | 1881.01 | 0 | 1881.01 | 1881.01 | 1881.01 | 0 | 1881.01 | 1881.01 | HR | 4853 | 0 | 4853 | 4853 | SF | 0 | 0 | 0 | 222260.86
Y | IPCRP1-0817-1020-E | IPCRP1 | IPCRP1 | 0817-1020 | Place Conc Found for 10th St C.S. Footing | N | E |  | NR | P | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | Y | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 167 | 0 | 167 | 167 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0817-1020-L | IPCRP1 | IPCRP1 | 0817-1020 | Place Conc Found for 10th St C.S. Footing | N | L |  | NR | P | 23142.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23142.84 | N | 23142.84 | N | 0 | 0 | 0 | 23142.84 | 0 | 0 | 23142.84 | N | 0 | 0 | 0 | 23142.84 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23142.84 | 0 | 0 | 23142.84 | 0 | 0 | 0 | 0 | 0 | 0 | -23142.84 | 0 | 0 | 23142.84 | 23142.84 | 0 | 0 | 0 | 216 | 0 | 216 | 216 | 216 | 0 | 216 | 216 | HR | 167 | 0 | 167 | 167 | CY | 0 | 0 | 0 | 23142.84
Y | IPCRP1-0817-1030-E | IPCRP1 | IPCRP1 | 0817-1030 | Backfill for 10th St C.S. Footing | N | E |  | NR | P | 3930.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3930.8 | 0 | 0 | 3930.8 | 0 | 0 | 0 | Y | 3930.8 | 0 | 0 | 3930.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 317 | 0 | 317 | 317 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0817-1030-L | IPCRP1 | IPCRP1 | 0817-1030 | Backfill for 10th St C.S. Footing | N | L |  | NR | P | 13573.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13573.5 | N | 13573.5 | N | 0 | 0 | 0 | 13573.5 | 0 | 0 | 13573.5 | N | 0 | 0 | 0 | 13573.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13573.5 | 0 | 0 | 13573.5 | 0 | 0 | 0 | 0 | 0 | 0 | -13573.5 | 0 | 0 | 13573.5 | 13573.5 | 0 | 0 | 0 | 126.8 | 0 | 126.8 | 126.8 | 126.8 | 0 | 126.8 | 126.8 | HR | 317 | 0 | 317 | 317 | CY | 0 | 0 | 0 | 13573.5
Y | IPCRP1-0817-1030-S | IPCRP1 | IPCRP1 | 0817-1030 | Backfill for 10th St C.S. Footing | N | S |  | UNIT | A | 0 | 987.34 | 987.34 | 987.34 | 987.34 | 100 | 0 | 0 | 0 | 0 | N | 987.34 | N | -987.34 | 0 | 0 | 0 | 0 | 0 | 987.34 | N | -987.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -987.34 | 0 | 0 | 987.34 | 0 | 0 | 0 | 0 | 0 | 0 | -987.34 | 0 | 0 | 987.34 | 987.34 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 8 | NA | 317 | 0 | 317 | 317 | CY | 987.34 | 0 | 987.34 | 0
Y | IPCRP1-0817-1040-C | IPCRP1 | IPCRP1 | 0817-1040 | CM - Furn Forms & Sheeting, 10th St C.S. | N | C |  | NR | P | 19017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19017 | N | 19017 | N | 0 | 0 | 0 | 19017 | 0 | 0 | 19017 | N | 0 | 0 | 0 | 19017 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19017 | 0 | 0 | 19017 | 0 | 0 | 0 | 0 | 0 | 0 | -19017 | 0 | 0 | 19017 | 19017 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 6095 | 0 | 6095 | 6095 | SF | 0 | 0 | 0 | 19017
Y | IPCRP1-0817-1040-L | IPCRP1 | IPCRP1 | 0817-1040 | CM - Furn Forms & Sheeting, 10th St C.S. | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6095 | 0 | 6095 | 6095 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0817-1050-L | IPCRP1 | IPCRP1 | 0817-1050 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5100 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0817-1050-S | IPCRP1 | IPCRP1 | 0817-1050 | F&I 3 Rigid Insulation Found (Waterproof) Sub | N | S |  | NR | P | 15730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 15730 | 0 | 0 | 15730 | 0 | 0 | 0 | N | 15730 | 0 | 0 | 15730 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5100 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work included in Sheet Applied Waterproofing Membrane Sub (D-Star), cost code 0178-1000
Y | IPCRP1-0818-0000-L | IPCRP1 | IPCRP1 | 0818-0000 | M+O CANOPY STRUCT, AREA 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0818-0000-R | IPCRP1 | IPCRP1 | 0818-0000 | M+O CANOPY STRUCT, AREA 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 1500000 | 705000 | 0 | N | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-0000-L | IPCRP1 | IPCRP1 | 0819-0000 | M+O CANOPY STRUCT, AREA 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-0000-R | IPCRP1 | IPCRP1 | 0819-0000 | M+O CANOPY STRUCT, AREA 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2100000 | 0 | 0 | 2100000 | 0 | 2100000 | 987000 | 0 | N | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1000-C | IPCRP1 | IPCRP1 | 0819-1000 | Excav-sht-form-pour-bfill, M&O Canopy Area 1 Foot | N | C |  | NR | P | 2717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2717 | 0 | 0 | 2717 | 0 | 0 | 0 | Y | 2717 | 0 | 0 | 2717 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1000-E | IPCRP1 | IPCRP1 | 0819-1000 | Excav-sht-form-pour-bfill, M&O Canopy Area 1 Foot | N | E |  | NR | P | 1286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1286 | 0 | 0 | 1286 | 0 | 0 | 0 | Y | 1286 | 0 | 0 | 1286 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1000-L | IPCRP1 | IPCRP1 | 0819-1000 | Excav-sht-form-pour-bfill, M&O Canopy Area 1 Foot | N | L |  | NR | P | 17779.14 | 25973.76 | 25973.76 | 25973.76 | 25973.76 | 100 | 0 | 0 | 0 | 0 | Y | 25973.76 | Y | -8194.62 | 0 | 0 | 17779.14 | 0 | 0 | 25973.76 | Y | -8194.62 | 0 | 0 | 17779.14 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25973.76 | 0 | 0 | 25973.76 | 0 | 0 | 0 | 0 | 0 | 0 | -25973.76 | 0 | 0 | 25973.76 | 25973.76 | 0 | 0 | 0 | 153.86 | 0 | 200 | 200 | 153.86 | 200 | 0 | 200 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1000-S | IPCRP1 | IPCRP1 | 0819-1000 | Excav-sht-form-pour-bfill, M&O Canopy Area 1 Foot | N | S |  | UNIT | A | 0 | 1078.89 | 1078.89 | 1078.89 | 1078.89 | 100 | 0 | 0 | 0 | 0 | N | 1078.89 | N | -1078.89 | 0 | 0 | 0 | 0 | 0 | 1078.89 | N | -1078.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1078.89 | 0 | 0 | 1078.89 | 0 | 0 | 0 | 0 | 0 | 0 | -1078.89 | 0 | 0 | 1078.89 | 1078.89 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8.5 | 0 | 8.5 | 0 | 8.5 | NA | 1 | 1 | 0 | 1 | LS | 1078.89 | 0 | 1078.89 | 0
Y | IPCRP1-0819-1005-C | IPCRP1 | IPCRP1 | 0819-1005 | Ex-Sht-Frm-Pour-BF MO Canop Area 2 Footing | N | C |  | UNIT | U | 4568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 4568 | 0 | 0 | 4568 | 0 | 0 | 0 | Y | 4568 | 0 | 0 | 4568 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1005-E | IPCRP1 | IPCRP1 | 0819-1005 | Ex-Sht-Frm-Pour-BF MO Canop Area 2 Footing | N | E |  | UNIT | A | 2582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2582 | 0 | 0 | 2582 | 0 | 0 | 0 | Y | 2582 | 0 | 0 | 2582 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1005-L | IPCRP1 | IPCRP1 | 0819-1005 | Ex-Sht-Frm-Pour-BF MO Canop Area 2 Footing | N | L |  | UNIT | P | 26768.3 | 34128.9 | 34128.9 | 34128.9 | 34128.9 | 100 | 0 | 0 | 0 | 0 | Y | 34128.9 | Y | -7360.6 | 0 | 0 | 26768.3 | 0 | 0 | 34128.9 | Y | -7360.6 | 0 | 0 | 26768.3 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -34128.9 | 0 | 234.78 | 34128.9 | 0 | 0 | 0 | 0 | 0 | 0 | -34128.9 | 0 | 0 | 34128.9 | 34128.9 | 0 | 0 | 0 | 231.06 | 0 | 267 | 267 | 231.06 | 267 | 0 | 267 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1005-S | IPCRP1 | IPCRP1 | 0819-1005 | Ex-Sht-Frm-Pour-BF MO Canop Area 2 Footing | N | S |  | UNIT | A | 0 | 626.85 | 626.85 | 626.85 | 626.85 | 100 | 0 | 0 | 0 | 0 | N | 626.85 | N | -626.85 | 0 | 0 | 0 | 0 | 0 | 626.85 | N | -626.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -626.85 | 0 | 0 | 626.85 | 0 | 0 | 0 | 0 | 0 | 0 | -626.85 | 0 | 0 | 626.85 | 626.85 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | NA | 1 | 1 | 0 | 1 | LS | 626.85 | 0 | 626.85 | 0
N | IPCRP1-0819-1010-L | IPCRP1 | IPCRP1 | 0819-1010 | HP Piles 12X53 Sub, M&O Canopy Area 1 & 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2288 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1010-S | IPCRP1 | IPCRP1 | 0819-1010 | HP Piles 12X53 Sub, M&O Canopy Area 1 & 2 | N | S |  | NR | A | 343200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 343190 | 0 | 0 | 343200 | 0 | 0 | 10 | Y | 343190 | 0 | 0 | 343200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 2288 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 10
Y | IPCRP1-0819-1020-C | IPCRP1 | IPCRP1 | 0819-1020 | SS Roof Panel & Cladding Sub | N | C |  | UNIT | U | 0 | 21822 | 21822 | 21822 | 21822 | 100 | 0 | 0 | 0 | 0 | N | 21822 | N | -21822 | 0 | 0 | 0 | 0 | 0 | 21822 | N | -21822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21822 | 0 | 0 | 21822 | 0 | 0 | 0 | 0 | 0 | 0 | -21822 | 0 | 0 | 21822 | 21822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 0.1 | 0.9 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1020-L | IPCRP1 | IPCRP1 | 0819-1020 | SS Roof Panel & Cladding Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.1 | 0.9 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0819-1020-S | IPCRP1 | IPCRP1 | 0819-1020 | SS Roof Panel & Cladding Sub | N | S |  | NR | A | 1382992 | 1328120.35 | 1328120.35 | 158936.52 | 1328120.35 | 11.967 | 0 | 0 | 0 | 0 | Y | 1328120.35 | Y | 54871.65 | 0 | 0 | 1382992 | 0 | 0 | 1328120.35 | Y | 54871.65 | 0 | 0 | 1382992 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1328120.35 | 0 | 23258.42 | 1328120.35 | 0 | 0 | 0 | 0 | 0 | 0 | -1328120.35 | 0 | 0 | 1328120.35 | 1328120.35 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.26 | 0.74 | 1 | NA | 1 | 0.1 | 0.9 | 1 | LS | 1328120.35 | 1169183.83 | 158936.52 | 0 | MARIANI METAL Base Contract @$ 1,273,676.00
Y | IPCRP1-0819-1050-L | IPCRP1 | IPCRP1 | 0819-1050 | Ex-Sht-Frm-Pour-BF MO Canop Area 2 Footing | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-0820-0000-L | IPCRP1 | IPCRP1 | 0820-0000 | SAND BASE FOR UTIL LINE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0820-0000-R | IPCRP1 | IPCRP1 | 0820-0000 | SAND BASE FOR UTIL LINE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 207570 | 0 | 0 | 207570 | 0 | 207570 | 53216.8 | 0 | N | 207570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0821-0000-L | IPCRP1 | IPCRP1 | 0821-0000 | WET CONNECTION - 6 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0821-0000-R | IPCRP1 | IPCRP1 | 0821-0000 | WET CONNECTION - 6 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 304000 | 0 | 0 | 304000 | 0 | 304000 | 0 | 0 | N | 304000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0822-0000-L | IPCRP1 | IPCRP1 | 0822-0000 | WET CONNECTION - 8 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0822-0000-R | IPCRP1 | IPCRP1 | 0822-0000 | WET CONNECTION - 8 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | N | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0823-0000-L | IPCRP1 | IPCRP1 | 0823-0000 | RPZ & WATER METER W/REMOTE & HEATED ENCLOSURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0823-0000-R | IPCRP1 | IPCRP1 | 0823-0000 | RPZ & WATER METER W/REMOTE & HEATED ENCLOSURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 159000 | 0 | 0 | 159000 | 0 | 159000 | 53000 | 0 | N | 159000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0824-0000-L | IPCRP1 | IPCRP1 | 0824-0000 | 4 DIA. DI CEMENT WATER PIPE LINE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0824-0000-R | IPCRP1 | IPCRP1 | 0824-0000 | 4 DIA. DI CEMENT WATER PIPE LINE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 21000 | 0 | 0 | 21000 | 0 | 21000 | 14147 | 0 | N | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0825-0000-L | IPCRP1 | IPCRP1 | 0825-0000 | 6 DIA. DI CEMENT WATER PIPE LINE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0825-0000-R | IPCRP1 | IPCRP1 | 0825-0000 | 6 DIA. DI CEMENT WATER PIPE LINE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 245000 | 0 | 0 | 245000 | 0 | 245000 | 98269.5 | 0 | N | 245000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0826-0000-L | IPCRP1 | IPCRP1 | 0826-0000 | 8 DIA. DI CEMENT WATER PIPE LINE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0826-0000-R | IPCRP1 | IPCRP1 | 0826-0000 | 8 DIA. DI CEMENT WATER PIPE LINE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 90000 | 0 | 0 | 90000 | 0 | 90000 | 1275270 | 0 | N | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0827-0000-L | IPCRP1 | IPCRP1 | 0827-0000 | 10 DIA. DI CEMENT WATER PIPE LINE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0827-0000-R | IPCRP1 | IPCRP1 | 0827-0000 | 10 DIA. DI CEMENT WATER PIPE LINE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2700000 | 0 | 0 | 2700000 | 0 | 2700000 | 0 | 0 | N | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0828-0000-L | IPCRP1 | IPCRP1 | 0828-0000 | WET CONNECTION - 4 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0828-0000-R | IPCRP1 | IPCRP1 | 0828-0000 | WET CONNECTION - 4 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10000 | 0 | 0 | 10000 | 0 | 10000 | 20000 | 0 | N | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0829-0000-L | IPCRP1 | IPCRP1 | 0829-0000 | GATE VALVE - MJ - 4 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0829-0000-R | IPCRP1 | IPCRP1 | 0829-0000 | GATE VALVE - MJ - 4 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4000 | 0 | 0 | 4000 | 0 | 4000 | 8000 | 0 | N | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0830-0000-L | IPCRP1 | IPCRP1 | 0830-0000 | GATE VALVE - MJ - 6 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0830-0000-R | IPCRP1 | IPCRP1 | 0830-0000 | GATE VALVE - MJ - 6 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4200 | 0 | 0 | 4200 | 0 | 4200 | 0 | 0 | N | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0831-0000-L | IPCRP1 | IPCRP1 | 0831-0000 | GATE VALVE - MJ - 8 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0831-0000-R | IPCRP1 | IPCRP1 | 0831-0000 | GATE VALVE - MJ - 8 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15300 | 0 | 0 | 15300 | 0 | 15300 | 25500 | 0 | N | 15300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0832-0000-L | IPCRP1 | IPCRP1 | 0832-0000 | GATE VALVE - MJ - 10 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0832-0000-R | IPCRP1 | IPCRP1 | 0832-0000 | GATE VALVE - MJ - 10 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0832-1000-L | IPCRP1 | IPCRP1 | 0832-1000 | Parks Utility Subcontractor (Akela) | N | L |  | UNIT | P | 0 | 96606.88 | 96606.88 | 96606.88 | 96606.88 | 100 | 0 | 0 | 0 | 0 | Y | 96606.88 | Y | -96606.88 | 0 | 0 | 0 | 0 | 0 | 96606.88 | Y | -96606.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -96606.88 | 0 | 0 | 96606.88 | 0 | 0 | 0 | 0 | 0 | 0 | -96606.88 | 0 | 0 | 96606.88 | 96606.88 | 0 | 0 | 0 | 0 | 0 | 783 | 783 | 0 | 783 | 0 | 783 | HR | 1 | 0.34 | 0.66 | 1 | LS | 0 | 0 | 0 | 0 | added on 01/31/22 as advised by VS - labor required for 8” DIA ductile iron cement water Pipeline
Y | IPCRP1-0832-1000-S | IPCRP1 | IPCRP1 | 0832-1000 | Parks Utility Subcontractor (Akela) | N | S |  | NR | A | 13644378 | 22310479.76 | 22310479.76 | 7854540.78 | 22310479.76 | 35.3642 | 0 | 0 | 0 | -100061.67 | Y | 22210418.09 | Y | -8566040.09 | 0 | 0 | 13644378 | 0 | 0 | 22210418.09 | Y | -8566040.09 | 0 | 0 | 13644378 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22210418.09 | 88205.88 | 9000 | 22210418.09 | 0 | 0 | 0 | 0 | 72205.88 | 0 | -22210418.09 | 0 | 0 | 22210418.09 | 22210418.09 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 145319.57 | -145318.57 | 1 | NA | 1 | 0.34 | 0.66 | 1 | LS | 22310479.76 | 14455938.98 | 7854540.78 | -100061.67 | AKELA Base Contract @$13,757,525.62
Y | IPCRP1-0833-0000-L | IPCRP1 | IPCRP1 | 0833-0000 | QUICK COUPLING VALVE & VACUUM BREAKER W/CHAMBER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0833-0000-R | IPCRP1 | IPCRP1 | 0833-0000 | QUICK COUPLING VALVE & VACUUM BREAKER W/CHAMBER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 80000 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0834-0000-L | IPCRP1 | IPCRP1 | 0834-0000 | FIRE HYDRANT W/FENDERS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0834-0000-R | IPCRP1 | IPCRP1 | 0834-0000 | FIRE HYDRANT W/FENDERS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 341000 | 0 | 0 | 341000 | 0 | 341000 | 187000 | 0 | N | 341000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0835-0000-L | IPCRP1 | IPCRP1 | 0835-0000 | DECORATIVE ST SPRAY FIXTURES DELANCY ST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0835-0000-R | IPCRP1 | IPCRP1 | 0835-0000 | DECORATIVE ST SPRAY FIXTURES DELANCY ST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 85000 | 0 | 0 | 85000 | 0 | 85000 | 85000 | 0 | N | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0836-0000-L | IPCRP1 | IPCRP1 | 0836-0000 | DECORATIVE ST SPRAY FIXTURES HOUSTON ST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0836-0000-R | IPCRP1 | IPCRP1 | 0836-0000 | DECORATIVE ST SPRAY FIXTURES HOUSTON ST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0837-0000-L | IPCRP1 | IPCRP1 | 0837-0000 | DECORATIVE ST SPRAY FIXTURES 10TH ST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0837-0000-R | IPCRP1 | IPCRP1 | 0837-0000 | DECORATIVE ST SPRAY FIXTURES 10TH ST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 85000 | 0 | 0 | 85000 | 0 | 85000 | 0 | 0 | N | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0838-0000-L | IPCRP1 | IPCRP1 | 0838-0000 | SPORT ST SPRAY FIXTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0838-0000-R | IPCRP1 | IPCRP1 | 0838-0000 | SPORT ST SPRAY FIXTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 440000 | 0 | 0 | 440000 | 0 | 440000 | 140000 | 0 | N | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0839-0000-L | IPCRP1 | IPCRP1 | 0839-0000 | WATER TAP 2 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0839-0000-R | IPCRP1 | IPCRP1 | 0839-0000 | WATER TAP 2 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 81000 | 0 | 0 | 81000 | 0 | 81000 | 0 | 0 | N | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0840-0000-L | IPCRP1 | IPCRP1 | 0840-0000 | CURB & PROPERTY LINE VALVES - 2 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0840-0000-R | IPCRP1 | IPCRP1 | 0840-0000 | CURB & PROPERTY LINE VALVES - 2 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 1500 | 0 | N | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0841-0000-L | IPCRP1 | IPCRP1 | 0841-0000 | PLUG VALVE - 1 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0841-0000-R | IPCRP1 | IPCRP1 | 0841-0000 | PLUG VALVE - 1 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13800 | 0 | 0 | 13800 | 0 | 13800 | 2400 | 0 | N | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-0842-0000-L | IPCRP1 | IPCRP1 | 0842-0000 | PLUG VALVE - 1.5 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0842-0000-R | IPCRP1 | IPCRP1 | 0842-0000 | PLUG VALVE - 1.5 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 84000 | 0 | 0 | 84000 | 0 | 84000 | 31800 | 0 | N | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0843-0000-L | IPCRP1 | IPCRP1 | 0843-0000 | PLUG VALVE - 2 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0843-0000-R | IPCRP1 | IPCRP1 | 0843-0000 | PLUG VALVE - 2 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3000 | 0 | 0 | 3000 | 0 | 3000 | 600 | 0 | N | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0844-0000-L | IPCRP1 | IPCRP1 | 0844-0000 | TYPE K COPPER TUBING - 1 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0844-0000-R | IPCRP1 | IPCRP1 | 0844-0000 | TYPE K COPPER TUBING - 1 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 111000 | 0 | 0 | 111000 | 0 | 111000 | 3912 | 0 | N | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0845-0000-L | IPCRP1 | IPCRP1 | 0845-0000 | TYPE K COPPER TUBING - 1.25 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0845-0000-R | IPCRP1 | IPCRP1 | 0845-0000 | TYPE K COPPER TUBING - 1.25 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19500 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | N | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0846-0000-L | IPCRP1 | IPCRP1 | 0846-0000 | TYPE K COPPER TUBING - 1.5 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0846-0000-R | IPCRP1 | IPCRP1 | 0846-0000 | TYPE K COPPER TUBING - 1.5 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 539250 | 0 | 0 | 539250 | 0 | 539250 | 218031 | 0 | N | 539250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0847-0000-L | IPCRP1 | IPCRP1 | 0847-0000 | TYPE K COPPER TUBING - 2 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0847-0000-R | IPCRP1 | IPCRP1 | 0847-0000 | TYPE K COPPER TUBING - 2 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1226250 | 0 | 0 | 1226250 | 0 | 1226250 | 490860 | 0 | N | 1226250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0847-1000-L | IPCRP1 | IPCRP1 | 0847-1000 | Water Main Subcontractor (Akela) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | Work included in Parks Utility Sub (Akela)
Y | IPCRP1-0847-1000-S | IPCRP1 | IPCRP1 | 0847-1000 | Water Main Subcontractor (Akela) | N | S |  | NR | A | 5358859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5358859 | 0 | 0 | 5358859 | 0 | 0 | 0 | Y | 5358859 | 0 | 0 | 5358859 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0848-0000-L | IPCRP1 | IPCRP1 | 0848-0000 | CAST IRON VALVE BOX, 5.25 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0848-0000-R | IPCRP1 | IPCRP1 | 0848-0000 | CAST IRON VALVE BOX, 5.25 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35550 | 0 | 0 | 35550 | 0 | 35550 | 10800 | 0 | N | 35550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0849-0000-L | IPCRP1 | IPCRP1 | 0849-0000 | BOTTLE FILLER W/ HI-LO DRINKING FOUNTAIN BASINS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0849-0000-R | IPCRP1 | IPCRP1 | 0849-0000 | BOTTLE FILLER W/ HI-LO DRINKING FOUNTAIN BASINS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 357000 | 0 | 0 | 357000 | 0 | 357000 | 51000 | 0 | N | 357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0850-0000-L | IPCRP1 | IPCRP1 | 0850-0000 | TYPE K COPPER TUBING - 3 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0850-0000-R | IPCRP1 | IPCRP1 | 0850-0000 | TYPE K COPPER TUBING - 3 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 241200 | 0 | 0 | 241200 | 0 | 241200 | 0 | 0 | N | 241200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0851-0000-L | IPCRP1 | IPCRP1 | 0851-0000 | IN-GROUND IRRIGATION SYSTEM-AUTOMATIC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0851-0000-R | IPCRP1 | IPCRP1 | 0851-0000 | IN-GROUND IRRIGATION SYSTEM-AUTOMATIC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2194280 | 0 | 0 | 2194280 | 0 | 2194280 | 345181.54 | 0 | N | 2194280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2194280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0851-1000-L | IPCRP1 | IPCRP1 | 0851-1000 | In Ground Irrigation Sub (National Lawn Sprinklers | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 199480 | 22016.72 | 85162.28 | 107179 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0851-1000-S | IPCRP1 | IPCRP1 | 0851-1000 | In Ground Irrigation Sub (National Lawn Sprinklers | N | S |  | NR | A | 1994800 | 3452043.75 | 3452043.75 | 1037486.21 | 3452043.75 | 30.0543 | 0 | 0 | 0 | 0 | Y | 3452043.75 | Y | -1457243.75 | 0 | 0 | 1994800 | 0 | 0 | 3452043.75 | Y | -1457243.75 | 0 | 0 | 1994800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3452043.75 | 0 | 75220.96 | 3452043.75 | 0 | 0 | 0 | 0 | 0 | 0 | -3452043.75 | 0 | 0 | 3452043.75 | 3452043.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 398964.9 | -398964.9 | 0 | NA | 199480 | 22016.72 | 85162.28 | 107179 | SY | 3452043.75 | 2414557.54 | 1037486.21 | 0 | National Irrigation Services ($3,449,009.20). Field take-off is 50% of the Engineer's Estimate. Potential underrun and loss of $1M.
Y | IPCRP1-0851-1010-L | IPCRP1 | IPCRP1 | 0851-1010 | Support fr Irrigation Sub(National Lawn Sprinkler) | N | L |  | UNIT | P | 0 | 22804.4 | 22804.4 | 22804.4 | 22804.4 | 37.8866 | 0 | 0 | 0 | 37386.81 | Y | 60191.21 | Y | -60191.21 | 0 | 0 | 0 | 0 | 0 | 60191.21 | Y | -60191.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60191.21 | 0 | 594.95 | 60191.21 | 0 | 0 | 0 | 0 | 0 | 0 | -60191.21 | 0 | 0 | 60191.21 | 60191.21 | 0 | 0 | 0 | 0 | 0 | 499.59 | 499.59 | 0 | 189 | 310.59 | 499.59 | HR | 0 | 70 | 75 | 145 | EA | 0 | 0 | 0 | 37386.81 | SL (10/23) QTD = 47.0 as of 9/30/24 Phase 1 quantity (68ea). Phase 2 drawings not done yet. Estimate 68ea for Phase 2. - total 136ea. See Sam Litman email dated 2/8/24 w takeoffs for sleeves. Quantity was increased 4x, due to response to RFI#881, which requires 3 extra sleeves for every crossing.
Y | IPCRP1-0851-1010-M | IPCRP1 | IPCRP1 | 0851-1010 | Support fr Irrigation Sub(National Lawn Sprinkler) | N | M |  | UNIT | U | 0 | 63920.27 | 63920.27 | 56140.98 | 63920.27 | 66.8345 | 0 | 0 | 0 | 20079.73 | Y | 84000 | Y | -84000 | 0 | 0 | 0 | 0 | 0 | 84000 | Y | -84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -84000 | 0 | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | -84000 | 0 | 0 | 84000 | 84000 | 0 | 0 | 0 | 0 | 0 | 6634.93 | 6634.93 | 0 | 6285 | 349.93 | 6634.93 | NA | 0 | 70 | 75 | 145 | EA | 63920.27 | 7779.29 | 56140.98 | 20079.73 | Phase 1 quantity (68ea). Phase 2 drawings not done yet. Estimate 68ea for Phase 2. - total 136ea. See Sam Litman email dated 2/8/24 w takeoffs for sleeves. Quantity was increased 4x, due to response to RFI#881, which requires 3 extra sleeves for every crossing.
Y | IPCRP1-0852-0000-L | IPCRP1 | IPCRP1 | 0852-0000 | 3 GAS LINE TO FIREBOAT HOUSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0852-0000-R | IPCRP1 | IPCRP1 | 0852-0000 | 3 GAS LINE TO FIREBOAT HOUSE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 370000 | 0 | 0 | 370000 | 0 | 370000 | 0 | 0 | N | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0852-1000-E | IPCRP1 | IPCRP1 | 0852-1000 | Inst 3 CE Steel Pipe to Fireboat House, Complete | N | E |  | NR | P | 33646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 33646 | 0 | 0 | 33646 | 0 | 0 | 0 | Y | 33646 | 0 | 0 | 33646 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1480 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0852-1000-L | IPCRP1 | IPCRP1 | 0852-1000 | Inst 3 CE Steel Pipe to Fireboat House, Complete | N | L |  | NR | P | 127439 | 0.01 | 0.01 | 0.01 | 0.01 | 100 | 0 | 0 | 0 | 0 | Y | 0.01 | Y | 127438.99 | 0 | 0 | 127439 | 0 | 0 | 0.01 | Y | 127438.99 | 0 | 0 | 127439 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -0.01 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 752.12 | 0 | 0 | 0 | 752.12 | 0 | 0 | 0 | HR | 1480 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Completed work under JB-900, not contract item, as scope was modified.
Y | IPCRP1-0852-1010-L | IPCRP1 | IPCRP1 | 0852-1010 | Furn Steel Gas Pipe, Fittings, etc for 3 Gas Lin | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1480 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | Completed work under JB-900, not contract item, as scope was modified.
Y | IPCRP1-0852-1010-M | IPCRP1 | IPCRP1 | 0852-1010 | Furn Steel Gas Pipe, Fittings, etc for 3 Gas Lin | N | M |  | NR | P | 123802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 123802 | 0 | 0 | 123802 | 0 | 0 | 0 | N | 123802 | 0 | 0 | 123802 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1480 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0853-0000-L | IPCRP1 | IPCRP1 | 0853-0000 | 4 GAS MAIN - TRACK & FIELD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0853-0000-R | IPCRP1 | IPCRP1 | 0853-0000 | 4 GAS MAIN - TRACK & FIELD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 27500 | 0 | 0 | 27500 | 0 | 27500 | 0 | 0 | N | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0853-1000-E | IPCRP1 | IPCRP1 | 0853-1000 | Inst 4 Gas to Track & Fiend Building, Complete | N | E |  | NR | P | 2322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2322 | 0 | 0 | 2322 | 0 | 0 | 0 | Y | 2322 | 0 | 0 | 2322 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 100 | 0 | 100 | 100 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0853-1000-L | IPCRP1 | IPCRP1 | 0853-1000 | Inst 4 Gas to Track & Fiend Building, Complete | N | L |  | NR | P | 8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8794 | N | 8794 | N | 0 | 0 | 0 | 8794 | 0 | 0 | 8794 | N | 0 | 0 | 0 | 8794 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8794 | 0 | 0 | 8794 | 0 | 0 | 0 | 0 | 0 | 0 | -8794 | 0 | 0 | 8794 | 8794 | 0 | 0 | 0 | 51.92 | 0 | 51.92 | 51.92 | 51.92 | 0 | 51.92 | 51.92 | HR | 100 | 0 | 100 | 100 | LF | 0 | 0 | 0 | 8794
Y | IPCRP1-0853-1010-L | IPCRP1 | IPCRP1 | 0853-1010 | Furnish Steel Gas Pipe, Fittings, Sleeves & Appur | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 100 | 0 | 100 | 100 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0853-1010-M | IPCRP1 | IPCRP1 | 0853-1010 | Furnish Steel Gas Pipe, Fittings, Sleeves & Appur | N | M |  | NR | P | 8365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8365 | N | 8365 | N | 0 | 0 | 0 | 8365 | 0 | 0 | 8365 | N | 0 | 0 | 0 | 8365 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8365 | 0 | 0 | 8365 | 0 | 0 | 0 | 0 | 0 | 0 | -8365 | 0 | 0 | 8365 | 8365 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 100 | 0 | 100 | 100 | LF | 0 | 0 | 0 | 8365
Y | IPCRP1-0854-0000-L | IPCRP1 | IPCRP1 | 0854-0000 | SERVICE CAST IRON SOIL PIPE - 4 DIA. | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0854-0000-R | IPCRP1 | IPCRP1 | 0854-0000 | SERVICE CAST IRON SOIL PIPE - 4 DIA. | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 23750 | 0 | 0 | 23750 | 0 | 23750 | 5791.25 | 0 | N | 23750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0854-1000-L | IPCRP1 | IPCRP1 | 0854-1000 | Service Cast Iron Soil Pipe - 4 Dia | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 190 | 46.33 | 143.67 | 190 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0854-1000-S | IPCRP1 | IPCRP1 | 0854-1000 | Service Cast Iron Soil Pipe - 4 Dia | N | S |  | NR | A | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22800 | N | 22800 | N | 0 | 0 | 0 | 22800 | 0 | 0 | 22800 | N | 0 | 0 | 0 | 22800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22800 | 0 | 0 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | -22800 | 0 | 0 | 22800 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 190 | 46.33 | 143.67 | 190 | LF | 0 | 0 | 0 | 22800
Y | IPCRP1-0855-0000-L | IPCRP1 | IPCRP1 | 0855-0000 | 1 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0855-0000-R | IPCRP1 | IPCRP1 | 0855-0000 | 1 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19250 | 0 | 0 | 19250 | 0 | 19250 | 0 | 0 | N | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0856-0000-L | IPCRP1 | IPCRP1 | 0856-0000 | MISC IRON & STEEL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0856-0000-R | IPCRP1 | IPCRP1 | 0856-0000 | MISC IRON & STEEL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 90750 | 0 | 0 | 90750 | 0 | 90750 | 83385 | 0 | N | 90750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0856-1000-C | IPCRP1 | IPCRP1 | 0856-1000 | MISC IRON & STEEL | N | C |  | UNIT | U | 0 | -482387.94 | -482387.94 | -482387.94 | -482387.94 | 103.4453 | 0 | 0 | 0 | 16066.08 | Y | -466321.86 | Y | 466321.86 | 0 | 0 | 0 | 0 | 0 | -466321.86 | Y | 466321.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 466321.86 | -16066.08 | -36673.23 | -466321.86 | 0 | 0 | 0 | 0 | 0 | 0 | 466321.86 | 0 | 0 | -466321.86 | -466321.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 36300 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 16066.08
Y | IPCRP1-0856-1000-L | IPCRP1 | IPCRP1 | 0856-1000 | MISC IRON & STEEL | N | L |  | UNIT | P | 0 | -7.29 | -7.29 | -7.29 | -7.29 | 100 | 0 | 0 | 0 | 0 | Y | -7.29 | Y | 7.29 | 0 | 0 | 0 | 0 | 0 | -7.29 | Y | 7.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 7.29 | 0 | 0 | -7.29 | 0 | 0 | 0 | 0 | 0 | 0 | 7.29 | 0 | 0 | -7.29 | -7.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -3 | 0 | HR | 36300 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | Work added to Akela subcontract via SCO#16 (cc: 0832-1000)
Y | IPCRP1-0856-1000-S | IPCRP1 | IPCRP1 | 0856-1000 | MISC IRON & STEEL | N | S |  | NR | A | 76269.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 76269.93 | 0 | 0 | 76269.93 | 0 | 0 | 0 | Y | 76269.93 | 0 | 0 | 76269.93 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 36300 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-0857-0000-L | IPCRP1 | IPCRP1 | 0857-0000 | TEMP POWER FIREBOAT HOUSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0857-0000-R | IPCRP1 | IPCRP1 | 0857-0000 | TEMP POWER FIREBOAT HOUSE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 252000 | 0 | 0 | 252000 | 0 | 252000 | 0 | 0 | N | 252000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-0858-0000-L | IPCRP1 | IPCRP1 | 0858-0000 | ELEC VEHICLE (EV) SINGLE CHARGING STATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0858-0000-R | IPCRP1 | IPCRP1 | 0858-0000 | ELEC VEHICLE (EV) SINGLE CHARGING STATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 22000 | 0 | 0 | 22000 | 0 | 22000 | 0 | 0 | N | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0859-0000-L | IPCRP1 | IPCRP1 | 0859-0000 | ELEC VEHICLE (EV) DUAL CHARGING STATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0859-0000-R | IPCRP1 | IPCRP1 | 0859-0000 | ELEC VEHICLE (EV) DUAL CHARGING STATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 75000 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | N | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0860-0000-L | IPCRP1 | IPCRP1 | 0860-0000 | PHOTOVOLTAIC SYSTEM - SOUTHERN M&O CANOPY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0860-0000-R | IPCRP1 | IPCRP1 | 0860-0000 | PHOTOVOLTAIC SYSTEM - SOUTHERN M&O CANOPY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 70000 | 0 | 0 | 70000 | 0 | 70000 | 0 | 0 | N | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0861-0000-L | IPCRP1 | IPCRP1 | 0861-0000 | PHOTOVOLTAIC SYSTEM - NORTHERN M&O CANOPY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0861-0000-R | IPCRP1 | IPCRP1 | 0861-0000 | PHOTOVOLTAIC SYSTEM - NORTHERN M&O CANOPY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 110000 | 0 | 0 | 110000 | 0 | 110000 | 0 | 0 | N | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0862-0000-L | IPCRP1 | IPCRP1 | 0862-0000 | ELEC SERVICE & DISTRIB WORK AT CENTRAL M&O FACIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0862-0000-R | IPCRP1 | IPCRP1 | 0862-0000 | ELEC SERVICE & DISTRIB WORK AT CENTRAL M&O FACIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 75000 | 0 | 0 | 75000 | 0 | 75000 | 73500 | 0 | N | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0863-0000-L | IPCRP1 | IPCRP1 | 0863-0000 | ELEC SERVICE & DISTRIB WORK AT NORTHERN M&O FACIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0863-0000-R | IPCRP1 | IPCRP1 | 0863-0000 | ELEC SERVICE & DISTRIB WORK AT NORTHERN M&O FACIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 65000 | 0 | 0 | 65000 | 0 | 65000 | 0 | 0 | N | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0864-0000-L | IPCRP1 | IPCRP1 | 0864-0000 | ELEC SERVICE & DISTRIB WORK AT AMPITHEATER & FLOO | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0864-0000-R | IPCRP1 | IPCRP1 | 0864-0000 | ELEC SERVICE & DISTRIB WORK AT AMPITHEATER & FLOO | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 85000 | 0 | 0 | 85000 | 0 | 85000 | 85000 | 0 | N | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0865-0000-L | IPCRP1 | IPCRP1 | 0865-0000 | ELEC SERVICE & DISTRIB WORK AT GRAND ST FERRY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0865-0000-R | IPCRP1 | IPCRP1 | 0865-0000 | ELEC SERVICE & DISTRIB WORK AT GRAND ST FERRY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35000 | 0 | 0 | 35000 | 0 | 35000 | 35000 | 0 | N | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0866-0000-L | IPCRP1 | IPCRP1 | 0866-0000 | SPORTS FIELD FLOOD LIGHTING - FIELDS 1 & 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0866-0000-R | IPCRP1 | IPCRP1 | 0866-0000 | SPORTS FIELD FLOOD LIGHTING - FIELDS 1 & 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 450000 | 0 | 0 | 450000 | 0 | 450000 | 445500 | 0 | N | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0867-0000-L | IPCRP1 | IPCRP1 | 0867-0000 | SPORTS FIELD FLOOD LIGHTING - FIELD 6 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0867-0000-R | IPCRP1 | IPCRP1 | 0867-0000 | SPORTS FIELD FLOOD LIGHTING - FIELD 6 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 350000 | 0 | 0 | 350000 | 0 | 350000 | 0 | 0 | N | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0868-0000-L | IPCRP1 | IPCRP1 | 0868-0000 | LED SOLAR LIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0868-0000-R | IPCRP1 | IPCRP1 | 0868-0000 | LED SOLAR LIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 801900 | 0 | 0 | 801900 | 0 | 801900 | 340200 | 0 | N | 801900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0869-0000-L | IPCRP1 | IPCRP1 | 0869-0000 | LED 120 V LIGHT SIMILAR TO SOLAR LIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0869-0000-R | IPCRP1 | IPCRP1 | 0869-0000 | LED 120 V LIGHT SIMILAR TO SOLAR LIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 56700 | 0 | 0 | 56700 | 0 | 56700 | 56700 | 0 | N | 56700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0870-0000-L | IPCRP1 | IPCRP1 | 0870-0000 | ELECT SERVICE & DISTRIB WORK AT EAST 10TH ST BRID | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0870-0000-R | IPCRP1 | IPCRP1 | 0870-0000 | ELECT SERVICE & DISTRIB WORK AT EAST 10TH ST BRID | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15000 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | N | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0871-0000-L | IPCRP1 | IPCRP1 | 0871-0000 | INST FDNY SOLAR FIRE ALARM CALL BOX, FURN BY FDNY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0871-0000-R | IPCRP1 | IPCRP1 | 0871-0000 | INST FDNY SOLAR FIRE ALARM CALL BOX, FURN BY FDNY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 24000 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | N | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0872-0000-L | IPCRP1 | IPCRP1 | 0872-0000 | #10 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0872-0000-R | IPCRP1 | IPCRP1 | 0872-0000 | #10 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7300 | 0 | 0 | 7300 | 0 | 7300 | 2150 | 0 | N | 7300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0873-0000-L | IPCRP1 | IPCRP1 | 0873-0000 | #8 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0873-0000-R | IPCRP1 | IPCRP1 | 0873-0000 | #8 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 990 | 0 | 0 | 990 | 0 | 990 | 3450 | 0 | N | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0874-0000-L | IPCRP1 | IPCRP1 | 0874-0000 | #4 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0874-0000-R | IPCRP1 | IPCRP1 | 0874-0000 | #4 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 62050 | 0 | 0 | 62050 | 0 | 62050 | 16625 | 0 | N | 62050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0875-0000-L | IPCRP1 | IPCRP1 | 0875-0000 | 2 D HI DENSITY POLYETHYLENE (HDPE) SCH 80 COND | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0875-0000-R | IPCRP1 | IPCRP1 | 0875-0000 | 2 D HI DENSITY POLYETHYLENE (HDPE) SCH 80 COND | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2125000 | 0 | 0 | 2125000 | 0 | 2125000 | 474050 | 0 | N | 2125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0876-0000-L | IPCRP1 | IPCRP1 | 0876-0000 | 0.75 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0876-0000-R | IPCRP1 | IPCRP1 | 0876-0000 | 0.75 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12750 | 0 | 0 | 12750 | 0 | 12750 | 7375 | 0 | N | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0877-0000-L | IPCRP1 | IPCRP1 | 0877-0000 | 1.5 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0877-0000-R | IPCRP1 | IPCRP1 | 0877-0000 | 1.5 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 82000 | 0 | 0 | 82000 | 0 | 82000 | 0 | 0 | N | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0878-0000-L | IPCRP1 | IPCRP1 | 0878-0000 | 2 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0878-0000-R | IPCRP1 | IPCRP1 | 0878-0000 | 2 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 104000 | 0 | 0 | 104000 | 0 | 104000 | 32440 | 0 | N | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0879-0000-L | IPCRP1 | IPCRP1 | 0879-0000 | 3 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0879-0000-R | IPCRP1 | IPCRP1 | 0879-0000 | 3 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 614600 | 0 | 0 | 614600 | 0 | 614600 | 268765 | 0 | N | 614600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0880-0000-L | IPCRP1 | IPCRP1 | 0880-0000 | 4 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0880-0000-R | IPCRP1 | IPCRP1 | 0880-0000 | 4 D HDG/ HVY GAUGE RIGID ST CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 369600 | 0 | 0 | 369600 | 0 | 369600 | 184360 | 0 | N | 369600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0881-0000-L | IPCRP1 | IPCRP1 | 0881-0000 | TELEPHONE CONDUIT - 4 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0881-0000-R | IPCRP1 | IPCRP1 | 0881-0000 | TELEPHONE CONDUIT - 4 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 557700 | 0 | 0 | 557700 | 0 | 557700 | 137500 | 0 | N | 557700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0882-0000-L | IPCRP1 | IPCRP1 | 0882-0000 | PULLBOXES W/F&C, 24L X 18W X 26D, TYPE 2418 (2-R) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0882-0000-R | IPCRP1 | IPCRP1 | 0882-0000 | PULLBOXES W/F&C, 24L X 18W X 26D, TYPE 2418 (2-R) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 92400 | 0 | 0 | 92400 | 0 | 92400 | 8400 | 0 | N | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0883-0000-L | IPCRP1 | IPCRP1 | 0883-0000 | PULLBOXES W/F&C, 48L X 24W X 26D, TYPE 4824 (6-R) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0883-0000-R | IPCRP1 | IPCRP1 | 0883-0000 | PULLBOXES W/F&C, 48L X 24W X 26D, TYPE 4824 (6-R) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 244000 | 0 | 0 | 244000 | 0 | 244000 | 97600 | 0 | N | 244000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0884-0000-L | IPCRP1 | IPCRP1 | 0884-0000 | ELECTRICAL MH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0884-0000-R | IPCRP1 | IPCRP1 | 0884-0000 | ELECTRICAL MH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 37500 | 0 | 0 | 37500 | 0 | 37500 | 15000 | 0 | N | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0885-0000-L | IPCRP1 | IPCRP1 | 0885-0000 | #12 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0885-0000-R | IPCRP1 | IPCRP1 | 0885-0000 | #12 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3800 | 0 | 0 | 3800 | 0 | 3800 | 0 | 0 | N | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0886-0000-L | IPCRP1 | IPCRP1 | 0886-0000 | #6 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0886-0000-R | IPCRP1 | IPCRP1 | 0886-0000 | #6 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 81000 | 0 | 0 | 81000 | 0 | 81000 | 540 | 0 | N | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0887-0000-L | IPCRP1 | IPCRP1 | 0887-0000 | #2 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0887-0000-R | IPCRP1 | IPCRP1 | 0887-0000 | #2 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 72780 | 0 | 0 | 72780 | 0 | 72780 | 3240 | 0 | N | 72780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0888-0000-L | IPCRP1 | IPCRP1 | 0888-0000 | #1/0 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0888-0000-R | IPCRP1 | IPCRP1 | 0888-0000 | #1/0 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 50240 | 0 | 0 | 50240 | 0 | 50240 | 4240 | 0 | N | 50240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0889-0000-L | IPCRP1 | IPCRP1 | 0889-0000 | #4/0 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0889-0000-R | IPCRP1 | IPCRP1 | 0889-0000 | #4/0 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 71500 | 0 | 0 | 71500 | 0 | 71500 | 20332 | 0 | N | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0890-0000-L | IPCRP1 | IPCRP1 | 0890-0000 | 500 KCMIL COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0890-0000-R | IPCRP1 | IPCRP1 | 0890-0000 | 500 KCMIL COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 261360 | 0 | 0 | 261360 | 0 | 261360 | 46640 | 0 | N | 261360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0891-0000-L | IPCRP1 | IPCRP1 | 0891-0000 | #2/0 AWG COPPER, 600V WIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0891-0000-R | IPCRP1 | IPCRP1 | 0891-0000 | #2/0 AWG COPPER, 600V WIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 379600 | 0 | 0 | 379600 | 0 | 379600 | 133000 | 0 | N | 379600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0892-0000-L | IPCRP1 | IPCRP1 | 0892-0000 | SS ENCLOSURE FOR GAS METER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0892-0000-R | IPCRP1 | IPCRP1 | 0892-0000 | SS ENCLOSURE FOR GAS METER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5600 | 0 | 0 | 5600 | 0 | 5600 | 0 | 0 | N | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0893-0000-L | IPCRP1 | IPCRP1 | 0893-0000 | CONDUIT INTERIOR SEALING FITTING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0893-0000-R | IPCRP1 | IPCRP1 | 0893-0000 | CONDUIT INTERIOR SEALING FITTING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 87600 | 0 | 0 | 87600 | 0 | 87600 | 0 | 0 | N | 87600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0894-0000-L | IPCRP1 | IPCRP1 | 0894-0000 | BRICK MAS/ PC CONC FOR DRAINAGE STRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0894-0000-R | IPCRP1 | IPCRP1 | 0894-0000 | BRICK MAS/ PC CONC FOR DRAINAGE STRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 785000 | 0 | 0 | 785000 | 0 | 785000 | 158310 | 0 | N | 785000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0895-0000-L | IPCRP1 | IPCRP1 | 0895-0000 | ELEC SERV & PANEL WORK AT E RIVER HOUSES PARK LOT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0895-0000-R | IPCRP1 | IPCRP1 | 0895-0000 | ELEC SERV & PANEL WORK AT E RIVER HOUSES PARK LOT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10000 | 0 | 0 | 10000 | 0 | 10000 | 7000 | 0 | N | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0896-0000-L | IPCRP1 | IPCRP1 | 0896-0000 | DOUBLE CHECK VALVE - 2 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0896-0000-R | IPCRP1 | IPCRP1 | 0896-0000 | DOUBLE CHECK VALVE - 2 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 600 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | N | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0897-0000-L | IPCRP1 | IPCRP1 | 0897-0000 | SAFETY SURFACE 8ft FALL HEIGHT, OTHER COLOR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0897-0000-R | IPCRP1 | IPCRP1 | 0897-0000 | SAFETY SURFACE 8ft FALL HEIGHT, OTHER COLOR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 369975 | 0 | 0 | 369975 | 0 | 369975 | 0 | 0 | N | 369975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0898-0000-L | IPCRP1 | IPCRP1 | 0898-0000 | ADULT FITNESS EQUIPMENT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0898-0000-R | IPCRP1 | IPCRP1 | 0898-0000 | ADULT FITNESS EQUIPMENT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 120000 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | N | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0899-0000-L | IPCRP1 | IPCRP1 | 0899-0000 | ADULT FITNESS EQUIPMENT, CHALLENGE COURSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0899-0000-R | IPCRP1 | IPCRP1 | 0899-0000 | ADULT FITNESS EQUIPMENT, CHALLENGE COURSE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 90000 | 0 | 0 | 90000 | 0 | 90000 | 0 | 0 | N | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0900-0000-L | IPCRP1 | IPCRP1 | 0900-0000 | SWING - 7ft W/INCLUS SEAT & TOT BUCKET SEAT - TYPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0900-0000-R | IPCRP1 | IPCRP1 | 0900-0000 | SWING - 7ft W/INCLUS SEAT & TOT BUCKET SEAT - TYPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11000 | 0 | 0 | 11000 | 0 | 11000 | 0 | 0 | N | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0901-0000-L | IPCRP1 | IPCRP1 | 0901-0000 | PLAY SWING - 10ft HIGH W/FLAT SEAT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0901-0000-R | IPCRP1 | IPCRP1 | 0901-0000 | PLAY SWING - 10ft HIGH W/FLAT SEAT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | N | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0902-0000-L | IPCRP1 | IPCRP1 | 0902-0000 | PIPE RAIL FENCE TYPE B 3 RAIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0902-0000-R | IPCRP1 | IPCRP1 | 0902-0000 | PIPE RAIL FENCE TYPE B 3 RAIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 142500 | 0 | 0 | 142500 | 0 | 142500 | 0 | 0 | N | 142500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0903-0000-L | IPCRP1 | IPCRP1 | 0903-0000 | ALLOW FOR SECUR CAMERA SYST WORK AT E RIVER HOUSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0903-0000-R | IPCRP1 | IPCRP1 | 0903-0000 | ALLOW FOR SECUR CAMERA SYST WORK AT E RIVER HOUSE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16740 | 0 | 0 | 16740 | 0 | 16740 | 16740 | 0 | N | 16740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0903-1000-C | IPCRP1 | IPCRP1 | 0903-1000 | ALLOW FOR SECUR CAMERA SYST WORK AT E RIVER HOUSE | N | C |  | NR | P | 16740 | 245539.06 | 245539.06 | 245539.06 | 245539.06 | 100 | 0 | 0 | 0 | 0 | Y | 245539.06 | Y | -228799.06 | 0 | 0 | 16740 | 0 | 0 | 245539.06 | Y | -228799.06 | 0 | 0 | 16740 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -245539.06 | 0 | 0 | 245539.06 | 0 | 0 | 0 | 0 | 0 | 0 | -245539.06 | 0 | 0 | 245539.06 | 245539.06 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 1 | 0 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0903-1000-L | IPCRP1 | IPCRP1 | 0903-1000 | ALLOW FOR SECUR CAMERA SYST WORK AT E RIVER HOUSE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | FP | 0 | 0 | 0 | 0 | Cost was check written to ERH to obtain Access Agreement.
Y | IPCRP1-0904-0000-L | IPCRP1 | IPCRP1 | 0904-0000 | CLF SLIDING GATE AT E RIVER HOUSING | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0904-0000-R | IPCRP1 | IPCRP1 | 0904-0000 | CLF SLIDING GATE AT E RIVER HOUSING | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 22000 | 0 | 0 | 22000 | 0 | 22000 | 22000 | 0 | N | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0905-0000-L | IPCRP1 | IPCRP1 | 0905-0000 | CLF SLIDING GATE AT MONTGOMERY ST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0905-0000-R | IPCRP1 | IPCRP1 | 0905-0000 | CLF SLIDING GATE AT MONTGOMERY ST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16000 | 0 | 0 | 16000 | 0 | 16000 | 16000 | 0 | N | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0906-0000-L | IPCRP1 | IPCRP1 | 0906-0000 | SHREDDED BARK MULCH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0906-0000-R | IPCRP1 | IPCRP1 | 0906-0000 | SHREDDED BARK MULCH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 189500 | 0 | 0 | 189500 | 0 | 189500 | 319.5 | 0 | N | 189500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0907-0000-L | IPCRP1 | IPCRP1 | 0907-0000 | PICNIC TABLE - FIXED, ACCESSIBLE, W/UMBRELLA HOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0907-0000-R | IPCRP1 | IPCRP1 | 0907-0000 | PICNIC TABLE - FIXED, ACCESSIBLE, W/UMBRELLA HOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 88000 | 0 | 0 | 88000 | 0 | 88000 | 72000 | 0 | N | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0908-0000-L | IPCRP1 | IPCRP1 | 0908-0000 | PICNIC TABLE - FIXED, ACCESSIBLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0908-0000-R | IPCRP1 | IPCRP1 | 0908-0000 | PICNIC TABLE - FIXED, ACCESSIBLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 10000 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | N | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0909-0000-L | IPCRP1 | IPCRP1 | 0909-0000 | BENCH 1964 WORLDS FAIR W/ RPL SLATS BACKLESS 8ft | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0909-0000-R | IPCRP1 | IPCRP1 | 0909-0000 | BENCH 1964 WORLDS FAIR W/ RPL SLATS BACKLESS 8ft | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 77000 | 0 | 0 | 77000 | 0 | 77000 | 44000 | 0 | N | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0910-0000-L | IPCRP1 | IPCRP1 | 0910-0000 | BENCH 1964 WORLDs FAIR W/ RPL SLATS W/ ARMS 8ft | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0910-0000-R | IPCRP1 | IPCRP1 | 0910-0000 | BENCH 1964 WORLDs FAIR W/ RPL SLATS W/ ARMS 8ft | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 591800 | 0 | 0 | 591800 | 0 | 591800 | 189200 | 0 | N | 591800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0910-1000-L | IPCRP1 | IPCRP1 | 0910-1000 | Park Work & Amenities Subcontractor (AFoA) | N | L |  | UNIT | P | 0 | 9677.33 | 9677.33 | 9677.33 | 9677.33 | 74.441 | 0 | 0 | 0 | 3322.67 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 101.07 | 101.07 | 0 | 77.5 | 23.57 | 101.07 | HR | 1 | 0.43 | 0.57 | 1 | LS | 0 | 0 | 0 | 3322.67
Y | IPCRP1-0910-1000-S | IPCRP1 | IPCRP1 | 0910-1000 | Park Work & Amenities Subcontractor (AFoA) | N | S |  | NR | A | 10177375 | 11515841.32 | 11515841.32 | 5071692.63 | 11515841.32 | 44.041 | 0 | 0 | 0 | 0 | Y | 11515841.32 | Y | -1338466.32 | 0 | 0 | 10177375 | 0 | 0 | 11515841.32 | Y | -1338466.32 | 0 | 0 | 10177375 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11515841.32 | 0 | 37500 | 11515841.32 | 0 | 0 | 0 | 0 | 0 | 0 | -11515841.32 | 0 | 0 | 11515841.32 | 11515841.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 133972.86 | -31229.84 | 102743.02 | NA | 1 | 0.43 | 0.57 | 1 | LS | 11515841.32 | 6444148.69 | 5071692.63 | 0 | ATHLETIC FIELDS OF AMERICA Base Contract @$10,042,799.09
Y | IPCRP1-0911-0000-L | IPCRP1 | IPCRP1 | 0911-0000 | PERMEABLE CONC PAVER & STONE BASE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0911-0000-R | IPCRP1 | IPCRP1 | 0911-0000 | PERMEABLE CONC PAVER & STONE BASE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 218575 | 0 | 0 | 218575 | 0 | 218575 | 217652.75 | 0 | N | 218575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0912-0000-L | IPCRP1 | IPCRP1 | 0912-0000 | SUBBASE MATERIAL FOR PERMEABLE PVMNT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0912-0000-R | IPCRP1 | IPCRP1 | 0912-0000 | SUBBASE MATERIAL FOR PERMEABLE PVMNT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7800 | 0 | 0 | 7800 | 0 | 7800 | 118942.5 | 0 | N | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0913-0000-L | IPCRP1 | IPCRP1 | 0913-0000 | ST FLAGPOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0913-0000-R | IPCRP1 | IPCRP1 | 0913-0000 | ST FLAGPOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 32000 | 0 | 0 | 32000 | 0 | 32000 | 32000 | 0 | N | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0914-0000-L | IPCRP1 | IPCRP1 | 0914-0000 | ST PIPE BOLLARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0914-0000-R | IPCRP1 | IPCRP1 | 0914-0000 | ST PIPE BOLLARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 243800 | 0 | 0 | 243800 | 0 | 243800 | 190800 | 0 | N | 243800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0914-1000-L | IPCRP1 | IPCRP1 | 0914-1000 | St Pipe Bollards, M&O Areas 1, 2, 3 | N | L |  | UNIT | P | 0 | 17395.17 | 17395.17 | 17395.17 | 17395.17 | 9.5777 | 0 | 0 | 0 | 164227.13 | Y | 181622.3 | Y | -181622.3 | 0 | 0 | 0 | 0 | 0 | 181622.3 | Y | -181622.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -181622.3 | 0 | 0 | 181622.3 | 0 | 0 | 0 | 0 | 0 | 0 | -181622.3 | 0 | 0 | 181622.3 | 181622.3 | 0 | 0 | 0 | 0 | 0 | 1379.77 | 1379.77 | 0 | 149.5 | 1230.27 | 1379.77 | HR | 46 | 36 | 44 | 80 | EA | 0 | 0 | 0 | 164227.13
Y | IPCRP1-0914-1000-M | IPCRP1 | IPCRP1 | 0914-1000 | St Pipe Bollards, M&O Areas 1, 2, 3 | N | M |  | UNIT | U | 0 | 55300 | 55300 | 35700 | 55300 | 59.5 | 0 | 0 | 0 | 4700 | Y | 60000 | Y | -60000 | 0 | 0 | 0 | 0 | 0 | 60000 | Y | -60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60000 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | -60000 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 46 | 51 | -51 | 0 | EA | 46 | 36 | 44 | 80 | EA | 55300 | 19600 | 35700 | 4700
Y | IPCRP1-0914-1000-S | IPCRP1 | IPCRP1 | 0914-1000 | St Pipe Bollards, M&O Areas 1, 2, 3 | N | S |  | NR | A | 241622.3 | 322.75 | 322.75 | 322.75 | 322.75 | 100 | 0 | 0 | 0 | 0 | Y | 322.75 | Y | 241299.55 | 0 | 0 | 241622.3 | 0 | 0 | 322.75 | Y | 241299.55 | 0 | 0 | 241622.3 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -322.75 | 0 | 0 | 322.75 | 0 | 0 | 0 | 0 | 0 | 0 | -322.75 | 0 | 0 | 322.75 | 322.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.5 | -2.5 | 0 | NA | 46 | 36 | 44 | 80 | EA | 322.75 | 0 | 322.75 | 0
Y | IPCRP1-0915-0000-L | IPCRP1 | IPCRP1 | 0915-0000 | RESILIENT SPORTS SURFACE - 13MM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0915-0000-R | IPCRP1 | IPCRP1 | 0915-0000 | RESILIENT SPORTS SURFACE - 13MM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 513162 | 0 | 0 | 513162 | 0 | 513162 | 0 | 0 | N | 513162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0916-0000-L | IPCRP1 | IPCRP1 | 0916-0000 | TRACK PERIMETER DRAIN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0916-0000-R | IPCRP1 | IPCRP1 | 0916-0000 | TRACK PERIMETER DRAIN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19200 | 0 | 0 | 19200 | 0 | 19200 | 0 | 0 | N | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0917-0000-L | IPCRP1 | IPCRP1 | 0917-0000 | BBQ - 2 GRILL TYPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0917-0000-R | IPCRP1 | IPCRP1 | 0917-0000 | BBQ - 2 GRILL TYPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 44000 | 0 | 0 | 44000 | 0 | 44000 | 22000 | 0 | N | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0918-0000-L | IPCRP1 | IPCRP1 | 0918-0000 | BBQ - 3 GRILL TYPE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0918-0000-R | IPCRP1 | IPCRP1 | 0918-0000 | BBQ - 3 GRILL TYPE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 88000 | 0 | 0 | 88000 | 0 | 88000 | 44000 | 0 | N | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0919-0000-L | IPCRP1 | IPCRP1 | 0919-0000 | FULL DEPTH ASPHALT PVMNT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0919-0000-R | IPCRP1 | IPCRP1 | 0919-0000 | FULL DEPTH ASPHALT PVMNT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 376390 | 0 | 0 | 376390 | 0 | 376390 | 252859.6 | 0 | N | 376390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0920-0000-L | IPCRP1 | IPCRP1 | 0920-0000 | ASPHALT PVMNT FOR TENNIS COURTS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0920-0000-R | IPCRP1 | IPCRP1 | 0920-0000 | ASPHALT PVMNT FOR TENNIS COURTS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 951225 | 0 | 0 | 951225 | 0 | 951225 | 621868.5 | 0 | N | 951225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0920-1000-C | IPCRP1 | IPCRP1 | 0920-1000 | Asphalt Sub (CAC) Tennis, Track, Shared Path | N | C |  | UNIT | U | 0 | 83971.26 | 83971.26 | 83971.26 | 83971.26 | 55.9808 | 0 | 0 | 0 | 66028.74 | Y | 150000 | Y | -150000 | 0 | 0 | 0 | 0 | 0 | 150000 | Y | -150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | -150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 29876 | 11903.86 | 17972.14 | 29876 | SY | 0 | 0 | 0 | 66028.74 | Converted to self-perform
Y | IPCRP1-0920-1000-L | IPCRP1 | IPCRP1 | 0920-1000 | Asphalt Sub (CAC) Tennis, Track, Shared Path | N | L |  | UNIT | P | 0 | 283252.76 | 283252.76 | 283252.76 | 283252.76 | 40.4487 | 0 | 0 | 0 | 417023.09 | Y | 700275.85 | Y | -700275.85 | 0 | 0 | 0 | 0 | 0 | 700275.85 | Y | -700275.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -700275.85 | 0 | 0 | 700275.85 | 0 | 0 | 0 | 0 | 0 | 0 | -700275.85 | 0 | 0 | 700275.85 | 700275.85 | 0 | 0 | 0 | 0 | 0 | 5080 | 5080 | 0 | 2023.5 | 3056.5 | 5080 | HR | 29876 | 11903.86 | 17972.14 | 29876 | SY | 0 | 0 | 0 | 417023.09 | Converted to self-perform
Y | IPCRP1-0920-1000-M | IPCRP1 | IPCRP1 | 0920-1000 | Asphalt Sub (CAC) Tennis, Track, Shared Path | N | M |  | UNIT | U | 0 | 1128844.83 | 1128844.83 | 431642.88 | 1128844.83 | 38.2376 | 0 | 0 | 0 | 0 | Y | 1128844.83 | Y | -1128844.83 | 0 | 0 | 0 | 0 | 0 | 1128844.83 | Y | -1128844.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1128844.83 | 0 | 0 | 1128844.83 | 0 | 0 | 0 | 0 | 0 | 0 | -1128844.83 | 0 | 0 | 1128844.83 | 1128844.83 | 0 | 0 | 0 | 0 | 0 | 151633.69 | 151633.69 | 0 | 69971.99 | 81661.7 | 151633.69 | NA | 29876 | 11903.86 | 17972.14 | 29876 | SY | 1128844.83 | 697201.95 | 431642.88 | 0
Y | IPCRP1-0920-1000-S | IPCRP1 | IPCRP1 | 0920-1000 | Asphalt Sub (CAC) Tennis, Track, Shared Path | N | S |  | NR | A | 2379176 | 5399.09 | 5399.09 | 5399.09 | 5399.09 | 21.5964 | 0 | 0 | 0 | 19600.91 | Y | 25000 | Y | 2354176 | 0 | 0 | 2379176 | 0 | 0 | 25000 | Y | 2354176 | 0 | 0 | 2379176 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 43.5 | 59469.37 | 59512.87 | NA | 29876 | 11903.86 | 17972.14 | 29876 | SY | 5399.09 | 0 | 5399.09 | 19600.91 | Citywide Paving Base Contract @$1,194,368.00
Y | IPCRP1-0921-0000-L | IPCRP1 | IPCRP1 | 0921-0000 | FOUND MAT FOR CONC (TRUCK MEASURE) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0921-0000-R | IPCRP1 | IPCRP1 | 0921-0000 | FOUND MAT FOR CONC (TRUCK MEASURE) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 228470 | 0 | 0 | 228470 | 0 | 228470 | 26044.7 | 0 | N | 228470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0921-1000-L | IPCRP1 | IPCRP1 | 0921-1000 | FOUND MAT FOR CONC (TRUCK MEASURE) | N | L |  | UNIT | P | 0 | 82733.13 | 82733.13 | 82733.13 | 82733.13 | 37.9171 | 0 | 0 | 0 | 135461.87 | Y | 218195 | Y | -218195 | 0 | 0 | 0 | 0 | 0 | 218195 | Y | -218195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -218195 | 9928.91 | 0 | 218195 | 0 | 0 | 0 | 0 | 0 | 0 | -218195 | 0 | 0 | 218195 | 218195 | 0 | 0 | 0 | 0 | 0 | 1649.97 | 1649.97 | 0 | 663.5 | 986.47 | 1649.97 | HR | 2077 | 274.5 | 1802.5 | 2077 | CY | 0 | 0 | 0 | 135461.87
Y | IPCRP1-0921-1000-S | IPCRP1 | IPCRP1 | 0921-1000 | FOUND MAT FOR CONC (TRUCK MEASURE) | N | S |  | NR | A | 218195.5 | 7172.26 | 7172.26 | 7172.26 | 7172.26 | 136.9996 | 0 | 0 | 0 | -1937.02 | Y | 5235.24 | Y | 212960.26 | 0 | 0 | 218195.5 | 0 | 0 | 5235.24 | Y | 212960.26 | 0 | 0 | 218195.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5235.24 | 1937.02 | 0 | 5235.24 | 0 | 0 | 0 | 0 | 1937.02 | 0 | -5235.24 | 0 | 0 | 5235.24 | 5235.24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 42.5 | -42.5 | 0 | NA | 2077 | 274.5 | 1802.5 | 2077 | CY | 7172.26 | 0 | 7172.26 | -1937.02
Y | IPCRP1-0922-0000-L | IPCRP1 | IPCRP1 | 0922-0000 | FOUND MAT FOR ASPHALT (TRUCK MEASURE) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0922-0000-R | IPCRP1 | IPCRP1 | 0922-0000 | FOUND MAT FOR ASPHALT (TRUCK MEASURE) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 536250 | 0 | 0 | 536250 | 0 | 536250 | 113787.3 | 0 | N | 536250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0922-1000-L | IPCRP1 | IPCRP1 | 0922-1000 | FOUND MAT FOR ASPHALT (TRUCK MEASURE) | N | L |  | UNIT | P | 0 | 99521.58 | 99521.58 | 99521.58 | 99521.58 | 38.2775 | 0 | 0 | 0 | 160478.42 | Y | 260000 | Y | -260000 | 0 | 0 | 0 | 0 | 0 | 260000 | Y | -260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -260000 | 0 | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | -260000 | 0 | 0 | 260000 | 260000 | 0 | 0 | 0 | 0 | 0 | 2021.33 | 2021.33 | 0 | 791.5 | 1229.83 | 2021.33 | HR | 4875 | 1034.43 | 3840.57 | 4875 | CY | 0 | 0 | 0 | 160478.42
Y | IPCRP1-0922-1000-S | IPCRP1 | IPCRP1 | 0922-1000 | FOUND MAT FOR ASPHALT (TRUCK MEASURE) | N | S |  | NR | A | 512134.35 | 8164.13 | 8164.13 | 8164.13 | 8164.13 | 3.238 | 0 | 0 | 0 | 243970.22 | Y | 252134.35 | Y | 260000 | 0 | 0 | 512134.35 | 0 | 0 | 252134.35 | Y | 260000 | 0 | 0 | 512134.35 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -252134.35 | 0 | 0 | 252134.35 | 0 | 0 | 0 | 0 | 0 | 0 | -252134.35 | 0 | 0 | 252134.35 | 252134.35 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 64.5 | -64.5 | 0 | NA | 4875 | 1034.43 | 3840.57 | 4875 | CY | 8164.13 | 0 | 8164.13 | 243970.22
Y | IPCRP1-0923-0000-L | IPCRP1 | IPCRP1 | 0923-0000 | ST PICNIC TABLE, W/UMBRELLA HOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0923-0000-R | IPCRP1 | IPCRP1 | 0923-0000 | ST PICNIC TABLE, W/UMBRELLA HOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 221000 | 0 | 0 | 221000 | 0 | 221000 | 119000 | 0 | N | 221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0924-0000-L | IPCRP1 | IPCRP1 | 0924-0000 | ST PICNIC TABLE, ACCESSIBLE, W/UMBRELLA HOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0924-0000-R | IPCRP1 | IPCRP1 | 0924-0000 | ST PICNIC TABLE, ACCESSIBLE, W/UMBRELLA HOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 110500 | 0 | 0 | 110500 | 0 | 110500 | 59500 | 0 | N | 110500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0925-0000-L | IPCRP1 | IPCRP1 | 0925-0000 | TOPSOIL FOR PLANTING PITS & BEDS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0925-0000-R | IPCRP1 | IPCRP1 | 0925-0000 | TOPSOIL FOR PLANTING PITS & BEDS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 395600 | 0 | 0 | 395600 | 0 | 395600 | 0 | 0 | N | 395600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0926-0000-L | IPCRP1 | IPCRP1 | 0926-0000 | TEMP WOODEN TREE GUARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0926-0000-R | IPCRP1 | IPCRP1 | 0926-0000 | TEMP WOODEN TREE GUARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 632000 | 0 | 0 | 632000 | 0 | 632000 | 16800 | 0 | N | 632000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0927-0000-L | IPCRP1 | IPCRP1 | 0927-0000 | TEMP WOODEN TREE GUARD FOR GROVES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0927-0000-R | IPCRP1 | IPCRP1 | 0927-0000 | TEMP WOODEN TREE GUARD FOR GROVES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 170250 | 0 | 0 | 170250 | 0 | 170250 | 67537.5 | 0 | N | 170250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0928-0000-L | IPCRP1 | IPCRP1 | 0928-0000 | ITS SINGLE MODE, FIBER OPTIC CABLE, 12 STRAND | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0928-0000-R | IPCRP1 | IPCRP1 | 0928-0000 | ITS SINGLE MODE, FIBER OPTIC CABLE, 12 STRAND | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | N | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0929-0000-L | IPCRP1 | IPCRP1 | 0929-0000 | ITS SINGLE MODE, FIBER OPTIC CABLE, 48 STRAND | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0929-0000-R | IPCRP1 | IPCRP1 | 0929-0000 | ITS SINGLE MODE, FIBER OPTIC CABLE, 48 STRAND | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | N | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0930-0000-L | IPCRP1 | IPCRP1 | 0930-0000 | ITS SINGLE MODE, FO CAB, 48 STRAND, REDUC OD, HI | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0930-0000-R | IPCRP1 | IPCRP1 | 0930-0000 | ITS SINGLE MODE, FO CAB, 48 STRAND, REDUC OD, HI | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3500 | 0 | 0 | 3500 | 0 | 3500 | 0 | 0 | N | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0931-0000-L | IPCRP1 | IPCRP1 | 0931-0000 | ITS SINGLE MODE, FIBER OPTIC CABLE, 216 STRAND | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0931-0000-R | IPCRP1 | IPCRP1 | 0931-0000 | ITS SINGLE MODE, FIBER OPTIC CABLE, 216 STRAND | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0932-0000-L | IPCRP1 | IPCRP1 | 0932-0000 | ITS SING MODE, FO CAB, 48 STRND, SELF SUP, AERIAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0932-0000-R | IPCRP1 | IPCRP1 | 0932-0000 | ITS SING MODE, FO CAB, 48 STRND, SELF SUP, AERIAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0933-0000-L | IPCRP1 | IPCRP1 | 0933-0000 | ITS FIBER OPTIC INNERDUCT, 1 CHANNEL, 1in | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0933-0000-R | IPCRP1 | IPCRP1 | 0933-0000 | ITS FIBER OPTIC INNERDUCT, 1 CHANNEL, 1in | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 133000 | 0 | 0 | 133000 | 0 | 133000 | 0 | 0 | N | 133000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0934-0000-L | IPCRP1 | IPCRP1 | 0934-0000 | ADJUST TOP OF UTIL STRUCT TO GRADE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0934-0000-R | IPCRP1 | IPCRP1 | 0934-0000 | ADJUST TOP OF UTIL STRUCT TO GRADE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9600 | 0 | 0 | 9600 | 0 | 9600 | 3600 | 0 | N | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0934-1000-C | IPCRP1 | IPCRP1 | 0934-1000 | Adjust Top of Utility Struct to Grade | N | C |  | NR | P | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | N | 2000 | N | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | N | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8 | 3 | 5 | 8 | EA | 0 | 0 | 0 | 2000
Y | IPCRP1-0934-1000-E | IPCRP1 | IPCRP1 | 0934-1000 | Adjust Top of Utility Struct to Grade | N | E |  | NR | P | 1640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1640 | 0 | 0 | 1640 | 0 | 0 | 0 | Y | 1640 | 0 | 0 | 1640 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8 | 3 | 5 | 8 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0934-1000-L | IPCRP1 | IPCRP1 | 0934-1000 | Adjust Top of Utility Struct to Grade | N | L |  | NR | P | 5452.56 | 1098.28 | 1098.28 | 1098.28 | 1098.28 | 20.1425 | 0 | 0 | 0 | 4354.28 | N | 5452.56 | N | 0 | 0 | 0 | 5452.56 | 0 | 0 | 5452.56 | N | 0 | 0 | 0 | 5452.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5452.56 | 0 | 0 | 5452.56 | 0 | 0 | 0 | 0 | 0 | 0 | -5452.56 | 0 | 0 | 5452.56 | 5452.56 | 0 | 0 | 0 | 48 | 0 | 48 | 48 | 48 | 10 | 38 | 48 | HR | 8 | 3 | 5 | 8 | EA | 0 | 0 | 0 | 4354.28
Y | IPCRP1-0935-0000-L | IPCRP1 | IPCRP1 | 0935-0000 | ALLOWANCE FOR UTIL COMPANY FEES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0935-0000-R | IPCRP1 | IPCRP1 | 0935-0000 | ALLOWANCE FOR UTIL COMPANY FEES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 167405 | 0 | 0 | 167405 | 0 | 167405 | 0 | 0 | N | 167405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0935-1000-C | IPCRP1 | IPCRP1 | 0935-1000 | ALLOWANCE FOR UTIL COMPANY FEES | N | C |  | NR | P | 167405 | 2.9 | 2.9 | 2.9 | 2.9 | 0.0017323 | 0 | 0 | 0 | 167402.1 | N | 167405 | N | 0 | 0 | 0 | 167405 | 0 | 0 | 167405 | N | 0 | 0 | 0 | 167405 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -167405 | 0 | 0 | 167405 | 0 | 0 | 0 | 0 | 0 | 0 | -167405 | 0 | 0 | 167405 | 167405 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 167402.1
Y | IPCRP1-0935-1000-L | IPCRP1 | IPCRP1 | 0935-1000 | ALLOWANCE FOR UTIL COMPANY FEES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-0936-0000-L | IPCRP1 | IPCRP1 | 0936-0000 | ST FENCE W/ CLIMBING PROTECTION 6ft HT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0936-0000-R | IPCRP1 | IPCRP1 | 0936-0000 | ST FENCE W/ CLIMBING PROTECTION 6ft HT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 945250 | 0 | 0 | 945250 | 0 | 945250 | 974700 | 0 | N | 945250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0937-0000-L | IPCRP1 | IPCRP1 | 0937-0000 | 1964 WORLDS FAIR CHAISE LOUNGE CHAIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0937-0000-R | IPCRP1 | IPCRP1 | 0937-0000 | 1964 WORLDS FAIR CHAISE LOUNGE CHAIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 204000 | 0 | 0 | 204000 | 0 | 204000 | 72000 | 0 | N | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0938-0000-L | IPCRP1 | IPCRP1 | 0938-0000 | RPL BAR TOP TABLE - LOW HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0938-0000-R | IPCRP1 | IPCRP1 | 0938-0000 | RPL BAR TOP TABLE - LOW HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 45500 | 0 | 0 | 45500 | 0 | 45500 | 26169 | 0 | N | 45500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0939-0000-L | IPCRP1 | IPCRP1 | 0939-0000 | RPL BAR TOP TABLE - HIGH HEIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0939-0000-R | IPCRP1 | IPCRP1 | 0939-0000 | RPL BAR TOP TABLE - HIGH HEIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 72800 | 0 | 0 | 72800 | 0 | 72800 | 43611.75 | 0 | N | 72800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0940-0000-L | IPCRP1 | IPCRP1 | 0940-0000 | PICNIC TABLE, FIXED, W/UMBRELLA HOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0940-0000-R | IPCRP1 | IPCRP1 | 0940-0000 | PICNIC TABLE, FIXED, W/UMBRELLA HOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 136000 | 0 | 0 | 136000 | 0 | 136000 | 128000 | 0 | N | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0941-0000-L | IPCRP1 | IPCRP1 | 0941-0000 | SOD NEW LAWN, SPORTS FIELDS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0941-0000-R | IPCRP1 | IPCRP1 | 0941-0000 | SOD NEW LAWN, SPORTS FIELDS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 188744.4 | 0 | 0 | 188744.4 | 0 | 188744.4 | 0 | 0 | N | 188744.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188744.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0942-0000-L | IPCRP1 | IPCRP1 | 0942-0000 | CONC PAVERS TYPE 1 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0942-0000-R | IPCRP1 | IPCRP1 | 0942-0000 | CONC PAVERS TYPE 1 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3857400 | 0 | 0 | 3857400 | 0 | 3857400 | 2316387 | 0 | N | 3857400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3857400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0943-0000-L | IPCRP1 | IPCRP1 | 0943-0000 | CONC PAVERS TYPE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0943-0000-R | IPCRP1 | IPCRP1 | 0943-0000 | CONC PAVERS TYPE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1928700 | 0 | 0 | 1928700 | 0 | 1928700 | 877695 | 0 | N | 1928700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0944-0000-L | IPCRP1 | IPCRP1 | 0944-0000 | CONC PAVERS TYPE 3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0944-0000-R | IPCRP1 | IPCRP1 | 0944-0000 | CONC PAVERS TYPE 3 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1928700 | 0 | 0 | 1928700 | 0 | 1928700 | 401088 | 0 | N | 1928700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SY | 0 | 0 | 0 | 0
Y | IPCRP1-0944-1000-L | IPCRP1 | IPCRP1 | 0944-1000 | Place 5 in Concrete Base | N | L |  | NR | P | 101482 | 496260.37 | 496260.37 | 496260.37 | 496260.37 | 57.0414 | 0 | 0 | 0 | 373739.63 | Y | 870000 | Y | -768518 | 0 | 0 | 101482 | 0 | 0 | 870000 | Y | -768518 | 0 | 0 | 101482 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -870000 | 5590.93 | 0 | 870000 | 0 | 0 | 0 | 0 | 0 | 0 | -870000 | 0 | 0 | 870000 | 870000 | 0 | 0 | 0 | 1008 | 0 | 7088.34 | 7088.34 | 1008 | 4126.2 | 2962.14 | 7088.34 | HR | 3600 | 1968.51 | 1631.49 | 3600 | CY | 0 | 0 | 0 | 373739.63
Y | IPCRP1-0944-1000-S | IPCRP1 | IPCRP1 | 0944-1000 | Place 5 in Concrete Base | N | S |  | UNIT | A | 0 | 9746.48 | 9746.48 | 9746.48 | 9746.48 | 100 | 0 | 0 | 0 | 0 | N | 9746.48 | N | -9746.48 | 0 | 0 | 0 | 0 | 0 | 9746.48 | N | -9746.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9746.48 | 0 | 0 | 9746.48 | 0 | 0 | 0 | 0 | 0 | 0 | -9746.48 | 0 | 0 | 9746.48 | 9746.48 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 0 | 78.5 | 0 | 78.5 | NA | 3600 | 1968.51 | 1631.49 | 3600 | CY | 9746.48 | 0 | 9746.48 | 0
Y | IPCRP1-0944-1010-L | IPCRP1 | IPCRP1 | 0944-1010 | Seal Joints | N | L |  | NR | P | 75006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 1 | Y | 75005 | 0 | 0 | 75006 | 0 | 0 | 1 | Y | 75005 | 0 | 0 | 75006 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 740.64 | 0 | 0 | 0 | 740.64 | 0 | 0 | 0 | HR | 46290 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 1
Y | IPCRP1-0944-1020-L | IPCRP1 | IPCRP1 | 0944-1020 | Sawcut Joints - Sub | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 46290 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 1
Y | IPCRP1-0944-1020-S | IPCRP1 | IPCRP1 | 0944-1020 | Sawcut Joints - Sub | N | S |  | NR | A | 277740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 277740 | 0 | 0 | 277740 | 0 | 0 | 0 | Y | 277740 | 0 | 0 | 277740 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 46290 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0945-0000-L | IPCRP1 | IPCRP1 | 0945-0000 | RPL TABLE SEAT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0945-0000-R | IPCRP1 | IPCRP1 | 0945-0000 | RPL TABLE SEAT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 24576 | 0 | 0 | 24576 | 0 | 24576 | 15816 | 0 | N | 24576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0946-0000-L | IPCRP1 | IPCRP1 | 0946-0000 | ST SLAT DOUBLE SWING GATE, 8ft H X 15ft W | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0946-0000-R | IPCRP1 | IPCRP1 | 0946-0000 | ST SLAT DOUBLE SWING GATE, 8ft H X 15ft W | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9200 | 0 | 0 | 9200 | 0 | 9200 | 0 | 0 | N | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0947-0000-L | IPCRP1 | IPCRP1 | 0947-0000 | AMPHITHEATER PC CONC SEATWALL MODULE A | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0947-0000-R | IPCRP1 | IPCRP1 | 0947-0000 | AMPHITHEATER PC CONC SEATWALL MODULE A | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 144100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 212850 | 144100 | 0 | 68750 | 0 | 356950 | 212316.5 | 0 | N | 356950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0948-0000-L | IPCRP1 | IPCRP1 | 0948-0000 | AMPHITHEATER PC CONC SEATWALL MODULE B | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0948-0000-R | IPCRP1 | IPCRP1 | 0948-0000 | AMPHITHEATER PC CONC SEATWALL MODULE B | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 237150 | 0 | 0 | 0 | 0 | 0 | N | 0 | 351900 | 237150 | 0 | 114750 | 0 | 589050 | 366868.5 | 0 | N | 589050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 589050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0949-0000-L | IPCRP1 | IPCRP1 | 0949-0000 | AMPHITHEATER PC CONC SEATWALL MODULE C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0949-0000-R | IPCRP1 | IPCRP1 | 0949-0000 | AMPHITHEATER PC CONC SEATWALL MODULE C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 148750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 220500 | 148750 | 0 | 71750 | 0 | 369250 | 219791.25 | 0 | N | 369250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0950-0000-L | IPCRP1 | IPCRP1 | 0950-0000 | AMPHITHEATER PC CONC SEATWALL MODULE D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0950-0000-R | IPCRP1 | IPCRP1 | 0950-0000 | AMPHITHEATER PC CONC SEATWALL MODULE D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 83125 | 0 | 0 | 0 | 0 | 0 | N | 0 | 123025 | 83125 | 0 | 39900 | 0 | 206150 | 121752 | 0 | N | 206150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0951-0000-L | IPCRP1 | IPCRP1 | 0951-0000 | AMPHITHEATER PC CONC SEATWALL MODULE E | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0951-0000-R | IPCRP1 | IPCRP1 | 0951-0000 | AMPHITHEATER PC CONC SEATWALL MODULE E | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 12000 | 8000 | 0 | 4000 | 0 | 20000 | 6080 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0952-0000-L | IPCRP1 | IPCRP1 | 0952-0000 | FISH CLEANING TABLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0952-0000-R | IPCRP1 | IPCRP1 | 0952-0000 | FISH CLEANING TABLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 30000 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | N | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0953-0000-L | IPCRP1 | IPCRP1 | 0953-0000 | NATURE EXPLORATION FABRICATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0953-0000-R | IPCRP1 | IPCRP1 | 0953-0000 | NATURE EXPLORATION FABRICATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 32000 | 0 | 0 | 32000 | 0 | 32000 | 23200 | 0 | N | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0953-1000-L | IPCRP1 | IPCRP1 | 0953-1000 | Nature Exploration Fabrication | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.48 | 0.52 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0953-1000-M | IPCRP1 | IPCRP1 | 0953-1000 | Nature Exploration Fabrication | N | M |  | UNIT | U | 30000 | 136750 | 136750 | 64600 | 136750 | 47.2395 | 0 | 0 | 0 | 0 | N | 136750 | N | -106750 | 0 | 0 | 30000 | 0 | 0 | 136750 | N | -106750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -136750 | 0 | 0 | 136750 | 0 | 0 | 0 | 0 | 0 | 0 | -136750 | 0 | 0 | 136750 | 136750 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 0 | 18.45 | 0.55 | 19 | NA | 1 | 0.48 | 0.52 | 1 | LS | 136750 | 72150 | 64600 | 0 | TRI-LOX MILLWORKS LLC PO@$136,750
Y | IPCRP1-0954-0000-L | IPCRP1 | IPCRP1 | 0954-0000 | NATURE PLAY - LOG SCRAMBLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0954-0000-R | IPCRP1 | IPCRP1 | 0954-0000 | NATURE PLAY - LOG SCRAMBLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3600 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | N | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0955-0000-L | IPCRP1 | IPCRP1 | 0955-0000 | TREE ROUND BORDER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0955-0000-R | IPCRP1 | IPCRP1 | 0955-0000 | TREE ROUND BORDER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 26000 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | N | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0956-0000-L | IPCRP1 | IPCRP1 | 0956-0000 | TREE ROUND MAZE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0956-0000-R | IPCRP1 | IPCRP1 | 0956-0000 | TREE ROUND MAZE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 26000 | 0 | 0 | 26000 | 0 | 26000 | 26000 | 0 | N | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0957-0000-L | IPCRP1 | IPCRP1 | 0957-0000 | TREE ROUND SEAT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0957-0000-R | IPCRP1 | IPCRP1 | 0957-0000 | TREE ROUND SEAT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11000 | 0 | 0 | 11000 | 0 | 11000 | 0 | 0 | N | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0957-1000-L | IPCRP1 | IPCRP1 | 0957-1000 | Nature Exploration Installation | N | L |  | UNIT | P | 0 | 4763.23 | 4763.23 | 4763.23 | 4763.23 | 7.5007 | 0 | 0 | 0 | 58740.21 | Y | 63503.44 | Y | -63503.44 | 0 | 0 | 0 | 0 | 0 | 63503.44 | Y | -63503.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63503.44 | 0 | 0 | 63503.44 | 0 | 0 | 0 | 0 | 0 | 0 | -63503.44 | 0 | 0 | 63503.44 | 63503.44 | 0 | 0 | 0 | 0 | 0 | 488 | 488 | 0 | 39.5 | 448.5 | 488 | HR | 1 | 0.25 | 0.75 | 1 | LS | 0 | 0 | 0 | 58740.21
Y | IPCRP1-0957-1000-S | IPCRP1 | IPCRP1 | 0957-1000 | Nature Exploration Installation | N | S |  | UNIT | A | 63500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 63500 | 0 | 0 | 63500 | 0 | 0 | 0 | Y | 63500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.25 | 0.75 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0958-0000-L | IPCRP1 | IPCRP1 | 0958-0000 | TREE SELECTION, STORAGE, PREPARATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0958-0000-R | IPCRP1 | IPCRP1 | 0958-0000 | TREE SELECTION, STORAGE, PREPARATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9600000 | 0 | 0 | 9600000 | 0 | 9600000 | 9600000 | 0 | N | 9600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0958-1000-L | IPCRP1 | IPCRP1 | 0958-1000 | Special Tree Handle, Treat, Fab & Install | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0958-1000-S | IPCRP1 | IPCRP1 | 0958-1000 | Special Tree Handle, Treat, Fab & Install | N | S |  | NR | P | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 150000 | 0 | 0 | 150000 | 0 | 0 | 0 | Y | 150000 | 0 | 0 | 243500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | Moved to cc: 0756-1000 Landscape Subcontractor (Eastern)
Y | IPCRP1-0959-0000-L | IPCRP1 | IPCRP1 | 0959-0000 | CIRCULAR TABLES & CHAIRS TYPE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0959-0000-R | IPCRP1 | IPCRP1 | 0959-0000 | CIRCULAR TABLES & CHAIRS TYPE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9000 | 0 | 0 | 9000 | 0 | 9000 | 4522 | 0 | N | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0960-0000-L | IPCRP1 | IPCRP1 | 0960-0000 | CIRCULAR TABLES & CHAIRS TYPE 2, ACCESSIBLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0960-0000-R | IPCRP1 | IPCRP1 | 0960-0000 | CIRCULAR TABLES & CHAIRS TYPE 2, ACCESSIBLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4500 | 0 | 0 | 4500 | 0 | 4500 | 2261 | 0 | N | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0961-0000-L | IPCRP1 | IPCRP1 | 0961-0000 | CIRCULAR TABLES & CHAIRS TYPE 2, W/UMBRELLA HOLE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0961-0000-R | IPCRP1 | IPCRP1 | 0961-0000 | CIRCULAR TABLES & CHAIRS TYPE 2, W/UMBRELLA HOLE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 55000 | 0 | 0 | 55000 | 0 | 55000 | 28783 | 0 | N | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0962-0000-L | IPCRP1 | IPCRP1 | 0962-0000 | CIRCULAR TABLES & CHAIRS TYPE 2, ACCESSIBLE, W/UM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0962-0000-R | IPCRP1 | IPCRP1 | 0962-0000 | CIRCULAR TABLES & CHAIRS TYPE 2, ACCESSIBLE, W/UM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 22000 | 0 | 0 | 22000 | 0 | 22000 | 13261 | 0 | N | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0963-0000-L | IPCRP1 | IPCRP1 | 0963-0000 | REM, SALV, STORE & REINSTALL - GOUVERNEUR GARDENS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0963-0000-R | IPCRP1 | IPCRP1 | 0963-0000 | REM, SALV, STORE & REINSTALL - GOUVERNEUR GARDENS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 550000 | 0 | 0 | 550000 | 0 | 550000 | 385000 | 0 | N | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0963-1000-C | IPCRP1 | IPCRP1 | 0963-1000 | REM, SALV, STORE & REINSTALL - GOUVERNEUR GARDENS | N | C |  | UNIT | U | 0 | 17776.25 | 17776.25 | 16856.59 | 17776.25 | 94.8265 | 0 | 0 | 0 | 0 | N | 17776.25 | N | -17776.25 | 0 | 0 | 0 | 0 | 0 | 17776.25 | N | -17776.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17776.25 | 0 | 0 | 17776.25 | 0 | 0 | 0 | 0 | 0 | 0 | -17776.25 | 0 | 0 | 17776.25 | 17776.25 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 2 | NA | 1 | 0.7 | 0.3 | 1 | LS | 17776.25 | 919.66 | 16856.59 | 0
Y | IPCRP1-0963-1000-L | IPCRP1 | IPCRP1 | 0963-1000 | REM, SALV, STORE & REINSTALL - GOUVERNEUR GARDENS | N | L |  | UNIT | P | 0 | 10145.76 | 10145.76 | 10145.76 | 10145.76 | 39.0173 | 0 | 0 | 0 | 15857.45 | Y | 26003.21 | Y | -26003.21 | 0 | 0 | 0 | 0 | 0 | 26003.21 | Y | -26003.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26003.21 | 0 | 0 | 26003.21 | 0 | 0 | 0 | 0 | 0 | 0 | -26003.21 | 0 | 0 | 26003.21 | 26003.21 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 94 | 106 | 200 | HR | 1 | 0.7 | 0.3 | 1 | LS | 0 | 0 | 0 | 15857.45
Y | IPCRP1-0963-1000-S | IPCRP1 | IPCRP1 | 0963-1000 | REM, SALV, STORE & REINSTALL - GOUVERNEUR GARDENS | N | S |  | NR | A | 525265.88 | 6662.45 | 6662.45 | 347.7 | 6662.45 | 5.2032 | 0 | 0 | 0 | 20 | Y | 6682.45 | Y | 518583.43 | 0 | 0 | 525265.88 | 0 | 0 | 6682.45 | Y | 518583.43 | 0 | 0 | 525265.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6682.45 | 0 | 0 | 6682.45 | 0 | 0 | 0 | 0 | 0 | 0 | -6682.45 | 0 | 0 | 6682.45 | 6682.45 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3 | -2 | 1 | NA | 1 | 0.7 | 0.3 | 1 | LS | 6662.45 | 6314.75 | 347.7 | 20
Y | IPCRP1-0964-0000-L | IPCRP1 | IPCRP1 | 0964-0000 | REM, SALV, STORE & REINSTALL - EAST RIVER PARK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0964-0000-R | IPCRP1 | IPCRP1 | 0964-0000 | REM, SALV, STORE & REINSTALL - EAST RIVER PARK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 550000 | 0 | 0 | 550000 | 0 | 550000 | 550000 | 0 | N | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0964-1000-C | IPCRP1 | IPCRP1 | 0964-1000 | REM, SALV, STORE & REINSTALL - EAST RIVER PARK | N | C |  | UNIT | U | 0 | 33545.14 | 33545.14 | 33545.14 | 33545.14 | 100 | 0 | 0 | 0 | 0 | Y | 33545.14 | Y | -33545.14 | 0 | 0 | 0 | 0 | 0 | 33545.14 | Y | -33545.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -33545.14 | 0 | 0 | 33545.14 | 0 | 0 | 0 | 0 | 0 | 0 | -33545.14 | 0 | 0 | 33545.14 | 33545.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792 | -792 | 0 | NA | 1 | 1 | 0 | 1 | LS | 33545.14 | 0 | 33545.14 | 0
Y | IPCRP1-0964-1000-L | IPCRP1 | IPCRP1 | 0964-1000 | REM, SALV, STORE & REINSTALL - EAST RIVER PARK | N | L |  | UNIT | P | 0 | 38506.3 | 38506.3 | 38506.3 | 38506.3 | 100 | 0 | 0 | 0 | 0 | Y | 38506.3 | Y | -38506.3 | 0 | 0 | 0 | 0 | 0 | 38506.3 | Y | -38506.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -38506.3 | 0 | 0 | 38506.3 | 0 | 0 | 0 | 0 | 0 | 0 | -38506.3 | 0 | 0 | 38506.3 | 38506.3 | 0 | 0 | 0 | 0 | 0 | 364 | 364 | 0 | 364 | 0 | 364 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0964-1000-M | IPCRP1 | IPCRP1 | 0964-1000 | REM, SALV, STORE & REINSTALL - EAST RIVER PARK | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0964-1000-S | IPCRP1 | IPCRP1 | 0964-1000 | REM, SALV, STORE & REINSTALL - EAST RIVER PARK | N | S |  | NR | A | 525265.88 | 500.39 | 500.39 | 500.39 | 500.39 | 100 | 0 | 0 | 0 | 0 | Y | 500.39 | Y | 524765.49 | 0 | 0 | 525265.88 | 0 | 0 | 500.39 | Y | 524765.49 | 0 | 0 | 525265.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -500.39 | 0 | 0 | 500.39 | 0 | 0 | 0 | 0 | 0 | 0 | -500.39 | 0 | 0 | 500.39 | 500.39 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 261.14 | 8807.8 | 9068.94 | NA | 1 | 1 | 0 | 1 | LS | 500.39 | 0 | 500.39 | 0 | Site Protection at P42, FBH, WBB Piers, E6th St, & Along FDR Drive (Ph 1 & Ph 2) This note will be deleted after Building Conservation PO# IPCRP1-0098 ($12,411.75) and Tulnoy PO#IPCRP1-0170 ($6,802.51) is moved from category S to C.
Y | IPCRP1-0965-0000-L | IPCRP1 | IPCRP1 | 0965-0000 | HORTICULTURAL DRAINAGE LAYER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0965-0000-R | IPCRP1 | IPCRP1 | 0965-0000 | HORTICULTURAL DRAINAGE LAYER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 922725 | 0 | 0 | 922725 | 0 | 922725 | 339952.5 | 0 | N | 922725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0966-0000-L | IPCRP1 | IPCRP1 | 0966-0000 | HORTICULTURAL SUBSOIL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0966-0000-R | IPCRP1 | IPCRP1 | 0966-0000 | HORTICULTURAL SUBSOIL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7105250 | 0 | 0 | 7105250 | 0 | 7105250 | 2694987.5 | 0 | N | 7105250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7105250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0967-0000-L | IPCRP1 | IPCRP1 | 0967-0000 | PLANTING SOIL FOR BEDS & PITS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0967-0000-R | IPCRP1 | IPCRP1 | 0967-0000 | PLANTING SOIL FOR BEDS & PITS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5190625 | 0 | 0 | 5190625 | 0 | 5190625 | 1919681.25 | 0 | N | 5190625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5190625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0968-0000-L | IPCRP1 | IPCRP1 | 0968-0000 | CHINKING STONE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0968-0000-R | IPCRP1 | IPCRP1 | 0968-0000 | CHINKING STONE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 394500 | 0 | 0 | 394500 | 0 | 394500 | 0 | 0 | N | 394500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0968-1000-L | IPCRP1 | IPCRP1 | 0968-1000 | CHINKING STONE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3156 | 0 | 3156 | 3156 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0968-1000-M | IPCRP1 | IPCRP1 | 0968-1000 | CHINKING STONE | N | M |  | UNIT | U | 0 | 94150 | 94150 | 0 | 94150 | 0 | 0 | 0 | 0 | 0 | N | 94150 | N | -94150 | 0 | 0 | 0 | 0 | 0 | 94150 | N | -94150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -94150 | 0 | 0 | 94150 | 0 | 0 | 0 | 0 | 0 | 0 | -94150 | 0 | 0 | 94150 | 94150 | 0 | 0 | 0 | 0 | 0 | 3766 | 3766 | 0 | 0 | 3766 | 3766 | NA | 3156 | 0 | 3156 | 3156 | CY | 94150 | 94150 | 0 | 0
Y | IPCRP1-0968-1000-S | IPCRP1 | IPCRP1 | 0968-1000 | CHINKING STONE | N | S |  | NR | A | 315600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221450 | Y | 221450 | Y | 94150 | 0 | 0 | 315600 | 0 | 0 | 221450 | Y | 94150 | 0 | 0 | 315600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -221450 | 0 | 0 | 221450 | 0 | 0 | 0 | 0 | 0 | 0 | -221450 | 0 | 0 | 221450 | 221450 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3156 | 0 | 3156 | 3156 | CY | 0 | 0 | 0 | 221450
Y | IPCRP1-0969-0000-L | IPCRP1 | IPCRP1 | 0969-0000 | PLANTING SOIL FOR SEEDED & SODDED LAWN AREAS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0969-0000-R | IPCRP1 | IPCRP1 | 0969-0000 | PLANTING SOIL FOR SEEDED & SODDED LAWN AREAS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 378520 | 0 | 0 | 378520 | 0 | 378520 | 59840 | 0 | N | 378520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0970-0000-L | IPCRP1 | IPCRP1 | 0970-0000 | GALV ST CHAIN LINK FENCE - 4ft H | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0970-0000-R | IPCRP1 | IPCRP1 | 0970-0000 | GALV ST CHAIN LINK FENCE - 4ft H | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18900 | 0 | 0 | 18900 | 0 | 18900 | 0 | 0 | N | 18900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0971-0000-L | IPCRP1 | IPCRP1 | 0971-0000 | FIXED BOLLARD TYPE 2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0971-0000-R | IPCRP1 | IPCRP1 | 0971-0000 | FIXED BOLLARD TYPE 2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 143000 | 0 | 0 | 143000 | 0 | 143000 | 66000 | 0 | N | 143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0971-1000-L | IPCRP1 | IPCRP1 | 0971-1000 | Bollards at CHP Wst, Montg St, Houston St | N | L |  | UNIT | P | 0 | 13537.73 | 13537.73 | 13537.73 | 13537.73 | 23.932 | 0 | 0 | 0 | 43029.67 | Y | 56567.4 | Y | -56567.4 | 0 | 0 | 0 | 0 | 0 | 56567.4 | Y | -56567.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -56567.4 | 0 | 0 | 56567.4 | 0 | 0 | 0 | 0 | 0 | 0 | -56567.4 | 0 | 0 | 56567.4 | 56567.4 | 0 | 0 | 0 | 0 | 0 | 435.01 | 435.01 | 0 | 113 | 322.01 | 435.01 | HR | 26 | 15 | 5 | 20 | EA | 0 | 0 | 0 | 43029.67 | 9ea CHP West, 3ea Montgomery St, 8ea Houston St.
Y | IPCRP1-0971-1000-M | IPCRP1 | IPCRP1 | 0971-1000 | Bollards at CHP Wst, Montg St, Houston St | N | M |  | UNIT | U | 0 | 75100 | 75100 | 45060 | 75100 | 56.325 | 0 | 0 | 0 | 4900 | Y | 80000 | Y | -80000 | 0 | 0 | 0 | 0 | 0 | 80000 | Y | -80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -80000 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | -80000 | 0 | 0 | 80000 | 80000 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 12 | -12 | 0 | EA | 26 | 15 | 5 | 20 | EA | 75100 | 30040 | 45060 | 4900
Y | IPCRP1-0971-1000-S | IPCRP1 | IPCRP1 | 0971-1000 | Bollards at CHP Wst, Montg St, Houston St | N | S |  | NR | A | 136569.13 | 322.75 | 322.75 | 322.75 | 322.75 | 100 | 0 | 0 | 0 | 0 | Y | 322.75 | Y | 136246.38 | 0 | 0 | 136569.13 | 0 | 0 | 322.75 | Y | 136246.38 | 0 | 0 | 136569.13 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -322.75 | 0 | 0 | 322.75 | 0 | 0 | 0 | 0 | 0 | 0 | -322.75 | 0 | 0 | 322.75 | 322.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.5 | -2.5 | 0 | NA | 26 | 15 | 5 | 20 | EA | 322.75 | 0 | 322.75 | 0
Y | IPCRP1-0972-0000-L | IPCRP1 | IPCRP1 | 0972-0000 | SECURITY GATE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0972-0000-R | IPCRP1 | IPCRP1 | 0972-0000 | SECURITY GATE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 80000 | 0 | 0 | 80000 | 0 | 80000 | 20000 | 0 | N | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0972-1000-E | IPCRP1 | IPCRP1 | 0972-1000 | Security Gate - Complete | N | E |  | NR | P | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 369 | 0 | 0 | 369 | 0 | 0 | 0 | Y | 369 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 4 | 1 | 2 | 3 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0972-1000-L | IPCRP1 | IPCRP1 | 0972-1000 | Security Gate - Complete | N | L |  | NR | P | 5190 | 15209.36 | 15209.36 | 15209.36 | 15209.36 | 25.4894 | 0 | 0 | 0 | 44460 | Y | 59669.36 | Y | -54479.36 | 0 | 0 | 5190 | 0 | 0 | 59669.36 | Y | -54479.36 | 0 | 0 | 5190 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -59669.36 | 0 | 0 | 59669.36 | 0 | 0 | 0 | 0 | 0 | 0 | -59669.36 | 0 | 0 | 59669.36 | 59669.36 | 0 | 0 | 0 | 49.84 | 0 | 500 | 500 | 49.84 | 129.5 | 370.5 | 500 | HR | 4 | 1 | 2 | 3 | EA | 0 | 0 | 0 | 44460
Y | IPCRP1-0972-1000-M | IPCRP1 | IPCRP1 | 0972-1000 | Security Gate - Complete | N | M |  | UNIT | U | 0 | 63000 | 63000 | 63000 | 63000 | 100 | 0 | 0 | 0 | 0 | Y | 63000 | Y | -63000 | 0 | 0 | 0 | 0 | 0 | 63000 | Y | -63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63000 | 0 | 0 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | -63000 | 0 | 0 | 63000 | 63000 | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 4 | 3 | 1 | 4 | EA | 4 | 1 | 2 | 3 | EA | 63000 | 0 | 63000 | 0
Y | IPCRP1-0972-1000-S | IPCRP1 | IPCRP1 | 0972-1000 | Security Gate - Complete | N | S |  | NR | A | 62987 | 740.51 | 740.51 | 740.51 | 740.51 | 100 | 0 | 0 | 0 | 0 | Y | 740.51 | Y | 62246.49 | 0 | 0 | 62987 | 0 | 0 | 740.51 | Y | 62246.49 | 0 | 0 | 62987 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -740.51 | 0 | 0 | 740.51 | 0 | 0 | 0 | 0 | 0 | 0 | -740.51 | 0 | 0 | 740.51 | 740.51 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6 | -6 | 0 | NA | 4 | 1 | 2 | 3 | EA | 740.51 | 0 | 740.51 | 0
Y | IPCRP1-0973-0000-L | IPCRP1 | IPCRP1 | 0973-0000 | REMOVABLE BOLLARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0973-0000-R | IPCRP1 | IPCRP1 | 0973-0000 | REMOVABLE BOLLARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31800 | 0 | 0 | 31800 | 0 | 31800 | 0 | 0 | N | 31800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0974-0000-L | IPCRP1 | IPCRP1 | 0974-0000 | FIXED BOLLARD TYPE 3 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0974-0000-R | IPCRP1 | IPCRP1 | 0974-0000 | FIXED BOLLARD TYPE 3 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5300 | 0 | 0 | 5300 | 0 | 5300 | 5300 | 0 | N | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0974-1000-L | IPCRP1 | IPCRP1 | 0974-1000 | Install Fixed Bollard Tpe 3 & Removable Bollard | N | L |  | UNIT | P | 0 | 2248.52 | 2248.52 | 2248.52 | 2248.52 | 10.8102 | 0 | 0 | 0 | 18551.48 | Y | 20800 | Y | -20800 | 0 | 0 | 0 | 0 | 0 | 20800 | Y | -20800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20800 | 1886.58 | 0 | 20800 | 0 | 0 | 0 | 0 | 0 | 0 | -20800 | 0 | 0 | 20800 | 20800 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 0 | 18 | 142 | 160 | HR | 7 | 2 | 6 | 8 | EA | 0 | 0 | 0 | 18551.48
Y | IPCRP1-0974-1000-M | IPCRP1 | IPCRP1 | 0974-1000 | Install Fixed Bollard Tpe 3 & Removable Bollard | N | M |  | UNIT | U | 0 | 31156 | 31156 | 31156 | 31156 | 100 | 0 | 0 | 0 | 0 | Y | 31156 | Y | -31156 | 0 | 0 | 0 | 0 | 0 | 31156 | Y | -31156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31156 | 0 | 0 | 31156 | 0 | 0 | 0 | 0 | 0 | 0 | -31156 | 0 | 0 | 31156 | 31156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | -8 | 0 | NA | 7 | 2 | 6 | 8 | EA | 31156 | 0 | 31156 | 0
Y | IPCRP1-0974-1000-S | IPCRP1 | IPCRP1 | 0974-1000 | Install Fixed Bollard Tpe 3 & Removable Bollard | N | S |  | NR | A | 36769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 36769 | 0 | 0 | 36769 | 0 | 0 | 0 | Y | 36769 | 0 | 0 | 36769 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 7 | 2 | 6 | 8 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0975-0000-L | IPCRP1 | IPCRP1 | 0975-0000 | COMPOST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0975-0000-R | IPCRP1 | IPCRP1 | 0975-0000 | COMPOST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7350 | 0 | 0 | 7350 | 0 | 7350 | 0 | 0 | N | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0976-0000-L | IPCRP1 | IPCRP1 | 0976-0000 | BIOCHAR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0976-0000-R | IPCRP1 | IPCRP1 | 0976-0000 | BIOCHAR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 738900 | 0 | 0 | 738900 | 0 | 738900 | 189585 | 0 | N | 738900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-0977-0000-L | IPCRP1 | IPCRP1 | 0977-0000 | GEOCOMPOSITE DRAINAGE BOARD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0977-0000-R | IPCRP1 | IPCRP1 | 0977-0000 | GEOCOMPOSITE DRAINAGE BOARD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 269496 | 0 | 0 | 269496 | 0 | 269496 | 163384.8 | 0 | N | 269496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0977-1000-E | IPCRP1 | IPCRP1 | 0977-1000 | Inst Geocomposite Drainage Board | N | E |  | NR | P | 14373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 14373 | 0 | 0 | 14373 | 0 | 0 | 0 | Y | 14373 | 0 | 0 | 14373 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 179664 | 540 | 0 | 540 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0977-1000-L | IPCRP1 | IPCRP1 | 0977-1000 | Inst Geocomposite Drainage Board | N | L |  | NR | P | 64251.26 | 2615.92 | 2615.92 | 2615.92 | 2615.92 | 581.7551 | 0 | 0 | 0 | -2166.26 | Y | 449.66 | Y | 63801.6 | 0 | 0 | 64251.26 | 0 | 0 | 449.66 | Y | 63801.6 | 0 | 0 | 64251.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -449.66 | 2166.26 | 0 | 449.66 | 0 | 0 | 0 | 0 | 0 | 0 | -449.66 | 0 | 0 | 449.66 | 449.66 | 0 | 0 | 0 | 574.92 | 0 | 4 | 4 | 574.92 | 22 | -18 | 4 | HR | 179664 | 540 | 0 | 540 | SF | 0 | 0 | 0 | -2166.26 | Work included in Eastern Landscape subcontract, seq #756
N | IPCRP1-0977-1000-S | IPCRP1 | IPCRP1 | 0977-1000 | Inst Geocomposite Drainage Board | N | S |  | UNIT | A | 0 | 258.27 | 258.27 | 258.27 | 258.27 | 100 | 0 | 0 | 0 | 0 | N | 258.27 | N | -258.27 | 0 | 0 | 0 | 0 | 0 | 258.27 | N | -258.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -258.27 | 258.27 | 0 | 258.27 | 0 | 0 | 0 | 0 | 258.27 | 0 | -258.27 | 0 | 0 | 258.27 | 258.27 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | NA | 179664 | 540 | 0 | 540 | SF | 258.27 | 0 | 258.27 | 0
Y | IPCRP1-0977-1010-L | IPCRP1 | IPCRP1 | 0977-1010 | PM - Geocomposite Drainage Board | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 179664 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | Work included in Eastern Landscape subcontract, seq #756
Y | IPCRP1-0977-1010-M | IPCRP1 | IPCRP1 | 0977-1010 | PM - Geocomposite Drainage Board | N | M |  | NR | P | 179664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 179654 | 0 | 0 | 179664 | 0 | 0 | 10 | Y | 179654 | 0 | 0 | 179664 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 179664 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 10
Y | IPCRP1-0978-0000-L | IPCRP1 | IPCRP1 | 0978-0000 | ST SLAT PRIVACY FENCE M&O | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0978-0000-R | IPCRP1 | IPCRP1 | 0978-0000 | ST SLAT PRIVACY FENCE M&O | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 165725 | 0 | 0 | 165725 | 0 | 165725 | 0 | 0 | N | 165725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0979-0000-L | IPCRP1 | IPCRP1 | 0979-0000 | SITE PROTECTION - GOUVERNEUR GARDENS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0979-0000-R | IPCRP1 | IPCRP1 | 0979-0000 | SITE PROTECTION - GOUVERNEUR GARDENS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 54000 | 0 | 0 | 54000 | 0 | 54000 | 54000 | 0 | N | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0980-0000-L | IPCRP1 | IPCRP1 | 0980-0000 | SITE PROTECTION - EAST RIVER PARK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0980-0000-R | IPCRP1 | IPCRP1 | 0980-0000 | SITE PROTECTION - EAST RIVER PARK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2000000 | 0 | 0 | 2000000 | 0 | 2000000 | 1650000 | 0 | N | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0980-1000-L | IPCRP1 | IPCRP1 | 0980-1000 | Inst MSE Retaining Wall Pad | N | L |  | NR | P | 60275.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | 13000 | Y | 47275.2 | 0 | 0 | 60275.2 | 0 | 0 | 13000 | Y | 47275.2 | 0 | 0 | 60275.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 560 | 0 | 100 | 100 | 560 | 0 | 100 | 100 | HR | 4550 | 0 | 4550 | 4550 | LF | 0 | 0 | 0 | 13000 | Site Protection at P42, FBH, WBB Piers, E6th St, & Along FDR Drive (Ph 1 & Ph 2)
Y | IPCRP1-0980-1010-E | IPCRP1 | IPCRP1 | 0980-1010 | Inst MSE Retaining Wall | N | E |  | NR | P | 16987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16987 | 0 | 0 | 16987 | 0 | 0 | 0 | Y | 16987 | 0 | 0 | 16987 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 31850 | 0 | 31850 | 31850 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0980-1010-L | IPCRP1 | IPCRP1 | 0980-1010 | Inst MSE Retaining Wall | N | L |  | NR | P | 110518.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | 13000 | Y | 97518.55 | 0 | 0 | 110518.55 | 0 | 0 | 13000 | Y | 97518.55 | 0 | 0 | 110518.55 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 1019.21 | 0 | 100 | 100 | 1019.21 | 0 | 100 | 100 | HR | 31850 | 0 | 31850 | 31850 | SF | 0 | 0 | 0 | 13000 | Site Protection at P42, FBH, WBB Piers, E6th St, & Along FDR Drive (Ph 1 & Ph 2)
Y | IPCRP1-0980-1020-L | IPCRP1 | IPCRP1 | 0980-1020 | PM - MSE Retaining Wall | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 31850 | 0 | 31850 | 31850 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0980-1020-M | IPCRP1 | IPCRP1 | 0980-1020 | PM - MSE Retaining Wall | N | M |  | NR | P | 637000 | 71217.33 | 71217.33 | 70279.77 | 71217.33 | 70.2798 | 0 | 0 | 0 | 28782.67 | Y | 100000 | Y | 537000 | 0 | 0 | 637000 | 0 | 0 | 100000 | Y | 537000 | 0 | 0 | 637000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 78 | 31.52 | 109.52 | NA | 31850 | 0 | 31850 | 31850 | SF | 71217.33 | 937.56 | 70279.77 | 28782.67 | Site Protection at P42, FBH, WBB Piers, E6th St, & Along FDR Drive (Ph 1 & Ph 2)
Y | IPCRP1-0981-0000-L | IPCRP1 | IPCRP1 | 0981-0000 | SITE PROTECTION - CORLEARS HOOK PARK | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0981-0000-R | IPCRP1 | IPCRP1 | 0981-0000 | SITE PROTECTION - CORLEARS HOOK PARK | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 225000 | 0 | 0 | 225000 | 0 | 225000 | 196875 | 0 | N | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0982-0000-L | IPCRP1 | IPCRP1 | 0982-0000 | COMPOST TEA - SHRUBS & PERENNIALS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0
Y | IPCRP1-0982-0000-R | IPCRP1 | IPCRP1 | 0982-0000 | COMPOST TEA - SHRUBS & PERENNIALS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8730 | 0 | 0 | 8730 | 0 | 8730 | 1629 | 0 | N | 8730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0
Y | IPCRP1-0983-0000-L | IPCRP1 | IPCRP1 | 0983-0000 | COMPOST TEA - PLANTING BED & PIT AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0
Y | IPCRP1-0983-0000-R | IPCRP1 | IPCRP1 | 0983-0000 | COMPOST TEA - PLANTING BED & PIT AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11160 | 0 | 0 | 11160 | 0 | 11160 | 2403 | 0 | N | 11160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0
Y | IPCRP1-0984-0000-L | IPCRP1 | IPCRP1 | 0984-0000 | SURVEY TRACK LINES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0984-0000-R | IPCRP1 | IPCRP1 | 0984-0000 | SURVEY TRACK LINES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 31000 | 0 | 0 | 31000 | 0 | 31000 | 0 | 0 | N | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0985-0000-L | IPCRP1 | IPCRP1 | 0985-0000 | POLE VAULT PIT & COVER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0985-0000-R | IPCRP1 | IPCRP1 | 0985-0000 | POLE VAULT PIT & COVER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 41000 | 0 | 0 | 41000 | 0 | 41000 | 0 | 0 | N | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-0986-0000-L | IPCRP1 | IPCRP1 | 0986-0000 | BIKEWAY SYMBOLS ETCHED INTO CONC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0986-0000-R | IPCRP1 | IPCRP1 | 0986-0000 | BIKEWAY SYMBOLS ETCHED INTO CONC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3200 | 0 | 0 | 3200 | 0 | 3200 | 5625 | 0 | N | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0986-1000-L | IPCRP1 | IPCRP1 | 0986-1000 | BIKEWAY SYMBOLS ETCHED INTO CONC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0986-1000-S | IPCRP1 | IPCRP1 | 0986-1000 | BIKEWAY SYMBOLS ETCHED INTO CONC | N | S |  | NR | A | 2941.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.49 | N | 2941.49 | N | 0 | 0 | 0 | 2941.49 | 0 | 0 | 2941.49 | N | 0 | 0 | 0 | 2941.49 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2941.49 | 0 | 0 | 2941.49 | 0 | 0 | 0 | 0 | 0 | 0 | -2941.49 | 0 | 0 | 2941.49 | 2941.49 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 2941.49
Y | IPCRP1-0987-0000-L | IPCRP1 | IPCRP1 | 0987-0000 | POROUS GRASS PAVERS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0987-0000-R | IPCRP1 | IPCRP1 | 0987-0000 | POROUS GRASS PAVERS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 36270 | 0 | 0 | 36270 | 0 | 36270 | 0 | 0 | N | 36270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-0988-0000-L | IPCRP1 | IPCRP1 | 0988-0000 | UNDERDRAINAGE FOR NATURAL TURF FIELD | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0988-0000-R | IPCRP1 | IPCRP1 | 0988-0000 | UNDERDRAINAGE FOR NATURAL TURF FIELD | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 153600 | 0 | 0 | 153600 | 0 | 153600 | 0 | 0 | N | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0988-1000-L | IPCRP1 | IPCRP1 | 0988-1000 | Underdrain for Natural Turf Field | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 9600 | 0 | 9600 | 9600 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-0988-1000-S | IPCRP1 | IPCRP1 | 0988-1000 | Underdrain for Natural Turf Field | N | S |  | NR | A | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144000 | N | 144000 | N | 0 | 0 | 0 | 144000 | 0 | 0 | 144000 | N | 0 | 0 | 0 | 144000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -144000 | 0 | 0 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | -144000 | 0 | 0 | 144000 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 9600 | 0 | 9600 | 9600 | LF | 0 | 0 | 0 | 144000
Y | IPCRP1-0989-0000-L | IPCRP1 | IPCRP1 | 0989-0000 | REM-SALVAGE TREE, 12-18 CL 2 - NYC DELIVERY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0989-0000-R | IPCRP1 | IPCRP1 | 0989-0000 | REM-SALVAGE TREE, 12-18 CL 2 - NYC DELIVERY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 41275 | 0 | 0 | 41275 | 0 | 41275 | 10042.5 | 0 | N | 41275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0990-0000-L | IPCRP1 | IPCRP1 | 0990-0000 | REM-SALVAGE TREE, 18-24 CL 3 - NYC DELIVERY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0990-0000-R | IPCRP1 | IPCRP1 | 0990-0000 | REM-SALVAGE TREE, 18-24 CL 3 - NYC DELIVERY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 95250 | 0 | 0 | 95250 | 0 | 95250 | 83925 | 0 | N | 95250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0991-0000-L | IPCRP1 | IPCRP1 | 0991-0000 | REM-SALVAGE TREE, 24-30 CL 4 - NYC DELIVERY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0991-0000-R | IPCRP1 | IPCRP1 | 0991-0000 | REM-SALVAGE TREE, 24-30 CL 4 - NYC DELIVERY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 139700 | 0 | 0 | 139700 | 0 | 139700 | 77880 | 0 | N | 139700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0992-0000-L | IPCRP1 | IPCRP1 | 0992-0000 | REM-SALVAGE TREE, 30+ CL 3 - NYC DELIVERY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0992-0000-R | IPCRP1 | IPCRP1 | 0992-0000 | REM-SALVAGE TREE, 30+ CL 3 - NYC DELIVERY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 176400 | 0 | 0 | 176400 | 0 | 176400 | 22260 | 0 | N | 176400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0992-1000-L | IPCRP1 | IPCRP1 | 0992-1000 | Rem Salvage Tree, All Sizes, NYC Delivery.Dont use | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 507 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0992-1000-S | IPCRP1 | IPCRP1 | 0992-1000 | Rem Salvage Tree, All Sizes, NYC Delivery.Dont use | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | LS | 507 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | Moved to cc: 0756-1000 Landscape Subcontractor (Eastern)
Y | IPCRP1-0993-0000-L | IPCRP1 | IPCRP1 | 0993-0000 | F&I FOUND FOR TYPE WF LAMPPOST, AS/ DWG E-5124 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0993-0000-R | IPCRP1 | IPCRP1 | 0993-0000 | F&I FOUND FOR TYPE WF LAMPPOST, AS/ DWG E-5124 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 934200 | 0 | 0 | 934200 | 0 | 934200 | 334800 | 0 | N | 934200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0994-0000-L | IPCRP1 | IPCRP1 | 0994-0000 | F&I STAND TYPE ANCHOR BOLT FOUND, AS/ DWG E-3788 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0994-0000-R | IPCRP1 | IPCRP1 | 0994-0000 | F&I STAND TYPE ANCHOR BOLT FOUND, AS/ DWG E-3788 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 11250 | 0 | 0 | 11250 | 0 | 11250 | 4500 | 0 | N | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0995-0000-L | IPCRP1 | IPCRP1 | 0995-0000 | F&I STAND TYPE ANCHOR BOLT FOUND, AS/ DWG J-5253 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0995-0000-R | IPCRP1 | IPCRP1 | 0995-0000 | F&I STAND TYPE ANCHOR BOLT FOUND, AS/ DWG J-5253 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18750 | 0 | 0 | 18750 | 0 | 18750 | 0 | 0 | N | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0996-0000-L | IPCRP1 | IPCRP1 | 0996-0000 | ROTOR FOUND, F&I RIGID CONDUIT BEND, SIZE AS ORDE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0996-0000-R | IPCRP1 | IPCRP1 | 0996-0000 | ROTOR FOUND, F&I RIGID CONDUIT BEND, SIZE AS ORDE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 875 | 0 | 0 | 875 | 0 | 875 | 0 | 0 | N | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0997-0000-L | IPCRP1 | IPCRP1 | 0997-0000 | REM STAND TYPE ANCHOR BOLT CONC FOUND | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0997-0000-R | IPCRP1 | IPCRP1 | 0997-0000 | REM STAND TYPE ANCHOR BOLT CONC FOUND | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 27500 | 0 | 0 | 27500 | 0 | 27500 | 6600 | 0 | N | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0998-0000-L | IPCRP1 | IPCRP1 | 0998-0000 | F&I WF LAMPPOST W/OUT TRANSFORMET BASE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0998-0000-R | IPCRP1 | IPCRP1 | 0998-0000 | F&I WF LAMPPOST W/OUT TRANSFORMET BASE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35000 | 0 | 0 | 35000 | 0 | 35000 | 48579.66 | 0 | N | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0999-0000-L | IPCRP1 | IPCRP1 | 0999-0000 | F&I TYPE 2S, 4S, 6S, 8S OR 12S LAMPPOST W/T-FORM | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-0999-0000-R | IPCRP1 | IPCRP1 | 0999-0000 | F&I TYPE 2S, 4S, 6S, 8S OR 12S LAMPPOST W/T-FORM | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 37500 | 0 | 0 | 37500 | 0 | 37500 | 10000 | 0 | N | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1000-0000-L | IPCRP1 | IPCRP1 | 1000-0000 | F&I TYPE 14ft H ST DAVIT LAMPPOST (SINGLE ARM) / J | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1000-0000-R | IPCRP1 | IPCRP1 | 1000-0000 | F&I TYPE 14ft H ST DAVIT LAMPPOST (SINGLE ARM) / J | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 37500 | 0 | 0 | 37500 | 0 | 37500 | 22500 | 0 | N | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1001-0000-L | IPCRP1 | IPCRP1 | 1001-0000 | F&I TYPE M LAMPPOST W/ PEC RECEPTACLE, / DWG H- | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1001-0000-R | IPCRP1 | IPCRP1 | 1001-0000 | F&I TYPE M LAMPPOST W/ PEC RECEPTACLE, / DWG H- | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250000 | 0 | 0 | 250000 | 0 | 250000 | 0 | 0 | N | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1002-0000-L | IPCRP1 | IPCRP1 | 1002-0000 | F&I TYPE FLUSH MEADOWS PARK LAMPPOST, / H-5305 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1002-0000-R | IPCRP1 | IPCRP1 | 1002-0000 | F&I TYPE FLUSH MEADOWS PARK LAMPPOST, / H-5305 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 333900 | 0 | 0 | 333900 | 0 | 333900 | 173720.16 | 0 | N | 333900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1003-0000-L | IPCRP1 | IPCRP1 | 1003-0000 | REM STAND FAB ST, SPUN ALUM NO. 10, W/ ARM,LUM, C | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1003-0000-R | IPCRP1 | IPCRP1 | 1003-0000 | REM STAND FAB ST, SPUN ALUM NO. 10, W/ ARM,LUM, C | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15000 | 0 | 0 | 15000 | 0 | 15000 | 16200 | 0 | N | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1004-0000-L | IPCRP1 | IPCRP1 | 1004-0000 | REM ORNAM LAMPPOST (TYPE BC, M, F, 5TH AVE, LYRE, | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1004-0000-R | IPCRP1 | IPCRP1 | 1004-0000 | REM ORNAM LAMPPOST (TYPE BC, M, F, 5TH AVE, LYRE, | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | N | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1005-0000-L | IPCRP1 | IPCRP1 | 1005-0000 | F&I TYPE 2085 100 W HPS LUMIN W/ 55 V LAMP | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1005-0000-R | IPCRP1 | IPCRP1 | 1005-0000 | F&I TYPE 2085 100 W HPS LUMIN W/ 55 V LAMP | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 15400 | 0 | 0 | 15400 | 0 | 15400 | 14779.02 | 0 | N | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1006-0000-L | IPCRP1 | IPCRP1 | 1006-0000 | F&I MAX 150 W LED TYPE TEAR DROP LUMINAIRE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1006-0000-R | IPCRP1 | IPCRP1 | 1006-0000 | F&I MAX 150 W LED TYPE TEAR DROP LUMINAIRE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 35000 | 0 | 0 | 35000 | 0 | 35000 | 0 | 0 | N | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1007-0000-L | IPCRP1 | IPCRP1 | 1007-0000 | INST FLOODLIGHT. LAMP FURNISHED BY CONTRACTOR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1007-0000-R | IPCRP1 | IPCRP1 | 1007-0000 | INST FLOODLIGHT. LAMP FURNISHED BY CONTRACTOR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | N | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1008-0000-L | IPCRP1 | IPCRP1 | 1008-0000 | F&I 70 W MAX LED FLUSH MEADOW PARK TYPE LUMIN | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1008-0000-R | IPCRP1 | IPCRP1 | 1008-0000 | F&I 70 W MAX LED FLUSH MEADOW PARK TYPE LUMIN | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 238500 | 0 | 0 | 238500 | 0 | 238500 | 149926.78 | 0 | N | 238500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1009-0000-L | IPCRP1 | IPCRP1 | 1009-0000 | F&I ROADWAY TYPE LED FIXTURE AS/ SPEC 466 W/ PEC | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1009-0000-R | IPCRP1 | IPCRP1 | 1009-0000 | F&I ROADWAY TYPE LED FIXTURE AS/ SPEC 466 W/ PEC | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9900 | 0 | 0 | 9900 | 0 | 9900 | 5850 | 0 | N | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1010-0000-L | IPCRP1 | IPCRP1 | 1010-0000 | FURNISH LED FLOODLIGHT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1010-0000-R | IPCRP1 | IPCRP1 | 1010-0000 | FURNISH LED FLOODLIGHT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7500 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | N | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1011-0000-L | IPCRP1 | IPCRP1 | 1011-0000 | F&I FAB ST 8ft ARM ON LP OR M-2 TRAF POLE SHAFT EX | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1011-0000-R | IPCRP1 | IPCRP1 | 1011-0000 | F&I FAB ST 8ft ARM ON LP OR M-2 TRAF POLE SHAFT EX | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 20800 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | N | 20800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1012-0000-L | IPCRP1 | IPCRP1 | 1012-0000 | F&I TROUGH FOR 3 FLOODLIGHTS OR 3 PEC, AS/ J-5229 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1012-0000-R | IPCRP1 | IPCRP1 | 1012-0000 | F&I TROUGH FOR 3 FLOODLIGHTS OR 3 PEC, AS/ J-5229 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3850 | 0 | 0 | 3850 | 0 | 3850 | 1100 | 0 | N | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1013-0000-L | IPCRP1 | IPCRP1 | 1013-0000 | REM PLUG-IN CONTROL, OR SHORT BRIDGE. INST PLUG-I | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1013-0000-R | IPCRP1 | IPCRP1 | 1013-0000 | REM PLUG-IN CONTROL, OR SHORT BRIDGE. INST PLUG-I | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6125 | 0 | 0 | 6125 | 0 | 6125 | 1500 | 0 | N | 6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1014-0000-L | IPCRP1 | IPCRP1 | 1014-0000 | F&I ALUM TAG ON A LAMPPOST, AS PER DRAWING D-2861 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1014-0000-R | IPCRP1 | IPCRP1 | 1014-0000 | F&I ALUM TAG ON A LAMPPOST, AS PER DRAWING D-2861 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 27455 | 0 | 0 | 27455 | 0 | 27455 | 10370 | 0 | N | 27455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1015-0000-L | IPCRP1 | IPCRP1 | 1015-0000 | F&I COPPER WELD GRND ROD & CLAMP ... AS/ DWG H-50 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1015-0000-R | IPCRP1 | IPCRP1 | 1015-0000 | F&I COPPER WELD GRND ROD & CLAMP ... AS/ DWG H-50 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 17850 | 0 | 0 | 17850 | 0 | 17850 | 0 | 0 | N | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1016-0000-L | IPCRP1 | IPCRP1 | 1016-0000 | F, I, M, & REM EQUIP FOR TEMP LIGHT, AS/ DWG J-52 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1016-0000-R | IPCRP1 | IPCRP1 | 1016-0000 | F, I, M, & REM EQUIP FOR TEMP LIGHT, AS/ DWG J-52 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 187500 | 0 | 0 | 187500 | 0 | 187500 | 65000 | 0 | N | 187500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1017-0000-L | IPCRP1 | IPCRP1 | 1017-0000 | F&I AN IN-LINE FUSED CONNECTOR KIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1017-0000-R | IPCRP1 | IPCRP1 | 1017-0000 | F&I AN IN-LINE FUSED CONNECTOR KIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 9495 | 0 | 0 | 9495 | 0 | 9495 | 0 | 0 | N | 9495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1018-0000-L | IPCRP1 | IPCRP1 | 1018-0000 | F&I NO. 6 AWG XLP COPPER CABLE OR = IN CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1018-0000-R | IPCRP1 | IPCRP1 | 1018-0000 | F&I NO. 6 AWG XLP COPPER CABLE OR = IN CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 87815 | 0 | 0 | 87815 | 0 | 87815 | 29662.5 | 0 | N | 87815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1019-0000-L | IPCRP1 | IPCRP1 | 1019-0000 | F&I NO. 2 AWG XLP COPPER CABLE OR = IN CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1019-0000-R | IPCRP1 | IPCRP1 | 1019-0000 | F&I NO. 2 AWG XLP COPPER CABLE OR = IN CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 542100 | 0 | 0 | 542100 | 0 | 542100 | 181848 | 0 | N | 542100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1020-0000-L | IPCRP1 | IPCRP1 | 1020-0000 | F&I NO. 2/0 AWG XLP COPPER CABLE OR = IN CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1020-0000-R | IPCRP1 | IPCRP1 | 1020-0000 | F&I NO. 2/0 AWG XLP COPPER CABLE OR = IN CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 760 | 0 | 0 | 760 | 0 | 760 | 10260 | 0 | N | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1021-0000-L | IPCRP1 | IPCRP1 | 1021-0000 | F&I #6 BARE COPPER CONDUCTOR IN CONDUIT OR OH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1021-0000-R | IPCRP1 | IPCRP1 | 1021-0000 | F&I #6 BARE COPPER CONDUCTOR IN CONDUIT OR OH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 114170 | 0 | 0 | 114170 | 0 | 114170 | 36939 | 0 | N | 114170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1022-0000-L | IPCRP1 | IPCRP1 | 1022-0000 | F&I #2 BARE COPPER CONDUCTOR IN CONDUIT OR OH | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1022-0000-R | IPCRP1 | IPCRP1 | 1022-0000 | F&I #2 BARE COPPER CONDUCTOR IN CONDUIT OR OH | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 124200 | 0 | 0 | 124200 | 0 | 124200 | 3006 | 0 | N | 124200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1023-0000-L | IPCRP1 | IPCRP1 | 1023-0000 | F&I 1.5 HDG ST CONDUIT IN PAVED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1023-0000-R | IPCRP1 | IPCRP1 | 1023-0000 | F&I 1.5 HDG ST CONDUIT IN PAVED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 65600 | 0 | 0 | 65600 | 0 | 65600 | 0 | 0 | N | 65600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1024-0000-L | IPCRP1 | IPCRP1 | 1024-0000 | F&I 2 HDG ST CONDUIT IN PAVED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1024-0000-R | IPCRP1 | IPCRP1 | 1024-0000 | F&I 2 HDG ST CONDUIT IN PAVED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 13800 | 0 | 0 | 13800 | 0 | 13800 | 4508 | 0 | N | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1025-0000-L | IPCRP1 | IPCRP1 | 1025-0000 | F&I 3 HDG ST CONDUIT IN PAVED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1025-0000-R | IPCRP1 | IPCRP1 | 1025-0000 | F&I 3 HDG ST CONDUIT IN PAVED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 195500 | 0 | 0 | 195500 | 0 | 195500 | 6205 | 0 | N | 195500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1026-0000-L | IPCRP1 | IPCRP1 | 1026-0000 | F&I 1.5 HDG ST CONDUIT IN UNPAVED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1026-0000-R | IPCRP1 | IPCRP1 | 1026-0000 | F&I 1.5 HDG ST CONDUIT IN UNPAVED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7400 | 0 | 0 | 7400 | 0 | 7400 | 0 | 0 | N | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1027-0000-L | IPCRP1 | IPCRP1 | 1027-0000 | F&I 2 HDG ST CONDUIT IN UNPAVED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1027-0000-R | IPCRP1 | IPCRP1 | 1027-0000 | F&I 2 HDG ST CONDUIT IN UNPAVED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 102180 | 0 | 0 | 102180 | 0 | 102180 | 1950 | 0 | N | 102180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1028-0000-L | IPCRP1 | IPCRP1 | 1028-0000 | F&I 2 HDPE SCH 80 CONDUIT IN UNPAVED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1028-0000-R | IPCRP1 | IPCRP1 | 1028-0000 | F&I 2 HDPE SCH 80 CONDUIT IN UNPAVED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 33600 | 0 | 0 | 33600 | 0 | 33600 | 0 | 0 | N | 33600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1029-0000-L | IPCRP1 | IPCRP1 | 1029-0000 | F&I 3 HDG ST CONDUIT IN UNPAVED AREA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1029-0000-R | IPCRP1 | IPCRP1 | 1029-0000 | F&I 3 HDG ST CONDUIT IN UNPAVED AREA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 57720 | 0 | 0 | 57720 | 0 | 57720 | 11100 | 0 | N | 57720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1030-0000-L | IPCRP1 | IPCRP1 | 1030-0000 | F&I 1.5 HDG ST CONDUIT ON STRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1030-0000-R | IPCRP1 | IPCRP1 | 1030-0000 | F&I 1.5 HDG ST CONDUIT ON STRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18200 | 0 | 0 | 18200 | 0 | 18200 | 13677.3 | 0 | N | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1031-0000-L | IPCRP1 | IPCRP1 | 1031-0000 | F&I 2 HDG ST CONDUIT ON STRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1031-0000-R | IPCRP1 | IPCRP1 | 1031-0000 | F&I 2 HDG ST CONDUIT ON STRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 156800 | 0 | 0 | 156800 | 0 | 156800 | 161680 | 0 | N | 156800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1032-0000-L | IPCRP1 | IPCRP1 | 1032-0000 | REM COND(S) W/OR W/OUT CONDUCT & EQUIP ON STRUCT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1032-0000-R | IPCRP1 | IPCRP1 | 1032-0000 | REM COND(S) W/OR W/OUT CONDUCT & EQUIP ON STRUCT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 16250 | 0 | 0 | 16250 | 0 | 16250 | 9615 | 0 | N | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1033-0000-L | IPCRP1 | IPCRP1 | 1033-0000 | F&I CI BOX UP TO 5184 CI MAX MNTD ON STRUCTURE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1033-0000-R | IPCRP1 | IPCRP1 | 1033-0000 | F&I CI BOX UP TO 5184 CI MAX MNTD ON STRUCTURE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 73800 | 0 | 0 | 73800 | 0 | 73800 | 31980 | 0 | N | 73800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1034-0000-L | IPCRP1 | IPCRP1 | 1034-0000 | F&I TYPE 2418 ROADWAY CONC BOX W/CI F&C, DWG J-31 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1034-0000-R | IPCRP1 | IPCRP1 | 1034-0000 | F&I TYPE 2418 ROADWAY CONC BOX W/CI F&C, DWG J-31 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 468000 | 0 | 0 | 468000 | 0 | 468000 | 176400 | 0 | N | 468000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1035-0000-L | IPCRP1 | IPCRP1 | 1035-0000 | F&I TYPE 3624 ROADWAY CONC BOX W/CI F&C, DWG J-31 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1035-0000-R | IPCRP1 | IPCRP1 | 1035-0000 | F&I TYPE 3624 ROADWAY CONC BOX W/CI F&C, DWG J-31 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3600 | 0 | 0 | 3600 | 0 | 3600 | 10800 | 0 | N | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1036-0000-L | IPCRP1 | IPCRP1 | 1036-0000 | F&I TYPE 4824 ROADWAY CONC BOX W/CI F&C, DWG J-31 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1036-0000-R | IPCRP1 | IPCRP1 | 1036-0000 | F&I TYPE 4824 ROADWAY CONC BOX W/CI F&C, DWG J-31 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 133300 | 0 | 0 | 133300 | 0 | 133300 | 3200 | 0 | N | 133300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1037-0000-L | IPCRP1 | IPCRP1 | 1037-0000 | F&I FLUSH MNT OR PED MNT 6 RELAY CONTROL CABINET | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1037-0000-R | IPCRP1 | IPCRP1 | 1037-0000 | F&I FLUSH MNT OR PED MNT 6 RELAY CONTROL CABINET | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 48000 | 0 | 0 | 48000 | 0 | 48000 | 48000 | 0 | N | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1038-0000-L | IPCRP1 | IPCRP1 | 1038-0000 | REM TYPE M SERIES FOUNDATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1038-0000-R | IPCRP1 | IPCRP1 | 1038-0000 | REM TYPE M SERIES FOUNDATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | N | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1039-0000-L | IPCRP1 | IPCRP1 | 1039-0000 | INST TYPE M2-5S FOUNDATION | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1039-0000-R | IPCRP1 | IPCRP1 | 1039-0000 | INST TYPE M2-5S FOUNDATION | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | N | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1040-0000-L | IPCRP1 | IPCRP1 | 1040-0000 | REM TYPE M SERIES POST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1040-0000-R | IPCRP1 | IPCRP1 | 1040-0000 | REM TYPE M SERIES POST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1200 | 0 | 0 | 1200 | 0 | 1200 | 0 | 0 | N | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1041-0000-L | IPCRP1 | IPCRP1 | 1041-0000 | REM ANY OTHER TYPE POST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1041-0000-R | IPCRP1 | IPCRP1 | 1041-0000 | REM ANY OTHER TYPE POST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1600 | 0 | 0 | 1600 | 0 | 1600 | 800 | 0 | N | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1042-0000-L | IPCRP1 | IPCRP1 | 1042-0000 | INST TYPE M-2 POST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1042-0000-R | IPCRP1 | IPCRP1 | 1042-0000 | INST TYPE M-2 POST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1700 | 0 | 0 | 1700 | 0 | 1700 | 0 | 0 | N | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1043-0000-L | IPCRP1 | IPCRP1 | 1043-0000 | FURN 20ft SIGNAL MAST ARM POLE ASSEMBLY TYPE M-2 | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-1043-0000-R | IPCRP1 | IPCRP1 | 1043-0000 | FURN 20ft SIGNAL MAST ARM POLE ASSEMBLY TYPE M-2 | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4200 | 0 | 0 | 4200 | 0 | 4200 | 0 | 0 | N | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-1044-0000-L | IPCRP1 | IPCRP1 | 1044-0000 | A) FURN 5ft EXTEN ARM ASSEMBLY W/FITTINGS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1044-0000-R | IPCRP1 | IPCRP1 | 1044-0000 | A) FURN 5ft EXTEN ARM ASSEMBLY W/FITTINGS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2000 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | N | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1045-0000-L | IPCRP1 | IPCRP1 | 1045-0000 | C) FURN 1.25 ANCHOR BOLT ASSEMB FOR M-2, 4 REQD/ | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1045-0000-R | IPCRP1 | IPCRP1 | 1045-0000 | C) FURN 1.25 ANCHOR BOLT ASSEMB FOR M-2, 4 REQD/ | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 300 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | N | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1046-0000-L | IPCRP1 | IPCRP1 | 1046-0000 | INST 1-WAY SIGNAL UNIT ON MAST ARM OR TOP OF TRAF | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1046-0000-R | IPCRP1 | IPCRP1 | 1046-0000 | INST 1-WAY SIGNAL UNIT ON MAST ARM OR TOP OF TRAF | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 900 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | N | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1047-0000-L | IPCRP1 | IPCRP1 | 1047-0000 | REM SIGNAL HEAD FROM ANY TYPE POST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1047-0000-R | IPCRP1 | IPCRP1 | 1047-0000 | REM SIGNAL HEAD FROM ANY TYPE POST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 850 | 0 | 0 | 850 | 0 | 850 | 0 | 0 | N | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1048-0000-L | IPCRP1 | IPCRP1 | 1048-0000 | INST 1-WAY SIGNAL UNIT ON THE SHAFT OF ANY POST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1048-0000-R | IPCRP1 | IPCRP1 | 1048-0000 | INST 1-WAY SIGNAL UNIT ON THE SHAFT OF ANY POST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 425 | 0 | 0 | 425 | 0 | 425 | 0 | 0 | N | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1049-0000-L | IPCRP1 | IPCRP1 | 1049-0000 | REM PED SIGNAL, SIGN UNIT, ILLUM SIGN FROM ANY PO | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1049-0000-R | IPCRP1 | IPCRP1 | 1049-0000 | REM PED SIGNAL, SIGN UNIT, ILLUM SIGN FROM ANY PO | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2550 | 0 | 0 | 2550 | 0 | 2550 | 850 | 0 | N | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1050-0000-L | IPCRP1 | IPCRP1 | 1050-0000 | INST PED SIGNAL ON ANY TYPE POST | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1050-0000-R | IPCRP1 | IPCRP1 | 1050-0000 | INST PED SIGNAL ON ANY TYPE POST | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1275 | 0 | 0 | 1275 | 0 | 1275 | 850 | 0 | N | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1051-0000-L | IPCRP1 | IPCRP1 | 1051-0000 | FURN ADJ 3 SECT 1-WAY, DC AL TRAF SIGNAL, 8 W/LE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1051-0000-R | IPCRP1 | IPCRP1 | 1051-0000 | FURN ADJ 3 SECT 1-WAY, DC AL TRAF SIGNAL, 8 W/LE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1275 | 0 | 0 | 1275 | 0 | 1275 | 0 | 0 | N | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1052-0000-L | IPCRP1 | IPCRP1 | 1052-0000 | E) VB ASSEMBLY *ASSEMBLY IS = TO ONE PAIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1052-0000-R | IPCRP1 | IPCRP1 | 1052-0000 | E) VB ASSEMBLY *ASSEMBLY IS = TO ONE PAIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 75 | 0 | 0 | 75 | 0 | 75 | 0 | 0 | N | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1053-0000-L | IPCRP1 | IPCRP1 | 1053-0000 | FURN MAST ARM SIGNAL MNT ASSEMBLY - A) 1MS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-1053-0000-R | IPCRP1 | IPCRP1 | 1053-0000 | FURN MAST ARM SIGNAL MNT ASSEMBLY - A) 1MS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 150 | 0 | 0 | 150 | 0 | 150 | 0 | 0 | N | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-1054-0000-L | IPCRP1 | IPCRP1 | 1054-0000 | H) HUB ASSEMBLY *ASSEMBLY IS = TO ONE PAIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1054-0000-R | IPCRP1 | IPCRP1 | 1054-0000 | H) HUB ASSEMBLY *ASSEMBLY IS = TO ONE PAIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 90 | 0 | 0 | 90 | 0 | 90 | 0 | 0 | N | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1055-0000-L | IPCRP1 | IPCRP1 | 1055-0000 | B) 2MS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-1055-0000-R | IPCRP1 | IPCRP1 | 1055-0000 | B) 2MS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250 | 0 | 0 | 250 | 0 | 250 | 0 | 0 | N | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-1056-0000-L | IPCRP1 | IPCRP1 | 1056-0000 | G) VB-2P ASSEMBLY *ASSEMBLY IS = TO ONE PAIR | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1056-0000-R | IPCRP1 | IPCRP1 | 1056-0000 | G) VB-2P ASSEMBLY *ASSEMBLY IS = TO ONE PAIR | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 250 | 0 | 0 | 250 | 0 | 250 | 0 | 0 | N | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1057-0000-L | IPCRP1 | IPCRP1 | 1057-0000 | FURN POLYCARB PED SIGNAL (16 X 16) W/LED COUNT LE | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1057-0000-R | IPCRP1 | IPCRP1 | 1057-0000 | FURN POLYCARB PED SIGNAL (16 X 16) W/LED COUNT LE | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 850 | 0 | 0 | 850 | 0 | 850 | 0 | 0 | N | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1058-0000-L | IPCRP1 | IPCRP1 | 1058-0000 | INST ADV SS TRAFFIC SIGNAL CONTROL & CAB ON METAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1058-0000-R | IPCRP1 | IPCRP1 | 1058-0000 | INST ADV SS TRAFFIC SIGNAL CONTROL & CAB ON METAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2500 | 0 | 0 | 2500 | 0 | 2500 | 2500 | 0 | N | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1059-0000-L | IPCRP1 | IPCRP1 | 1059-0000 | REM 1 CONTROL BOX & CONTROL FROM ANY POST/SUPPORT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1059-0000-R | IPCRP1 | IPCRP1 | 1059-0000 | REM 1 CONTROL BOX & CONTROL FROM ANY POST/SUPPORT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2000 | 0 | 0 | 2000 | 0 | 2000 | 2000 | 0 | N | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1060-0000-L | IPCRP1 | IPCRP1 | 1060-0000 | F&I 3 RIGID UG CONDUIT IN UNPAVED ROADWAY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1060-0000-R | IPCRP1 | IPCRP1 | 1060-0000 | F&I 3 RIGID UG CONDUIT IN UNPAVED ROADWAY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4000 | 0 | 0 | 4000 | 0 | 4000 | 0 | 0 | N | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1061-0000-L | IPCRP1 | IPCRP1 | 1061-0000 | F&I ADDITIONAL 2 HDPE CONDUIT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1061-0000-R | IPCRP1 | IPCRP1 | 1061-0000 | F&I ADDITIONAL 2 HDPE CONDUIT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 500 | 0 | N | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1062-0000-L | IPCRP1 | IPCRP1 | 1062-0000 | F&I 2 HDPE UG CONDUIT IN PAVED ROADWAY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1062-0000-R | IPCRP1 | IPCRP1 | 1062-0000 | F&I 2 HDPE UG CONDUIT IN PAVED ROADWAY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6750 | 0 | 0 | 6750 | 0 | 6750 | 0 | 0 | N | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1063-0000-L | IPCRP1 | IPCRP1 | 1063-0000 | PERM RESTORATION OF PAVED ROADWAY | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1063-0000-R | IPCRP1 | IPCRP1 | 1063-0000 | PERM RESTORATION OF PAVED ROADWAY | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 19500 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | N | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1064-0000-L | IPCRP1 | IPCRP1 | 1064-0000 | INST CABLE (INCLUDES OH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1064-0000-R | IPCRP1 | IPCRP1 | 1064-0000 | INST CABLE (INCLUDES OH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 2600 | 0 | N | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1065-0000-L | IPCRP1 | IPCRP1 | 1065-0000 | REM CABLE (INCLUDES OH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1065-0000-R | IPCRP1 | IPCRP1 | 1065-0000 | REM CABLE (INCLUDES OH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2500 | 0 | 0 | 2500 | 0 | 2500 | 1000 | 0 | N | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1066-0000-L | IPCRP1 | IPCRP1 | 1066-0000 | INST MULTIPLE CABLE (INCLUDES OH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1066-0000-R | IPCRP1 | IPCRP1 | 1066-0000 | INST MULTIPLE CABLE (INCLUDES OH) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3500 | 0 | 0 | 3500 | 0 | 3500 | 980 | 0 | N | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1067-0000-L | IPCRP1 | IPCRP1 | 1067-0000 | FURN 2 C # 10B (BD = 2#10 W/3RD WIRE FOR GRND) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1067-0000-R | IPCRP1 | IPCRP1 | 1067-0000 | FURN 2 C # 10B (BD = 2#10 W/3RD WIRE FOR GRND) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 800 | 0 | 0 | 800 | 0 | 800 | 2740 | 0 | N | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1068-0000-L | IPCRP1 | IPCRP1 | 1068-0000 | C) 7 CONDUCTOR, 14 AWG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1068-0000-R | IPCRP1 | IPCRP1 | 1068-0000 | C) 7 CONDUCTOR, 14 AWG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 600 | 0 | 0 | 600 | 0 | 600 | 160 | 0 | N | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1069-0000-L | IPCRP1 | IPCRP1 | 1069-0000 | E) 13 CONDUCTOR, 14 AWG | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1069-0000-R | IPCRP1 | IPCRP1 | 1069-0000 | E) 13 CONDUCTOR, 14 AWG | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 900 | 0 | N | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1070-0000-L | IPCRP1 | IPCRP1 | 1070-0000 | INSTALL CONC PYLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1070-0000-R | IPCRP1 | IPCRP1 | 1070-0000 | INSTALL CONC PYLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 2600 | 0 | 0 | 2600 | 0 | 2600 | 13000 | 0 | N | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1071-0000-L | IPCRP1 | IPCRP1 | 1071-0000 | REM CONC PYLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1071-0000-R | IPCRP1 | IPCRP1 | 1071-0000 | REM CONC PYLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1600 | 0 | 0 | 1600 | 0 | 1600 | 0 | 0 | N | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1072-0000-L | IPCRP1 | IPCRP1 | 1072-0000 | FURN CONC PYLON | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1072-0000-R | IPCRP1 | IPCRP1 | 1072-0000 | FURN CONC PYLON | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 2250 | 0 | N | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1072-1000-L | IPCRP1 | IPCRP1 | 1072-1000 | Electric Subcontractor (EJ Electric) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.43 | 0.57 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-1072-1000-S | IPCRP1 | IPCRP1 | 1072-1000 | Electric Subcontractor (EJ Electric) | N | S |  | NR | A | 11480112 | 12544555.87 | 12544555.87 | 5379668.85 | 12544555.87 | 43.3036 | 0 | 0 | 0 | -121415.8 | Y | 12423140.07 | Y | -943028.07 | 0 | 0 | 11480112 | 0 | 0 | 12423140.07 | Y | -943028.07 | 0 | 0 | 11480112 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12423140.07 | 75728.89 | 0 | 12423140.07 | 0 | 0 | 0 | 0 | 0 | 0 | -12423140.07 | 0 | 0 | 12423140.07 | 12423140.07 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4231356.87 | 5768643.13 | 10000000 | NA | 1 | 0.43 | 0.57 | 1 | LS | 12544555.87 | 7164887.02 | 5379668.85 | -121415.8 | EJ Electric Base Contract @$10,991,745.00. April'22 CO@$32,439.96
Y | IPCRP1-1073-0000-L | IPCRP1 | IPCRP1 | 1073-0000 | GAS MAIN CROSS SEWER 36 THRU 42 D | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1073-0000-R | IPCRP1 | IPCRP1 | 1073-0000 | GAS MAIN CROSS SEWER 36 THRU 42 D | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | N | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1074-0000-L | IPCRP1 | IPCRP1 | 1074-0000 | EXTRA EXC FOR INST OF CB SEWER DR PIPE W/ GAS INT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1074-0000-R | IPCRP1 | IPCRP1 | 1074-0000 | EXTRA EXC FOR INST OF CB SEWER DR PIPE W/ GAS INT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1600 | 0 | 0 | 1600 | 0 | 1600 | 0 | 0 | N | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1074-1000-E | IPCRP1 | IPCRP1 | 1074-1000 | Gas Main X-ing and Extra Excav w/ Gas Interferenc | N | E |  | NR | P | 951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 951 | 0 | 0 | 951 | 0 | 0 | 0 | Y | 951 | 0 | 0 | 951 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 4 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1074-1000-L | IPCRP1 | IPCRP1 | 1074-1000 | Gas Main X-ing and Extra Excav w/ Gas Interferenc | N | L |  | NR | P | 3479 | 19057.29 | 19057.29 | 19057.29 | 19057.29 | 62.1403 | 0 | 0 | 0 | 11610.9 | Y | 30668.19 | Y | -27189.19 | 0 | 0 | 3479 | 0 | 0 | 30668.19 | Y | -27189.19 | 0 | 0 | 3479 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30668.19 | 0 | 0 | 30668.19 | 0 | 0 | 0 | 0 | 0 | 0 | -30668.19 | 0 | 0 | 30668.19 | 30668.19 | 0 | 0 | 0 | 28 | 0 | 232.8 | 232.8 | 28 | 145.5 | 87.3 | 232.8 | HR | 4 | 2 | 2 | 4 | EA | 0 | 0 | 0 | 11610.9
Y | IPCRP1-1074-1000-S | IPCRP1 | IPCRP1 | 1074-1000 | Gas Main X-ing and Extra Excav w/ Gas Interferenc | N | S |  | UNIT | A | 0 | 682.93 | 682.93 | 682.93 | 682.93 | 100 | 0 | 0 | 0 | 0 | N | 682.93 | N | -682.93 | 0 | 0 | 0 | 0 | 0 | 682.93 | N | -682.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -682.93 | 0 | 0 | 682.93 | 0 | 0 | 0 | 0 | 0 | 0 | -682.93 | 0 | 0 | 682.93 | 682.93 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 4 | 2 | 2 | 4 | EA | 682.93 | 0 | 682.93 | 0
Y | IPCRP1-1075-0000-L | IPCRP1 | IPCRP1 | 1075-0000 | REM OF ABAND GAS FACIL ALL SIZES | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1075-0000-R | IPCRP1 | IPCRP1 | 1075-0000 | REM OF ABAND GAS FACIL ALL SIZES | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 21750 | 0 | 0 | 21750 | 0 | 21750 | 1475 | 0 | N | 21750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1076-0000-L | IPCRP1 | IPCRP1 | 1076-0000 | REM OF ABAND GAS FACIL W/POSS COAL TAR WRAP (CE O | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1076-0000-R | IPCRP1 | IPCRP1 | 1076-0000 | REM OF ABAND GAS FACIL W/POSS COAL TAR WRAP (CE O | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3750 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | N | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1076-1000-E | IPCRP1 | IPCRP1 | 1076-1000 | Rem Aband Gas Facilities for CE | N | E |  | NR | P | 3062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3062 | 0 | 0 | 3062 | 0 | 0 | 0 | Y | 3062 | 0 | 0 | 3062 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 150 | 59 | 91 | 150 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-1076-1000-L | IPCRP1 | IPCRP1 | 1076-1000 | Rem Aband Gas Facilities for CE | N | L |  | NR | P | 9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9875 | N | 9875 | N | 0 | 0 | 0 | 9875 | 0 | 0 | 9875 | N | 0 | 0 | 0 | 9875 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9875 | 0 | 0 | 9875 | 0 | 0 | 0 | 0 | 0 | 0 | -9875 | 0 | 0 | 9875 | 9875 | 0 | 0 | 0 | 80 | 0 | 80 | 80 | 80 | 0 | 80 | 80 | HR | 150 | 59 | 91 | 150 | LF | 0 | 0 | 0 | 9875
Y | IPCRP1-1077-0000-L | IPCRP1 | IPCRP1 | 1077-0000 | ADJUST HW TO GRADE, SPACE RINGS/ ADAPT (STRT REPA | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1077-0000-R | IPCRP1 | IPCRP1 | 1077-0000 | ADJUST HW TO GRADE, SPACE RINGS/ ADAPT (STRT REPA | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 750 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | N | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1078-0000-L | IPCRP1 | IPCRP1 | 1078-0000 | ADJUST HW TO GRADE BY RESET, ROAD RECONST (S6.05) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1078-0000-R | IPCRP1 | IPCRP1 | 1078-0000 | ADJUST HW TO GRADE BY RESET, ROAD RECONST (S6.05) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1500 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | N | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1078-1000-C | IPCRP1 | IPCRP1 | 1078-1000 | Adjust Hardware to Grade for CE | N | C |  | NR | P | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | N | 420 | N | 0 | 0 | 0 | 420 | 0 | 0 | 420 | N | 0 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -420 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | -420 | 0 | 0 | 420 | 420 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 20 | 0 | 20 | 20 | EA | 0 | 0 | 0 | 420
Y | IPCRP1-1078-1000-L | IPCRP1 | IPCRP1 | 1078-1000 | Adjust Hardware to Grade for CE | N | L |  | NR | P | 1580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1580 | N | 1580 | N | 0 | 0 | 0 | 1580 | 0 | 0 | 1580 | N | 0 | 0 | 0 | 1580 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1580 | 0 | 0 | 1580 | 0 | 0 | 0 | 0 | 0 | 0 | -1580 | 0 | 0 | 1580 | 1580 | 0 | 0 | 0 | 15 | 0 | 15 | 15 | 15 | 0 | 15 | 15 | HR | 20 | 0 | 20 | 20 | EA | 0 | 0 | 0 | 1580
Y | IPCRP1-1079-0000-L | IPCRP1 | IPCRP1 | 1079-0000 | SPECIAL CARE EXCAV & BACKFILL (S6.06) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1079-0000-R | IPCRP1 | IPCRP1 | 1079-0000 | SPECIAL CARE EXCAV & BACKFILL (S6.06) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 41400 | 0 | 0 | 41400 | 0 | 41400 | 8596.8 | 0 | N | 41400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1079-1000-E | IPCRP1 | IPCRP1 | 1079-1000 | SPECIAL CARE EXCAV & BACKFILL (S6.06) | N | E |  | NR | P | 6123.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6123.6 | 0 | 0 | 6123.6 | 0 | 0 | 0 | Y | 6123.6 | 0 | 0 | 6123.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 230 | 47.76 | 182.24 | 230 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1079-1000-L | IPCRP1 | IPCRP1 | 1079-1000 | SPECIAL CARE EXCAV & BACKFILL (S6.06) | N | L |  | NR | P | 19749.79 | 8624.39 | 8624.39 | 8624.39 | 8624.39 | 43.6683 | 0 | 0 | 0 | 11125.4 | N | 19749.79 | N | 0 | 0 | 0 | 19749.79 | 0 | 0 | 19749.79 | N | 0 | 0 | 0 | 19749.79 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19749.79 | 0 | 0 | 19749.79 | 0 | 0 | 0 | 0 | 0 | 0 | -19749.79 | 0 | 0 | 19749.79 | 19749.79 | 0 | 0 | 0 | 160 | 0 | 160 | 160 | 160 | 63 | 97 | 160 | HR | 230 | 47.76 | 182.24 | 230 | CY | 0 | 0 | 0 | 11125.4
Y | IPCRP1-1079-1000-S | IPCRP1 | IPCRP1 | 1079-1000 | SPECIAL CARE EXCAV & BACKFILL (S6.06) | N | S |  | UNIT | A | 0 | 694.51 | 694.51 | 694.51 | 694.51 | 100 | 0 | 0 | 0 | 0 | N | 694.51 | N | -694.51 | 0 | 0 | 0 | 0 | 0 | 694.51 | N | -694.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -694.51 | 0 | 0 | 694.51 | 0 | 0 | 0 | 0 | 0 | 0 | -694.51 | 0 | 0 | 694.51 | 694.51 | 0 | 0 | 0 | 0 | 0 | 5.5 | 5.5 | 0 | 5.5 | 0 | 5.5 | NA | 230 | 47.76 | 182.24 | 230 | CY | 694.51 | 0 | 694.51 | 0
Y | IPCRP1-1080-0000-L | IPCRP1 | IPCRP1 | 1080-0000 | TEST PITS FOR GAS FACIL (S6.07) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1080-0000-R | IPCRP1 | IPCRP1 | 1080-0000 | TEST PITS FOR GAS FACIL (S6.07) | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 25000 | 0 | 0 | 25000 | 0 | 25000 | 1627.5 | 0 | N | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1080-1000-E | IPCRP1 | IPCRP1 | 1080-1000 | Test Pits for Gas Facilities (S6.07) | N | E |  | NR | P | 1560.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1560.52 | 0 | 0 | 1560.52 | 0 | 0 | 0 | Y | 1560.52 | 0 | 0 | 1560.52 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 100 | 6.51 | 93.49 | 100 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1080-1000-L | IPCRP1 | IPCRP1 | 1080-1000 | Test Pits for Gas Facilities (S6.07) | N | L |  | NR | P | 9294.88 | 9906.36 | 9906.36 | 9906.36 | 9906.36 | 65.7138 | 0 | 0 | 0 | 5168.64 | Y | 15075 | Y | -5780.12 | 0 | 0 | 9294.88 | 0 | 0 | 15075 | Y | -5780.12 | 0 | 0 | 9294.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15075 | 0 | 0 | 15075 | 0 | 0 | 0 | 0 | 0 | 0 | -15075 | 0 | 0 | 15075 | 15075 | 0 | 0 | 0 | 80 | 0 | 140 | 140 | 80 | 92 | 48 | 140 | HR | 100 | 6.51 | 93.49 | 100 | CY | 0 | 0 | 0 | 5168.64
Y | IPCRP1-1081-0000-L | IPCRP1 | IPCRP1 | 1081-0000 | PIER &/OR PLATE METH, PROTECT DI WM, <24 COVER | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1081-0000-R | IPCRP1 | IPCRP1 | 1081-0000 | PIER &/OR PLATE METH, PROTECT DI WM, <24 COVER | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 17000 | 0 | 0 | 17000 | 0 | 17000 | 0 | 0 | N | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1081-1000-C | IPCRP1 | IPCRP1 | 1081-1000 | PIER &/OR PLATE METH, PROTECT DI WM, <24 COVER | N | C |  | NR | P | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | N | 77 | N | 0 | 0 | 0 | 77 | 0 | 0 | 77 | N | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -77 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | -77 | 0 | 0 | 77 | 77 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 77
Y | IPCRP1-1081-1000-E | IPCRP1 | IPCRP1 | 1081-1000 | PIER &/OR PLATE METH, PROTECT DI WM, <24 COVER | N | E |  | NR | P | 1561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1561 | 0 | 0 | 1561 | 0 | 0 | 0 | Y | 1561 | 0 | 0 | 1561 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-1081-1000-L | IPCRP1 | IPCRP1 | 1081-1000 | PIER &/OR PLATE METH, PROTECT DI WM, <24 COVER | N | L |  | NR | P | 9295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9295 | N | 9295 | N | 0 | 0 | 0 | 9295 | 0 | 0 | 9295 | N | 0 | 0 | 0 | 9295 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9295 | 0 | 0 | 9295 | 0 | 0 | 0 | 0 | 0 | 0 | -9295 | 0 | 0 | 9295 | 9295 | 0 | 0 | 0 | 80 | 0 | 80 | 80 | 80 | 0 | 80 | 80 | HR | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 9295
Y | IPCRP1-1081-1000-M | IPCRP1 | IPCRP1 | 1081-1000 | PIER &/OR PLATE METH, PROTECT DI WM, <24 COVER | N | M |  | NR | P | 2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168 | N | 2168 | N | 0 | 0 | 0 | 2168 | 0 | 0 | 2168 | N | 0 | 0 | 0 | 2168 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2168 | 0 | 0 | 2168 | 0 | 0 | 0 | 0 | 0 | 0 | -2168 | 0 | 0 | 2168 | 2168 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 2168
Y | IPCRP1-1082-0000-L | IPCRP1 | IPCRP1 | 1082-0000 | TREN EX & BACKFILL FOR GAS MAINS (MAIN INST BY OT | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1082-0000-R | IPCRP1 | IPCRP1 | 1082-0000 | TREN EX & BACKFILL FOR GAS MAINS (MAIN INST BY OT | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 271600 | 0 | 0 | 271600 | 0 | 271600 | 164507 | 0 | N | 271600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1082-1000-C | IPCRP1 | IPCRP1 | 1082-1000 | TREN EX & BACKFILL FOR GAS MAINS (MAIN INST BY OT | N | C |  | UNIT | U | 0 | 7055.1 | 7055.1 | 7055.1 | 7055.1 | 27.3984 | 0 | 0 | 0 | 18694.91 | Y | 25750.01 | Y | -25750.01 | 0 | 0 | 0 | 0 | 0 | 25750.01 | Y | -25750.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25750.01 | 0 | 0 | 25750.01 | 0 | 0 | 0 | 0 | 0 | 0 | -25750.01 | 0 | 0 | 25750.01 | 25750.01 | 0 | 0 | 0 | 0 | 0 | 360 | 360 | 0 | 2011 | -1651 | 360 | NA | 776 | 470.02 | 305.98 | 776 | CY | 0 | -7055.1 | 7055.1 | 18694.91
Y | IPCRP1-1082-1000-E | IPCRP1 | IPCRP1 | 1082-1000 | TREN EX & BACKFILL FOR GAS MAINS (MAIN INST BY OT | N | E |  | NR | P | 23060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 23060 | 0 | 0 | 23060 | 0 | 0 | 0 | Y | 23060 | 0 | 0 | 23060 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 776 | 470.02 | 305.98 | 776 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-1082-1000-L | IPCRP1 | IPCRP1 | 1082-1000 | TREN EX & BACKFILL FOR GAS MAINS (MAIN INST BY OT | N | L |  | NR | P | 117829 | 96769.68 | 96769.68 | 96769.68 | 96769.68 | 82.1272 | 0 | 0 | 0 | 21059.32 | N | 117829 | N | 0 | 0 | 0 | 117829 | 0 | 0 | 117829 | N | 0 | 0 | 0 | 117829 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -117829 | 0 | 0 | 117829 | 0 | 0 | 0 | 0 | 0 | 0 | -117829 | 0 | 0 | 117829 | 117829 | 0 | 0 | 0 | 1152 | 0 | 1152 | 1152 | 1152 | 863.5 | 288.5 | 1152 | HR | 776 | 470.02 | 305.98 | 776 | CY | 0 | 0 | 0 | 21059.32
Y | IPCRP1-1083-0000-L | IPCRP1 | IPCRP1 | 1083-0000 | ALLOW - GAS INTERFERENCES & ACCOMMODATIONS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-1083-0000-R | IPCRP1 | IPCRP1 | 1083-0000 | ALLOW - GAS INTERFERENCES & ACCOMMODATIONS | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 100000 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | N | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-1083-1000-C | IPCRP1 | IPCRP1 | 1083-1000 | ALLOW - GAS INTERFERENCES & ACCOMMODATIONS | N | C |  | NR | P | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | N | 100000 | N | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | N | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 100000
Y | IPCRP1-1083-1000-L | IPCRP1 | IPCRP1 | 1083-1000 | ALLOW - GAS INTERFERENCES & ACCOMMODATIONS | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | FP | 0 | 0 | 0 | 0
Y | IPCRP1-1084-0000-L | IPCRP1 | IPCRP1 | 1084-0000 | MOBILIZATION NTE 8% OF THE ABOVE SUB-TOTAL | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-1084-0000-R | IPCRP1 | IPCRP1 | 1084-0000 | MOBILIZATION NTE 8% OF THE ABOVE SUB-TOTAL | N | R |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 94000000 | 0 | 0 | 94000000 | 0 | 94000000 | 94000000 | 0 | N | 94000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-1112-0000-R | IPCRP1 | IPCRP1 | 1112-0000 | ESCR-8.01C1 OR #2 Hand, Trans, & Disp of Non Haz C | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-1121-0000-R | IPCRP1 | IPCRP1 | 1121-0000 | 70.13 MN OR #3 Mini-Piles (Grouted) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-1122-0000-R | IPCRP1 | IPCRP1 | 1122-0000 | 70.13 MN OR #3 Mini-Piles (Grouted) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-1123-0000-R | IPCRP1 | IPCRP1 | 1123-0000 | 70.13 MN Mini-Piles (Grouted) OR No. 3 <125% | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-1124-0000-R | IPCRP1 | IPCRP1 | 1124-0000 | 70.13 MN Mini-Piles (Grouted) OR No. 3 >125% | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-1125-0000-R | IPCRP1 | IPCRP1 | 1125-0000 | OR#4 Item 565.1924, 565.1925, PK-227B ADA, PK-ESCR | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-1126-0000-R | IPCRP1 | IPCRP1 | 1126-0000 | ESCR-8.01C1 OR #5 Hand, Trans, & Disp of Non Haz C | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-1127-0000-R | IPCRP1 | IPCRP1 | 1127-0000 | ESCR-8.01C1 OR #8 Hand, Trans, & Disp of Non Haz C | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1000-E | IPCRP1 | IPCRP1 | 2000-1000 | Rebar Summary (All) | N | E |  | NR | P | 39813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 39813 | 0 | 0 | 39813 | 0 | 0 | 0 | Y | 39813 | 0 | 0 | 39813 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 8759374 | 5374187.83 | 2650751.17 | 8024939 | LB | 0 | 0 | 0 | 0 | 1. VS (Feb 24) used contract historical data to project out Rebar Support costs from $0.005/lb to $0.10/lb). 2. SUBS: Rodbusters $5,360,767.85, Metro Rebar $6,964,436.95, Posillico Civil SC = $510,000.00, KMA SC = $44,659.72. Total = $12,879,864.52. 3. MAT: CFS Steel $4,639,133.28, plus 6 others $213,779.31. Total = $4,852,912.59
Y | IPCRP1-2000-1000-L | IPCRP1 | IPCRP1 | 2000-1000 | Rebar Summary (All) | N | L |  | NR | P | 42655 | 931349.1 | 931349.1 | 931349.1 | 931349.1 | 68.0828 | 0 | 0 | 0 | 436615.27 | Y | 1367964.37 | Y | -1325309.37 | 0 | 0 | 42655 | 0 | 0 | 1367964.37 | Y | -1325309.37 | 0 | 0 | 42655 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1367964.37 | 53020.15 | 46184.09 | 1367964.37 | 0 | 0 | 0 | 0 | 0 | 0 | -1367964.37 | 0 | 0 | 1367964.37 | 1367964.37 | 0 | 0 | 0 | 318.5 | 0 | 10857.35 | 10857.35 | 318.5 | 7361 | 3496.35 | 10857.35 | HR | 8759374 | 5374187.83 | 2650751.17 | 8024939 | LB | 0 | 0 | 0 | 436615.27 | 1. VS (Feb 24) used contract historical data to project out Rebar Support costs from $0.005/lb to $0.10/lb). 2. SUBS: Rodbusters $5,360,767.85, Metro Rebar $6,964,436.95, Posillico Civil SC = $510,000.00, KMA SC = $44,659.72. Total = $12,879,864.52. 3. MAT: CFS Steel $4,639,133.28, plus 6 others $213,779.31. Total = $4,852,912.59
Y | IPCRP1-2000-1000-M | IPCRP1 | IPCRP1 | 2000-1000 | Rebar Summary (All) | N | M |  | NR | P | 2505137 | 5393752.02 | 5393752.02 | 2739981.55 | 5393752.02 | 52.4426 | 0 | 0 | 0 | -169031.82 | Y | 5224720.2 | Y | -2719583.2 | 0 | 0 | 2505137 | 0 | 0 | 5224720.2 | Y | -2719583.2 | 0 | 0 | 2505137 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5224720.2 | 336487.74 | 228814.88 | 5224720.2 | 0 | 0 | 0 | 67266.67 | 33952.44 | 0 | -5224720.2 | 0 | 0 | 5224720.2 | 5224720.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3274459.11 | -1086381.26 | 2188077.85 | NA | 8759374 | 5374187.83 | 2650751.17 | 8024939 | LB | 5423084.32 | 2653770.47 | 2769313.85 | -169031.82 | New Note - Install quantity thru Jan 2025: Rodbusters (2,664,800), Posillico (614,644), Metro (526,804) = 3,806,248 lbs total. Refer to VS email to VT on 1/20/24. CFS Steel PO@$4,028.38 New Note - Install quantity thru Dec 2024: Rodbusters (2,664,800), Posillico (614,644), Metro (363,676) = 3,643,000 lbs total. Refer o VS email to VT on 1/20/24.
Y | IPCRP1-2000-1000-S | IPCRP1 | IPCRP1 | 2000-1000 | Rebar Summary (All) | N | S |  | NR | A | 12962283.6 | 13186351.79 | 13186351.79 | 8204759.66 | 13186351.79 | 62.2875 | 0 | 0 | 0 | -13944.84 | Y | 13172406.95 | Y | -210123.35 | 0 | 0 | 12962283.6 | 0 | 0 | 13172406.95 | Y | -210123.35 | 0 | 0 | 12962283.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13172406.95 | 5940.19 | 2883.18 | 13172406.95 | 0 | 0 | 0 | 0 | 5940.19 | 0 | -13172406.95 | 0 | 0 | 13172406.95 | 13172406.95 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 11316264.8 | -11316263.8 | 1 | NA | 8759374 | 5374187.83 | 2650751.17 | 8024939 | LB | 13186351.79 | 4981592.13 | 8204759.66 | -13944.84
Y | IPCRP1-2000-1002-L | IPCRP1 | IPCRP1 | 2000-1002 | Rebar Costs Above Rodbusters Earned CV | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1002-S | IPCRP1 | IPCRP1 | 2000-1002 | Rebar Costs Above Rodbusters Earned CV | N | S |  | UNIT | A | 0 | 196567.9 | 196567.9 | 196567.9 | 196567.9 | 100 | 0 | 0 | 0 | 0 | N | 196567.9 | N | -196567.9 | 0 | 0 | 0 | 0 | 0 | 196567.9 | N | -196567.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -196567.9 | 0 | 0 | 196567.9 | 0 | 0 | 0 | 0 | 0 | 0 | -196567.9 | 0 | 0 | 196567.9 | 196567.9 | 0 | 0 | 0 | 0 | 0 | 2.04 | 2.04 | 0 | 2 | 0.04 | 2.04 | NA | 0 | 1 | 0 | 1 | LS | 196567.9 | 0 | 196567.9 | 0
Y | IPCRP1-2000-1010-L | IPCRP1 | IPCRP1 | 2000-1010 | Mesh Summary | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 22028 | 0 | 160000 | 160000 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1010-M | IPCRP1 | IPCRP1 | 2000-1010 | Mesh Summary | N | M |  | NR | P | 1800 | 38546.11 | 38546.11 | 26786.95 | 38546.11 | 20.9273 | 0 | 0 | 0 | 89453.89 | Y | 128000 | Y | -126200 | 0 | 0 | 1800 | 0 | 0 | 128000 | Y | -126200 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -128000 | 0 | 0 | 128000 | 0 | 0 | 0 | 13897.59 | 0 | 0 | -128000 | 0 | 0 | 128000 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 424 | -424 | 0 | NA | 22028 | 0 | 160000 | 160000 | SF | 38546.11 | 11759.16 | 26786.95 | 89453.89 | Furnish mesh not included in Rodbusters subcontract due to crazy market pricing @ time of writing subcontract (VS, 2/17/2022)
Y | IPCRP1-2000-1010-S | IPCRP1 | IPCRP1 | 2000-1010 | Mesh Summary | N | S |  | NR | A | 44236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 44236 | 0 | 0 | 44236 | 0 | 0 | 0 | Y | 44236 | 0 | 0 | 44236 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 22028 | 0 | 160000 | 160000 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1020-C | IPCRP1 | IPCRP1 | 2000-1020 | Concrete Summary | N | C |  | UNIT | U | 0 | 710879.11 | 710879.11 | 592809.42 | 710879.11 | 86.8676 | 0 | 0 | 0 | -28450.61 | Y | 682428.5 | Y | -682428.5 | 0 | 0 | 0 | 0 | 0 | 682428.5 | Y | -682428.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -682428.5 | 26624.51 | 22158.24 | 682428.5 | 0 | 0 | 0 | 6924.45 | 4154.67 | 0 | -682428.5 | 0 | 0 | 682428.5 | 682428.5 | 0 | 0 | 0 | 0 | 0 | 463.46 | 463.46 | 0 | 550.91 | -87.45 | 463.46 | NA | 59694 | 35478.5 | 17437.5 | 52916 | CY | 710879.11 | 118069.69 | 592809.42 | -28450.61
Y | IPCRP1-2000-1020-L | IPCRP1 | IPCRP1 | 2000-1020 | Concrete Summary | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 59694 | 35478.5 | 17437.5 | 52916 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1020-M | IPCRP1 | IPCRP1 | 2000-1020 | Concrete Summary | N | M |  | NR | P | 10544517.5 | 9184719.84 | 9184719.84 | 6248549.2 | 9184719.84 | 66.0867 | 0 | 0 | 0 | 270362.53 | Y | 9455082.37 | Y | 1089435.13 | 0 | 0 | 10544517.5 | 0 | 0 | 9455082.37 | Y | 1089435.13 | 0 | 0 | 10544517.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9455082.37 | 97309.76 | 163495.91 | 9455082.37 | 0 | 0 | 0 | 0 | 0 | 0 | -9455082.37 | 0 | 0 | 9455082.37 | 9455082.37 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 223062.3 | -177523.19 | 45539.11 | NA | 59694 | 35478.5 | 17437.5 | 52916 | CY | 9184719.84 | 2936170.64 | 6248549.2 | 270362.53 | US CONCRETE INC Base PO@$10,338,282.37
Y | IPCRP1-2000-1020-S | IPCRP1 | IPCRP1 | 2000-1020 | Concrete Summary | N | S |  | UNIT | A | 0 | 193.65 | 193.65 | 193.65 | 193.65 | 100 | 0 | 0 | 0 | 0 | N | 193.65 | N | -193.65 | 0 | 0 | 0 | 0 | 0 | 193.65 | N | -193.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -193.65 | 0 | 0 | 193.65 | 0 | 0 | 0 | 0 | 0 | 0 | -193.65 | 0 | 0 | 193.65 | 193.65 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 1.5 | 0 | 1.5 | NA | 59694 | 35478.5 | 17437.5 | 52916 | CY | 193.65 | 0 | 193.65 | 0
Y | IPCRP1-2000-1022-C | IPCRP1 | IPCRP1 | 2000-1022 | Spoils Control for JG Work - Other than Houston St | N | C |  | UNIT | U | 0 | 10124.51 | 10124.51 | 9299.21 | 10124.51 | 3.0997 | 0 | 0 | 0 | 289875.49 | Y | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | -300000 | 0 | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235.56 | -235.56 | 0 | NA | 0 | 7042.3 | 7269 | 14311.3 | CY | 10124.51 | 825.3 | 9299.21 | 289875.49
Y | IPCRP1-2000-1022-E | IPCRP1 | IPCRP1 | 2000-1022 | Spoils Control for JG Work - Other than Houston St | N | E |  | UNIT | A | 0 | 27130.05 | 27130.05 | 24918.52 | 27130.05 | 91.8484 | 0 | 0 | 0 | 0 | Y | 27130.05 | Y | -27130.05 | 0 | 0 | 0 | 0 | 0 | 27130.05 | Y | -27130.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27130.05 | 0 | 0 | 27130.05 | 0 | 0 | 0 | 0 | 0 | 0 | -27130.05 | 0 | 0 | 27130.05 | 27130.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.82 | -365.82 | 0 | NA | 0 | 7042.3 | 7269 | 14311.3 | CY | 27130.05 | 2211.53 | 24918.52 | 0
Y | IPCRP1-2000-1022-L | IPCRP1 | IPCRP1 | 2000-1022 | Spoils Control for JG Work - Other than Houston St | N | L |  | UNIT | P | 0 | 539796.02 | 539796.02 | 539796.02 | 539796.02 | 23.9105 | 0 | 0 | 0 | 1717772.26 | Y | 2257568.28 | Y | -2257568.28 | 0 | 0 | 0 | 0 | 0 | 2257568.28 | Y | -2257568.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2257568.28 | 0 | 0 | 2257568.28 | 0 | 0 | 0 | 0 | 0 | 0 | -2257568.28 | 0 | 0 | 2257568.28 | 2257568.28 | 0 | 0 | 0 | 0 | 0 | 17184.5 | 17184.5 | 0 | 4021.5 | 13163 | 17184.5 | HR | 0 | 7042.3 | 7269 | 14311.3 | CY | 0 | 0 | 0 | 1717772.26
Y | IPCRP1-2000-1022-S | IPCRP1 | IPCRP1 | 2000-1022 | Spoils Control for JG Work - Other than Houston St | N | S |  | UNIT | A | 0 | 1083739.01 | 1083739.01 | 779167.01 | 1083739.01 | 38.9584 | 0 | 0 | 0 | 916260.99 | Y | 2000000 | Y | -2000000 | 0 | 0 | 0 | 0 | 0 | 2000000 | Y | -2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2000000 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | -2000000 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210.88 | -210.88 | 0 | NA | 0 | 7042.3 | 7269 | 14311.3 | CY | 1083739.01 | 304572 | 779167.01 | 916260.99 | T&D Cost: 11,108cy x 2.00fluff = 22,216cy x 27cf/cy = 600,000cf x 130#/cf = 78,000,000lbs = 39,000T x $60/T (T&D) = $2,340,000
Y | IPCRP1-2000-1030-C | IPCRP1 | IPCRP1 | 2000-1030 | MH Accessories (steps, chain holes, slabs, chlori | N | C |  | NR | P | 988 | 15633.46 | 15633.46 | 15591.31 | 15633.46 | 99.7304 | 0 | 0 | 0 | 0 | Y | 15633.46 | Y | -14645.46 | 0 | 0 | 988 | 0 | 0 | 15633.46 | Y | -14645.46 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15633.46 | 0 | 0 | 15633.46 | 0 | 0 | 0 | 0 | 0 | 0 | -15633.46 | 0 | 0 | 15633.46 | 15633.46 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7 | -7 | 0 | NA | 59 | 0 | 59 | 59 | EA | 15633.46 | 42.15 | 15591.31 | 0
Y | IPCRP1-2000-1030-L | IPCRP1 | IPCRP1 | 2000-1030 | MH Accessories (steps, chain holes, slabs, chlori | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 59 | 0 | 59 | 59 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1030-M | IPCRP1 | IPCRP1 | 2000-1030 | MH Accessories (steps, chain holes, slabs, chlori | N | M |  | NR | P | 35455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 35455 | 0 | 0 | 35455 | 0 | 0 | 0 | Y | 35455 | 0 | 0 | 35455 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 544 | 544 | NA | 59 | 0 | 59 | 59 | EA | 0 | 0 | 0 | 0 | CAMPBELL FOUNDRY Base PO@$12,489.00
Y | IPCRP1-2000-1040-L | IPCRP1 | IPCRP1 | 2000-1040 | DEP Castings | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 205 | 0 | 208 | 208 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1040-M | IPCRP1 | IPCRP1 | 2000-1040 | DEP Castings | N | M |  | NR | P | 254400 | 207196 | 207196 | 105637 | 207196 | 50.9841 | 0 | 0 | 0 | 0 | Y | 207196 | Y | 47204 | 0 | 0 | 254400 | 0 | 0 | 207196 | Y | 47204 | 0 | 0 | 254400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -207196 | 0 | 0 | 207196 | 0 | 0 | 0 | 0 | 0 | 0 | -207196 | 0 | 0 | 207196 | 207196 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 296 | -296 | 0 | NA | 205 | 0 | 208 | 208 | EA | 207196 | 101559 | 105637 | 0 | CAMPBELL FOUNDRY Base PO@$156,894.00
Y | IPCRP1-2000-1050-L | IPCRP1 | IPCRP1 | 2000-1050 | CB Hoods & Hooks | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 12 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1050-M | IPCRP1 | IPCRP1 | 2000-1050 | CB Hoods & Hooks | N | M |  | NR | P | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1680 | 0 | 0 | 1680 | 0 | 0 | 0 | N | 1680 | 0 | 0 | 1680 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 12 | 12 | NA | 12 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | Can change PM Forecast once PO is executed. (VS, 2/17/22)
Y | IPCRP1-2000-1060-C | IPCRP1 | IPCRP1 | 2000-1060 | Brick/ement for Castings & Adjustments | N | C |  | NR | P | 26850 | 7785.11 | 7785.11 | 7785.11 | 7785.11 | 51.9007 | 0 | 0 | 0 | 7214.89 | Y | 15000 | Y | 11850 | 0 | 0 | 26850 | 0 | 0 | 15000 | Y | 11850 | 0 | 0 | 26850 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | -15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 686 | 635.75 | 1321.75 | NA | 1 | 0 | 1 | 1 | LS | 6109.91 | 0 | 6109.91 | 7214.89
Y | IPCRP1-2000-1060-L | IPCRP1 | IPCRP1 | 2000-1060 | Brick/ement for Castings & Adjustments | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1060-M | IPCRP1 | IPCRP1 | 2000-1060 | Brick/ement for Castings & Adjustments | N | M |  | NR | P | 71550 | 1620.32 | 1620.32 | 1533.93 | 1620.32 | 4.3827 | 0 | 0 | 0 | 33379.68 | Y | 35000 | Y | 36550 | 0 | 0 | 71550 | 0 | 0 | 35000 | Y | 36550 | 0 | 0 | 71550 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -35000 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | 0 | 0 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 763 | 15745.13 | 16508.13 | NA | 1 | 0 | 1 | 1 | LS | 1620.32 | 86.39 | 1533.93 | 33379.68
Y | IPCRP1-2000-1070-L | IPCRP1 | IPCRP1 | 2000-1070 | Aggregate Fill | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 644521 | 280776.2 | 363744.8 | 644521 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1070-M | IPCRP1 | IPCRP1 | 2000-1070 | Aggregate Fill | N | M |  | NR | P | 18344754 | 19752053.77 | 19752053.77 | 7448919.04 | 19752053.77 | 37.6424 | 0 | 0 | 0 | 36600 | Y | 19788653.77 | Y | -1443899.77 | 0 | 0 | 18344754 | 0 | 0 | 19788653.77 | Y | -1443899.77 | 0 | 0 | 18344754 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19788653.77 | 0 | 0 | 19788653.77 | 0 | 0 | 0 | 0 | 0 | 0 | -19788653.77 | 0 | 0 | 19788653.77 | 19788653.77 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 358984.06 | -352584.06 | 6400 | NA | 644521 | 280776.2 | 363744.8 | 644521 | CY | 19752053.77 | 12303134.73 | 7448919.04 | 36600
Y | IPCRP1-2000-1080-L | IPCRP1 | IPCRP1 | 2000-1080 | Aggregate Stone | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 10502 | 63831.43 | 12168.57 | 76000 | CY | 0 | 0 | 0 | 0 | Delivery claimed quantity is 18,222.59 (Athens 10,493.29 CY + Tilcon 6,098.05 CY + Evergreen 1,631.25 CY)
Y | IPCRP1-2000-1080-M | IPCRP1 | IPCRP1 | 2000-1080 | Aggregate Stone | N | M |  | NR | P | 341776 | 4315356.95 | 4315356.95 | 2700472.21 | 4315356.95 | 64.1967 | 0 | 0 | 0 | -108796.92 | Y | 4206560.03 | Y | -3864784.03 | 0 | 0 | 341776 | 0 | 0 | 4206560.03 | Y | -3864784.03 | 0 | 0 | 341776 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4206560.03 | 103512.09 | 93417.35 | 4206560.03 | 0 | 0 | 0 | 10039.66 | 49402.73 | 0 | -4206560.03 | 0 | 0 | 4206560.03 | 4206560.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 217333.66 | -38860.7 | 178472.96 | NA | 10502 | 63831.43 | 12168.57 | 76000 | CY | 4324140.35 | 1614884.74 | 2709255.61 | -108796.92 | Delivery claimed quantity is 18,222.59 (Athens 10,493.29 CY + Tilcon 6,098.05 CY + Evergreen 1,631.25 CY)
Y | IPCRP1-2000-1090-L | IPCRP1 | IPCRP1 | 2000-1090 | Aggregate Sand | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 61979 | 38469.58 | 3880.42 | 42350 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1090-M | IPCRP1 | IPCRP1 | 2000-1090 | Aggregate Sand | N | M |  | NR | P | 1961221 | 2293563.57 | 2293563.57 | 1906920.7 | 2293563.57 | 89.6955 | 0 | 0 | 0 | -167570.43 | Y | 2125993.14 | Y | -164772.14 | 0 | 0 | 1961221 | 0 | 0 | 2125993.14 | Y | -164772.14 | 0 | 0 | 1961221 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2125993.14 | 13688.89 | 59844.35 | 2125993.14 | 0 | 0 | 0 | 0 | 5650.96 | 0 | -2125993.14 | 0 | 0 | 2125993.14 | 2125993.14 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 114632.78 | -11429.9 | 103202.88 | NA | 61979 | 38469.58 | 3880.42 | 42350 | CY | 2293563.57 | 386642.87 | 1906920.7 | -167570.43 | ATHENS AGGREGATES LLC @$40,400.33, HUNTERS POINT RECYCLING, INC @$26,250.33, REDWOOD CONTRACTING CORP @$4,168.33, DUN-RITE SAND & GRAVEL CO INC @$346,223.33, EVERGREEN RECYCLING OF CORONA @$28,500.33
Y | IPCRP1-2000-1090-S | IPCRP1 | IPCRP1 | 2000-1090 | Aggregate Sand | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.66 | 98.66 | 0 | 98.66 | 0 | 98.66 | NA | 61979 | 38469.58 | 3880.42 | 42350 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1100-C | IPCRP1 | IPCRP1 | 2000-1100 | Dump Asph/Dirt/Mixed/Conc/C&G/ Excess Surcharge, | N | C |  | NR | P | 19319104 | 4960297.68 | 4960297.68 | 3272268.28 | 4960297.68 | 41.8422 | 0 | 0 | 0 | 2860207.32 | Y | 7820505 | Y | 11498599 | 0 | 0 | 19319104 | 0 | 0 | 7820505 | Y | 11498599 | 0 | 0 | 19319104 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7820505 | 22637.3 | 6818.1 | 7820505 | 0 | 0 | 0 | 20375.5 | 35564.34 | 0 | -7820505 | 0 | 0 | 7820505 | 7820505 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2663429.18 | 138774.23 | 2802203.41 | NA | 328858 | 60749.3 | 81442.7 | 142192 | CY | 4959812.44 | 1688029.4 | 3271783.04 | 2860207.32
Y | IPCRP1-2000-1100-L | IPCRP1 | IPCRP1 | 2000-1100 | Dump Asph/Dirt/Mixed/Conc/C&G/ Excess Surcharge, | N | L |  | UNIT | P | 0 | -3.44 | -3.44 | -3.44 | -3.44 | 100 | 0 | 0 | 0 | 0 | Y | -3.44 | Y | 3.44 | 0 | 0 | 0 | 0 | 0 | -3.44 | Y | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 3.44 | 0 | 0 | -3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 | 0 | 0 | -3.44 | -3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 328858 | 60749.3 | 81442.7 | 142192 | CY | 0 | 0 | 0 | 0 | 1.5T/CY = 130#/CF. Deduct 200,000T (133,333CY) of quantity, as a result of disposed material being included under Haz Mat disposal.
Y | IPCRP1-2000-1110-L | IPCRP1 | IPCRP1 | 2000-1110 | Trucking | N | L |  | UNIT | P | 0 | 1385 | 1385 | 0 | 1385 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8051 | 4900 | 3151 | 8051 | TD | 1385 | 1385 | 0 | 0
Y | IPCRP1-2000-1110-S | IPCRP1 | IPCRP1 | 2000-1110 | Trucking | N | S |  | NR | A | 11427869 | 12343197.14 | 12343197.14 | 9251216.92 | 12343197.14 | 72.8186 | 0 | 0 | 0 | 361280.86 | Y | 12704478 | Y | -1276609 | 0 | 0 | 11427869 | 0 | 0 | 12704478 | Y | -1276609 | 0 | 0 | 11427869 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12704478 | 0 | 123359.65 | 12704478 | 0 | 0 | 0 | 0 | 50000 | 0 | -12704478 | 0 | 0 | 12704478 | 12704478 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 60220.81 | -60219.81 | 1 | NA | 8051 | 4900 | 3151 | 8051 | TD | 12343197.14 | 3091980.22 | 9251216.92 | 361280.86 | KMA base @43,500; Phantom base @50,000; Redwood @351,040
Y | IPCRP1-2000-1111-C | IPCRP1 | IPCRP1 | 2000-1111 | Barge Rentals | N | C |  | UNIT | U | 0 | 201547.92 | 201547.92 | 155292.66 | 201547.92 | 77.05 | 0 | 0 | 0 | 0 | Y | 201547.92 | Y | -201547.92 | 0 | 0 | 0 | 0 | 0 | 201547.92 | Y | -201547.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -201547.92 | 0 | 0 | 201547.92 | 0 | 0 | 0 | 0 | 0 | 0 | -201547.92 | 0 | 0 | 201547.92 | 201547.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.67 | -24.67 | 0 | NA | 20 | 14 | 6 | 20 | BM | 201297.92 | 46255.26 | 155042.66 | 0 | VS added, based on 20 barge months @ 6.5K/mo + tax. If used, this should reduce the # of truck days needed in activity 2000-1110 (Trucking)
Y | IPCRP1-2000-1111-L | IPCRP1 | IPCRP1 | 2000-1111 | Barge Rentals | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 20 | 14 | 6 | 20 | BM | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1120-C | IPCRP1 | IPCRP1 | 2000-1120 | 20/30 CY C&D Containers | N | C |  | NR | P | 1860518 | 3122139.17 | 3122139.17 | 2516989.73 | 3122139.17 | 85.0999 | 0 | 0 | 0 | -164451.85 | Y | 2957687.32 | Y | -1097169.32 | 0 | 0 | 1860518 | 0 | 0 | 2957687.32 | Y | -1097169.32 | 0 | 0 | 1860518 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2957687.32 | 23871.7 | 186580.13 | 2957687.32 | 0 | 0 | 0 | 29263.49 | 105706.21 | 0 | -2957687.32 | 0 | 0 | 2957687.32 | 2957687.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 38838.63 | -4340.3 | 34498.33 | NA | 1796 | 2536 | 314 | 2850 | EA | 3122139.17 | 605149.44 | 2516989.73 | -164451.85
Y | IPCRP1-2000-1120-L | IPCRP1 | IPCRP1 | 2000-1120 | 20/30 CY C&D Containers | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1796 | 2536 | 314 | 2850 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1120-S | IPCRP1 | IPCRP1 | 2000-1120 | 20/30 CY C&D Containers | N | S |  | UNIT | A | 0 | 4816870.09 | 4816870.09 | 4449768.11 | 4816870.09 | 92.3788 | 0 | 0 | 0 | 0 | Y | 4816870.09 | Y | -4816870.09 | 0 | 0 | 0 | 0 | 0 | 4816870.09 | Y | -4816870.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4816870.09 | 0 | 59095.12 | 4816870.09 | 0 | 0 | 0 | 0 | 0 | 0 | -4816870.09 | 0 | 0 | 4816870.09 | 4816870.09 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2574.98 | -2573.98 | 1 | NA | 1796 | 2536 | 314 | 2850 | EA | 4816870.09 | 367101.98 | 4449768.11 | 0 | Cardella Base Contract @$599,901.25
Y | IPCRP1-2000-1130-C | IPCRP1 | IPCRP1 | 2000-1130 | Sewer Work Forms & Timber Lagging | N | C |  | NR | P | 951102 | 4242449.73 | 4242449.73 | 4078256.94 | 4242449.73 | 90.6279 | 0 | 0 | 0 | 257550.27 | Y | 4500000 | Y | -3548898 | 0 | 0 | 951102 | 0 | 0 | 4500000 | Y | -3548898 | 0 | 0 | 951102 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4500000 | 22155.37 | 10285.99 | 4500000 | 0 | 0 | 0 | 22157.26 | 11214.08 | 0 | -4500000 | 0 | 0 | 4500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 138298.9 | -137752.9 | 546 | NA | 229877 | 198869.51 | 31007.49 | 229877 | SF | 4167684.05 | 164192.79 | 4003491.26 | 257550.27 | INTSEL STEEL EAST (000004-1) @$1,095,352.15; INFINITY LUMBER (IPCRP1-0300-1)@$3,997.89; CARTER, MILCHMAN & FRANK (IPCRP1-0306-1)@$914.42 . Potential buyback of Intsel Steel sheet system btwn 20% - 50% (2 year – 5 years). New Commitments issued in June'22: Insteel, T Mina, Afendi, Holbrook, Bruce Total = $121,394.99 (as of 6-29-2022)
Y | IPCRP1-2000-1130-L | IPCRP1 | IPCRP1 | 2000-1130 | Sewer Work Forms & Timber Lagging | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 229877 | 198869.51 | 31007.49 | 229877 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1140-C | IPCRP1 | IPCRP1 | 2000-1140 | Subcontractor Support (General) | N | C |  | NR | P | 1000000 | 158320.54 | 158320.54 | 109604.46 | 158320.54 | 73.0696 | 0 | 0 | 0 | -8320.54 | Y | 150000 | Y | 850000 | 0 | 0 | 1000000 | 0 | 0 | 150000 | Y | 850000 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | -150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 23989.08 | 890.47 | 24879.55 | NA | 1 | 0.7 | 0.3 | 1 | LS | 149374.29 | 48716.08 | 100658.21 | -8320.54 | Atlantic States Lubricants posted in July 2023.
Y | IPCRP1-2000-1140-L | IPCRP1 | IPCRP1 | 2000-1140 | Subcontractor Support (General) | N | L |  | UNIT | P | 0 | 2345951.24 | 2345951.24 | 2345951.24 | 2345951.24 | 74.4656 | 0 | 0 | 0 | 804430.96 | Y | 3150382.2 | Y | -3150382.2 | 0 | 0 | 0 | 0 | 0 | 3150382.2 | Y | -3150382.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3150382.2 | 62752.78 | 47858.81 | 3150382.2 | 0 | 0 | 0 | 0 | 0 | 0 | -3150382.2 | 0 | 0 | 3150382.2 | 3150382.2 | 0 | 0 | 0 | 0 | 0 | 25200 | 25200 | 0 | 18931 | 6269 | 25200 | HR | 1 | 0.7 | 0.3 | 1 | LS | 0 | 0 | 0 | 804430.96
Y | IPCRP1-2000-1140-S | IPCRP1 | IPCRP1 | 2000-1140 | Subcontractor Support (General) | N | S |  | UNIT | A | 0 | 169019.19 | 169019.19 | 169019.17 | 169019.19 | 84.5096 | 0 | 0 | 0 | 30980.81 | Y | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200000 | 7812.65 | 3866.08 | 200000 | 0 | 0 | 0 | 0 | 7812.65 | 0 | -200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 1282 | -1271 | 11 | NA | 1 | 0.7 | 0.3 | 1 | LS | 169019.19 | 0.02 | 169019.17 | 30980.81
Y | IPCRP1-2000-1150-E | IPCRP1 | IPCRP1 | 2000-1150 | Support Structural Steel Sub (ASW) | N | E |  | NR | P | 10000 | 62225.43 | 62225.43 | 60773.04 | 62225.43 | 97.6659 | 0 | 0 | 0 | 0 | Y | 62225.43 | Y | -52225.43 | 0 | 0 | 10000 | 0 | 0 | 62225.43 | Y | -52225.43 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -62225.43 | 0 | 0 | 62225.43 | 0 | 0 | 0 | 0 | 0 | 0 | -62225.43 | 0 | 0 | 62225.43 | 62225.43 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 116 | 0 | 116 | NA | 1 | 0.5 | 0.5 | 1 | LS | 62225.43 | 1452.39 | 60773.04 | 0
Y | IPCRP1-2000-1150-L | IPCRP1 | IPCRP1 | 2000-1150 | Support Structural Steel Sub (ASW) | N | L |  | NR | P | 80000 | 181247.51 | 181247.51 | 181247.51 | 181247.51 | 69.6955 | 0 | 0 | 0 | 78808.65 | Y | 260056.16 | Y | -180056.16 | 0 | 0 | 80000 | 0 | 0 | 260056.16 | Y | -180056.16 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -260056.16 | 3900.67 | 0 | 260056.16 | 0 | 0 | 0 | 0 | 0 | 0 | -260056.16 | 0 | 0 | 260056.16 | 260056.16 | 0 | 0 | 0 | 640 | 0 | 2000 | 2000 | 640 | 1457.5 | 542.5 | 2000 | HR | 1 | 0.5 | 0.5 | 1 | LS | 0 | 0 | 0 | 78808.65
Y | IPCRP1-2000-1150-S | IPCRP1 | IPCRP1 | 2000-1150 | Support Structural Steel Sub (ASW) | N | S |  | UNIT | A | 0 | 8253.89 | 8253.89 | 8253.89 | 8253.89 | 105.7931 | 0 | 0 | 0 | -451.97 | Y | 7801.92 | Y | -7801.92 | 0 | 0 | 0 | 0 | 0 | 7801.92 | Y | -7801.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7801.92 | 451.97 | 0 | 7801.92 | 0 | 0 | 0 | 0 | 451.97 | 0 | -7801.92 | 0 | 0 | 7801.92 | 7801.92 | 0 | 0 | 0 | 0 | 0 | 61 | 61 | 0 | 62.5 | -1.5 | 61 | NA | 1 | 0.5 | 0.5 | 1 | LS | 8253.89 | 0 | 8253.89 | -451.97
Y | IPCRP1-2000-1160-C | IPCRP1 | IPCRP1 | 2000-1160 | Support for Rigid Inclusion Sub (American Pile) | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | 10000
Y | IPCRP1-2000-1160-E | IPCRP1 | IPCRP1 | 2000-1160 | Support for Rigid Inclusion Sub (American Pile) | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1160-L | IPCRP1 | IPCRP1 | 2000-1160 | Support for Rigid Inclusion Sub (American Pile) | N | L |  | UNIT | P | 0 | 213226.28 | 213226.28 | 213226.28 | 213226.28 | 44.4221 | 0 | 0 | 0 | 266773.72 | Y | 480000 | Y | -480000 | 0 | 0 | 0 | 0 | 0 | 480000 | Y | -480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -480000 | 38078.37 | 13854.18 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | -480000 | 0 | 0 | 480000 | 480000 | 0 | 0 | 0 | 0 | 0 | 3501.45 | 3501.45 | 0 | 1545.5 | 1955.95 | 3501.45 | HR | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | 266773.72 | Placed all Rigid Inclusion Sub support here. While it shows no budget, we had a gain of $5,256,672.18 in the 3 rigid inclusion items in the report (0374-1000, 0374-1010, & 0374-1020) Sub, Test Program & Obstruction
Y | IPCRP1-2000-1160-M | IPCRP1 | IPCRP1 | 2000-1160 | Support for Rigid Inclusion Sub (American Pile) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1160-S | IPCRP1 | IPCRP1 | 2000-1160 | Support for Rigid Inclusion Sub (American Pile) | N | S |  | UNIT | A | 0 | 65381.94 | 65381.94 | 65381.94 | 65381.94 | 65.3819 | 0 | 0 | 0 | 34618.06 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 11428.41 | 7011.36 | 100000 | 0 | 0 | 0 | 0 | 11428.41 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376.5 | -376.5 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 65381.94 | 0 | 65381.94 | 34618.06
Y | IPCRP1-2000-1170-C | IPCRP1 | IPCRP1 | 2000-1170 | Support Microtunnel Sub (JR Cruz) | N | C |  | NR | P | 5300 | 39682 | 39682 | 39682 | 39682 | 100 | 0 | 0 | 0 | 0 | Y | 39682 | Y | -34382 | 0 | 0 | 5300 | 0 | 0 | 39682 | Y | -34382 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39682 | 0 | 0 | 39682 | 0 | 0 | 0 | 0 | 0 | 0 | -39682 | 0 | 0 | 39682 | 39682 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 1 | NA | 1 | 1 | 0 | 1 | LS | 39682 | 0 | 39682 | 0
Y | IPCRP1-2000-1170-E | IPCRP1 | IPCRP1 | 2000-1170 | Support Microtunnel Sub (JR Cruz) | N | E |  | NR | P | 14058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 14058 | 0 | 0 | 14058 | 0 | 0 | 0 | Y | 14058 | 0 | 0 | 14058 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1170-L | IPCRP1 | IPCRP1 | 2000-1170 | Support Microtunnel Sub (JR Cruz) | N | L |  | NR | P | 47797 | 15253.6 | 15253.6 | 15253.6 | 15253.6 | 100 | 0 | 0 | 0 | 0 | Y | 15253.6 | Y | 32543.4 | 0 | 0 | 47797 | 0 | 0 | 15253.6 | Y | 32543.4 | 0 | 0 | 47797 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15253.6 | 0 | 0 | 15253.6 | 0 | 0 | 0 | 0 | 0 | 0 | -15253.6 | 0 | 0 | 15253.6 | 15253.6 | 0 | 0 | 0 | 408 | 0 | 122.5 | 122.5 | 408 | 122.5 | 0 | 122.5 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1170-S | IPCRP1 | IPCRP1 | 2000-1170 | Support Microtunnel Sub (JR Cruz) | N | S |  | NR | A | 112000 | 2971.81 | 2971.81 | 2971.81 | 2971.81 | 100 | 0 | 0 | 0 | 0 | Y | 2971.81 | Y | 109028.19 | 0 | 0 | 112000 | 0 | 0 | 2971.81 | Y | 109028.19 | 0 | 0 | 112000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2971.81 | 0 | 0 | 2971.81 | 0 | 0 | 0 | 0 | 0 | 0 | -2971.81 | 0 | 0 | 2971.81 | 2971.81 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 24 | -24 | 0 | NA | 1 | 1 | 0 | 1 | LS | 2971.81 | 0 | 2971.81 | 0
Y | IPCRP1-2000-1180-C | IPCRP1 | IPCRP1 | 2000-1180 | Support for Elect Sub (1) - (EJ) Misc | N | C |  | NR | P | 3336.08 | 10665.12 | 10665.12 | 10133.79 | 10665.12 | 95.0181 | 0 | 0 | 0 | 0 | Y | 10665.12 | Y | -7329.04 | 0 | 0 | 3336.08 | 0 | 0 | 10665.12 | Y | -7329.04 | 0 | 0 | 3336.08 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10665.12 | 0 | 0 | 10665.12 | 0 | 0 | 0 | 0 | 0 | 0 | -10665.12 | 0 | 0 | 10665.12 | 10665.12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9 | 0.27 | 9.27 | NA | 1 | 0.5 | 0.5 | 1 | LS | 10665.12 | 531.33 | 10133.79 | 0
Y | IPCRP1-2000-1180-E | IPCRP1 | IPCRP1 | 2000-1180 | Support for Elect Sub (1) - (EJ) Misc | N | E |  | NR | P | 6120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 6120 | 0 | 0 | 6120 | 0 | 0 | 0 | Y | 6120 | 0 | 0 | 6120 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0.5 | 0.5 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1180-L | IPCRP1 | IPCRP1 | 2000-1180 | Support for Elect Sub (1) - (EJ) Misc | N | L |  | NR | P | 28002.3 | 92610.73 | 92610.73 | 92610.73 | 92610.73 | 94.9635 | 0 | 0 | 0 | 4911.68 | Y | 97522.41 | Y | -69520.11 | 0 | 0 | 28002.3 | 0 | 0 | 97522.41 | Y | -69520.11 | 0 | 0 | 28002.3 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -97522.41 | 109.84 | 9299.72 | 97522.41 | 0 | 0 | 0 | 0 | 0 | 0 | -97522.41 | 0 | 0 | 97522.41 | 97522.41 | 0 | 0 | 0 | 256 | 0 | 777.55 | 777.55 | 256 | 747.5 | 30.05 | 777.55 | HR | 1 | 0.5 | 0.5 | 1 | LS | 0 | 0 | 0 | 4911.68
Y | IPCRP1-2000-1180-M | IPCRP1 | IPCRP1 | 2000-1180 | Support for Elect Sub (1) - (EJ) Misc | N | M |  | NR | P | 3080.34 | 169.9 | 169.9 | 169.9 | 169.9 | 5.5156 | 0 | 0 | 0 | 2910.44 | N | 3080.34 | N | 0 | 0 | 0 | 3080.34 | 0 | 0 | 3080.34 | N | 0 | 0 | 0 | 3080.34 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3080.34 | 0 | 169.9 | 3080.34 | 0 | 0 | 0 | 0 | 169.89 | 0 | -3080.34 | 0 | 0 | 3080.34 | 3080.34 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | -4 | 0 | NA | 1 | 0.5 | 0.5 | 1 | LS | 169.89 | -0.01 | 169.9 | 2910.44
Y | IPCRP1-2000-1180-S | IPCRP1 | IPCRP1 | 2000-1180 | Support for Elect Sub (1) - (EJ) Misc | N | S |  | UNIT | A | 0 | 4291.03 | 4291.03 | 4291.03 | 4291.03 | 85.8206 | 0 | 0 | 0 | 708.97 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 129.13 | 0 | 5000 | 0 | 0 | 0 | 0 | 129.13 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 34 | -13 | 21 | NA | 1 | 0.5 | 0.5 | 1 | LS | 4291.03 | 0 | 4291.03 | 708.97 | KMA charged here @$2,520
Y | IPCRP1-2000-1190-C | IPCRP1 | IPCRP1 | 2000-1190 | Support for Elect Sub (2) - (EJ) Foundations | N | C |  | UNIT | U | 0 | 26400 | 26400 | 26400 | 26400 | 100 | 0 | 0 | 0 | 0 | N | 26400 | N | -26400 | 0 | 0 | 0 | 0 | 0 | 26400 | N | -26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26400 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | -26400 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 5280 | 5280 | 0 | 5280 | 0 | 5280 | NA | 254 | 78.3 | 159.7 | 238 | EA | 26400 | 0 | 26400 | 0
Y | IPCRP1-2000-1190-E | IPCRP1 | IPCRP1 | 2000-1190 | Support for Elect Sub (2) - (EJ) Foundations | N | E |  | NR | P | 69867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 69867 | 0 | 0 | 69867 | 0 | 0 | 0 | N | 69867 | 0 | 0 | 69867 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 254 | 78.3 | 159.7 | 238 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1190-L | IPCRP1 | IPCRP1 | 2000-1190 | Support for Elect Sub (2) - (EJ) Foundations | N | L |  | NR | P | 650290.21 | 178479.56 | 178479.56 | 178479.56 | 178479.56 | 29.2963 | 0 | 0 | 0 | 430742.73 | Y | 609222.29 | Y | 41067.92 | 0 | 0 | 650290.21 | 0 | 0 | 609222.29 | Y | 41067.92 | 0 | 0 | 650290.21 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -609222.29 | 0 | 685.34 | 609222.29 | 0 | 0 | 0 | 0 | 0 | 0 | -609222.29 | 0 | 0 | 609222.29 | 609222.29 | 0 | 0 | 0 | 5525.34 | 0 | 4999.64 | 4999.64 | 5525.34 | 1428 | 3571.64 | 4999.64 | HR | 254 | 78.3 | 159.7 | 238 | EA | 0 | 0 | 0 | 430742.73 | 1) Removed 16ea LP Foundations PMF Quantity and created a new cc for Stadium Light Foundations 2) James Robert’s takeoff is lower (206ea). Not using this at this time. Refer to JR email dated 1/5/24.
Y | IPCRP1-2000-1190-S | IPCRP1 | IPCRP1 | 2000-1190 | Support for Elect Sub (2) - (EJ) Foundations | N | S |  | UNIT | A | 0 | 745.99 | 745.99 | 745.99 | 745.99 | 100 | 0 | 0 | 0 | 0 | N | 745.99 | N | -745.99 | 0 | 0 | 0 | 0 | 0 | 745.99 | N | -745.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -745.99 | 0 | 0 | 745.99 | 0 | 0 | 0 | 0 | 0 | 0 | -745.99 | 0 | 0 | 745.99 | 745.99 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 254 | 78.3 | 159.7 | 238 | EA | 745.99 | 0 | 745.99 | 0
Y | IPCRP1-2000-1195-C | IPCRP1 | IPCRP1 | 2000-1195 | Support for Elect Sub (2A), (EJ) Stadium Light Fo | N | C |  | UNIT | U | 0 | 3027.83 | 3027.83 | 3027.83 | 3027.83 | 15.1392 | 0 | 0 | 0 | 16972.17 | Y | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | -53 | 0 | NA | 0 | 10 | 6 | 16 | EA | 3027.83 | 0 | 3027.83 | 16972.17 | this is for temp casing (Trinity)
Y | IPCRP1-2000-1195-L | IPCRP1 | IPCRP1 | 2000-1195 | Support for Elect Sub (2A), (EJ) Stadium Light Fo | N | L |  | UNIT | P | 0 | 332547.86 | 332547.86 | 332547.86 | 332547.86 | 61.5765 | 0 | 0 | 0 | 207508.44 | Y | 540056.3 | Y | -540056.3 | 0 | 0 | 0 | 0 | 0 | 540056.3 | Y | -540056.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -540056.3 | 0 | 0 | 540056.3 | 0 | 0 | 0 | 0 | 0 | 0 | -540056.3 | 0 | 0 | 540056.3 | 540056.3 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 2525 | 1475 | 4000 | HR | 0 | 10 | 6 | 16 | EA | 0 | 0 | 0 | 207508.44 | From Posillico Estimate dated 9/22/23 and adjusted by VS for quantity of 16ea (from 10ea
Y | IPCRP1-2000-1195-S | IPCRP1 | IPCRP1 | 2000-1195 | Support for Elect Sub (2A), (EJ) Stadium Light Fo | N | S |  | UNIT | A | 0 | 1823.74 | 1823.74 | 1823.74 | 1823.74 | 9.1187 | 0 | 0 | 0 | 18176.26 | Y | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | -16 | 0 | NA | 0 | 10 | 6 | 16 | EA | 1823.74 | 0 | 1823.74 | 18176.26 | this will be invoices from HMR for trucking
Y | IPCRP1-2000-1200-E | IPCRP1 | IPCRP1 | 2000-1200 | Support for Elect Sub (3) - (EJ) Trenching | N | E |  | NR | P | 310720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 310720 | 0 | 0 | 310720 | 0 | 0 | 0 | Y | 310720 | 0 | 0 | 310720 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 92500 | 13957.46 | 30042.54 | 44000 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1200-L | IPCRP1 | IPCRP1 | 2000-1200 | Support for Elect Sub (3) - (EJ) Trenching | N | L |  | NR | P | 805563.88 | 253466.22 | 253466.22 | 253466.22 | 253466.22 | 32.6013 | 0 | 0 | 0 | 524007.13 | N | 777473.35 | N | 28090.53 | 0 | 0 | 805563.88 | 0 | 0 | 777473.35 | N | 28090.53 | 0 | 0 | 805563.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -777473.35 | -6391.55 | 8619.08 | 777473.35 | 0 | 0 | 0 | 0 | 0 | 0 | -777473.35 | 0 | 0 | 777473.35 | 777473.35 | 0 | 0 | 0 | 6784 | 0 | 6533.28 | 6533.28 | 6784 | 2119.5 | 4413.78 | 6533.28 | HR | 92500 | 13957.46 | 30042.54 | 44000 | LF | 0 | 0 | 0 | 524007.13 | as per James Roberts email response 7/29/24
Y | IPCRP1-2000-1200-S | IPCRP1 | IPCRP1 | 2000-1200 | Support for Elect Sub (3) - (EJ) Trenching | N | S |  | UNIT | A | 0 | 6011.12 | 6011.12 | 6011.12 | 6011.12 | 178.6971 | 0 | 0 | 0 | 0 | N | 3363.86 | N | -3363.86 | 0 | 0 | 0 | 0 | 0 | 3363.86 | N | -3363.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3363.86 | 2647.26 | 0 | 3363.86 | 0 | 0 | 0 | 0 | 2647.26 | 0 | -3363.86 | 0 | 0 | 3363.86 | 3363.86 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 28 | 0 | 28 | NA | 92500 | 13957.46 | 30042.54 | 44000 | LF | 6011.12 | 0 | 6011.12 | 0
Y | IPCRP1-2000-1201-C | IPCRP1 | IPCRP1 | 2000-1201 | Sub Support for AP&F/ Keller for JG | N | C |  | UNIT | U | 0 | 64627.11 | 64627.11 | 64627.11 | 64627.11 | 100 | 0 | 0 | 0 | 0 | Y | 64627.11 | Y | -64627.11 | 0 | 0 | 0 | 0 | 0 | 64627.11 | Y | -64627.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -64627.11 | 0 | 0 | 64627.11 | 0 | 0 | 0 | 0 | 0 | 0 | -64627.11 | 0 | 0 | 64627.11 | 64627.11 | 0 | 0 | 0 | 0 | 0 | 986 | 986 | 0 | 886 | 100 | 986 | NA | 0 | 0.62 | 0.38 | 1 | LS | 51096.83 | -13454.27 | 64551.1 | 0 | Atlantic Pile
Y | IPCRP1-2000-1201-L | IPCRP1 | IPCRP1 | 2000-1201 | Sub Support for AP&F/ Keller for JG | N | L |  | UNIT | P | 0 | 387804.02 | 387804.02 | 387804.02 | 387804.02 | 68.0689 | 0 | 0 | 0 | 181919.01 | Y | 569723.03 | Y | -569723.03 | 0 | 0 | 0 | 0 | 0 | 569723.03 | Y | -569723.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -569723.03 | 0 | 0 | 569723.03 | 0 | 0 | 0 | 0 | 0 | 0 | -569723.03 | 0 | 0 | 569723.03 | 569723.03 | 0 | 0 | 0 | 0 | 0 | 4280 | 4280 | 0 | 2965.5 | 1314.5 | 4280 | HR | 0 | 0.62 | 0.38 | 1 | LS | 0 | 0 | 0 | 181919.01
Y | IPCRP1-2000-1201-S | IPCRP1 | IPCRP1 | 2000-1201 | Sub Support for AP&F/ Keller for JG | N | S |  | UNIT | A | 0 | 129106.53 | 129106.53 | 76216.54 | 129106.53 | 59.0338 | 0 | 0 | 0 | 0 | Y | 129106.53 | Y | -129106.53 | 0 | 0 | 0 | 0 | 0 | 129106.53 | Y | -129106.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -129106.53 | 0 | 0 | 129106.53 | 0 | 0 | 0 | 0 | 0 | 0 | -129106.53 | 0 | 0 | 129106.53 | 129106.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447.74 | -447.74 | 0 | LS | 0 | 0.62 | 0.38 | 1 | LS | 129106.53 | 52889.99 | 76216.54 | 0
Y | IPCRP1-2000-1210-L | IPCRP1 | IPCRP1 | 2000-1210 | Labor Support - Night Shift | N | L |  | NR | P | 2810504.4 | 33782.43 | 33782.43 | 33782.43 | 33782.43 | 1.202 | 0 | 0 | 0 | 2776722.07 | Y | 2810504.5 | Y | -0.1 | 0 | 0 | 2810504.4 | 0 | 0 | 2810504.5 | Y | -0.1 | 0 | 0 | 2810504.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2810504.5 | 0 | 0 | 2810504.5 | 0 | 0 | 0 | 0 | 0 | 0 | -2810504.5 | 0 | 0 | 2810504.5 | 2810504.5 | 0 | 0 | 0 | 21120 | 0 | 21113.68 | 21113.68 | 21120 | 252.5 | 20861.18 | 21113.68 | HR | 130 | 4 | 126 | 130 | WK | 0 | 0 | 0 | 2776722.07
Y | IPCRP1-2000-1210-S | IPCRP1 | IPCRP1 | 2000-1210 | Labor Support - Night Shift | N | S |  | UNIT | A | 0 | 1381.3 | 1381.3 | 1381.3 | 1381.3 | 100 | 0 | 0 | 0 | 0 | N | 1381.3 | N | -1381.3 | 0 | 0 | 0 | 0 | 0 | 1381.3 | N | -1381.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1381.3 | 0 | 0 | 1381.3 | 0 | 0 | 0 | 0 | 0 | 0 | -1381.3 | 0 | 0 | 1381.3 | 1381.3 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 11 | 0 | 11 | NA | 130 | 4 | 126 | 130 | WK | 1381.3 | 0 | 1381.3 | 0
Y | IPCRP1-2000-1220-C | IPCRP1 | IPCRP1 | 2000-1220 | Labor Support - Day Shift | N | C |  | UNIT | U | 0 | 54667.66 | 54667.66 | 54615.29 | 54667.66 | 100 | 0 | 0 | 0 | -52.37 | Y | 54615.29 | Y | -54615.29 | 0 | 0 | 0 | 0 | 0 | 54615.29 | Y | -54615.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -54615.29 | 0 | 0 | 54615.29 | 0 | 0 | 0 | 0 | 0 | 0 | -54615.29 | 0 | 0 | 54615.29 | 54615.29 | 0 | 0 | 0 | 0 | 0 | 512.51 | 512.51 | 0 | 513 | -0.49 | 512.51 | NA | 234 | 204 | 30 | 234 | WK | 14469.5 | 52.37 | 14417.13 | -52.37
Y | IPCRP1-2000-1220-L | IPCRP1 | IPCRP1 | 2000-1220 | Labor Support - Day Shift | N | L |  | NR | P | 3772684 | 2980677.86 | 2980677.86 | 2980677.86 | 2980677.86 | 81.158 | 0 | 0 | 0 | 692006.13 | Y | 3672683.99 | Y | 100000.01 | 0 | 0 | 3772684 | 0 | 0 | 3672683.99 | Y | 100000.01 | 0 | 0 | 3772684 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3672683.99 | 78047.15 | 105831.41 | 3672683.99 | 0 | 0 | 0 | 0 | 0 | 0 | -3672683.99 | 0 | 0 | 3672683.99 | 3672683.99 | 0 | 0 | 0 | 33264 | 0 | 31144.01 | 31144.01 | 33264 | 25518.5 | 5625.51 | 31144.01 | HR | 234 | 204 | 30 | 234 | WK | 0 | 0 | 0 | 692006.13 | Start counting from 6/5/2022. Quantity To Date as of 6/26/2022 is 4 WK
Y | IPCRP1-2000-1220-S | IPCRP1 | IPCRP1 | 2000-1220 | Labor Support - Day Shift | N | S |  | UNIT | A | 0 | 397896.1 | 397896.1 | 397896.09 | 397896.1 | 100 | 0 | 0 | 0 | 0 | Y | 397896.1 | Y | -397896.1 | 0 | 0 | 0 | 0 | 0 | 397896.1 | Y | -397896.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -397896.1 | 10007.93 | 16447.21 | 397896.1 | 0 | 0 | 0 | 0 | 10007.93 | 0 | -397896.1 | 0 | 0 | 397896.1 | 397896.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3031 | -3031 | 0 | NA | 234 | 204 | 30 | 234 | WK | 397896.1 | 0.01 | 397896.09 | 0
Y | IPCRP1-2000-1230-C | IPCRP1 | IPCRP1 | 2000-1230 | Job Site Bare Equipment | N | C |  | UNIT | U | 0 | 5773357.92 | 5773357.92 | 5267132.65 | 5773357.92 | 87.7855 | 0 | 0 | 0 | 226642.08 | Y | 6000000 | Y | -6000000 | 0 | 0 | 0 | 0 | 0 | 6000000 | Y | -6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6000000 | 193073.13 | 103673 | 6000000 | 0 | 0 | 0 | 126839.28 | 141046.64 | 0 | -6000000 | 0 | 0 | 6000000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 467088.67 | 467088.67 | 0 | 471593.44 | -4504.77 | 467088.67 | NA | 1 | 0.65 | 0.35 | 1 | LS | 4437919.56 | 506225.27 | 3931694.29 | 226642.08 | Assume resale value on EQUIP is 30% (6.8M) = 2.0M. Assume resale value of SHEET is 30% (2.0M) = 0.6K. TRENCH PLATE RENTAL CO. (IPCRP1-0139), 1,817,499.32 TRENCH PLATE RENTAL CO. (IPCRP1-0139), 1,817,499.32 3/18/24 - Re-allocate 2.7M from 2000-1240 to 2000-1230, increasing total to $16,019,521. VS (5/24) added 2M to equipment cost. We have 6.8M being depreciated. Of which we PTD 2.2M, leaving 4.6 in open costs. We have 2M is sheeting purchase. Assume 30% resale (0.6M). 4.6 - 2 -0.6 = 2M.
Y | IPCRP1-2000-1230-D | IPCRP1 | IPCRP1 | 2000-1230 | Job Site Bare Equipment | N | D |  | UNIT | A | 0 | 4534619.33 | 4534619.33 | 4534619.33 | 4534619.33 | 0 | 0 | 0 | 0 | -4534619.33 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 120260.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | -4534619.33
Y | IPCRP1-2000-1230-E | IPCRP1 | IPCRP1 | 2000-1230 | Job Site Bare Equipment | N | E |  | UNIT | A | 0 | 21482656.68 | 21482656.68 | 14398048.79 | 21482656.68 | 71.16 | 0 | 0 | 0 | -1249314.9 | Y | 20233341.78 | Y | -20233341.78 | 0 | 0 | 0 | 0 | 0 | 20233341.78 | Y | -20233341.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20233341.78 | 212208.66 | 246398.03 | 20233341.78 | 0 | 0 | 0 | 319869.32 | 376465.56 | 0 | -20233341.78 | 0 | 0 | 20233341.78 | 20233341.78 | 0 | 0 | 0 | 0 | 0 | 86.5 | 86.5 | 0 | 205074.68 | -204988.18 | 86.5 | NA | 1 | 0.65 | 0.35 | 1 | LS | 22382848.58 | 7084607.89 | 15298240.69 | -1249314.9 | Further reduced Bare Equipment by CAC Project Support ($4,277,583) leaving ($13,319,521). Split original equipment budget (27,397,104) into Bare Equipment (17,597,104) and Fuel/Maintenance (9,800,000)
Y | IPCRP1-2000-1230-L | IPCRP1 | IPCRP1 | 2000-1230 | Job Site Bare Equipment | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1230-M | IPCRP1 | IPCRP1 | 2000-1230 | Job Site Bare Equipment | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1230-S | IPCRP1 | IPCRP1 | 2000-1230 | Job Site Bare Equipment | N | S |  | UNIT | A | 0 | 650997.73 | 650997.73 | 570487.17 | 650997.73 | 95.3076 | 0 | 0 | 0 | -52423.06 | Y | 598574.67 | Y | -598574.67 | 0 | 0 | 0 | 0 | 0 | 598574.67 | Y | -598574.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -598574.67 | 18291 | 33315.75 | 598574.67 | 0 | 0 | 0 | 0 | 52423.06 | 0 | -598574.67 | 0 | 0 | 598574.67 | 598574.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42079.23 | -42079.23 | 0 | NA | 1 | 0.65 | 0.35 | 1 | LS | 650997.73 | 80510.56 | 570487.17 | -52423.06
Y | IPCRP1-2000-1240-C | IPCRP1 | IPCRP1 | 2000-1240 | Job Site Fuel & Maintenance | N | C |  | UNIT | U | 0 | 7890000.15 | 7890000.15 | 6181018.5 | 7890000.15 | 82.944 | 0 | 0 | 0 | -437958.63 | Y | 7452041.52 | Y | -7452041.52 | 0 | 0 | 0 | 0 | 0 | 7452041.52 | Y | -7452041.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7452041.52 | 138955.01 | 237063.16 | 7452041.52 | 0 | 0 | 0 | 36894.77 | 181746.69 | 0 | -7452041.52 | 0 | 0 | 7452041.52 | 7452041.52 | 0 | 0 | 0 | 0 | 0 | 1319661.85 | 1319661.85 | 0 | 1695640.23 | -375978.38 | 1319661.85 | NA | 54 | 51 | 9 | 60 | MO | 6808666.38 | 1708981.65 | 5099684.73 | -437958.63 | Will start measuring in Feb 2022. Note- 5/24/24 - Added 2M in PMF (to 9.3M) based on 155K avg x 60 mo. 3/18/24 - Re-allocate 2.7M from 2000-1240 to 2000-1230, decreasing total to $7,100,000.00.
Y | IPCRP1-2000-1240-D | IPCRP1 | IPCRP1 | 2000-1240 | Job Site Fuel & Maintenance | N | D |  | UNIT | A | 0 | 13026.78 | 13026.78 | 13026.78 | 13026.78 | 130 | 0 | 0 | 0 | 0 | N | 10020.6 | N | -10020.6 | 0 | 0 | 0 | 0 | 0 | 10020.6 | N | -10020.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10020.6 | 0 | 501.03 | 10020.6 | 0 | 0 | 0 | 0 | 0 | 0 | -10020.6 | 0 | 0 | 10020.6 | 10020.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 54 | 51 | 9 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1240-E | IPCRP1 | IPCRP1 | 2000-1240 | Job Site Fuel & Maintenance | N | E |  | UNIT | P | 0 | 798101.71 | 798101.71 | 781139.92 | 798101.71 | 39.057 | 0 | 0 | 0 | 1201898.29 | Y | 2000000 | Y | -2000000 | 0 | 0 | 0 | 0 | 0 | 2000000 | Y | -2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2000000 | 14184.33 | 9541.1 | 2000000 | 0 | 0 | 0 | 26093 | 9912.91 | 0 | -2000000 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 220521.72 | 220521.72 | 0 | 394106.99 | -173585.27 | 220521.72 | NA | 54 | 51 | 9 | 60 | MO | 810962.75 | 16961.79 | 794000.96 | 1201898.29 | Fuel/Maintenance is reduced to 6,800,000 for Petroscan @ $3M under subcontract category. 5/24/24 - Added 2M in PMF (to 9.3M) based on 155K avg x 60 mo
Y | IPCRP1-2000-1240-L | IPCRP1 | IPCRP1 | 2000-1240 | Job Site Fuel & Maintenance | N | L |  | UNIT | P | 0 | 24885.67 | 24885.67 | 24885.67 | 24885.67 | 100 | 0 | 0 | 0 | 0 | Y | 24885.67 | Y | -24885.67 | 0 | 0 | 0 | 0 | 0 | 24885.67 | Y | -24885.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24885.67 | 0 | 0 | 24885.67 | 0 | 0 | 0 | 0 | 0 | 0 | -24885.67 | 0 | 0 | 24885.67 | 24885.67 | 0 | 0 | 0 | 0 | 0 | 163.5 | 163.5 | 0 | 163.5 | 0 | 163.5 | HR | 54 | 51 | 9 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1240-S | IPCRP1 | IPCRP1 | 2000-1240 | Job Site Fuel & Maintenance | N | S |  | UNIT | P | 0 | 2646465.76 | 2646465.76 | 2646465.76 | 2646465.76 | 66.1616 | 0 | 0 | 0 | 1353534.24 | Y | 4000000 | Y | -4000000 | 0 | 0 | 0 | 0 | 0 | 4000000 | Y | -4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4000000 | 387.4 | 0 | 4000000 | 0 | 0 | 0 | 0 | 387.4 | 0 | -4000000 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 3312639.07 | 3312639.07 | 0 | 3806925.74 | -494286.67 | 3312639.07 | NA | 54 | 51 | 9 | 60 | MO | 2646465.76 | 0 | 2646465.76 | 1353534.24
Y | IPCRP1-2000-1245-C | IPCRP1 | IPCRP1 | 2000-1245 | CAC Project Support | N | C |  | UNIT | U | 0 | 5206936.25 | 5206936.25 | 5206936.25 | 5206936.25 | 96.9497 | 0 | 0 | 0 | 163822.25 | Y | 5370758.5 | Y | -5370758.5 | 0 | 0 | 0 | 0 | 0 | 5370758.5 | Y | -5370758.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5370758.5 | -33907.16 | 45000 | 5370758.5 | 0 | 0 | 0 | 0 | 0 | 0 | -5370758.5 | 0 | 0 | 5370758.5 | 5370758.5 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 0 | 3 | NA | 1 | 0.87 | 0.13 | 1 | LS | 0 | 0 | 0 | 163822.25 | CAC LS Equip Agree ($4,277,583.00) + CFW P1 (167K) + CFW P2 (136K) + CFW P3 (36K) + JB900 2022 ($82,584.54) + JB900 2023 ($201,184.99) + JB90 2024 ($233,392.31). TTD = $5,133,744.84. Old note is CAC LS Equipment Agreement ($4,277,583.00) over 48 months Extra Work - Carbon Fiber Work for CE in Reaches A/B ($167,000.00) Extra Work - 2022 JB900(CE) Equipment Costs ($82,584.54)
Y | IPCRP1-2000-1245-E | IPCRP1 | IPCRP1 | 2000-1245 | CAC Project Support | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.87 | 0.13 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-2000-1245-L | IPCRP1 | IPCRP1 | 2000-1245 | CAC Project Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.87 | 0.13 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0001-L | IPCRP1 | IPCRP1 | 3000-0001 | Correct Undermining at CH Bridge EA | N | L |  | UNIT | P | 0 | 23949.55 | 23949.55 | 23949.55 | 23949.55 | 100 | 0 | 0 | 0 | 0 | Y | 23949.55 | Y | -23949.55 | 0 | 0 | 0 | 0 | 0 | 23949.55 | Y | -23949.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23949.55 | 0 | 0 | 23949.55 | 0 | 0 | 0 | 0 | 0 | 0 | -23949.55 | 0 | 0 | 23949.55 | 23949.55 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 200 | 0 | 200 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0002-L | IPCRP1 | IPCRP1 | 3000-0002 | Fix Hydrant IPC Damaged | N | L |  | UNIT | P | 0 | 1677.96 | 1677.96 | 1677.96 | 1677.96 | 100 | 0 | 0 | 0 | 0 | Y | 1677.96 | Y | -1677.96 | 0 | 0 | 0 | 0 | 0 | 1677.96 | Y | -1677.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1677.96 | 0 | 0 | 1677.96 | 0 | 0 | 0 | 0 | 0 | 0 | -1677.96 | 0 | 0 | 1677.96 | 1677.96 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 12 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0003-L | IPCRP1 | IPCRP1 | 3000-0003 | Replacement of Removed P-42 Electrical Boxes | N | L |  | UNIT | P | 0 | 8070.57 | 8070.57 | 8070.57 | 8070.57 | 100 | 0 | 0 | 0 | 0 | Y | 8070.57 | Y | -8070.57 | 0 | 0 | 0 | 0 | 0 | 8070.57 | Y | -8070.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8070.57 | 0 | 0 | 8070.57 | 0 | 0 | 0 | 0 | 0 | 0 | -8070.57 | 0 | 0 | 8070.57 | 8070.57 | 0 | 0 | 0 | 0 | 0 | 41.5 | 41.5 | 0 | 41.5 | 0 | 41.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0003-S | IPCRP1 | IPCRP1 | 3000-0003 | Replacement of Removed P-42 Electrical Boxes | N | S |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0004-C | IPCRP1 | IPCRP1 | 3000-0004 | Replace Pedestals at Piers 2-5, Low Breaks | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 18 | 0 | 18 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0004-L | IPCRP1 | IPCRP1 | 3000-0004 | Replace Pedestals at Piers 2-5, Low Breaks | N | L |  | UNIT | P | 0 | 19459.76 | 19459.76 | 19459.76 | 19459.76 | 100 | 0 | 0 | 0 | 0 | Y | 19459.76 | Y | -19459.76 | 0 | 0 | 0 | 0 | 0 | 19459.76 | Y | -19459.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19459.76 | 0 | 0 | 19459.76 | 0 | 0 | 0 | 0 | 0 | 0 | -19459.76 | 0 | 0 | 19459.76 | 19459.76 | 0 | 0 | 0 | 0 | 0 | 167 | 167 | 0 | 167 | 0 | 167 | HR | 0 | 18 | 0 | 18 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0004-M | IPCRP1 | IPCRP1 | 3000-0004 | Replace Pedestals at Piers 2-5, Low Breaks | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 18 | 0 | 18 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0005-C | IPCRP1 | IPCRP1 | 3000-0005 | Repair to Damaged Exist Reg Chamber M-32 | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0005-L | IPCRP1 | IPCRP1 | 3000-0005 | Repair to Damaged Exist Reg Chamber M-32 | N | L |  | UNIT | P | 0 | 4533.69 | 4533.69 | 4533.69 | 4533.69 | 100 | 0 | 0 | 0 | 0 | Y | 4533.69 | Y | -4533.69 | 0 | 0 | 0 | 0 | 0 | 4533.69 | Y | -4533.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4533.69 | 0 | 0 | 4533.69 | 0 | 0 | 0 | 0 | 0 | 0 | -4533.69 | 0 | 0 | 4533.69 | 4533.69 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 0 | 33 | 0 | 33 | HR | 0 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0006-C | IPCRP1 | IPCRP1 | 3000-0006 | Repair Gaps in Combi Wall (B/C to Skanska) | N | C |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0006-L | IPCRP1 | IPCRP1 | 3000-0006 | Repair Gaps in Combi Wall (B/C to Skanska) | N | L |  | UNIT | P | 0 | 35847.35 | 35847.35 | 35847.35 | 35847.35 | 100 | 0 | 0 | 0 | 0 | Y | 35847.35 | Y | -35847.35 | 0 | 0 | 0 | 0 | 0 | 35847.35 | Y | -35847.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -35847.35 | 0 | 0 | 35847.35 | 0 | 0 | 0 | 0 | 0 | 0 | -35847.35 | 0 | 0 | 35847.35 | 35847.35 | 0 | 0 | 0 | 0 | 0 | 247 | 247 | 0 | 247 | 0 | 247 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0006-S | IPCRP1 | IPCRP1 | 3000-0006 | Repair Gaps in Combi Wall (B/C to Skanska) | N | S |  | UNIT | A | 0 | 253.32 | 253.32 | 253.32 | 253.32 | 100 | 0 | 0 | 0 | 0 | N | 253.32 | N | -253.32 | 0 | 0 | 0 | 0 | 0 | 253.32 | N | -253.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -253.32 | 0 | 0 | 253.32 | 0 | 0 | 0 | 0 | 0 | 0 | -253.32 | 0 | 0 | 253.32 | 253.32 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | NA | 0 | 0 | 1 | 1 | LS | 253.32 | 0 | 253.32 | 0
Y | IPCRP1-3000-0007-L | IPCRP1 | IPCRP1 | 3000-0007 | Replace NW Stairway at Fire Boat House | N | L |  | UNIT | P | 0 | 53455.07 | 53455.07 | 53455.07 | 53455.07 | 100 | 0 | 0 | 0 | 0 | Y | 53455.07 | Y | -53455.07 | 0 | 0 | 0 | 0 | 0 | 53455.07 | Y | -53455.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -53455.07 | 0 | 0 | 53455.07 | 0 | 0 | 0 | 0 | 0 | 0 | -53455.07 | 0 | 0 | 53455.07 | 53455.07 | 0 | 0 | 0 | 0 | 0 | 430.5 | 430.5 | 0 | 430.5 | 0 | 430.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0008-L | IPCRP1 | IPCRP1 | 3000-0008 | Repair Damaged Exist DEP MH 3315 & Pipe in Reach G | N | L |  | UNIT | P | 0 | 14400.25 | 14400.25 | 14400.25 | 14400.25 | 100 | 0 | 0 | 0 | 0 | Y | 14400.25 | Y | -14400.25 | 0 | 0 | 0 | 0 | 0 | 14400.25 | Y | -14400.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14400.25 | 0 | 0 | 14400.25 | 0 | 0 | 0 | 0 | 0 | 0 | -14400.25 | 0 | 0 | 14400.25 | 14400.25 | 0 | 0 | 0 | 0 | 0 | 59.5 | 59.5 | 0 | 59.5 | 0 | 59.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0009-L | IPCRP1 | IPCRP1 | 3000-0009 | Restoration Work to S. Embayment Combi Wall Cap | N | L |  | UNIT | P | 0 | 110252.92 | 110252.92 | 110252.92 | 110252.92 | 100 | 0 | 0 | 0 | 0 | N | 110252.92 | N | -110252.92 | 0 | 0 | 0 | 0 | 0 | 110252.92 | N | -110252.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -110252.92 | 0 | 0 | 110252.92 | 0 | 0 | 0 | 0 | 0 | 0 | -110252.92 | 0 | 0 | 110252.92 | 110252.92 | 0 | 0 | 0 | 0 | 0 | 950.5 | 950.5 | 0 | 950.5 | 0 | 950.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0009-S | IPCRP1 | IPCRP1 | 3000-0009 | Restoration Work to S. Embayment Combi Wall Cap | N | S |  | UNIT | A | 0 | 3165.51 | 3165.51 | 3165.51 | 3165.51 | 100 | 0 | 0 | 0 | 0 | N | 3165.51 | N | -3165.51 | 0 | 0 | 0 | 0 | 0 | 3165.51 | N | -3165.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3165.51 | 0 | 0 | 3165.51 | 0 | 0 | 0 | 0 | 0 | 0 | -3165.51 | 0 | 0 | 3165.51 | 3165.51 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 7 | NA | 0 | 1 | 0 | 1 | LS | 3165.51 | 0 | 3165.51 | 0
Y | IPCRP1-3000-0010-L | IPCRP1 | IPCRP1 | 3000-0010 | Type II Foundation Rework at Delancey | N | L |  | UNIT | P | 0 | 4134.65 | 4134.65 | 4134.65 | 4134.65 | 100 | 0 | 0 | 0 | 0 | Y | 4134.65 | Y | -4134.65 | 0 | 0 | 0 | 0 | 0 | 4134.65 | Y | -4134.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4134.65 | 0 | 0 | 4134.65 | 0 | 0 | 0 | 0 | 0 | 0 | -4134.65 | 0 | 0 | 4134.65 | 4134.65 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 35 | 0 | 35 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Doesnot display in the report
Y | IPCRP1-3000-0011-L | IPCRP1 | IPCRP1 | 3000-0011 | Rem & Replace Conc Paver Base for Pavers (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0012-L | IPCRP1 | IPCRP1 | 3000-0012 | Replacement of LP Footing LP-D401 (RFI#950) | N | L |  | UNIT | P | 13000 | 3725.6 | 3725.6 | 3725.6 | 3725.6 | 100 | 0 | 0 | 0 | 0 | Y | 3725.6 | Y | 9274.4 | 0 | 0 | 13000 | 0 | 0 | 3725.6 | Y | 9274.4 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3725.6 | 0 | 0 | 3725.6 | 0 | 0 | 0 | 0 | 0 | 0 | -3725.6 | 0 | 0 | 3725.6 | 3725.6 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 1 | 29 | 0 | 29 | HR | 1 | 4 | 0 | 4 | EA | 0 | 0 | 0 | 0 | As per RFI #950, we are to remove top 5’ of existing LP can/ foundation, and replace with spread footing in correct location.
Y | IPCRP1-3000-0013-L | IPCRP1 | IPCRP1 | 3000-0013 | Rem-Replace 5 Inch Base Concrete Placed Incorrectl | N | L |  | UNIT | P | 0 | 12473.27 | 12473.27 | 12473.27 | 12473.27 | 100 | 0 | 0 | 0 | 0 | Y | 12473.27 | Y | -12473.27 | 0 | 0 | 0 | 0 | 0 | 12473.27 | Y | -12473.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12473.27 | 0 | 0 | 12473.27 | 0 | 0 | 0 | 0 | 0 | 0 | -12473.27 | 0 | 0 | 12473.27 | 12473.27 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 110 | 0 | 110 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-0014-L | IPCRP1 | IPCRP1 | 3000-0014 | Remove & Replace of 130’ of Curb in CH Park | N | L |  | UNIT | P | 0 | 10729.24 | 10729.24 | 10729.24 | 10729.24 | 100 | 0 | 0 | 0 | 0 | Y | 10729.24 | Y | -10729.24 | 0 | 0 | 0 | 0 | 0 | 10729.24 | Y | -10729.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10729.24 | 0 | 0 | 10729.24 | 0 | 0 | 0 | 0 | 0 | 0 | -10729.24 | 0 | 0 | 10729.24 | 10729.24 | 0 | 0 | 0 | 0 | 0 | 71 | 71 | 0 | 71 | 0 | 71 | HR | 0 | 130 | 0 | 130 | FT | 0 | 0 | 0 | 0
Y | IPCRP1-3000-1015-L | IPCRP1 | IPCRP1 | 3000-1015 | Furn & Reset P42 Flood Gate Base Plate (RFI#1054) | N | L |  | UNIT | P | 0 | 6133.89 | 6133.89 | 6133.89 | 6133.89 | 100 | 0 | 0 | 0 | 0 | Y | 6133.89 | Y | -6133.89 | 0 | 0 | 0 | 0 | 0 | 6133.89 | Y | -6133.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6133.89 | 0 | 0 | 6133.89 | 0 | 0 | 0 | 0 | 0 | 0 | -6133.89 | 0 | 0 | 6133.89 | 6133.89 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 45 | 0 | 45 | HR | 0 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-3000-1015-M | IPCRP1 | IPCRP1 | 3000-1015 | Furn & Reset P42 Flood Gate Base Plate (RFI#1054) | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-3000-1016-L | IPCRP1 | IPCRP1 | 3000-1016 | Remove Damaged Exp. Agg Sidewalk (By IPC/Others | N | L |  | UNIT | P | 0 | 9886.54 | 9886.54 | 9886.54 | 9886.54 | 76.0503 | 0 | 0 | 0 | 3113.46 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 84.5 | 15.5 | 100 | HR | 0 | 0.28 | 0.72 | 1 | LS | 0 | 0 | 0 | 3113.46
Y | IPCRP1-3000-1016-S | IPCRP1 | IPCRP1 | 3000-1016 | Remove Damaged Exp. Agg Sidewalk (By IPC/Others | N | S |  | UNIT | A | 0 | 104000 | 104000 | 54463.72 | 104000 | 52.369 | 0 | 0 | 0 | 0 | Y | 104000 | Y | -104000 | 0 | 0 | 0 | 0 | 0 | 104000 | Y | -104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -104000 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | -104000 | 0 | 0 | 104000 | 104000 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 2036.22 | -36.22 | 2000 | NA | 0 | 0.28 | 0.72 | 1 | LS | 104000 | 49536.28 | 54463.72 | 0
Y | IPCRP1-3000-1017-L | IPCRP1 | IPCRP1 | 3000-1017 | Efforts to Combat & Remove Graffiti | N | L |  | UNIT | P | 0 | 38282.7 | 38282.7 | 38282.7 | 38282.7 | 58.8601 | 0 | 0 | 0 | 26757.41 | Y | 65040.11 | Y | -65040.11 | 0 | 0 | 0 | 0 | 0 | 65040.11 | Y | -65040.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -65040.11 | 0 | 0 | 65040.11 | 0 | 0 | 0 | 0 | 0 | 0 | -65040.11 | 0 | 0 | 65040.11 | 65040.11 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 333 | 167 | 500 | HR | 0 | 333 | 167 | 500 | HR | 0 | 0 | 0 | 26757.41
Y | IPCRP1-3000-1017-S | IPCRP1 | IPCRP1 | 3000-1017 | Efforts to Combat & Remove Graffiti | N | S |  | UNIT | A | 0 | 1504.52 | 1504.52 | 1504.52 | 1504.52 | 100 | 0 | 0 | 0 | 0 | N | 1504.52 | N | -1504.52 | 0 | 0 | 0 | 0 | 0 | 1504.52 | N | -1504.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1504.52 | 0 | 0 | 1504.52 | 0 | 0 | 0 | 0 | 0 | 0 | -1504.52 | 0 | 0 | 1504.52 | 1504.52 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 12 | NA | 0 | 333 | 167 | 500 | HR | 1504.52 | 0 | 1504.52 | 0
Y | IPCRP1-3000-1018-L | IPCRP1 | IPCRP1 | 3000-1018 | Modify/Extend LP Found to Correct Elevation | N | L |  | UNIT | P | 0 | 4166.22 | 4166.22 | 4166.22 | 4166.22 | 32.0478 | 0 | 0 | 0 | 8833.78 | Y | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 13000 | Y | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 0 | 30 | 100 | 130 | HR | 0 | 4 | 6 | 10 | EA | 0 | 0 | 0 | 8833.78
Y | IPCRP1-3000-1020-L | IPCRP1 | IPCRP1 | 3000-1020 | Relocate CE Elect/Gas at E10th, IPC Layout Issue | N | L |  | UNIT | P | 0 | 14286.39 | 14286.39 | 14286.39 | 14286.39 | 100 | 0 | 0 | 0 | 0 | Y | 14286.39 | Y | -14286.39 | 0 | 0 | 0 | 0 | 0 | 14286.39 | Y | -14286.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14286.39 | 0 | 0 | 14286.39 | 0 | 0 | 0 | 0 | 0 | 0 | -14286.39 | 0 | 0 | 14286.39 | 14286.39 | 0 | 0 | 0 | 0 | 0 | 108 | 108 | 0 | 108 | 0 | 108 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-3000-1020-S | IPCRP1 | IPCRP1 | 3000-1020 | Relocate CE Elect/Gas at E10th, IPC Layout Issue | N | S |  | UNIT | A | 0 | 6593.84 | 6593.84 | 6593.84 | 6593.84 | 100 | 0 | 0 | 0 | 0 | N | 6593.84 | N | -6593.84 | 0 | 0 | 0 | 0 | 0 | 6593.84 | N | -6593.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6593.84 | 0 | 0 | 6593.84 | 0 | 0 | 0 | 0 | 0 | 0 | -6593.84 | 0 | 0 | 6593.84 | 6593.84 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 0 | 53 | 0 | 53 | NA | 0 | 1 | 0 | 1 | LS | 6593.84 | 0 | 6593.84 | 0
Y | IPCRP1-3000-1025-L | IPCRP1 | IPCRP1 | 3000-1025 | Rem & Replace 165’ Park Curb in Reach F | N | L |  | UNIT | P | 0 | 9231.45 | 9231.45 | 9231.45 | 9231.45 | 100 | 0 | 0 | 0 | 0 | Y | 9231.45 | Y | -9231.45 | 0 | 0 | 0 | 0 | 0 | 9231.45 | Y | -9231.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9231.45 | 0 | 0 | 9231.45 | 0 | 0 | 0 | 0 | 0 | 0 | -9231.45 | 0 | 0 | 9231.45 | 9231.45 | 0 | 0 | 0 | 0 | 0 | 78 | 78 | 0 | 78 | 0 | 78 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Due to Survey Error, 2” Reveal vs Flush Mounted Curb, clover leaf between N Tennis Court & Field 4
Y | IPCRP1-3000-1025-S | IPCRP1 | IPCRP1 | 3000-1025 | Rem & Replace 165’ Park Curb in Reach F | N | S |  | UNIT | A | 0 | 765.17 | 765.17 | 765.17 | 765.17 | 100 | 0 | 0 | 0 | 0 | N | 765.17 | N | -765.17 | 0 | 0 | 0 | 0 | 0 | 765.17 | N | -765.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -765.17 | 0 | 0 | 765.17 | 0 | 0 | 0 | 0 | 0 | 0 | -765.17 | 0 | 0 | 765.17 | 765.17 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | NA | 1 | 1 | 0 | 1 | LS | 765.17 | 0 | 765.17 | 0
Y | IPCRP1-3000-1030-C | IPCRP1 | IPCRP1 | 3000-1030 | F, D, I, R Stairs to Skanska Field Office | N | C |  | UNIT | U | 0 | 963.54 | 963.54 | 963.54 | 963.54 | 100 | 0 | 0 | 0 | 0 | Y | 963.54 | Y | -963.54 | 0 | 0 | 0 | 0 | 0 | 963.54 | Y | -963.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -963.54 | 0 | 0 | 963.54 | 0 | 0 | 0 | 0 | 0 | 0 | -963.54 | 0 | 0 | 963.54 | 963.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -3 | 0 | NA | 0 | 1 | 0 | 1 | LS | 963.54 | 0 | 963.54 | 0 | Another user is updating data for this Contract, Year and Period. Try again later.
Y | IPCRP1-3000-1030-L | IPCRP1 | IPCRP1 | 3000-1030 | F, D, I, R Stairs to Skanska Field Office | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0 | Refer to VS email to SC 11/13/25. Thought stairs were lost, we found & are sending back stairs to Cassone.
N | IPCRP1-3000-1035-L | IPCRP1 | IPCRP1 | 3000-1035 | Reach B Floodwall Blowout 4/3/26 | N | L |  | UNIT | P | 0 | 15770.19 | 15770.19 | 15770.19 | 15770.19 | 100 | 0 | 0 | 0 | 0 | N | 15770.19 | N | -15770.19 | 0 | 0 | 0 | 0 | 0 | 15770.19 | N | -15770.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15770.19 | 15770.19 | 0 | 0 | -15770.19 | 0 | 0 | 0 | 0 | 0 | -15770.19 | 0 | 0 | 15770.19 | 15770.19 | 0 | 0 | 0 | 0 | 0 | 108.5 | 108.5 | 0 | 108.5 | 0 | 108.5 | HR | 0 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
N | IPCRP1-3000-1035-S | IPCRP1 | IPCRP1 | 3000-1035 | Reach B Floodwall Blowout 4/3/26 | N | S |  | UNIT | A | 0 | 1872.45 | 1872.45 | 1872.45 | 1872.45 | 100 | 0 | 0 | 0 | 0 | N | 1872.45 | N | -1872.45 | 0 | 0 | 0 | 0 | 0 | 1872.45 | N | -1872.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1872.45 | 1872.45 | 0 | 1872.45 | 0 | 0 | 0 | 0 | 1872.45 | 0 | -1872.45 | 0 | 0 | 1872.45 | 1872.45 | 0 | 0 | 0 | 0 | 0 | 14.5 | 14.5 | 0 | 0 | 14.5 | 14.5 | NA | 0 | 1 | 0 | 1 | LS | 1872.45 | 0 | 1872.45 | 0
Y | IPCRP1-5011-0000-R | IPCRP1 | IPCRP1 | 5011-0000 | CO# 1.1 VECP No. 1 Design Cost (Sewer Found Redesi | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 193350 | 0 | 0 | 193350 | 0 | 193350 | 193350 | 0 | N | 193350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5012-0000-R | IPCRP1 | IPCRP1 | 5012-0000 | CO# 1.2 VECP No. 1 Const Cost Savings (Sewer Found | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 8897799.43 | 0 | 0 | 8897799.43 | 0 | 8897799.43 | 6141583.44 | 0 | N | 8897799.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8897799.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5013-0000-R | IPCRP1 | IPCRP1 | 5013-0000 | CO# 1.3 Structural Steel H-Piles | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5021-0000-R | IPCRP1 | IPCRP1 | 5021-0000 | DO NOT USE | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -9091149.43 | 0 | 0 | -9091149.43 | 0 | -9091149.43 | 154533.21 | 0 | N | -9091149.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9091149.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-5022-0000-R | IPCRP1 | IPCRP1 | 5022-0000 | CO# 2.2 VECP No. 3 Const Cost Savings (H Piles for | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1020462.5 | 0 | 0 | 1020462.5 | 0 | 1020462.5 | 696403.9 | 0 | N | 1020462.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020462.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5023-0000-R | IPCRP1 | IPCRP1 | 5023-0000 | CO #2/ VECP #3 Structural Steel H-Piles | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 3342675 | 0 | 0 | 3342675 | 0 | 3342675 | 388757.25 | 0 | N | 3342675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3342675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5024-0000-R | IPCRP1 | IPCRP1 | 5024-0000 | CO #2/ VECP #3 Mini-Piles (Grouted) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -4113137.5 | 0 | 0 | -4113137.5 | 0 | -4113137.5 | 0 | 0 | N | -4113137.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4113137.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5025-0000-R | IPCRP1 | IPCRP1 | 5025-0000 | CO #2/ VECP #3 Mini-Piles, Load Test | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -250000 | 0 | 0 | -250000 | 0 | -250000 | 0 | 0 | N | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5031-0000-R | IPCRP1 | IPCRP1 | 5031-0000 | CO #3 Rem of 84in D, Conc filed Steel Casing Aroun | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 26535.26 | 0 | 0 | 26535.26 | 0 | 26535.26 | 26535.26 | 0 | N | 26535.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26535.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5041-0000-R | IPCRP1 | IPCRP1 | 5041-0000 | CO #4 Abatement of ACM encountered in Exist Aband | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 988868 | 0 | 0 | 988868 | 0 | 988868 | 988868 | 0 | N | 988868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5051-0000-R | IPCRP1 | IPCRP1 | 5051-0000 | CO #5.1 PCO #20/ RFI #148 Pedestrian Bridge Knuckl | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 72237.13 | 0 | 0 | 72237.13 | 0 | 72237.13 | 67662.83 | 0 | N | 72237.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72237.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5052-0000-R | IPCRP1 | IPCRP1 | 5052-0000 | CO #5.2 PCO #24/ RFI #105 Arch Rib Addeded Stiffen | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 38084.76 | 0 | 0 | 38084.76 | 0 | 38084.76 | 35675.56 | 0 | N | 38084.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38084.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5053-0000-R | IPCRP1 | IPCRP1 | 5053-0000 | CO #5.3 PCO #27/ RFI #128 Revised Girder Profile | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6112.4 | 0 | 0 | 6112.4 | 0 | 6112.4 | 4400 | 0 | N | 6112.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6112.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5054-0000-R | IPCRP1 | IPCRP1 | 5054-0000 | CO #5.4 PCO #35 / RFI #211 CHB Upper Lateral Braci | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 18757.73 | 0 | 0 | 18757.73 | 0 | 18757.73 | 17134.17 | 0 | N | 18757.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18757.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5055-0000-R | IPCRP1 | IPCRP1 | 5055-0000 | CO #5.5 PCO #56/ RFI #070 Pedestran Bridges Floorb | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 5251.66 | 0 | 0 | 5251.66 | 0 | 5251.66 | 3225.72 | 0 | N | 5251.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5251.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5061-0000-R | IPCRP1 | IPCRP1 | 5061-0000 | CO #7 Television Inspection & Digital A-V Recordin | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 62150.12 | 0 | 0 | 62150.12 | 0 | 62150.12 | 37097.9 | 0 | N | 62150.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62150.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5071-0000-R | IPCRP1 | IPCRP1 | 5071-0000 | CO #8.1 VECP No. 6 Overall Redesign Construction | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 4025010 | 0 | 0 | 4025010 | 0 | 4025010 | 4025010 | 0 | N | 4025010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4025010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5072-0000-R | IPCRP1 | IPCRP1 | 5072-0000 | CO #8.2 VECP No. 6 Construction Cost Savings (LHR) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 951285.5 | 0 | 0 | 951285.5 | 0 | 951285.5 | 951285.5 | 0 | N | 951285.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951285.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5073-0000-R | IPCRP1 | IPCRP1 | 5073-0000 | CO #8/ VECP #6 VECP No. 6 Design Cost (LHR) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 96250 | 0 | 0 | 96250 | 0 | 96250 | 96250 | 0 | N | 96250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5074-0000-R | IPCRP1 | IPCRP1 | 5074-0000 | CO #8/ VECP #6 Epoxy Coated Steel Reinforcement | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -145.5 | 0 | 0 | -145.5 | 0 | -145.5 | 0 | 0 | N | -145.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -145.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5075-0000-R | IPCRP1 | IPCRP1 | 5075-0000 | CO #8/ VECP #6 Coated AZ-46-700N or Eq St Sheet Pi | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -5072400 | 0 | 0 | -5072400 | 0 | -5072400 | 0 | 0 | N | -5072400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5076-0000-R | IPCRP1 | IPCRP1 | 5076-0000 | CO-08 12.75" x 0.5'' St Pipe Pile, Laterial Load T | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5077-0000-R | IPCRP1 | IPCRP1 | 5077-0000 | CO-08 12.75" OD x 0.50" Wall Thickness Micropile ( | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5078-0000-R | IPCRP1 | IPCRP1 | 5078-0000 | CO-08 Pile Load Test, 12.75" OD x 0.50" Wall MP, S | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5079-0000-R | IPCRP1 | IPCRP1 | 5079-0000 | CO-08 Pile Load Test, 12.75" OD x 0.50" Wall MP, T | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5081-0000-R | IPCRP1 | IPCRP1 | 5081-0000 | CO #9 Existing Outfall Differenting Site Condition | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 105602 | 0 | 0 | 105602 | 0 | 105602 | 105602 | 0 | N | 105602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5091-0000-R | IPCRP1 | IPCRP1 | 5091-0000 | CO #10 Change in Design, Rock Socket at Pipe-Pipe | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 258800 | 0 | 0 | 258800 | 0 | 258800 | 258800 | 0 | N | 258800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5101-0000-R | IPCRP1 | IPCRP1 | 5101-0000 | CO #11 Modif to Ped Bridge Painting (RFI#115) Chan | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 117269.07 | 0 | 0 | 117269.07 | 0 | 117269.07 | 78569.61 | 0 | N | 117269.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117269.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5111-0000-R | IPCRP1 | IPCRP1 | 5111-0000 | CO #12 Rem & Demo Exist Relief Slab w/in Phase 1 C | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 980085.69 | 0 | 0 | 980085.69 | 0 | 980085.69 | 980085.69 | 0 | N | 980085.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980085.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5121-0000-R | IPCRP1 | IPCRP1 | 5121-0000 | CO #13/ VECP #2 Helical Piles (Galvanized, Grouted | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 6810930 | 0 | 0 | 6810930 | 0 | 6810930 | 5756181.1 | 0 | N | 6810930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6810930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5122-0000-R | IPCRP1 | IPCRP1 | 5122-0000 | CO #13.1 VECP No. 2 VECP Design Cost (Helical Pile | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 7500 | 0 | 0 | 7500 | 0 | 7500 | 7500 | 0 | N | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5123-0000-R | IPCRP1 | IPCRP1 | 5123-0000 | CO #13.2 VECP No. 2 VECP Const Cost Savings (Helic | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 1749300 | 0 | 0 | 1749300 | 0 | 1749300 | 1478401.27 | 0 | N | 1749300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1749300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5124-0000-R | IPCRP1 | IPCRP1 | 5124-0000 | CO #13/ VECP #2 Mini-Piles (Grouted) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -2878201.2 | 0 | 0 | -2878201.2 | 0 | -2878201.2 | 0 | 0 | N | -2878201.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2878201.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5125-0000-R | IPCRP1 | IPCRP1 | 5125-0000 | DO NOT USE | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -2993050 | 0 | 0 | -2993050 | 0 | -2993050 | 0 | 0 | N | -2993050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2993050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-5126-0000-R | IPCRP1 | IPCRP1 | 5126-0000 | DO NOT USE | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | -2696480 | 0 | 0 | -2696480 | 0 | -2696480 | 0 | 0 | N | -2696480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2696480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-5131-0000-R | IPCRP1 | IPCRP1 | 5131-0000 | CO #14 PCO #72 - Add Ex Sewer Outfall Changed Cond | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464195.15 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-5131-R | IPCRP1 | IPCRP1 | 5131 | Do not use | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 464195.15 | 0 | 0 | 464195.15 | 0 | 464195.15 | 0 | 0 | N | 464195.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464195.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5141-0000-R | IPCRP1 | IPCRP1 | 5141-0000 | CO #15 PCO #070 - Repl Grand St Ferry Pull Box on | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 43093.05 | 0 | 0 | 43093.05 | 0 | 43093.05 | 43093.05 | 0 | N | 43093.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43093.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5161-0000-R | IPCRP1 | IPCRP1 | 5161-0000 | VECP No. 4. Remove Structural Concrete - Replace w | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051939.5 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5162-0000-R | IPCRP1 | IPCRP1 | 5162-0000 | VECP No. 4. Revised Design for Type E.P. Bearing ( | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314500 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5163-0000-R | IPCRP1 | IPCRP1 | 5163-0000 | VECP No. 4. Ultra High Performance Concrete | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3407616.86 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CF | 0 | 0 | 0 | 0 | CF | 0 | 0 | 0 | 0
Y | IPCRP1-5164-0000-R | IPCRP1 | IPCRP1 | 5164-0000 | VECP No. 4. Prestresed Concrete Esplanade Bulb Tee | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20626665.06 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5165-0000-R | IPCRP1 | IPCRP1 | 5165-0000 | VECP No 4 Construction Cost Saving | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414070.08 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5166-0000-R | IPCRP1 | IPCRP1 | 5166-0000 | VECP No 4 Design Cost Payment | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5167-0000-R | IPCRP1 | IPCRP1 | 5167-0000 | CO-016 Drilling and Grouting Bolts for Reinforceme | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321600 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5168-0000-R | IPCRP1 | IPCRP1 | 5168-0000 | CO. No. 16 VECP No. 4 Qnt. Negative | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5171-0000-R | IPCRP1 | IPCRP1 | 5171-0000 | PCO-063 Corlears Hooke Bridge Knuckle Handhole & S | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5172-0000-R | IPCRP1 | IPCRP1 | 5172-0000 | PCO 064 Pedestrian Bridge Paint Changes (RFI 145) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17905 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5181-0000-R | IPCRP1 | IPCRP1 | 5181-0000 | CR-0077 Additional Field Office - One Time Setup C | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5182-0000-R | IPCRP1 | IPCRP1 | 5182-0000 | CR-0077 Additional Field Office - Monthly Recurrin | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248975 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-5183-0000-R | IPCRP1 | IPCRP1 | 5183-0000 | CR-0077 Additional Field Office - Move Trailer Cha | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5191-0000-R | IPCRP1 | IPCRP1 | 5191-0000 | CR-0076A “Bulletin # 7 – Amphitheater Canopy Struc | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99200 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5201-0000-R | IPCRP1 | IPCRP1 | 5201-0000 | PCO#073 - NYCHA Utility Interference at East 10th | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399285 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5211-0000-R | IPCRP1 | IPCRP1 | 5211-0000 | VECP No 9 Construction Cost Saving (CO21) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440202.35 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-5212-0000-R | IPCRP1 | IPCRP1 | 5212-0000 | VECP No 9 Design Cost Payment (CO21) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-5213-0000-R | IPCRP1 | IPCRP1 | 5213-0000 | (CO. No. 21 VECP No. 9 Qnt. Negative | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Y | IPCRP1-5221-0000-R | IPCRP1 | IPCRP1 | 5221-0000 | CR-0087DOT Fiber Optic Conduit at Montgomery Stree | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83945.26 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5231-0000-R | IPCRP1 | IPCRP1 | 5231-0000 | VECP No.12 Design Cost Payment | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5232-0000-R | IPCRP1 | IPCRP1 | 5232-0000 | VECP No. 12 Construction Cost Saving | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23874.54 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5233-0000-R | IPCRP1 | IPCRP1 | 5233-0000 | 13" OD x 0.51" WALL THICKNESS MICROPILE" (VECP No. | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5234-0000-R | IPCRP1 | IPCRP1 | 5234-0000 | JET GROUTING FOR GATE AND FLOODWALL FOUNDATION (V | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954400 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5235-0000-R | IPCRP1 | IPCRP1 | 5235-0000 | CONCRETE FOR FLOODWALL AND GATES (VECP No.12) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80977 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5236-0000-R | IPCRP1 | IPCRP1 | 5236-0000 | CONCRETE FOR FLOODWALL AND GATES (CO. No. 23 VECP | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5237-0000-R | IPCRP1 | IPCRP1 | 5237-0000 | EPOXY-COATING STEEL REINFORCEMENT (VECP No.12) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16939.7 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5238-0000-R | IPCRP1 | IPCRP1 | 5238-0000 | EPOXY-COATING STEEL REINFORCEMENT (CO. No. 23 VECP | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5239-0000-R | IPCRP1 | IPCRP1 | 5239-0000 | COATED AZ-46-700N OR EQUAL STEEL SHEET PILE INSTAL | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5241-0000-R | IPCRP1 | IPCRP1 | 5241-0000 | VECP No.11 Design Cost Payment | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23250 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5242-0000-R | IPCRP1 | IPCRP1 | 5242-0000 | VECP No. 11 Construction Cost Saving | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5243-0000-R | IPCRP1 | IPCRP1 | 5243-0000 | 12.75" OD x 0.50" Wall Thickness Micropile (VECP N | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363187.5 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5244-0000-R | IPCRP1 | IPCRP1 | 5244-0000 | JET GROUTING FOR GATE AND FLOODWALL FOUNDATION (V | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166580 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5245-0000-R | IPCRP1 | IPCRP1 | 5245-0000 | CONCRETE FOR FLOODWALL AND GATES (VECP No.11) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5246-0000-R | IPCRP1 | IPCRP1 | 5246-0000 | EPOXY-COATING STEEL REINFORCEMENT (VECP No.11) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5247-0000-R | IPCRP1 | IPCRP1 | 5247-0000 | CO. No. 24 VECP No. 11 Qnt. Negative | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5251-0000-R | IPCRP1 | IPCRP1 | 5251-0000 | PCO#059 - Obstructions with Cathodic Protection In | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778386.33 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5261-0000-R | IPCRP1 | IPCRP1 | 5261-0000 | PCO#28 Pedestrian Bridges - Lower Lateral Bracing | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33957 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5271-0000-R | IPCRP1 | IPCRP1 | 5271-0000 | PCO#106 - Welding of Sliding Joint Closure Plate ( | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5281-0000-R | IPCRP1 | IPCRP1 | 5281-0000 | PCO #034 Corlears Hook Pedestrian Bridge Hanger to | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205644 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5282-0000-R | IPCRP1 | IPCRP1 | 5282-0000 | PCO #034 Delancey & E. 10 Str. Pedestrian Bridges | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205644 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5291-0000-R | IPCRP1 | IPCRP1 | 5291-0000 | CO-029 PCO #071 Grand St Ferry Electric & Distribu | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5292-0000-R | IPCRP1 | IPCRP1 | 5292-0000 | CO-029 PCO No. 094 - East River Houses Service Box | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4268.87 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5301-0000-R | IPCRP1 | IPCRP1 | 5301-0000 | CO-030 Inspection of existing Pier 42 Project Hydr | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1706 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5302-0000-R | IPCRP1 | IPCRP1 | 5302-0000 | CO-030 Cleaning of existing Pier 42 Project Hydrod | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5303-0000-R | IPCRP1 | IPCRP1 | 5303-0000 | CO-030 Debris disposal from the existing Pier 42 P | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-5311-0000-R | IPCRP1 | IPCRP1 | 5311-0000 | CO-031 PCO #107 Rebar Detailing Additional Costs ( | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5312-0000-R | IPCRP1 | IPCRP1 | 5312-0000 | CO-031 PCO #107 Rebar Detailing Additional Costs ( | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48600 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5321-0000-R | IPCRP1 | IPCRP1 | 5321-0000 | CO32 PCO #085 Corlears Hook Pedestrian Bridge Fayi | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80562 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5322-0000-R | IPCRP1 | IPCRP1 | 5322-0000 | CO32 PCO #085 Delancy and East 10th Street Pedestr | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148908 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5331-0000-R | IPCRP1 | IPCRP1 | 5331-0000 | CO33 PCO #115 Temporary Decking During Sewer Recon | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142380 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5341-0000-R | IPCRP1 | IPCRP1 | 5341-0000 | CO34 PCO#117 Corlears Hook Pedestrian Bridge End F | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832.9 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5342-0000-R | IPCRP1 | IPCRP1 | 5342-0000 | CO34 PCO #119 East 10th Street Pedestrian Bridge - | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15687 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5351-0000-R | IPCRP1 | IPCRP1 | 5351-0000 | CO35 PCO #133 “Corlears Hook Pedestrian Bridge” Re | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36455 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5352-0000-R | IPCRP1 | IPCRP1 | 5352-0000 | CO35 PCO #133 "Delancey Street Pedestrian Bridge” | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262358.19 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5361-0000-R | IPCRP1 | IPCRP1 | 5361-0000 | CO36 PCO #128 Design Modifications to Floodgates | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64421.28 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5371-000-R | IPCRP1 | IPCRP1 | 5371-000 | DO NOT USE | N | R |  | UNIT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5371-0000-R | IPCRP1 | IPCRP1 | 5371-0000 | CO-37 One Work Area MPT - Weekday (M-T) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002585.92 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5372-0000-R | IPCRP1 | IPCRP1 | 5372-0000 | CO-37 One Work Area - MPT (Friday) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350819 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5373-0000-R | IPCRP1 | IPCRP1 | 5373-0000 | CO-37 One Work Area - MPT (Saturday) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28293.56 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5374-0000-R | IPCRP1 | IPCRP1 | 5374-0000 | CO-37 Two Work Areas MPT - Weekday (M-T) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762444.1 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5375-0000-R | IPCRP1 | IPCRP1 | 5375-0000 | CO-37 Two Work Areas - MPT (Friday) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111525.2 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5376-0000-R | IPCRP1 | IPCRP1 | 5376-0000 | CO-37 Two Work Areas - MPT (Saturday) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5377-0000-R | IPCRP1 | IPCRP1 | 5377-0000 | CO-37 F&I 8” IWM DI Cem Lined FDR North | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457000.02 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $ | 0 | 0 | 0 | 0 | $ | 0 | 0 | 0 | 0
Y | IPCRP1-5381-0000-R | IPCRP1 | IPCRP1 | 5381-0000 | CO-38 PCO No.084 Procedure Qual Rec (PQR) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90552 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5391-0000-R | IPCRP1 | IPCRP1 | 5391-0000 | CO-39 VECP No.14 Design Cost Payment | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5392-0000-R | IPCRP1 | IPCRP1 | 5392-0000 | CO-39 VECP No. 14 Construction Cost Saving | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5393-0000-R | IPCRP1 | IPCRP1 | 5393-0000 | CO-39 ESCR-551.993.9625RS - 9.625 IN 0.0. x 0.5 IN | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5394-0000-R | IPCRP1 | IPCRP1 | 5394-0000 | CO-39 ESCR-551.993.9625 Qty Negative | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5395-0000-R | IPCRP1 | IPCRP1 | 5395-0000 | CO-39 ESCR-551.993.9625C Qty Negative | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5401-0000-R | IPCRP1 | IPCRP1 | 5401-0000 | CO-40 PCO#109 Houston St Br Sheet App Waterproof | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5411-0000-R | IPCRP1 | IPCRP1 | 5411-0000 | CO-41 Con Ed fund trnsfr btw 70.13MN & JB 900(CE) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2325000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5412-0000-R | IPCRP1 | IPCRP1 | 5412-0000 | CO-41 70.13MN MINI-PILES (GROUTED) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5421-0000-R | IPCRP1 | IPCRP1 | 5421-0000 | CO-42 PCO#140 Rmv Exst Shtng MH#2 AVE D & E10th | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127078.69 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $ | 0 | 0 | 0 | 0 | $ | 0 | 0 | 0 | 0
Y | IPCRP1-5431-0000-R | IPCRP1 | IPCRP1 | 5431-0000 | CO#43 PCO #049 the Montgomery St. 108" Sewer Inter | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38673.53 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5441-0000-R | IPCRP1 | IPCRP1 | 5441-0000 | CO#44.1 (PCO#211) 70.12AN - CFA Piles | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90757 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5442-0000-R | IPCRP1 | IPCRP1 | 5442-0000 | CO#44.2 (PCO#211) 70.13MN Mini Piles Qnt. Neg. | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0 | VF | 0 | 0 | 0 | 0
Y | IPCRP1-5451-0000-R | IPCRP1 | IPCRP1 | 5451-0000 | CO#045 698.06 Steel & Iron Price Adj (PCO#237) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058322.84 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5461-0000-R | IPCRP1 | IPCRP1 | 5461-0000 | CO-046.1 PCO#126 - CH Ped Brdg Knuckle Intr Paintn | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74636 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5462-0000-R | IPCRP1 | IPCRP1 | 5462-0000 | CO-046.2 PCO#126 - Del St & E10th St Ped Brdg Knuc | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74128.04 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5463-0000-R | IPCRP1 | IPCRP1 | 5463-0000 | CO-046.3 PCO#130 - CH Pedestrian Brdg Mod Hanger S | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13138.33 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5471-0000-R | IPCRP1 | IPCRP1 | 5471-0000 | CO-047 PCO#122 - Add CVN Testing Fork Sockets | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10140.97 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5481-0000-R | IPCRP1 | IPCRP1 | 5481-0000 | CO-048 PCO#182 - Mod to Drain Struc #DS-45 RFI#920 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12120.23 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5491-0000-R | IPCRP1 | IPCRP1 | 5491-0000 | CO-049 PCO#131 - Extra Prem Marine Grd Purple Reba | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78786.51 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5501-0000-R | IPCRP1 | IPCRP1 | 5501-0000 | CO-050.1 PCO#044 R1 - Bulletin No. 3 Plumbing Chan | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856.23 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5502-0000-R | IPCRP1 | IPCRP1 | 5502-0000 | CO-050.2 PCO#170 - Bulletin#12 M&O#2 Building Mods | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5511-0000-R | IPCRP1 | IPCRP1 | 5511-0000 | CO-051 PCO#105 Rem of Concrete Obs at Prop S Embay | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24006.12 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5521-0000-R | IPCRP1 | IPCRP1 | 5521-0000 | CO-52.1 VECP No. 15 Design Cost Payment | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562.5 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5522-0000-R | IPCRP1 | IPCRP1 | 5522-0000 | CO-52.2 VECP No. 15 Construction Cost Saving | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5523-0000-R | IPCRP1 | IPCRP1 | 5523-0000 | CO-52.3 Jet Grout for Gate and FW Foundation VE#15 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5524-0000-R | IPCRP1 | IPCRP1 | 5524-0000 | CO-52.4 ESCR-551.993.1275 (New) 12.75" OD x 0.50" | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5525-0000-R | IPCRP1 | IPCRP1 | 5525-0000 | CO-52.5 - ESCR-2.FD Jet Grout for Gate and FW Foun | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5526-0000-R | IPCRP1 | IPCRP1 | 5526-0000 | CO-52.6 - ESCR-552.11 46CP Coated AZ-46-700N or Eq | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5531-0000-R | IPCRP1 | IPCRP1 | 5531-0000 | CO-053 PCO#172 - Item PK-ESCR 636, Bottle Filler w | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86500 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5541-0000-R | IPCRP1 | IPCRP1 | 5541-0000 | CO#054 PCO#123 - Unidentified Underground Storage | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72426.4 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5542-0000-R | IPCRP1 | IPCRP1 | 5542-0000 | CO#055.1 VECP No. 07 Design Cost | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117750 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5543-0000-R | IPCRP1 | IPCRP1 | 5543-0000 | CO#055.2 VECP No. 07 Construction Cost Savings | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5544-0000-R | IPCRP1 | IPCRP1 | 5544-0000 | CO#055.3 ESCR-4.06 HP ES Concrete for Esplanade (V | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5545-0000-R | IPCRP1 | IPCRP1 | 5545-0000 | CO#055.4 ESCR-4.14 Epoxy Coating Steel Reinforceme | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5546-0000-R | IPCRP1 | IPCRP1 | 5546-0000 | CO#055.5 ESCR-551.36.05 DT 36in Dia x 0.5 in Wall | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5547-0000-R | IPCRP1 | IPCRP1 | 5547-0000 | CO#055.6 ESCR-551.36.05.CS Coated 36 in Dia x 0.5 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5548-0000-R | IPCRP1 | IPCRP1 | 5548-0000 | CO#055.7 ESCR-551.36.05.CSD Coated 36 in Dia x 0.5 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5549-0000-R | IPCRP1 | IPCRP1 | 5549-0000 | CO#055.8 ESCR-551.42.05 DT 42 in Dia x 0.5 in Wall | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5550-0000-R | IPCRP1 | IPCRP1 | 5550-0000 | CO#055.9 ESCR-552.11 20 C - Coated AZ-20-700N or E | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5551-0000-R | IPCRP1 | IPCRP1 | 5551-0000 | CO#055.10 ESCR-551.22 3.0TR - 3.0" Dia Hot Dip Gal | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5552-0000-R | IPCRP1 | IPCRP1 | 5552-0000 | CO#055.11 ESCR-552.11 4219CI Coated PAZ42/NZ19 or | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5553-0000-R | IPCRP1 | IPCRP1 | 5553-0000 | CO#055.12 ESCR-564.G Structural Steel (Galvanized) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5554-0000-R | IPCRP1 | IPCRP1 | 5554-0000 | CO#055.13 ESCR-551.993.13375 - 13.375" OD x 0.514" | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5555-0000-R | IPCRP1 | IPCRP1 | 5555-0000 | CO#055.14 ESCR-551.993.13375C Pile Load Testing fo | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5556-0000-R | IPCRP1 | IPCRP1 | 5556-0000 | CO#055.15 ESCR-551.993.13375T Pile Load Testing fo | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5557-0000-R | IPCRP1 | IPCRP1 | 5557-0000 | CO#055.16 ESCR-211.11 Grouted Tiebacks (Permanent) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5558-0000-R | IPCRP1 | IPCRP1 | 5558-0000 | CO#055 Deduct ESCR-4.06 HP ES Concrete for Esplana | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5559-0000-R | IPCRP1 | IPCRP1 | 5559-0000 | CO#055 Deduct ESCR-4.14 Epoxy-Coating Steel Reinfo | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5560-0000-R | IPCRP1 | IPCRP1 | 5560-0000 | CO#055 Deduct ESCR-551.30.01 RS Rock Socket for 30 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5561-0000-R | IPCRP1 | IPCRP1 | 5561-0000 | CO#055 Deduct ESCR-551.30.01.C Coated 30in Dia x 1 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5562-0000-R | IPCRP1 | IPCRP1 | 5562-0000 | CO#055 Deduct ESCR-551.36.05.CS Coated 36in Dia x | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5563-0000-R | IPCRP1 | IPCRP1 | 5563-0000 | CO#055 Deduct ESCR-551.36.05.CSD Coated 36in Dia x | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5564-0000-R | IPCRP1 | IPCRP1 | 5564-0000 | CO#056.1 PCO#149 - E. 14th Street Pedestrian Gate | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5565-0000-R | IPCRP1 | IPCRP1 | 5565-0000 | CO#056.2 PCO#179 - Comments on FDR NB & SB Swing G | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21344.89 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5567-0000-R | IPCRP1 | IPCRP1 | 5567-0000 | CO#057 JB 900(CE) Extra Utility Work Cost Allowanc | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450474.41 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5568-0000-R | IPCRP1 | IPCRP1 | 5568-0000 | CO#057 Deduct JB 301(CE) Special Care Excavation a | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5569-0000-R | IPCRP1 | IPCRP1 | 5569-0000 | CO#057 Deduct JB 302(CE) Field Coating of Oil-O-St | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5570-0000-R | IPCRP1 | IPCRP1 | 5570-0000 | CO#057 Deduct JB 401(CE) Trench Excavation for Adj | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5571-0000-R | IPCRP1 | IPCRP1 | 5571-0000 | CO#057 Deduct JB 404A(CE) Permanent Support Requir | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5572-0000-R | IPCRP1 | IPCRP1 | 5572-0000 | CO#057 Deduct JB 410.1(CE) Mass Trench Excavation | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5573-0000-R | IPCRP1 | IPCRP1 | 5573-0000 | CO#057 Deduct JB 410.2(CE) Mass Trench Excavation | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5574-0000-R | IPCRP1 | IPCRP1 | 5574-0000 | CO#057 Deduct JB 620.12(CE) Install 24" Dia Steam | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5575-0000-R | IPCRP1 | IPCRP1 | 5575-0000 | CO#057 Deduct JB 621.12(CE) Install 24" Dia Steam | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5576-0000-R | IPCRP1 | IPCRP1 | 5576-0000 | CO#057 Deduct JB 622.36(CE) Furnishing, Delivering | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5577-0000-R | IPCRP1 | IPCRP1 | 5577-0000 | CO#057 Deduct JB 622.48(CE) Furnishing, Delivering | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5578-0000-R | IPCRP1 | IPCRP1 | 5578-0000 | CO#057 Deduct JB 625E(CE) Installation of Steam An | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5579-0000-R | IPCRP1 | IPCRP1 | 5579-0000 | CO#057 Deduct JB 625F(CE) Installation of Steam Ma | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5581-0000-R | IPCRP1 | IPCRP1 | 5581-0000 | CO#058.1 PCO#162(A) - Building 12 Water Service Ti | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8074.73 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5582-0000-R | IPCRP1 | IPCRP1 | 5582-0000 | CO#058.2 PCO#162(B) - Building 7 Water Service Tie | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29284.79 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5583-0000-R | IPCRP1 | IPCRP1 | 5583-0000 | CO#058.3 PCO#163 - Building 11 Water Service Tie-I | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22678.04 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5584-0000-R | IPCRP1 | IPCRP1 | 5584-0000 | CO#058.4 PCO#144 - Building 11 Sewer Tie-In | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5585-0000-R | IPCRP1 | IPCRP1 | 5585-0000 | CO#058.5 PCO#155 - Building 9 Sewer Tie | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32464.99 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5591-0000-R | IPCRP1 | IPCRP1 | 5591-0000 | CO#059.1 PCO No. 090A Concrete Sealer RFI 246 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266.15 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5592-0000-R | IPCRP1 | IPCRP1 | 5592-0000 | CO#059.2 PCO No. 090A Anti-Graffiti Coating RFI 24 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20790 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5593-0000-R | IPCRP1 | IPCRP1 | 5593-0000 | CO#059.3 PCO No. 090B Anti-graffiti coating and se | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121252.44 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5594-0000-R | IPCRP1 | IPCRP1 | 5594-0000 | CO#059 Deduct 559.16960118 PROTECTIVE SEALING OF S | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5595-0000-R | IPCRP1 | IPCRP1 | 5595-0000 | CO#059 Deduct 6.43 D DIGITAL PHOTOGRAPHS (CO. No. | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-5601-0000-R | IPCRP1 | IPCRP1 | 5601-0000 | CO#60 Item 698.06 Steel & Iron Price Adjustment (O | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5611-0000-R | IPCRP1 | IPCRP1 | 5611-0000 | CO#061 Additional Trailer of 80’ X 32’ (2,560.00 S | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72300 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5612-0000-R | IPCRP1 | IPCRP1 | 5612-0000 | CO#061 Qnt. Negative from CO 18.3 "CR-0077 Additio | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5621-0000-R | IPCRP1 | IPCRP1 | 5621-0000 | CO#062 PCO#199 - Phase 2 Existing Combined Sewer O | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5631-0000-R | IPCRP1 | IPCRP1 | 5631-0000 | CO#063.1 VECP No. 18 - Construction Cost Savings - | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526807.5 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5632-0000-R | IPCRP1 | IPCRP1 | 5632-0000 | CO#063.2 ESCR-2.FD Jet Grouting for Gate and Flood | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5650-R | IPCRP1 | IPCRP1 | 5650 | 5650 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-5651-0000-R | IPCRP1 | IPCRP1 | 5651-0000 | CO#65.1 Pre Clearing and IPC Support at Houston St | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2240619.9 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5652-0000-R | IPCRP1 | IPCRP1 | 5652-0000 | CO#65.2 Trucking and Disposal of Jet Grout Spoils | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150627.6 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-5653-0000-R | IPCRP1 | IPCRP1 | 5653-0000 | CO#65.3 Jet Grouting (Pilot Program) - To mitigate | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706860 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5654-0000-R | IPCRP1 | IPCRP1 | 5654-0000 | CO#65.4 Jet Grouting (Unobstructed) - To mitigate | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6792392.25 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5655-0000-R | IPCRP1 | IPCRP1 | 5655-0000 | CO#65.5 Jet Grouting (Obstructed) - To mitigate i | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664705.75 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5661-0000-R | IPCRP1 | IPCRP1 | 5661-0000 | CO#66.1 PCO No. 151 & PCO No. 230 - Rebar Detailin | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243.34 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5662-0000-R | IPCRP1 | IPCRP1 | 5662-0000 | CO#66.2 PCO No. 151 & PCO No. 230 - Rebar Detailin | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57321.74 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5671-0000-R | IPCRP1 | IPCRP1 | 5671-0000 | CO-067.1 PCO#198 - Fire Boat House Deck Remediatio | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5672-0000-R | IPCRP1 | IPCRP1 | 5672-0000 | CO-067.2 PCO#214 - Field Memo No. 9 - Fire Boat Ho | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5673-0000-R | IPCRP1 | IPCRP1 | 5673-0000 | CO-067.3 PCO#257 - Fire Boat House Seawall Extensi | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5681-0000-R | IPCRP1 | IPCRP1 | 5681-0000 | CO#68 PCO #125A - Bulletin 10 IWM DOB Permit Costs | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5691-0000-R | IPCRP1 | IPCRP1 | 5691-0000 | CO#69 PCO #125E - Utility Connections for Proposed | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5701-0000-R | IPCRP1 | IPCRP1 | 5701-0000 | CO#70.1 PCO #96 - Floodwall Transition Expansion J | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5702-0000-R | IPCRP1 | IPCRP1 | 5702-0000 | CO#70.2 PCO #193 - Expansion Joint Material Precas | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5711-0000-R | IPCRP1 | IPCRP1 | 5711-0000 | CO#71.1 PCO #176 - Bulletin No. 14 - Tennis Buildi | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3007.57 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5712-0000-R | IPCRP1 | IPCRP1 | 5712-0000 | CO#71.2 6.34 D DIGITAL PHOTOGRAPHS (CO. No. 71 "No | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-5721-0000-R | IPCRP1 | IPCRP1 | 5721-0000 | CO#72.1 PCO #227 - Closure at Existing FBH South S | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56330.7 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5722-0000-R | IPCRP1 | IPCRP1 | 5722-0000 | CO#72.2 6.34 D DIGITAL PHOTOGRAPHS (CO. No. 72 "No | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-5731-0000-R | IPCRP1 | IPCRP1 | 5731-0000 | PCO #309 - NYCHA Building #11 - Sewer Service Repl | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5741-0000-R | IPCRP1 | IPCRP1 | 5741-0000 | PCO #147 - Fire Boat House Retaining Wall Conflict | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7412.9 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5742-0000-R | IPCRP1 | IPCRP1 | 5742-0000 | PCO #75A - Bulletin 6 - ADA Compliance Changes at | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10882.45 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5743-0000-R | IPCRP1 | IPCRP1 | 5743-0000 | DIGITAL PHOTOGRAPHS (CO. No. 74 "No Cost CO" Qnt. | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-5744-0000-R | IPCRP1 | IPCRP1 | 5744-0000 | Temporary Steel Sheeting (CO. No. 74 "No Cost CO" | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5751-0000-R | IPCRP1 | IPCRP1 | 5751-0000 | JB 900(CE) Extra Utility Costs Allowance | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153795.61 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5752-0000-R | IPCRP1 | IPCRP1 | 5752-0000 | CO#75 Qnt. Deduction (Multiple JB items) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5761-0000-R | IPCRP1 | IPCRP1 | 5761-0000 | CO#76.1.1 PCO No. 60 - Delancey St. Bridge: NYC-18 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5762-0000-R | IPCRP1 | IPCRP1 | 5762-0000 | CO#76.1.2 PCO No. 60 - East 10th St. Bridge: NYC-1 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5763-0000-R | IPCRP1 | IPCRP1 | 5763-0000 | CO#76.2 PCO No. 60 - Corlears Hook Bridge: NYC-180 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5764-0000-R | IPCRP1 | IPCRP1 | 5764-0000 | CO#76.3 Metal Architectural Mesh (Qnt. Deduct) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5765-0000-R | IPCRP1 | IPCRP1 | 5765-0000 | CO#76.4 Metal Architectural Mesh (Qnt. Deduct) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5771-0000-R | IPCRP1 | IPCRP1 | 5771-0000 | Delancey Pedestrian Bridge MPT - Weekday (M-T) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-5772-0000-R | IPCRP1 | IPCRP1 | 5772-0000 | Delancey Pedestrian Bridge - MPT (Friday-Saturday) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-5773-0000-R | IPCRP1 | IPCRP1 | 5773-0000 | Corlears Hook Pedestrian Bridge MPT - Weekday (M-T | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-5774-0000-R | IPCRP1 | IPCRP1 | 5774-0000 | Corlears Hook Pedestrian Bridge - MPT (Friday-Satu | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-5775-0000-R | IPCRP1 | IPCRP1 | 5775-0000 | E10 Street Pedestrian Bridge MPT - Weekday (M-T) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-5776-0000-R | IPCRP1 | IPCRP1 | 5776-0000 | E10 Street Pedestrian Bridge - MPT (Friday-Saturd | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-5777-0000-R | IPCRP1 | IPCRP1 | 5777-0000 | PCO#89 CO#37 Qnt Neg FDR Crossings | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5781-0000-R | IPCRP1 | IPCRP1 | 5781-0000 | PCO No. 164 - Waterproofing Under Parks M&O Area 2 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098.5 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5782-0000-R | IPCRP1 | IPCRP1 | 5782-0000 | PCO No. 164 - Waterproofing Under Parks M&O Area 3 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5783-0000-R | IPCRP1 | IPCRP1 | 5783-0000 | CO#78.3 ESCR-902-SSVS Qnt. Neg SSVS Work - M&O 2 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5784-0000-R | IPCRP1 | IPCRP1 | 5784-0000 | CO#78.4 ESCR-903-SSVS Qnt. Neg SSVS Work - M&O 3 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5791-0000-R | IPCRP1 | IPCRP1 | 5791-0000 | CO#79.1 PCO No. 111 - M&O 2 Building Changes: Gree | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5792-0000-R | IPCRP1 | IPCRP1 | 5792-0000 | CO#79.2 PCO No. 213 - M&O 3 Building Changes: Gree | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5801-0000-R | IPCRP1 | IPCRP1 | 5801-0000 | CO#80.1 PCO No. 296 - (Removal Shifts) Obstruction | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384750 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0 | SH | 0 | 0 | 0 | 0
Y | IPCRP1-5802-0000-R | IPCRP1 | IPCRP1 | 5802-0000 | CO#80.2 PCO No. 296 - (Disposal) Ostruction cleari | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5803-0000-R | IPCRP1 | IPCRP1 | 5803-0000 | CO#80.3 ESCR-901-SSVS_SSVS Work -Cmfrt Stn (DED.) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5804-0000-R | IPCRP1 | IPCRP1 | 5804-0000 | CO#80.4 ESCR-902-SSVS_SSVS Work -M&O2 (DED.) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5805-0000-R | IPCRP1 | IPCRP1 | 5805-0000 | CO#80.5 ESCR-903-SSVS_SSVS Work -M&O3 (DED.) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5806-0000-R | IPCRP1 | IPCRP1 | 5806-0000 | CO#80.6 ESCR-904-SSVS_SSVS Work -Tns Bldg. (DED.) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5807-0000-R | IPCRP1 | IPCRP1 | 5807-0000 | CO#80.7 ESCR-905-SSVS_SSVS Work -Trk Bldg. (DED.) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5808-0000-R | IPCRP1 | IPCRP1 | 5808-0000 | CO#80.8 6.43 D Digital Photographs (DED.) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-5809-0000-R | IPCRP1 | IPCRP1 | 5809-0000 | CO#80.9 PK-ESCR 642 3" Gas Line to FB House (DED.) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5811-0000-R | IPCRP1 | IPCRP1 | 5811-0000 | CO#81.1 PCONo.165 - SSPC-QP1 & QP2 Cert 2024 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5812-0000-R | IPCRP1 | IPCRP1 | 5812-0000 | CO#81.2 PCONo.165 - SSPC-QP1 & QP2 Cert 2025 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5813-0000-R | IPCRP1 | IPCRP1 | 5813-0000 | CO#81.3 PCONo.165 - SSPC-QP1 & QP2 Cert 2026 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5814-0000-R | IPCRP1 | IPCRP1 | 5814-0000 | CO#81.1 PCONo.165 - QP1 & QP2 Cert Trvl Exp. | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5831-0000-R | IPCRP1 | IPCRP1 | 5831-0000 | CO#83.1 PCO No.219-Removal of UGST at FDR &10th St | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5841-0000-R | IPCRP1 | IPCRP1 | 5841-0000 | CO#84.1 PCO No.166-Unknown 12" pipe interference w | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5842-0000-R | IPCRP1 | IPCRP1 | 5842-0000 | 6.43 D (CO#84 Qnt. Neg) Digital Photographs | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0 | ST | 0 | 0 | 0 | 0
Y | IPCRP1-5851-0000-R | IPCRP1 | IPCRP1 | 5851-0000 | CO#85.1 PCO No.196-Field Memo 5 -Amph H-Pile Rebar | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5852-0000-R | IPCRP1 | IPCRP1 | 5852-0000 | CO#85.2 PCO No.194-Changes to Access Weld-Delancey | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5853-0000-R | IPCRP1 | IPCRP1 | 5853-0000 | CO#85.3 PCO No.194-Changes to Access Weld-Corlears | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5854-0000-R | IPCRP1 | IPCRP1 | 5854-0000 | CO#85.4 PCO No.194-Changes to Access Weld-E.10th | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5855-0000-R | IPCRP1 | IPCRP1 | 5855-0000 | CO #65 (CO#85 Qnt. Neg.)-PCO No.150B-Houston Jet G | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5861-0000-R | IPCRP1 | IPCRP1 | 5861-0000 | CO#086.1-PCO No.205-Demo Exist Bulkhd at PC Trench | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5871-0000-R | IPCRP1 | IPCRP1 | 5871-0000 | CO#87.1-PCO No.370 - NYCHA Test Pits at E10th St. | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5872-0000-R | IPCRP1 | IPCRP1 | 5872-0000 | CO #65 (CO#87 Qnt. Neg.)-PCO No.150B-Houston Jet G | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5881-0000-R | IPCRP1 | IPCRP1 | 5881-0000 | PCO#343A - Demolition of Existing CSO's #10 & #11 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5882-0000-R | IPCRP1 | IPCRP1 | 5882-0000 | PCO#150B - CO#65 (CO#88 Qnt. Neg) Houston Jet Grou | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5891-0000-R | IPCRP1 | IPCRP1 | 5891-0000 | PCO No. 304 - FM#16 Del. St. Curb West of ERH Driv | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5892-0000-R | IPCRP1 | IPCRP1 | 5892-0000 | PCO#150B - CO#65 (CO#89 Qnt. Neg) Houston Jet Grou | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5901-0000-R | IPCRP1 | IPCRP1 | 5901-0000 | PCO No. 346 - Winterization Pit for Delancey Spray | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5902-0000-R | IPCRP1 | IPCRP1 | 5902-0000 | PCO#150B - CO#65 (CO#90 Qnt. Neg) Houston Jet Grou | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5903-0000-R | IPCRP1 | IPCRP1 | 5903-0000 | CO#91.1 VECP No. 19 Construction Cost Saving | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5904-0000-R | IPCRP1 | IPCRP1 | 5904-0000 | CO#91.2 ESCR-4.06 HP ES Conc for Espl (VECP19) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0 | CY | 0 | 0 | 0 | 0
Y | IPCRP1-5905-0000-R | IPCRP1 | IPCRP1 | 5905-0000 | ESCR-4.14 Epoxy Coating St. Reinf (VECP19) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5906-0000-R | IPCRP1 | IPCRP1 | 5906-0000 | ESCR-551.36.05 DT 36" DIA. X 0.5 IN Wall Thickness | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5907-0000-R | IPCRP1 | IPCRP1 | 5907-0000 | ESCR-551.36.05.CS Coated 36" DIA. X 0.5 IN Wall Th | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5908-0000-R | IPCRP1 | IPCRP1 | 5908-0000 | ESCR-551.36.05.CSD Coated 36' DIA. X 0.5 IN. Wall | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5909-0000-R | IPCRP1 | IPCRP1 | 5909-0000 | ESCR-551.42.05 DT 42" DIA. X 0.5 IN. Wall Thicknes | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5910-0000-R | IPCRP1 | IPCRP1 | 5910-0000 | ESCR-552.11 20 C - Coated AZ-20-700N or Equal Stee | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5911-0000-R | IPCRP1 | IPCRP1 | 5911-0000 | ESCR-552.11 3.0TR 3.0 IN. DIA. Hot-Dip Galvanized | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5912-0000-R | IPCRP1 | IPCRP1 | 5912-0000 | ESCR-552.11 4219CI Coated PAZ42/NZ19 or Equal Comb | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
Y | IPCRP1-5913-0000-R | IPCRP1 | IPCRP1 | 5913-0000 | ESCR-564 Structural Steel (Uncoated) (VECP No. 19) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0 | LB | 0 | 0 | 0 | 0
Y | IPCRP1-5914-0000-R | IPCRP1 | IPCRP1 | 5914-0000 | ESCR-551.993.13375 - 13.375" OD x 0.514" Wall Thic | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-5915-0000-R | IPCRP1 | IPCRP1 | 5915-0000 | ESCR-551.993.13375C Pile Load Testing for 13.375" | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5916-0000-R | IPCRP1 | IPCRP1 | 5916-0000 | ESCR-551.993.13375T Pile Load Testing for 13.375" | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0 | TE | 0 | 0 | 0 | 0
Y | IPCRP1-5917-0000-R | IPCRP1 | IPCRP1 | 5917-0000 | CO#91 VECP19 Deduction (Multiple Items) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5921-0000-R | IPCRP1 | IPCRP1 | 5921-0000 | CO#92.1 JB 900(CE) - Extra Utility Costs Allowance | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5922-0000-R | IPCRP1 | IPCRP1 | 5922-0000 | CO#92 JB 900(CE) Ext. Deducts (Multiple Items) | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5931-0000-R | IPCRP1 | IPCRP1 | 5931-0000 | 25ft Alum. LP w/ 8ft Alum. Arm on Transf. Base | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5932-0000-R | IPCRP1 | IPCRP1 | 5932-0000 | 25ft Alum. LP w/ 8ft Alum. Arm No Transf. Base | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5933-0000-R | IPCRP1 | IPCRP1 | 5933-0000 | SL-21.05.07 F&I Spun Alum. w/ Twin 8ft Arms No TB | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5934-0000-R | IPCRP1 | IPCRP1 | 5934-0000 | SL-20.03.11 F&I Fndn. on Conc. Barrier, dwg.H-5220 | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-5935-0000-R | IPCRP1 | IPCRP1 | 5935-0000 | CO#65 PCO No. 150B Qnt. Deduct. | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5941-0000-R | IPCRP1 | IPCRP1 | 5941-0000 | PCO No. 076C - Bulletin 7, Amphitheater Canopy Str | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5951-0000-R | IPCRP1 | IPCRP1 | 5951-0000 | CO95.1 PCO No. 212 - M&O2 Bldg Plumbing Changes | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5952-0000-R | IPCRP1 | IPCRP1 | 5952-0000 | CO95.2 PCO No. 212 - Tennis Bldg Plumbing Changes | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5953-0000-R | IPCRP1 | IPCRP1 | 5953-0000 | CO95.3 PCO#212 - Comfort Station Plumbing Changes | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5954-0000-R | IPCRP1 | IPCRP1 | 5954-0000 | CO95.4 PCO #213A - Bulletin #16 M&O3 Bldg Mods | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5955-0000-R | IPCRP1 | IPCRP1 | 5955-0000 | CO#95.5 CO#65 PCO150B HS Jet Grt Qnt. Deduct | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5961-0000-R | IPCRP1 | IPCRP1 | 5961-0000 | CO#96 ESCR-122-Incr. Cost for MGP Handling | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0 | TN | 0 | 0 | 0 | 0
Y | IPCRP1-5962-0000-R | IPCRP1 | IPCRP1 | 5962-0000 | CO#37(CO#96 Ded.) PCO 89 - Conduits Across FDR, MP | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5971-0000-R | IPCRP1 | IPCRP1 | 5971-0000 | CO#97 PCO 132: Add Construction Joints at CHP | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-5972-0000-R | IPCRP1 | IPCRP1 | 5972-0000 | ESCR 6.01 AB (CO#97 Ded.) CLEARING AND GRUBBING | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0 | AC | 0 | 0 | 0 | 0
Y | IPCRP1-7010-0000-R | IPCRP1 | IPCRP1 | 7010-0000 | Line H Adjustments | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1435806.17 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | DL | 0 | 0 | 0 | 0
Y | IPCRP1-7020-0000-R | IPCRP1 | IPCRP1 | 7020-0000 | Retainage Adjustments | N | R |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | DL | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1000-C | IPCRP1 | IPCRP1 | 9000-1000 | Supervision | N | C |  | NR | P | 1434000 | 48151806.52 | 48151806.52 | 48149263.37 | 48151806.52 | 82.5622 | 0 | 0 | 0 | 10166993.48 | Y | 58318800 | Y | -56884800 | 0 | 0 | 1434000 | 0 | 0 | 58318800 | Y | -56884800 | 0 | 0 | 1434000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -58318800 | 3189.9 | 1065449.27 | 58318800 | 0 | 0 | 0 | 0 | 0 | 0 | -58318800 | 0 | 0 | 58318800 | 58318800 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 133 | 0 | 133 | NA | 6639 | 10782 | 1899 | 12681 | MW | 2543.15 | 2543.15 | 0 | 10166993.48
Y | IPCRP1-9000-1000-L | IPCRP1 | IPCRP1 | 9000-1000 | Supervision | N | L |  | NR | P | 31064797 | 73927.86 | 73927.86 | 73927.86 | 73927.86 | 100 | 0 | 0 | 0 | 0 | Y | 73927.86 | Y | 30990869.14 | 0 | 0 | 31064797 | 0 | 0 | 73927.86 | Y | 30990869.14 | 0 | 0 | 31064797 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -73927.86 | 0 | 0 | 73927.86 | 0 | 0 | 0 | 0 | 0 | 0 | -73927.86 | 0 | 0 | 73927.86 | 73927.86 | 0 | 0 | 0 | 0 | 0 | 2075.88 | 2075.88 | 0 | 1591 | 484.88 | 2075.88 | HR | 6639 | 10782 | 1899 | 12681 | MW | 0 | 0 | 0 | 0 | VS (9/22/24) added 50 men x 52 weeks, 10,081 + 2,600 = 12,681
Y | IPCRP1-9000-1000-S | IPCRP1 | IPCRP1 | 9000-1000 | Supervision | N | S |  | UNIT | A | 0 | 2776707.49 | 2776707.49 | 2055286.89 | 2776707.49 | 78.0082 | 0 | 0 | 0 | -142000 | Y | 2634707.49 | Y | -2634707.49 | 0 | 0 | 0 | 0 | 0 | 2634707.49 | Y | -2634707.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2634707.49 | 0 | 27268.92 | 2634707.49 | 0 | 0 | 0 | 142000 | 0 | 0 | -2634707.49 | 0 | 0 | 2634707.49 | 2634707.49 | 0 | 0 | 0 | 0 | 0 | 4501 | 4501 | 0 | 29847.42 | -25346.42 | 4501 | NA | 6639 | 10782 | 1899 | 12681 | MW | 2637086.2 | 721420.6 | 1915665.6 | -142000
Y | IPCRP1-9000-1010-C | IPCRP1 | IPCRP1 | 9000-1010 | Supervision - WE Shifts | N | C |  | UNIT | U | 0 | 1031423.88 | 1031423.88 | 1031423.88 | 1031423.88 | 95.5022 | 0 | 0 | 0 | 48576.12 | Y | 1080000 | Y | -1080000 | 0 | 0 | 0 | 0 | 0 | 1080000 | Y | -1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1080000 | 0 | 34904.59 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | -1080000 | 0 | 0 | 1080000 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 750 | 874 | 26 | 900 | SH | 0 | 0 | 0 | 48576.12
Y | IPCRP1-9000-1010-L | IPCRP1 | IPCRP1 | 9000-1010 | Supervision - WE Shifts | N | L |  | NR | P | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 750000 | 0 | 0 | 750000 | 0 | 0 | 0 | Y | 750000 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 750 | 874 | 26 | 900 | SH | 0 | 0 | 0 | 0 | VS (8/23) added 150 shifts to bid total
Y | IPCRP1-9000-1015-C | IPCRP1 | IPCRP1 | 9000-1015 | Supervision Expenses | N | C |  | UNIT | U | 0 | 421277.59 | 421277.59 | 421277.59 | 421277.59 | 73.1385 | 0 | 0 | 0 | 154722.41 | Y | 576000 | Y | -576000 | 0 | 0 | 0 | 0 | 0 | 576000 | Y | -576000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -576000 | 1105.12 | 17251.01 | 576000 | 0 | 0 | 0 | 0 | 0 | 0 | -576000 | 0 | 0 | 576000 | 576000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620 | -620 | 0 | NA | 60 | 55 | 17 | 72 | MO | 23320.61 | -1732.85 | 25053.46 | 154722.41 | Expenses separated from Labor category.
Y | IPCRP1-9000-1015-L | IPCRP1 | IPCRP1 | 9000-1015 | Supervision Expenses | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 55 | 17 | 72 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1015-M | IPCRP1 | IPCRP1 | 9000-1015 | Supervision Expenses | N | M |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 60 | 55 | 17 | 72 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1020-C | IPCRP1 | IPCRP1 | 9000-1020 | Supervision - Legal | N | C |  | UNIT | U | 0 | 66562 | 66562 | 66562 | 66562 | 11.0937 | 0 | 0 | 0 | 533438 | Y | 600000 | Y | -600000 | 0 | 0 | 0 | 0 | 0 | 600000 | Y | -600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -600000 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | -600000 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 0.06 | 0.94 | 1 | LS | 0 | 0 | 0 | 533438 | Rigano invoice ($38,412.50) plus GT Law
Y | IPCRP1-9000-1020-L | IPCRP1 | IPCRP1 | 9000-1020 | Supervision - Legal | N | L |  | NR | P | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | Y | 600000 | Y | 600000 | 0 | 0 | 1200000 | 0 | 0 | 600000 | Y | 600000 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -600000 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | -600000 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 3000 | 3000 | HR | 1 | 0.06 | 0.94 | 1 | LS | 0 | 0 | 0 | 600000
Y | IPCRP1-9000-1030-C | IPCRP1 | IPCRP1 | 9000-1030 | Supervision - Comm Liason | N | C |  | UNIT | U | 0 | 12541.45 | 12541.45 | 10383.47 | 12541.45 | 41.6936 | 0 | 0 | 0 | 12362.78 | Y | 24904.23 | Y | -24904.23 | 0 | 0 | 0 | 0 | 0 | 24904.23 | Y | -24904.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24904.23 | 0 | 0 | 24904.23 | 0 | 0 | 0 | 0 | 0 | 0 | -24904.23 | 0 | 0 | 24904.23 | 24904.23 | 0 | 0 | 0 | 0 | 0 | 14.01 | 14.01 | 0 | 11.42 | 2.59 | 14.01 | NA | 60 | 55 | 5 | 60 | MO | 11663.79 | 2157.98 | 9505.81 | 12362.78 | FL&O COMMUNICATIONS PO@$22,673.24
Y | IPCRP1-9000-1030-L | IPCRP1 | IPCRP1 | 9000-1030 | Supervision - Comm Liason | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1030-S | IPCRP1 | IPCRP1 | 9000-1030 | Supervision - Comm Liason | N | S |  | NR | A | 600000 | 420000 | 420000 | 25602.5 | 420000 | 6.0958 | 0 | 0 | 0 | 0 | Y | 420000 | Y | 180000 | 0 | 0 | 600000 | 0 | 0 | 420000 | Y | 180000 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -420000 | 0 | 0 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | -420000 | 0 | 0 | 420000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 269.5 | 5674.79 | 5944.29 | NA | 60 | 55 | 5 | 60 | MO | 420000 | 394397.5 | 25602.5 | 0 | JOHNSON & ASBERRY Base Contract @$420,000.00
Y | IPCRP1-9000-1040-C | IPCRP1 | IPCRP1 | 9000-1040 | Supervision - Fees | N | C |  | NR | P | 2177600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2177600 | 0 | 0 | 2177600 | 0 | 0 | 0 | Y | 2177600 | 0 | 0 | 2177600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0 | Was for Head Hunter fees, don't anticipate using (VS)
Y | IPCRP1-9000-1040-L | IPCRP1 | IPCRP1 | 9000-1040 | Supervision - Fees | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1045-L | IPCRP1 | IPCRP1 | 9000-1045 | Supervision (Craft) | N | L |  | UNIT | P | 0 | -1.18 | -1.18 | -1.18 | -1.18 | 0 | 0 | 0 | 0 | 1.18 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 16 | 16 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 1.18
Y | IPCRP1-9000-1050-L | IPCRP1 | IPCRP1 | 9000-1050 | Master Mechanic | N | L |  | NR | P | 1682340 | 2838976.77 | 2838976.77 | 2838976.77 | 2838976.77 | 65.522 | 0 | 0 | 0 | 1493883.23 | Y | 4332860 | Y | -2650520 | 0 | 0 | 1682340 | 0 | 0 | 4332860 | Y | -2650520 | 0 | 0 | 1682340 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4332860 | 68110.2 | 56060.91 | 4332860 | 0 | 0 | 0 | 0 | 0 | 0 | -4332860 | 0 | 0 | 4332860 | 4332860 | 0 | 0 | 0 | 0 | 0 | 20850 | 20850 | 0 | 14095 | 6755 | 20850 | HR | 234 | 214 | 102 | 316 | MW | 0 | 0 | 0 | 1493883.23 | Teddy Preston, 1/3/22 - 2/20/22 (7 wks) As of 8/25/24 QTD = 129.00. Extending job until 8/29/27, requires 157 WKS to complete (PMF = 286.00).
Y | IPCRP1-9000-1060-L | IPCRP1 | IPCRP1 | 9000-1060 | Maintenance Foreman | N | L |  | NR | P | 2243130 | 3421579.43 | 3421579.43 | 3421579.43 | 3421579.43 | 64.6917 | 0 | 0 | 0 | 1867472.04 | Y | 5289051.47 | Y | -3045921.47 | 0 | 0 | 2243130 | 0 | 0 | 5289051.47 | Y | -3045921.47 | 0 | 0 | 2243130 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5289051.47 | 86450.97 | 82196.63 | 5289051.47 | 0 | 0 | 0 | 0 | 0 | 0 | -5289051.47 | 0 | 0 | 5289051.47 | 5289051.47 | 0 | 0 | 0 | 0 | 0 | 29380.01 | 29380.01 | 0 | 19159.5 | 10220.51 | 29380.01 | HR | 390 | 334 | 182 | 516 | MW | 0 | 0 | 0 | 1867472.04 | John Callahan, 12/27/21 - 2/20/22 (8 wks) As of 8/25/24 QTD = 161.00. Extending job until 8/29/27, & allowing for 2 years of night work (104 WKS) PMF requires 261 WKS to complete (PMF 422.00)
Y | IPCRP1-9000-1070-L | IPCRP1 | IPCRP1 | 9000-1070 | Teamster Steward | N | L |  | NR | P | 2489880 | -0.08 | -0.08 | -0.08 | -0.08 | 100 | 0 | 0 | 0 | 0 | Y | -0.08 | Y | 2489880.08 | 0 | 0 | 2489880 | 0 | 0 | -0.08 | Y | 2489880.08 | 0 | 0 | 2489880 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0.08 | 0 | 0 | -0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0 | -0.08 | -0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 468 | 425 | 210 | 635 | MW | 0 | 0 | 0 | 0 | Start Date 12/27/21.
Y | IPCRP1-9000-1070-S | IPCRP1 | IPCRP1 | 9000-1070 | Teamster Steward | N | S |  | UNIT | A | 0 | 3144274.73 | 3144274.73 | 2411828.43 | 3144274.73 | 68.9094 | 0 | 0 | 0 | 355725.27 | Y | 3500000 | Y | -3500000 | 0 | 0 | 0 | 0 | 0 | 3500000 | Y | -3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3500000 | 64502.74 | 47900.03 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | -3500000 | 0 | 0 | 3500000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 19432.76 | -19431.76 | 1 | NA | 468 | 425 | 210 | 635 | MW | 3144274.73 | 732446.3 | 2411828.43 | 355725.27 | KMA INDUSTRIES Base Contract @$2,000,000.00 As of 8/25/24, QTD = 261.00. Extending job until 8/29/27, requires 314 WKS (based on 2 men) to complete (PMF =575.00)
Y | IPCRP1-9000-1071-L | IPCRP1 | IPCRP1 | 9000-1071 | KMA Teamster Insurance Costs | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 41.62 | 58.38 | 100 | $ | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1071-S | IPCRP1 | IPCRP1 | 9000-1071 | KMA Teamster Insurance Costs | N | S |  | UNIT | A | 0 | 1000000 | 1000000 | 416241.2 | 1000000 | 41.6241 | 0 | 0 | 0 | 0 | N | 1000000 | N | -1000000 | 0 | 0 | 0 | 0 | 0 | 1000000 | N | -1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1000000 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 61881.19 | 61881.19 | 0 | 25757.5 | 36123.69 | 61881.19 | NA | 0 | 41.62 | 58.38 | 100 | $ | 1000000 | 583758.8 | 416241.2 | 0
Y | IPCRP1-9000-1080-L | IPCRP1 | IPCRP1 | 9000-1080 | Labor Steward | N | L |  | NR | P | 1177650 | 1505999.45 | 1505999.45 | 1505999.45 | 1505999.45 | 69.5754 | 0 | 0 | 0 | 658558.84 | Y | 2164558.29 | Y | -986908.29 | 0 | 0 | 1177650 | 0 | 0 | 2164558.29 | Y | -986908.29 | 0 | 0 | 1177650 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2164558.29 | 36350.67 | 32205.05 | 2164558.29 | 0 | 0 | 0 | 0 | 0 | 0 | -2164558.29 | 0 | 0 | 2164558.29 | 2164558.29 | 0 | 0 | 0 | 0 | 0 | 18600 | 18600 | 0 | 13007.5 | 5592.5 | 18600 | HR | 234 | 225 | 102 | 327 | MW | 0 | 0 | 0 | 658558.84 | Peter Cataldo, start date 12/3/21. As of 8/25/24, QTD = 139.00. Extending job until 8/29/27, requires 157 WKS to complete (PMF = 296.00)
Y | IPCRP1-9000-1082-L | IPCRP1 | IPCRP1 | 9000-1082 | Safety Boat Captain | N | L |  | UNIT | P | 0 | 598188 | 598188 | 598188 | 598188 | 68.8351 | 0 | 0 | 0 | 270827.51 | Y | 869015.51 | Y | -869015.51 | 0 | 0 | 0 | 0 | 0 | 869015.51 | Y | -869015.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -869015.51 | 32168.3 | 24027.61 | 869015.51 | 0 | 0 | 0 | 0 | 0 | 0 | -869015.51 | 0 | 0 | 869015.51 | 869015.51 | 0 | 0 | 0 | 0 | 0 | 5950 | 5950 | 0 | 4099 | 1851 | 5950 | HR | 0 | 480 | 220 | 700 | DY | 0 | 0 | 0 | 270827.51
Y | IPCRP1-9000-1090-L | IPCRP1 | IPCRP1 | 9000-1090 | Escalation | N | L |  | NR | P | 20500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500000 | Y | 20500000 | Y | 0 | 0 | 0 | 20500000 | 0 | 0 | 20500000 | Y | 0 | 0 | 0 | 20500000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20500000 | 0 | 0 | 20500000 | 0 | 0 | 0 | 0 | 0 | 0 | -20500000 | 0 | 0 | 20500000 | 20500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 20500000
Y | IPCRP1-9000-1090-M | IPCRP1 | IPCRP1 | 9000-1090 | Escalation | N | M |  | NR | P | 151246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 151246 | 0 | 0 | 151246 | 0 | 0 | 0 | Y | 151246 | 0 | 0 | 151246 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1100-L | IPCRP1 | IPCRP1 | 9000-1100 | Premium Cost | N | L |  | NR | P | 9850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9850000 | Y | 9850000 | Y | 0 | 0 | 0 | 9850000 | 0 | 0 | 9850000 | Y | 0 | 0 | 0 | 9850000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9850000 | 0 | 0 | 9850000 | 0 | 0 | 0 | 0 | 0 | 0 | -9850000 | 0 | 0 | 9850000 | 9850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 9850000
Y | IPCRP1-9000-1110-C | IPCRP1 | IPCRP1 | 9000-1110 | Lost Time | N | C |  | UNIT | U | 0 | 6651.71 | 6651.71 | 6305.58 | 6651.71 | 94.7964 | 0 | 0 | 0 | 0 | N | 6651.71 | N | -6651.71 | 0 | 0 | 0 | 0 | 0 | 6651.71 | N | -6651.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6651.71 | 0 | 0 | 6651.71 | 0 | 0 | 0 | 0 | 0 | 0 | -6651.71 | 0 | 0 | 6651.71 | 6651.71 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | NA | 36481 | 4551.5 | 25848.5 | 30400 | HR | 4246.13 | 346.13 | 3900 | 0
Y | IPCRP1-9000-1110-L | IPCRP1 | IPCRP1 | 9000-1110 | Lost Time | N | L |  | NR | P | 3648100 | 483091.6 | 483091.6 | 483091.6 | 483091.6 | 13.2423 | 0 | 0 | 0 | 3165008.4 | Y | 3648100 | Y | 0 | 0 | 0 | 3648100 | 0 | 0 | 3648100 | Y | 0 | 0 | 0 | 3648100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3648100 | 1346.61 | 5755.31 | 3648100 | 0 | 0 | 0 | 0 | 0 | 0 | -3648100 | 0 | 0 | 3648100 | 3648100 | 0 | 0 | 0 | 0 | 0 | 30400.94 | 30400.94 | 0 | 4551.5 | 25849.44 | 30400.94 | HR | 36481 | 4551.5 | 25848.5 | 30400 | HR | 0 | 0 | 0 | 3165008.4 | Forecast is 30,400 Man-hours for the project (CMiC rounding error/auto-adjust budget to flat $ 3,648,100.00)
Y | IPCRP1-9000-1110-S | IPCRP1 | IPCRP1 | 9000-1110 | Lost Time | N | S |  | UNIT | A | 0 | 31553.66 | 31553.66 | 31553.66 | 31553.66 | 100 | 0 | 0 | 0 | 0 | Y | 31553.66 | Y | -31553.66 | 0 | 0 | 0 | 0 | 0 | 31553.66 | Y | -31553.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -31553.66 | 0 | 0 | 31553.66 | 0 | 0 | 0 | 0 | 0 | 0 | -31553.66 | 0 | 0 | 31553.66 | 31553.66 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 258.5 | -218.5 | 40 | NA | 36481 | 4551.5 | 25848.5 | 30400 | HR | 31553.66 | 0 | 31553.66 | 0
Y | IPCRP1-9000-1120-L | IPCRP1 | IPCRP1 | 9000-1120 | Holiday | N | L |  | NR | P | 2920000 | 1633778.35 | 1633778.35 | 1633778.35 | 1633778.35 | 61.6481 | 0 | 0 | 0 | 1016391.63 | Y | 2650169.98 | Y | 269830.02 | 0 | 0 | 2920000 | 0 | 0 | 2650169.98 | Y | 269830.02 | 0 | 0 | 2920000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2650169.98 | 0 | 0 | 2650169.98 | 0 | 0 | 0 | 0 | 0 | 0 | -2650169.98 | 0 | 0 | 2650169.98 | 2650169.98 | 0 | 0 | 0 | 25000 | 0 | 21200 | 21200 | 25000 | 13255.5 | 7944.5 | 21200 | HR | 22461.54 | 13255.5 | 7944.5 | 21200 | HR | 0 | 0 | 0 | 1016391.63 | Forecast is 25,000 Man-hours for the project (CMiC rounding error/auto-adjust budget to flat $ 2,920,000.00
Y | IPCRP1-9000-1120-S | IPCRP1 | IPCRP1 | 9000-1120 | Holiday | N | S |  | UNIT | A | 0 | 244254.27 | 244254.27 | 244254.27 | 244254.27 | 90.4645 | 0 | 0 | 0 | 25745.73 | Y | 270000 | Y | -270000 | 0 | 0 | 0 | 0 | 0 | 270000 | Y | -270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -270000 | 0 | 9173.74 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | -270000 | 0 | 0 | 270000 | 270000 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 0 | 1930 | -1878 | 52 | NA | 22461.54 | 13255.5 | 7944.5 | 21200 | HR | 244254.27 | 0 | 244254.27 | 25745.73
Y | IPCRP1-9000-1130-C | IPCRP1 | IPCRP1 | 9000-1130 | Field Office Setup & Fitout (180 Maiden Lane - IPC | N | C |  | UNIT | U | 0 | 125393.03 | 125393.03 | 87652.14 | 125393.03 | 87.6521 | 0 | 0 | 0 | -25393.03 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 8502.35 | 8502.35 | 0 | 9638 | -1135.65 | 8502.35 | NA | 1 | 0.9 | 0.1 | 1 | LS | 44676.01 | 37740.89 | 6935.12 | -25393.03 | Will we end up over 115K. yes we will. Let this one play out another month, and hopefully we will be done setting up the Field Office. (VS, 4/5/22)
Y | IPCRP1-9000-1130-L | IPCRP1 | IPCRP1 | 9000-1130 | Field Office Setup & Fitout (180 Maiden Lane - IPC | N | L |  | NR | P | 0 | -94.14 | -94.14 | -94.14 | -94.14 | -941400 | 0 | 0 | 0 | 94.15 | Y | 0.01 | Y | -0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | Y | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -0.01 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.9 | 0.1 | 1 | LS | 0 | 0 | 0 | 94.15
Y | IPCRP1-9000-1130-M | IPCRP1 | IPCRP1 | 9000-1130 | Field Office Setup & Fitout (180 Maiden Lane - IPC | N | M |  | UNIT | U | 0 | 9949.85 | 9949.85 | 9949.85 | 9949.85 | 77.0946 | 0 | 0 | 0 | 2956.18 | Y | 12906.03 | Y | -12906.03 | 0 | 0 | 0 | 0 | 0 | 12906.03 | Y | -12906.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12906.03 | 0 | 0 | 12906.03 | 0 | 0 | 0 | 0 | 0 | 0 | -12906.03 | 0 | 0 | 12906.03 | 12906.03 | 0 | 0 | 0 | 0 | 0 | 37911.08 | 37911.08 | 0 | 49281 | -11369.92 | 37911.08 | NA | 1 | 0.9 | 0.1 | 1 | LS | 2240.65 | -7709.2 | 9949.85 | 2956.18
Y | IPCRP1-9000-1140-C | IPCRP1 | IPCRP1 | 9000-1140 | Field Office Monthly (180 Maiden Lane - IPC) | N | C |  | NR | P | 4680000 | 1633364.21 | 1633364.21 | 1633364.21 | 1633364.21 | 62.8217 | 0 | 0 | 0 | 966635.79 | Y | 2600000 | Y | 2080000 | 0 | 0 | 4680000 | 0 | 0 | 2600000 | Y | 2080000 | 0 | 0 | 4680000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2600000 | 27133.86 | 2531.81 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | -2600000 | 0 | 0 | 2600000 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1688.64 | 2828.9 | 4517.54 | NA | 60 | 59 | 33 | 92 | MO | 3464.64 | -4030.52 | 7495.16 | 966635.79 | 2. (VS - 1/26/26) extend thru 12/28 (add 36 mo) @ 30K/mo - 1.08M + 1.536M (CTD) = 2.618M, round down 2.6M 5 months @ 1010 NB + 6 years @ 180 Maiden Lane = 77 months. Spent $10K/mo x 5 months = $50K + 7 mo (rent abate) x 1/3 (75K/mo) = 25 K*(65 mo) + 250K (misc) = 50K + 1,625,000 +250 = $1.925M [Start: 5/21, End: 10/27]
Y | IPCRP1-9000-1140-L | IPCRP1 | IPCRP1 | 9000-1140 | Field Office Monthly (180 Maiden Lane - IPC) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 59 | 33 | 92 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1150-C | IPCRP1 | IPCRP1 | 9000-1150 | On Site Trailers Setup & Fitout | N | C |  | UNIT | U | 0 | 275993.22 | 275993.22 | 275993.22 | 275993.22 | 91.9977 | 0 | 0 | 0 | 24006.78 | Y | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | -300000 | 0 | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 353.6 | 353.6 | 0 | 309 | 44.6 | 353.6 | NA | 1 | 0.73 | 0.27 | 1 | LS | 78296.19 | -57071.54 | 135367.73 | 24006.78 | CAC, Carter Milchman, Cassone, MLJ, US Coffe, Virgo Flee, WB Mason
Y | IPCRP1-9000-1150-L | IPCRP1 | IPCRP1 | 9000-1150 | On Site Trailers Setup & Fitout | N | L |  | NR | P | 0 | 212473.89 | 212473.89 | 212473.89 | 212473.89 | 74.1269 | 0 | 0 | 0 | 74161.33 | Y | 286635.22 | Y | -286635.22 | 0 | 0 | 0 | 0 | 0 | 286635.22 | Y | -286635.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -286635.22 | 0 | 0 | 286635.22 | 0 | 0 | 0 | 0 | 0 | 0 | -286635.22 | 0 | 0 | 286635.22 | 286635.22 | 0 | 0 | 0 | 0 | 0 | 2273 | 2273 | 0 | 1731.5 | 541.5 | 2273 | HR | 1 | 0.73 | 0.27 | 1 | LS | 0 | 0 | 0 | 74161.33
Y | IPCRP1-9000-1150-M | IPCRP1 | IPCRP1 | 9000-1150 | On Site Trailers Setup & Fitout | N | M |  | UNIT | U | 0 | 83676.9 | 83676.9 | 83615.63 | 83676.9 | 83.6156 | 0 | 0 | 0 | 16323.1 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 341.21 | 341.21 | 0 | 286.58 | 54.63 | 341.21 | NA | 1 | 0.73 | 0.27 | 1 | LS | 85756.9 | 61.27 | 85695.63 | 16323.1
Y | IPCRP1-9000-1150-S | IPCRP1 | IPCRP1 | 9000-1150 | On Site Trailers Setup & Fitout | N | S |  | UNIT | A | 0 | 242733.15 | 242733.15 | 183875.31 | 242733.15 | 75.752 | 0 | 0 | 0 | 0 | Y | 242733.15 | Y | -242733.15 | 0 | 0 | 0 | 0 | 0 | 242733.15 | Y | -242733.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -242733.15 | 0 | 0 | 242733.15 | 0 | 0 | 0 | 0 | 0 | 0 | -242733.15 | 0 | 0 | 242733.15 | 242733.15 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 6820.36 | -6819.36 | 1 | NA | 1 | 0.73 | 0.27 | 1 | LS | 242733.15 | 58857.84 | 183875.31 | 0 | CASSONE LEASING, INC Base Contract @$67,529.72
Y | IPCRP1-9000-1160-C | IPCRP1 | IPCRP1 | 9000-1160 | On Site Trailers (Monthly) | N | C |  | NR | P | 283000 | 1172227.64 | 1172227.64 | 1132224.71 | 1172227.64 | 100.3727 | 0 | 0 | 0 | -44207.51 | Y | 1128020.13 | Y | -845020.13 | 0 | 0 | 283000 | 0 | 0 | 1128020.13 | Y | -845020.13 | 0 | 0 | 283000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1128020.13 | 4204.58 | 18440.85 | 1128020.13 | 0 | 0 | 0 | 0 | 300 | 0 | -1128020.13 | 0 | 0 | 1128020.13 | 1128020.13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4069 | -270.47 | 3798.53 | NA | 162 | 51 | 15 | 66 | MO | 629998.44 | 40002.93 | 589995.51 | -44207.51 | A List Cleaning Service @$108,021.42; Cassone Leasing @$39,438.88, US Coffee @$2.8K; Towerstream @$3.2K We need to get a better handle on costs that are hitting both 9000-1150 & 9000-1160. Yes, its very possible that we will spend another 100K on this code. It was never meant to be as a large trailer complex that we have today.
Y | IPCRP1-9000-1160-L | IPCRP1 | IPCRP1 | 9000-1160 | On Site Trailers (Monthly) | N | L |  | UNIT | P | 0 | 15217.85 | 15217.85 | 15217.85 | 15217.85 | 28.1812 | 0 | 0 | 0 | 38782.15 | Y | 54000 | Y | -54000 | 0 | 0 | 0 | 0 | 0 | 54000 | Y | -54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -54000 | 13721.26 | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | -54000 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 99 | 301 | 400 | HR | 162 | 51 | 15 | 66 | MO | 0 | 0 | 0 | 38782.15
Y | IPCRP1-9000-1160-S | IPCRP1 | IPCRP1 | 9000-1160 | On Site Trailers (Monthly) | N | S |  | UNIT | A | 0 | 402928.5 | 402928.5 | 219163.16 | 402928.5 | 54.4203 | 0 | 0 | 0 | -205.03 | Y | 402723.47 | Y | -402723.47 | 0 | 0 | 0 | 0 | 0 | 402723.47 | Y | -402723.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -402723.47 | 5468.76 | 0 | 402723.47 | 0 | 0 | 0 | 0 | 0 | 0 | -402723.47 | 0 | 0 | 402723.47 | 402723.47 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 9063.85 | -9062.85 | 1 | NA | 162 | 51 | 15 | 66 | MO | 402928.5 | 183765.34 | 219163.16 | -205.03 | Start in Jan 2022. Cassone Leasing subcontract $192,055.50
Y | IPCRP1-9000-1170-C | IPCRP1 | IPCRP1 | 9000-1170 | Telephone & Electric | N | C |  | NR | P | 120000 | 490881.93 | 490881.93 | 403874.41 | 490881.93 | 85.489 | 0 | 0 | 0 | -18453.66 | Y | 472428.27 | Y | -352428.27 | 0 | 0 | 120000 | 0 | 0 | 472428.27 | Y | -352428.27 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -472428.27 | 3309.09 | 6246.57 | 472428.27 | 0 | 0 | 0 | 2966.85 | 3647.31 | 0 | -472428.27 | 0 | 0 | 472428.27 | 472428.27 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 252.75 | -7.01 | 245.74 | NA | 60 | 51 | 9 | 60 | MO | 419555.77 | 87007.52 | 332548.25 | -18453.66 | Start in January 2022
Y | IPCRP1-9000-1170-L | IPCRP1 | IPCRP1 | 9000-1170 | Telephone & Electric | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 51 | 9 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1180-C | IPCRP1 | IPCRP1 | 9000-1180 | Portable Toilets | N | C |  | NR | P | 249710 | 510481.31 | 510481.31 | 410093.41 | 510481.31 | 81.4333 | 0 | 0 | 0 | -6887.36 | Y | 503593.95 | Y | -253883.95 | 0 | 0 | 249710 | 0 | 0 | 503593.95 | Y | -253883.95 | 0 | 0 | 249710 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -503593.95 | 6968 | 6968 | 503593.95 | 0 | 0 | 0 | 6968 | 6968 | 0 | -503593.95 | 0 | 0 | 503593.95 | 503593.95 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8360.86 | -32 | 8328.86 | NA | 1814 | 1085 | 115 | 1200 | UM | 510561.95 | 100387.9 | 410174.05 | -6887.36
Y | IPCRP1-9000-1180-L | IPCRP1 | IPCRP1 | 9000-1180 | Portable Toilets | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1814 | 1085 | 115 | 1200 | UM | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1190-C | IPCRP1 | IPCRP1 | 9000-1190 | Sea Boxes | N | C |  | NR | P | 80000 | 280393.66 | 280393.66 | 264601.18 | 280393.66 | 94.4962 | 0 | 0 | 0 | -381.06 | Y | 280012.6 | Y | -200012.6 | 0 | 0 | 80000 | 0 | 0 | 280012.6 | Y | -200012.6 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -280012.6 | 217.75 | 217.76 | 280012.6 | 0 | 0 | 0 | 0 | 0 | 0 | -280012.6 | 0 | 0 | 280012.6 | 280012.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 112 | -23.56 | 88.44 | NA | 20 | 21 | 2 | 23 | EA | 274393.66 | 15792.48 | 258601.18 | -381.06 | Purchased 3ea CAC (used 6K), 5ea Cassone (used), and 13ea Cassone (new) heated boxes when parking was eliminated so men could use them as change shanties. CASSONE 16,035.12 Purchased 3ea from CAC (house bill).
Y | IPCRP1-9000-1190-L | IPCRP1 | IPCRP1 | 9000-1190 | Sea Boxes | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 20 | 21 | 2 | 23 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1190-S | IPCRP1 | IPCRP1 | 9000-1190 | Sea Boxes | N | S |  | UNIT | A | 0 | 19562.66 | 19562.66 | 19562.66 | 19562.66 | 100 | 0 | 0 | 0 | 0 | N | 19562.66 | N | -19562.66 | 0 | 0 | 0 | 0 | 0 | 19562.66 | N | -19562.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19562.66 | 0 | 0 | 19562.66 | 0 | 0 | 0 | 0 | 0 | 0 | -19562.66 | 0 | 0 | 19562.66 | 19562.66 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | NA | 20 | 21 | 2 | 23 | EA | 19562.66 | 0 | 19562.66 | 0
Y | IPCRP1-9000-1200-C | IPCRP1 | IPCRP1 | 9000-1200 | 20CY Garbage Containersl (CLOSED) | N | C |  | NR | P | 91800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 91800 | 0 | 0 | 91800 | 0 | 0 | 0 | N | 91800 | 0 | 0 | 91800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 108 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1200-L | IPCRP1 | IPCRP1 | 9000-1200 | 20CY Garbage Containersl (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 108 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1210-C | IPCRP1 | IPCRP1 | 9000-1210 | Temporary Fence (CLOSED) | N | C |  | NR | P | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 36000 | 0 | 0 | 36000 | 0 | 0 | 0 | N | 36000 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 400 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1210-L | IPCRP1 | IPCRP1 | 9000-1210 | Temporary Fence (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 400 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1220-C | IPCRP1 | IPCRP1 | 9000-1220 | Vehicles | N | C |  | NR | P | 762160 | 796472.05 | 796472.05 | 692225.78 | 796472.05 | 76.914 | 0 | 0 | 0 | 103527.95 | Y | 900000 | Y | -137840 | 0 | 0 | 762160 | 0 | 0 | 900000 | Y | -137840 | 0 | 0 | 762160 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -900000 | 21203.06 | 72068.86 | 900000 | 0 | 0 | 0 | 12097.99 | 12338.91 | 0 | -900000 | 0 | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100208.61 | -5367.25 | 94841.36 | NA | 14 | 15 | 0 | 15 | EA | 368659.12 | 104246.27 | 264412.85 | 103527.95
Y | IPCRP1-9000-1220-D | IPCRP1 | IPCRP1 | 9000-1220 | Vehicles | N | D |  | UNIT | A | 0 | 561333.25 | 561333.25 | 561333.25 | 561333.25 | 115.3231 | 0 | 0 | 0 | -74584.8 | Y | 486748.45 | Y | -486748.45 | 0 | 0 | 0 | 0 | 0 | 486748.45 | Y | -486748.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -486748.45 | 0 | 12430.8 | 486748.45 | 0 | 0 | 0 | 0 | 0 | 0 | -486748.45 | 0 | 0 | 486748.45 | 486748.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 14 | 15 | 0 | 15 | EA | 0 | 0 | 0 | -74584.8
Y | IPCRP1-9000-1220-E | IPCRP1 | IPCRP1 | 9000-1220 | Vehicles | N | E |  | NR | P | 36000 | 303928.51 | 303928.51 | 113227.86 | 303928.51 | 37.2548 | 0 | 0 | 0 | 0 | Y | 303928.51 | Y | -267928.51 | 0 | 0 | 36000 | 0 | 0 | 303928.51 | Y | -267928.51 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -303928.51 | 0 | 0 | 303928.51 | 0 | 0 | 0 | 0 | 0 | 0 | -303928.51 | 0 | 0 | 303928.51 | 303928.51 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12 | 0 | 12 | NA | 14 | 15 | 0 | 15 | EA | 194103 | 190700.65 | 3402.35 | 0
Y | IPCRP1-9000-1220-L | IPCRP1 | IPCRP1 | 9000-1220 | Vehicles | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 14 | 15 | 0 | 15 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1225-C | IPCRP1 | IPCRP1 | 9000-1225 | Consultant (Nautilus) for Delay Claim | N | C |  | UNIT | U | 0 | 100000 | 100000 | 71690 | 100000 | 71.69 | 0 | 0 | 0 | 0 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 3000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71690 | -71690 | 0 | NA | 0 | 0 | 0 | 0 | LS | 100000 | 28310 | 71690 | 0 | IPC Estimate is 400K. Writing PO to Nautilus for 25% of our value, based on estimated budget from Nautilus (4/29/25) for Delay & Entitlement and Development of Initial TE Request.
Y | IPCRP1-9000-1225-L | IPCRP1 | IPCRP1 | 9000-1225 | Consultant (Nautilus) for Delay Claim | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1230-C | IPCRP1 | IPCRP1 | 9000-1230 | Access Road | N | C |  | NR | P | 12000 | 12009.99 | 12009.99 | 11333.04 | 12009.99 | 94.3634 | 0 | 0 | 0 | 0 | Y | 12009.99 | Y | -9.99 | 0 | 0 | 12000 | 0 | 0 | 12009.99 | Y | -9.99 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12009.99 | 0 | 0 | 12009.99 | 0 | 0 | 0 | 0 | 0 | 0 | -12009.99 | 0 | 0 | 12009.99 | 12009.99 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 140 | -140 | 0 | NA | 1 | 0.51 | 0.49 | 1 | LS | 11259.99 | 676.95 | 10583.04 | 0
Y | IPCRP1-9000-1230-L | IPCRP1 | IPCRP1 | 9000-1230 | Access Road | N | L |  | UNIT | P | 108000 | 114005.27 | 114005.27 | 114005.27 | 114005.27 | 57.0009 | 0 | 0 | 0 | 86000.83 | Y | 200006.1 | Y | -92006.1 | 0 | 0 | 108000 | 0 | 0 | 200006.1 | Y | -92006.1 | 0 | 0 | 108000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200006.1 | 0 | 0 | 200006.1 | 0 | 0 | 0 | 0 | 0 | 0 | -200006.1 | 0 | 0 | 200006.1 | 200006.1 | 0 | 0 | 0 | 900 | 0 | 1540 | 1540 | 900 | 885 | 655 | 1540 | HR | 1 | 0.51 | 0.49 | 1 | LS | 0 | 0 | 0 | 86000.83
Y | IPCRP1-9000-1230-M | IPCRP1 | IPCRP1 | 9000-1230 | Access Road | N | M |  | UNIT | U | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | 5000 | Y | 25000 | 0 | 0 | 30000 | 0 | 0 | 5000 | Y | 25000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1 | 0.51 | 0.49 | 1 | LS | 0 | 0 | 0 | 5000
Y | IPCRP1-9000-1230-S | IPCRP1 | IPCRP1 | 9000-1230 | Access Road | N | S |  | UNIT | A | 0 | 2056.92 | 2056.92 | 2056.92 | 2056.92 | 20.5692 | 0 | 0 | 0 | 7943.08 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 17 | -3 | 14 | NA | 1 | 0.51 | 0.49 | 1 | LS | 2056.92 | 0 | 2056.92 | 7943.08
Y | IPCRP1-9000-1240-C | IPCRP1 | IPCRP1 | 9000-1240 | Small Tools & Supplies (4%DL) | N | C |  | NR | P | 6333476 | 6586086.45 | 6586086.45 | 6216637.09 | 6586086.45 | 81.7979 | 0 | 0 | 0 | 1013913.55 | Y | 7600000 | Y | -1266524 | 0 | 0 | 6333476 | 0 | 0 | 7600000 | Y | -1266524 | 0 | 0 | 6333476 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7600000 | 91783.66 | 105928.28 | 7600000 | 0 | 0 | 0 | 125456.76 | 108144 | 0 | -7600000 | 0 | 0 | 7600000 | 7600000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 574343.44 | 110663.3 | 685006.74 | NA | 1000000 | 817640.5 | 382359.5 | 1200000 | HR | 6573925.81 | 369449.36 | 6204476.45 | 1013913.55
Y | IPCRP1-9000-1240-L | IPCRP1 | IPCRP1 | 9000-1240 | Small Tools & Supplies (4%DL) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1000000 | 817640.5 | 382359.5 | 1200000 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1250-C | IPCRP1 | IPCRP1 | 9000-1250 | Safety Small Tools & Supplies (1/DLMH) | N | C |  | NR | P | 1381560 | 1407445.92 | 1407445.92 | 1302683.38 | 1407445.92 | 78.6645 | 0 | 0 | 0 | 248554.08 | Y | 1656000 | Y | -274440 | 0 | 0 | 1381560 | 0 | 0 | 1656000 | Y | -274440 | 0 | 0 | 1381560 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1656000 | 32997.89 | 16441.76 | 1656000 | 0 | 0 | 0 | 40368.71 | 13559.04 | 0 | -1656000 | 0 | 0 | 1656000 | 1656000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 63077.53 | 5714.16 | 68791.69 | NA | 1000000 | 817640.5 | 382359.5 | 1200000 | HR | 1397997.04 | 104762.54 | 1293234.5 | 248554.08
Y | IPCRP1-9000-1250-L | IPCRP1 | IPCRP1 | 9000-1250 | Safety Small Tools & Supplies (1/DLMH) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1000000 | 817640.5 | 382359.5 | 1200000 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1260-C | IPCRP1 | IPCRP1 | 9000-1260 | Jobsite Safety System (Arrow Site) | N | C |  | NR | P | 1500000 | 2708557.23 | 2708557.23 | 2277641.23 | 2708557.23 | 81.3443 | 0 | 0 | 0 | 91442.77 | Y | 2800000 | Y | -1300000 | 0 | 0 | 1500000 | 0 | 0 | 2800000 | Y | -1300000 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2800000 | 36500 | 36500 | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | -2800000 | 0 | 0 | 2800000 | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13946.4 | -11224.79 | 2721.61 | MO | 60 | 51 | 18 | 69 | MO | 2685170.64 | 430916 | 2254254.64 | 91442.77 | Arrowsight: Set Up Fee (65K) + Monthly Fee 69 Mo @36.5K/mo = 65K + 2.518M = 2.109M + tax = 2.8M. Labor to Install (100K). Equipment (300K), Contingency (200K) = 3.8M First month claimed in Jan 2022. Extend Arrow Site rental projection from 60mo to 69mo, concluding in Sep 2027. PMF = 69.00 MO. Arrowsight: Set Up Fee (65K) + Monthly Fee 56 Mo @36.5K/mo = 65K + 2.044M = 2.109M + tax = 2.3M. Labor to Install (300K). Equipment (500K). Internet (500K), Contingency (200K) = 3.8M
Y | IPCRP1-9000-1260-E | IPCRP1 | IPCRP1 | 9000-1260 | Jobsite Safety System (Arrow Site) | N | E |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | Y | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | -300000 | 0 | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 60 | 51 | 18 | 69 | MO | 0 | 0 | 0 | 300000 | Arrowsight: Set Up Fee (65K) + Monthly Fee 56 Mo @36.5K/mo = 65K + 2.044M = 2.109M + tax = 2.3M. Labor to Install (300K). Equipment (500K). Internet (500K), Contingency (200K) = 3.8M
Y | IPCRP1-9000-1260-L | IPCRP1 | IPCRP1 | 9000-1260 | Jobsite Safety System (Arrow Site) | N | L |  | UNIT | P | 0 | 316.75 | 316.75 | 316.75 | 316.75 | 0.31522 | 0 | 0 | 0 | 100170 | Y | 100486.75 | Y | -100486.75 | 0 | 0 | 0 | 0 | 0 | 100486.75 | Y | -100486.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100486.75 | 0 | 0 | 100486.75 | 0 | 0 | 0 | 0 | 0 | 0 | -100486.75 | 0 | 0 | 100486.75 | 100486.75 | 0 | 0 | 0 | 0 | 0 | 632 | 632 | 0 | 2 | 630 | 632 | HR | 60 | 51 | 18 | 69 | MO | 0 | 0 | 0 | 100170 | Arrowsight: Set Up Fee (65K) + Monthly Fee 56 Mo @36.5K/mo = 65K + 2.044M = 2.109M + tax = 2.3M. Labor to Install (300K). Equipment (500K). Internet (500K), Contingency (200K) = 3.8M
Y | IPCRP1-9000-1270-C | IPCRP1 | IPCRP1 | 9000-1270 | Jobsite Security | N | C |  | NR | P | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1200000 | 0 | 0 | 1200000 | 0 | 0 | 0 | Y | 1200000 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 60 | 52 | 18 | 70 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1270-L | IPCRP1 | IPCRP1 | 9000-1270 | Jobsite Security | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 52 | 18 | 70 | MO | 0 | 0 | 0 | 0 | Extend Dreamland Security projection until Sep 2027. As of 8/31/24, QTD = 33.00. Extending job until 8/29/27, requires 37 MO to complete (PMF = 70.00). We added 2 add guards in Apr 2024, Avg cost per MO since is 122K/MO. 122 x 37 = 4.5M + CTD (2.5M) = 6.975M
Y | IPCRP1-9000-1270-S | IPCRP1 | IPCRP1 | 9000-1270 | Jobsite Security | N | S |  | NR | A | 336000 | 6626460.42 | 6626460.42 | 4743043.84 | 6626460.42 | 68.0006 | 0 | 0 | 0 | 348539.58 | Y | 6975000 | Y | -6639000 | 0 | 0 | 336000 | 0 | 0 | 6975000 | Y | -6639000 | 0 | 0 | 336000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6975000 | 0 | 125232.9 | 6975000 | 0 | 0 | 0 | 0 | 0 | 0 | -6975000 | 0 | 0 | 6975000 | 6975000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 162218.29 | -162217.29 | 1 | NA | 60 | 52 | 18 | 70 | MO | 6626460.42 | 1883416.58 | 4743043.84 | 348539.58 | ... 122K/mo. 122 x 37 = 4.5 + CTD (2.5) = 6.975M. Started counting months as of Dec 2021. .... Dreamland start on 11/15/21. Start counting months as of Dec 2021 DREAMLAND Security Base Contract @$2,070,867.30; T&M USA LLC Base Contract @$103,800.00 DREAMLAND Security Base Contract @$2,070,867.30; T&M USA LLC Base Contract @$103,800.00
Y | IPCRP1-9000-1280-C | IPCRP1 | IPCRP1 | 9000-1280 | Punch List | N | C |  | NR | P | 1000000 | 1846.6 | 1846.6 | 1846.6 | 1846.6 | 3.0806 | 0 | 0 | 0 | 58095.62 | Y | 59942.22 | Y | 940057.78 | 0 | 0 | 1000000 | 0 | 0 | 59942.22 | Y | 940057.78 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -59942.22 | 0 | 0 | 59942.22 | 0 | 0 | 0 | 0 | 0 | 0 | -59942.22 | 0 | 0 | 59942.22 | 59942.22 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 64 | 2013.71 | 2077.71 | NA | 1 | 0.2 | 0.8 | 1 | LS | 1846.6 | 0 | 1846.6 | 58095.62
Y | IPCRP1-9000-1280-L | IPCRP1 | IPCRP1 | 9000-1280 | Punch List | N | L |  | UNIT | P | 0 | 170483.61 | 170483.61 | 170483.61 | 170483.61 | 18.9414 | 0 | 0 | 0 | 729574.17 | Y | 900057.78 | Y | -900057.78 | 0 | 0 | 0 | 0 | 0 | 900057.78 | Y | -900057.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -900057.78 | 4079.1 | 0 | 900057.78 | 0 | 0 | 0 | 0 | 0 | 0 | -900057.78 | 0 | 0 | 900057.78 | 900057.78 | 0 | 0 | 0 | 0 | 0 | 7000 | 7000 | 0 | 1494.5 | 5505.5 | 7000 | HR | 1 | 0.2 | 0.8 | 1 | LS | 0 | 0 | 0 | 729574.17
Y | IPCRP1-9000-1280-M | IPCRP1 | IPCRP1 | 9000-1280 | Punch List | N | M |  | UNIT | U | 0 | 1789.02 | 1789.02 | 1789.02 | 1789.02 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 1789.02 | 0 | 0 | 0 | 0 | 0 | 1789.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | -4 | 0 | NA | 1 | 0.2 | 0.8 | 1 | LS | 1789.02 | 0 | 1789.02 | 0
Y | IPCRP1-9000-1280-S | IPCRP1 | IPCRP1 | 9000-1280 | Punch List | N | S |  | UNIT | A | 0 | 11097.05 | 11097.05 | 11097.05 | 11097.05 | 126.8397 | 0 | 0 | 0 | -2348.17 | Y | 8748.88 | Y | -8748.88 | 0 | 0 | 0 | 0 | 0 | 8748.88 | Y | -8748.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8748.88 | 0 | 0 | 8748.88 | 0 | 0 | 0 | 0 | 0 | 0 | -8748.88 | 0 | 0 | 8748.88 | 8748.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.5 | -88.5 | 0 | NA | 1 | 0.2 | 0.8 | 1 | LS | 11097.05 | 0 | 11097.05 | -2348.17
Y | IPCRP1-9000-1290-C | IPCRP1 | IPCRP1 | 9000-1290 | Insurance - Premiums (excluding BR, Umbrella) | N | C |  | NR | P | 3530004 | 3649045.91 | 3649045.91 | 3649045.91 | 3649045.91 | 53.6624 | 0 | 0 | 0 | 3150954.09 | Y | 6800000 | Y | -3269996 | 0 | 0 | 3530004 | 0 | 0 | 6800000 | Y | -3269996 | 0 | 0 | 3530004 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6800000 | 106818 | 164578.69 | 6800000 | 0 | 0 | 0 | 0 | 0 | 0 | -6800000 | 0 | 0 | 6800000 | 6800000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 3150954.09 | Fixed Premiums (5.0) + Prof/Poll (0.3) + Alliant Fee (2.0) = 7.3M
Y | IPCRP1-9000-1290-L | IPCRP1 | IPCRP1 | 9000-1290 | Insurance - Premiums (excluding BR, Umbrella) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1300-C | IPCRP1 | IPCRP1 | 9000-1300 | Insurance - GL Claims/ Deductibles | N | C |  | NR | P | 30000000 | 192558.72 | 192558.72 | 190383.48 | 192558.72 | 0.67837 | 0 | 0 | 0 | 27872441.28 | Y | 28065000 | Y | 1935000 | 0 | 0 | 30000000 | 0 | 0 | 28065000 | Y | 1935000 | 0 | 0 | 30000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28065000 | 652.99 | 27429.05 | 28065000 | 0 | 0 | 0 | 0 | 0 | 0 | -28065000 | 0 | 0 | 28065000 | 28065000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2457.09 | -2457.09 | 0 | NA | 1 | 0 | 1 | 1 | LS | 41350.19 | 2175.24 | 39174.95 | 27872441.28 | Loss Pick (23.1) +85% x Est Claim Fee (85% x 2.9 = 2.465) + 18.75% x 16M max loss (3) = 28.565M
Y | IPCRP1-9000-1300-L | IPCRP1 | IPCRP1 | 9000-1300 | Insurance - GL Claims/ Deductibles | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1310-C | IPCRP1 | IPCRP1 | 9000-1310 | Insurance - WC Claims/ Deductables | N | C |  | NR | P | 21000000 | 574309.14 | 574309.14 | 574309.14 | 574309.14 | 3.4037 | 0 | 0 | 0 | 16298690.86 | Y | 16873000 | Y | 4127000 | 0 | 0 | 21000000 | 0 | 0 | 16873000 | Y | 4127000 | 0 | 0 | 21000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16873000 | 0 | 49715.99 | 16873000 | 0 | 0 | 0 | 0 | 0 | 0 | -16873000 | 0 | 0 | 16873000 | 16873000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 16298690.86 | Loss Pick (3.8) + 15% x Est Claim Fee (15% x 2.9 = 0.435) + 81.25% x 16M max loss (13M) = 17.235M
Y | IPCRP1-9000-1310-L | IPCRP1 | IPCRP1 | 9000-1310 | Insurance - WC Claims/ Deductables | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1320-C | IPCRP1 | IPCRP1 | 9000-1320 | Insurance - Builders Risk | N | C |  | NR | P | 10000000 | 128443.34 | 128443.34 | 128443.34 | 128443.34 | 88.5816 | 0 | 0 | 0 | 16556.66 | Y | 145000 | Y | 9855000 | 0 | 0 | 10000000 | 0 | 0 | 145000 | Y | 9855000 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -145000 | 0 | 2334.97 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | -145000 | 0 | 0 | 145000 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 16556.66 | BR Premium
Y | IPCRP1-9000-1320-L | IPCRP1 | IPCRP1 | 9000-1320 | Insurance - Builders Risk | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1330-C | IPCRP1 | IPCRP1 | 9000-1330 | Insurance - Railroad Protective | N | C |  | NR | P | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 104000 | 0 | 0 | 104000 | 0 | 0 | 0 | N | 104000 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0 | RR Protect Premium
Y | IPCRP1-9000-1330-L | IPCRP1 | IPCRP1 | 9000-1330 | Insurance - Railroad Protective | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1340-C | IPCRP1 | IPCRP1 | 9000-1340 | Insurance - Umbrella Policy | N | C |  | NR | P | 33375000 | 18332676.14 | 18332676.14 | 18332676.14 | 18332676.14 | 90.1312 | 0 | 0 | 0 | 2007323.86 | Y | 20340000 | Y | 13035000 | 0 | 0 | 33375000 | 0 | 0 | 20340000 | Y | 13035000 | 0 | 0 | 33375000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20340000 | 0 | 337122.36 | 20340000 | 0 | 0 | 0 | 0 | 0 | 0 | -20340000 | 0 | 0 | 20340000 | 20340000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 2007323.86 | Total Excess Premium
Y | IPCRP1-9000-1340-L | IPCRP1 | IPCRP1 | 9000-1340 | Insurance - Umbrella Policy | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1350-C | IPCRP1 | IPCRP1 | 9000-1350 | Tri-Venture Fee | N | C |  | NR | P | 5000000 | 4629384.3 | 4629384.3 | 4629384.3 | 4629384.3 | 89.891 | 0 | 0 | 0 | 520615.7 | Y | 5150000 | Y | -150000 | 0 | 0 | 5000000 | 0 | 0 | 5150000 | Y | -150000 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5150000 | 0 | 500040.8 | 5150000 | 0 | 0 | 0 | 0 | 0 | 0 | -5150000 | 0 | 0 | 5150000 | 5150000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 5 | 4.5 | 0.5 | 5 | YR | 0 | 0 | 0 | 520615.7
Y | IPCRP1-9000-1350-L | IPCRP1 | IPCRP1 | 9000-1350 | Tri-Venture Fee | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5 | 4.5 | 0.5 | 5 | YR | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1360-C | IPCRP1 | IPCRP1 | 9000-1360 | Permits, Fees, Violations | N | C |  | NR | P | 100000 | 391459.85 | 391459.85 | 372674.75 | 391459.85 | 96.0848 | 0 | 0 | 0 | -3599.44 | Y | 387860.41 | Y | -287860.41 | 0 | 0 | 100000 | 0 | 0 | 387860.41 | Y | -287860.41 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -387860.41 | 2963.28 | 6374.44 | 387860.41 | 0 | 0 | 0 | 0 | 0 | 0 | -387860.41 | 0 | 0 | 387860.41 | 387860.41 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4936.75 | -4903.75 | 33 | NA | 1 | 0.7 | 0.3 | 1 | LS | 79678.85 | 18785.1 | 60893.75 | -3599.44 | VACHRIS ENGINEERING, P.C
Y | IPCRP1-9000-1360-L | IPCRP1 | IPCRP1 | 9000-1360 | Permits, Fees, Violations | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.7 | 0.3 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1360-S | IPCRP1 | IPCRP1 | 9000-1360 | Permits, Fees, Violations | N | S |  | UNIT | A | 0 | 132071.2 | 132071.2 | 36876.3 | 132071.2 | 28.6011 | 0 | 0 | 0 | -3138 | Y | 128933.2 | Y | -128933.2 | 0 | 0 | 0 | 0 | 0 | 128933.2 | Y | -128933.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -128933.2 | 3986.67 | 1938 | 128933.2 | 0 | 0 | 0 | 0 | 1200 | 0 | -128933.2 | 0 | 0 | 128933.2 | 128933.2 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 22737.63 | 77262.37 | 100000 | NA | 1 | 0.7 | 0.3 | 1 | LS | 132071.2 | 95194.9 | 36876.3 | -3138
Y | IPCRP1-9000-1370-C | IPCRP1 | IPCRP1 | 9000-1370 | Temporary Power (CLOSED) | N | C |  | NR | P | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Y | 10 | Y | 149990 | 0 | 0 | 150000 | 0 | 0 | 10 | Y | 149990 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 10
Y | IPCRP1-9000-1370-L | IPCRP1 | IPCRP1 | 9000-1370 | Temporary Power (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1380-C | IPCRP1 | IPCRP1 | 9000-1380 | Equipment Moves | N | C |  | NR | P | 221600 | 149386.58 | 149386.58 | 95723.8 | 149386.58 | 43.1967 | 0 | 0 | 0 | 72213.42 | N | 221600 | N | 0 | 0 | 0 | 221600 | 0 | 0 | 221600 | N | 0 | 0 | 0 | 221600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -221600 | 0 | 1869.88 | 221600 | 0 | 0 | 0 | 0 | 2035.83 | 0 | -221600 | 0 | 0 | 221600 | 221600 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4075.23 | -4075.23 | 0 | NA | 900 | 0 | 900 | 900 | HR | 126602.79 | 53662.78 | 72940.01 | 72213.42
Y | IPCRP1-9000-1380-L | IPCRP1 | IPCRP1 | 9000-1380 | Equipment Moves | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 900 | 0 | 900 | 900 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1390-C | IPCRP1 | IPCRP1 | 9000-1390 | Cell Phones/ Office Supplies/ Phones (CLOSED) | N | C |  | NR | P | 358405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 358405 | 0 | 0 | 358405 | 0 | 0 | 0 | N | 358405 | 0 | 0 | 358405 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 6340 | 0 | 0 | 0 | MW | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1390-L | IPCRP1 | IPCRP1 | 9000-1390 | Cell Phones/ Office Supplies/ Phones (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6340 | 0 | 0 | 0 | MW | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1400-C | IPCRP1 | IPCRP1 | 9000-1400 | Computers, Phones, IT Support | N | C |  | NR | P | 216834 | 841559.7 | 841559.7 | 841559.7 | 841559.7 | 93.5066 | 0 | 0 | 0 | 58440.3 | Y | 900000 | Y | -683166 | 0 | 0 | 216834 | 0 | 0 | 900000 | Y | -683166 | 0 | 0 | 216834 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -900000 | 0 | 14841.27 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | -900000 | 0 | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3 | -3 | 0 | NA | 29 | 23 | 6 | 29 | EA | 0 | 0 | 0 | 58440.3
Y | IPCRP1-9000-1400-L | IPCRP1 | IPCRP1 | 9000-1400 | Computers, Phones, IT Support | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 29 | 23 | 6 | 29 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1410-C | IPCRP1 | IPCRP1 | 9000-1410 | Copiers, Printers, Plotters | N | C |  | NR | P | 97992 | 83738.88 | 83738.88 | 83738.87 | 83738.88 | 85.4548 | 0 | 0 | 0 | 14253.12 | Y | 97992 | Y | 0 | 0 | 0 | 97992 | 0 | 0 | 97992 | Y | 0 | 0 | 0 | 97992 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -97992 | 0 | 1409.94 | 97992 | 0 | 0 | 0 | 0 | 0 | 0 | -97992 | 0 | 0 | 97992 | 97992 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7 | 0 | 7 | NA | 60 | 53 | 19 | 72 | MO | 590.71 | 0.01 | 590.7 | 14253.12 | Start monthly count in Nov 2021, end in Oct 2027.
Y | IPCRP1-9000-1410-L | IPCRP1 | IPCRP1 | 9000-1410 | Copiers, Printers, Plotters | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 53 | 19 | 72 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1420-C | IPCRP1 | IPCRP1 | 9000-1420 | Boat | N | C |  | NR | P | 76216 | -574.11 | -42472.53 | -42472.53 | -574.11 | 100 | 0 | 0 | 0 | -41898.42 | Y | -42472.53 | Y | 118688.53 | 0 | 0 | 76216 | 0 | 0 | -42472.53 | Y | 118688.53 | 0 | 0 | 76216 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 42472.53 | 0 | 0 | -42472.53 | 0 | 0 | 0 | 0 | 0 | 0 | 42472.53 | 0 | 0 | -42472.53 | -42472.53 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 625.75 | -625.75 | 0 | NA | 1 | 1 | 0 | 1 | EA | -574.11 | 41898.42 | -42472.53 | -41898.42 | SOUND MARINE SERVICE AND SUPPL PO@$42K
Y | IPCRP1-9000-1420-D | IPCRP1 | IPCRP1 | 9000-1420 | Boat | N | D |  | UNIT | A | 0 | 33456.74 | 33456.74 | 33456.74 | 33456.74 | 129.4117 | 0 | 0 | 0 | -7603.8 | Y | 25852.94 | Y | -25852.94 | 0 | 0 | 0 | 0 | 0 | 25852.94 | Y | -25852.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25852.94 | 0 | 760.38 | 25852.94 | 0 | 0 | 0 | 0 | 0 | 0 | -25852.94 | 0 | 0 | 25852.94 | 25852.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | -7603.8
Y | IPCRP1-9000-1420-E | IPCRP1 | IPCRP1 | 9000-1420 | Boat | N | E |  | UNIT | A | 0 | 45727.5 | 45727.5 | 45622.5 | 45727.5 | 62.4998 | 0 | 0 | 0 | 27268.7 | Y | 72996.2 | Y | -72996.2 | 0 | 0 | 0 | 0 | 0 | 72996.2 | Y | -72996.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -72996.2 | 0 | 0 | 72996.2 | 0 | 0 | 0 | 0 | 0 | 0 | -72996.2 | 0 | 0 | 72996.2 | 72996.2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | NA | 1 | 1 | 0 | 1 | EA | 45727.5 | 105 | 45622.5 | 27268.7 | Change PMF (Equipment) from $90,727.50 to $45,727.50
Y | IPCRP1-9000-1420-L | IPCRP1 | IPCRP1 | 9000-1420 | Boat | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1422-L | IPCRP1 | IPCRP1 | 9000-1422 | Handling of Safety Boat, In/Out of Water | N | L |  | UNIT | P | 0 | 182193.08 | 182193.08 | 182193.08 | 182193.08 | 60.2159 | 0 | 0 | 0 | 120373.34 | Y | 302566.42 | Y | -302566.42 | 0 | 0 | 0 | 0 | 0 | 302566.42 | Y | -302566.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -302566.42 | 12160.87 | 8604.97 | 302566.42 | 0 | 0 | 0 | 0 | 0 | 0 | -302566.42 | 0 | 0 | 302566.42 | 302566.42 | 0 | 0 | 0 | 0 | 0 | 1800.02 | 1800.02 | 0 | 1112 | 688.02 | 1800.02 | HR | 0 | 363 | 237 | 600 | DY | 0 | 0 | 0 | 120373.34
Y | IPCRP1-9000-1422-S | IPCRP1 | IPCRP1 | 9000-1422 | Handling of Safety Boat, In/Out of Water | N | S |  | UNIT | A | 0 | 507.21 | 507.21 | 507.21 | 507.21 | 100 | 0 | 0 | 0 | 0 | N | 507.21 | N | -507.21 | 0 | 0 | 0 | 0 | 0 | 507.21 | N | -507.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -507.21 | 0 | 0 | 507.21 | 0 | 0 | 0 | 0 | 0 | 0 | -507.21 | 0 | 0 | 507.21 | 507.21 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | NA | 0 | 363 | 237 | 600 | DY | 507.21 | 0 | 507.21 | 0
Y | IPCRP1-9000-1430-C | IPCRP1 | IPCRP1 | 9000-1430 | Golf Carts | N | C |  | NR | P | 16332 | 74097.41 | 74097.41 | -50803.91 | 74097.41 | 100 | 0 | 0 | 0 | -124901.32 | Y | -50803.91 | Y | 67135.91 | 0 | 0 | 16332 | 0 | 0 | -50803.91 | Y | 67135.91 | 0 | 0 | 16332 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 50803.91 | 0 | 0 | -50803.91 | 0 | 0 | 0 | 0 | 0 | 0 | 50803.91 | 0 | 0 | -50803.91 | -50803.91 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 209.73 | 0 | 209.73 | NA | 3 | 6 | 0 | 6 | EA | 73629.92 | 124901.32 | -51271.4 | -124901.32 | Angie is checking to see if we can remove duplicated commitments (PO# IPCRP1-0346 to be void)
Y | IPCRP1-9000-1430-D | IPCRP1 | IPCRP1 | 9000-1430 | Golf Carts | N | D |  | UNIT | A | 0 | 100288.15 | 100288.15 | 100288.15 | 100288.15 | 0 | 0 | 0 | 0 | -100288.15 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 1953.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 3 | 6 | 0 | 6 | EA | 0 | 0 | 0 | -100288.15 | depreciation category.
Y | IPCRP1-9000-1430-E | IPCRP1 | IPCRP1 | 9000-1430 | Golf Carts | N | E |  | UNIT | A | 0 | 139611.48 | 139611.48 | 139611.48 | 139611.48 | 58.1715 | 0 | 0 | 0 | 100388.52 | Y | 240000 | Y | -240000 | 0 | 0 | 0 | 0 | 0 | 240000 | Y | -240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -240000 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | -240000 | 0 | 0 | 240000 | 240000 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 0 | 41 | 99 | 140 | NA | 3 | 6 | 0 | 6 | EA | 136842.99 | -2768.49 | 139611.48 | 100388.52 | Change PMF (Equipment) from $122,900.91 to $140,000.00. Purchased 6ea from Teixteira Polaris, which get depreciated under E cataegory for 140K. Rented others prior to purchsae from multiple sources, w/ CTD as of 10/31/23 of 83K, and projecting to 100K. (re-entered on 1-12-2024
Y | IPCRP1-9000-1430-L | IPCRP1 | IPCRP1 | 9000-1430 | Golf Carts | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1440-E | IPCRP1 | IPCRP1 | 9000-1440 | 35T Cherry Picker (CLOSED) | N | E |  | NR | P | 1188000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 1188000 | 0 | 0 | 1188000 | 0 | 0 | 0 | N | 1188000 | 0 | 0 | 1188000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 234 | 0 | 0 | 0 | WK | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1440-L | IPCRP1 | IPCRP1 | 9000-1440 | 35T Cherry Picker (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 234 | 0 | 0 | 0 | WK | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1450-C | IPCRP1 | IPCRP1 | 9000-1450 | Boom Truck | N | C |  | UNIT | U | 0 | 101567.42 | 101567.42 | 101567.42 | 101567.42 | 101.5674 | 0 | 0 | 0 | -1567.42 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 3085.52 | 1898.78 | 100000 | 0 | 0 | 0 | 0 | 1898.78 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 43423.3 | 43423.3 | 0 | 34149.25 | 9274.05 | 43423.3 | NA | 288 | 948.75 | 132.75 | 1081.5 | HR | 84724.66 | -16402.68 | 101127.34 | -1567.42 | Heavy Metal is under Consumable category.
Y | IPCRP1-9000-1450-E | IPCRP1 | IPCRP1 | 9000-1450 | Boom Truck | N | E |  | NR | P | 880106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 880106 | 0 | 0 | 880106 | 0 | 0 | 0 | N | 880106 | 0 | 0 | 880106 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 288 | 948.75 | 132.75 | 1081.5 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1450-L | IPCRP1 | IPCRP1 | 9000-1450 | Boom Truck | N | L |  | NR | P | 43442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 43442 | 0 | 0 | 43442 | 0 | 0 | 0 | Y | 43442 | 0 | 0 | 43442 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407 | 0 | 0 | 0 | 407 | 0 | 0 | 0 | HR | 288 | 948.75 | 132.75 | 1081.5 | HR | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1450-S | IPCRP1 | IPCRP1 | 9000-1450 | Boom Truck | N | S |  | UNIT | A | 0 | 318596.25 | 318596.25 | 288912.13 | 318596.25 | 90.6828 | 0 | 0 | 0 | 0 | Y | 318596.25 | Y | -318596.25 | 0 | 0 | 0 | 0 | 0 | 318596.25 | Y | -318596.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -318596.25 | 0 | 19162 | 318596.25 | 0 | 0 | 0 | 0 | 0 | 0 | -318596.25 | 0 | 0 | 318596.25 | 318596.25 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 15491.56 | -15490.56 | 1 | LS | 288 | 948.75 | 132.75 | 1081.5 | HR | 318596.25 | 29684.12 | 288912.13 | 0 | KMA INDUSTRIES @$21,800.00
Y | IPCRP1-9000-1460-E | IPCRP1 | IPCRP1 | 9000-1460 | Flatbed Truck (CLOSED) | N | E |  | NR | P | 237600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 237600 | 0 | 0 | 237600 | 0 | 0 | 0 | N | 237600 | 0 | 0 | 237600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 234 | 0 | 0 | 0 | WK | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1460-L | IPCRP1 | IPCRP1 | 9000-1460 | Flatbed Truck (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 234 | 0 | 0 | 0 | WK | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1470-L | IPCRP1 | IPCRP1 | 9000-1470 | CPM Schedule | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.6 | 0.4 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1470-S | IPCRP1 | IPCRP1 | 9000-1470 | CPM Schedule | N | S |  | NR | P | 385000 | 216250 | 216250 | 138715 | 216250 | 64.1457 | 0 | 0 | 0 | 0 | Y | 216250 | Y | 168750 | 0 | 0 | 385000 | 0 | 0 | 216250 | Y | 168750 | 0 | 0 | 385000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -216250 | 0 | 2985 | 216250 | 0 | 0 | 0 | 0 | 0 | 0 | -216250 | 0 | 0 | 216250 | 216250 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 346 | 1097.86 | 1443.86 | NA | 1 | 0.6 | 0.4 | 1 | LS | 216250 | 77535 | 138715 | 0 | L.B. CONSULTING Base Contract @$216,250.00
Y | IPCRP1-9000-1480-C | IPCRP1 | IPCRP1 | 9000-1480 | Engineering | N | C |  | UNIT | U | 0 | 282415.14 | 282415.14 | 275184.32 | 282415.14 | 91.7281 | 0 | 0 | 0 | 17584.86 | Y | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 300000 | Y | -300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | -300000 | 0 | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 6419.08 | -6404.08 | 15 | NA | 1 | 0.8 | 0.2 | 1 | LS | 79605.14 | 7230.82 | 72374.32 | 17584.86 | CONSUMABLE (BIM) 50K TO DATE + 10MO (10K) + 30MO (5K)
Y | IPCRP1-9000-1480-L | IPCRP1 | IPCRP1 | 9000-1480 | Engineering | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.8 | 0.2 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1480-S | IPCRP1 | IPCRP1 | 9000-1480 | Engineering | N | S |  | NR | A | 1150000 | 3168005.56 | 3168005.56 | 2880380.05 | 3168005.56 | 92.3191 | 0 | 0 | 0 | -47980 | Y | 3120025.56 | Y | -1970025.56 | 0 | 0 | 1150000 | 0 | 0 | 3120025.56 | Y | -1970025.56 | 0 | 0 | 1150000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3120025.56 | 0 | 38235.28 | 3120025.56 | 0 | 0 | 0 | 0 | 33980 | 0 | -3120025.56 | 0 | 0 | 3120025.56 | 3120025.56 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 122517.39 | -122516.39 | 1 | NA | 1 | 0.8 | 0.2 | 1 | LS | 3168005.56 | 287625.51 | 2880380.05 | -47980 | GEI $527,700 + $8,000; Greenman GPI $39,300 + 20,000; E4Science $12,000 = $607,000
Y | IPCRP1-9000-1490-E | IPCRP1 | IPCRP1 | 9000-1490 | Yard Operator/Loader | N | E |  | NR | P | 261229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 261229 | 0 | 0 | 261229 | 0 | 0 | 0 | Y | 261229 | 0 | 0 | 261229 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 223 | 209 | 72 | 281 | WK | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1490-L | IPCRP1 | IPCRP1 | 9000-1490 | Yard Operator/Loader | N | L |  | NR | P | 659238 | 863521.32 | 863521.32 | 863521.32 | 863521.32 | 77.6009 | 0 | 0 | 0 | 249251.04 | Y | 1112772.36 | Y | -453534.36 | 0 | 0 | 659238 | 0 | 0 | 1112772.36 | Y | -453534.36 | 0 | 0 | 659238 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1112772.36 | 28601.23 | 23672.93 | 1112772.36 | 0 | 0 | 0 | 0 | 0 | 0 | -1112772.36 | 0 | 0 | 1112772.36 | 1112772.36 | 0 | 0 | 0 | 3907.5 | 0 | 10116 | 10116 | 3907.5 | 7933 | 2183 | 10116 | HR | 223 | 209 | 72 | 281 | WK | 0 | 0 | 0 | 249251.04 | As of 8/25/24, QTD = 124.00. Extending job until 8/29/27, requires 157 WKS to complete (PMF = 281.00)
Y | IPCRP1-9000-1500-C | IPCRP1 | IPCRP1 | 9000-1500 | Training & Requals | N | C |  | NR | P | 130099 | 89375.99 | 89375.99 | 89021.87 | 89375.99 | 68.4263 | 0 | 0 | 0 | 40723.01 | Y | 130099 | Y | 0 | 0 | 0 | 130099 | 0 | 0 | 130099 | Y | 0 | 0 | 0 | 130099 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130099 | 1321.63 | 6152.41 | 130099 | 0 | 0 | 0 | 1193.26 | 0 | 0 | -130099 | 0 | 0 | 130099 | 130099 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1325 | -1325 | 0 | NA | 1 | 0.85 | 0.15 | 1 | LS | 54468.69 | 354.12 | 54114.57 | 40723.01
Y | IPCRP1-9000-1500-L | IPCRP1 | IPCRP1 | 9000-1500 | Training & Requals | N | L |  | UNIT | P | 0 | 215508.69 | 215508.69 | 215508.69 | 215508.69 | 86.1698 | 0 | 0 | 0 | 34588.95 | Y | 250097.64 | Y | -250097.64 | 0 | 0 | 0 | 0 | 0 | 250097.64 | Y | -250097.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250097.64 | 0 | 0 | 250097.64 | 0 | 0 | 0 | 0 | 0 | 0 | -250097.64 | 0 | 0 | 250097.64 | 250097.64 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 1742 | 258 | 2000 | HR | 1 | 0.85 | 0.15 | 1 | LS | 0 | 0 | 0 | 34588.95
Y | IPCRP1-9000-1510-C | IPCRP1 | IPCRP1 | 9000-1510 | Material Testing & Inspection Services | N | C |  | NR | P | 258195 | 10220.1 | 10220.1 | 10220.1 | 10220.1 | 20.4402 | 0 | 0 | 0 | 39779.9 | Y | 50000 | Y | 208195 | 0 | 0 | 258195 | 0 | 0 | 50000 | Y | 208195 | 0 | 0 | 258195 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3 | -1 | 2 | NA | 1 | 0.6 | 0.4 | 1 | LS | 10220.1 | 0 | 10220.1 | 39779.9 | S&B ENVIRONMENTAL LLC PO@$2,177.50
Y | IPCRP1-9000-1510-L | IPCRP1 | IPCRP1 | 9000-1510 | Material Testing & Inspection Services | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.6 | 0.4 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1510-S | IPCRP1 | IPCRP1 | 9000-1510 | Material Testing & Inspection Services | N | S |  | NR | A | 37300 | 2208400 | 2208400 | 1967043.19 | 2208400 | 89.071 | 0 | 0 | 0 | 0 | Y | 2208400 | Y | -2171100 | 0 | 0 | 37300 | 0 | 0 | 2208400 | Y | -2171100 | 0 | 0 | 37300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2208400 | 52385.88 | 37714 | 2208400 | 0 | 0 | 0 | 0 | 0 | 0 | -2208400 | 0 | 0 | 2208400 | 2208400 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 550542.75 | -550542.75 | 0 | NA | 1 | 0.6 | 0.4 | 1 | LS | 2208400 | 241356.81 | 1967043.19 | 0
Y | IPCRP1-9000-1520-C | IPCRP1 | IPCRP1 | 9000-1520 | Legal Fees for Tullys Dispute | N | C |  | UNIT | U | 0 | 772513.4 | 772513.4 | 772513.4 | 772513.4 | 100 | 0 | 0 | 0 | 0 | Y | 772513.4 | Y | -772513.4 | 0 | 0 | 0 | 0 | 0 | 772513.4 | Y | -772513.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -772513.4 | 0 | 0 | 772513.4 | 0 | 0 | 0 | 0 | 0 | 0 | -772513.4 | 0 | 0 | 772513.4 | 772513.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 0 | 1 | 0 | 1 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1520-L | IPCRP1 | IPCRP1 | 9000-1520 | Legal Fees for Tullys Dispute | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 1 | 0 | 1 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1530-C | IPCRP1 | IPCRP1 | 9000-1530 | Interest Fees | N | C |  | UNIT | P | 0 | 648732.01 | 648732.01 | 648732.01 | 648732.01 | 87.0415 | 0 | 0 | 0 | 96581.66 | Y | 745313.67 | Y | -745313.67 | 0 | 0 | 0 | 0 | 0 | 745313.67 | Y | -745313.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -745313.67 | 0 | 0 | 745313.67 | 0 | 0 | 0 | 0 | 0 | 0 | -745313.67 | 0 | 0 | 745313.67 | 745313.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 1 | 0.87 | 0.13 | 1 | LS | 0 | 0 | 0 | 96581.66 | MLJ ($175,750.60), Posillico ($117,516.87), CAC ($77,046.20). Subtotal = $370,313,67 PLUS Alliant (75K per year x 5yr = 375K). New total: $745,313.67 Alliant invoices are annual Financial Guarantee Bonds for each company.
Y | IPCRP1-9000-1530-L | IPCRP1 | IPCRP1 | 9000-1530 | Interest Fees | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.87 | 0.13 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-9000-1540-C | IPCRP1 | IPCRP1 | 9000-1540 | Financial Audits (G&A) | N | C |  | UNIT | P | 0 | 220912.51 | 220912.51 | 220912.51 | 220912.51 | 78.8973 | 0 | 0 | 0 | 59087.49 | Y | 280000 | Y | -280000 | 0 | 0 | 0 | 0 | 0 | 280000 | Y | -280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -280000 | 0 | 16054.69 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | -280000 | 0 | 0 | 280000 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | LS | 1 | 0.5 | 0.5 | 1 | LS | 0 | 0 | 0 | 59087.49 | Annual audit, assume 25K per year x 6 years = 150K
Y | IPCRP1-9000-1540-L | IPCRP1 | IPCRP1 | 9000-1540 | Financial Audits (G&A) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.5 | 0.5 | 1 | LS | 0 | 0 | 0 | 0
Y | IPCRP1-99-9999-A | IPCRP1 | IPCRP1 | 99-9999 | Accurals (CLOSED) | N | A |  | UNIT | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-99-9999-L | IPCRP1 | IPCRP1 | 99-9999 | Accurals (CLOSED) | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-99-9999-O | IPCRP1 | IPCRP1 | 99-9999 | Accurals (CLOSED) | N | O |  | UNIT | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-9999-9000-C | IPCRP1 | IPCRP1 | 9999-9000 | Bond | N | C |  | NR | P | 9168524 | 8472830.8 | 8472830.8 | 8472830.8 | 8472830.8 | 91.8735 | 0 | 0 | 0 | 749450.2 | Y | 9222281 | Y | -53757 | 0 | 0 | 9168524 | 0 | 0 | 9222281 | Y | -53757 | 0 | 0 | 9168524 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9222281 | 0 | 153665.1 | 9222281 | 0 | 0 | 0 | 0 | 0 | 0 | -9222281 | 0 | 0 | 9222281 | 9222281 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 749450.2 | #1. Will pay at 1 time, after we receive mobilization money, but cost will be amortized over 60 months, at $153,665/mo, starting w/ Sep 2021 (month 1). #2 Total Cost includes P&P Bond ($9,219,906.00) + Permit & Union Bond cost ($2,375.00).
Y | IPCRP1-9999-9000-L | IPCRP1 | IPCRP1 | 9999-9000 | Bond | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 60 | 55 | 5 | 60 | MO | 0 | 0 | 0 | 0
Y | IPCRP1-9999-9960-INS | IPCRP1 | IPCRP1 | 9999-9960 | Insurance | N | INS |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-9999-9960-L | IPCRP1 | IPCRP1 | 9999-9960 | Insurance | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-9999-9970-C | IPCRP1 | IPCRP1 | 9999-9970 | Legal Fees | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-9999-9970-L | IPCRP1 | IPCRP1 | 9999-9970 | Legal Fees | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
Y | IPCRP1-9999-9999-A | IPCRP1 | IPCRP1 | 9999-9999 | Accruals | N | A |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | -11917495.32 | 1220457.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | test 2026-01-23 0909
Y | IPCRP1-9999-9999-L | IPCRP1 | IPCRP1 | 9999-9999 | Accruals | N | L |  | UNIT | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 1 | PMF is 0. test 2-3-25